## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : UGWT-PCC Work-M15
Page 1 of 1
Total Records: 2 Records 1 to 2
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | UGWT-PCC Work-M15 | 10 | Started | Material | (M)Ready Mix Concrete M-15 Grade( D/P) - | Cu.Mtrs | 20.46 | 3500 | 71610 | 0 | 0 | 0 | 2 | 3500 | 7000 | 0 | 0 | 0 | 6 | 4252.06 | 25512.36 | 18.46 | 14.46 | 64610 | 46097.64
2 | UGWT-PCC Work-M15 | 10 | Started | Material | (M)Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 20.46 | 2125 | 43477.5 | 0 | 0 | 0 | 2 | 2125 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 18.46 | 20.46 | 39227.5 | 43477.5