## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : D
Page 1 of 1
Total Records: 3 Records 1 to 3
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | D&E Bldg Between-P2-3rd Slab RCC 3rd Slab,Beam Concrete - | 10 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Pumpable) | Cu.Mtrs | 0.01 | 100 | 1 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 1 | 1
2 | D&E Bldg Between-P2-3rd Slab RCC 3rd Slab,Beam Concrete - | 10 | Started | Material | (M)Sand-Metal Mix M35 (Downpour) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | D&E Bldg Between-P2-3rd Slab RCC 3rd Slab,Beam Concrete - | 10 | Started | Material | (M)Sand-Metal Mix M35 (Pumpable) | Cu.Mtrs | 209.14 | 2175 | 454879.5 | 204.2624 | 2175 | 444270.72 | 21 | 2175 | 45675 | 204.2624 | 3880.81 | 792704.2256 | 209.14 | 4067.97 | 850774.96 | 188.14 | 0 | 409204.5 | -395895.46