## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : D
Page 1 of 1
Total Records: 2 Records 1 to 2
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | D&E Bldg Between-P5-5th Slab RCC 5th Slab,Beam Concrete - | 10 | Started | Material | (M)Sand-Metal Mix M35 (Downpour) | Cu.Mtrs | 30 | 2125 | 63750 | 30 | 2125 | 63750 | 3 | 2125 | 6375 | 28.9724 | 3755.77 | 108813.5383 | 30 | 3873.98 | 116219.47 | 27 | 0 | 57375 | -52469.47
2 | D&E Bldg Between-P5-5th Slab RCC 5th Slab,Beam Concrete - | 10 | Started | Material | (M)Sand-Metal Mix M35 (Pumpable) | Cu.Mtrs | 179.14 | 2175 | 389629.5 | 171.28 | 2175 | 372534 | 18 | 2175 | 39150 | 171.28 | 3971.36 | 680213.8707 | 171.28 | 3978.93 | 681511.8 | 161.14 | 7.86 | 350479.5 | -291882.3