## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : A 2nd Slab (Parking) Column 1st to 2nd Concrete M35
Page 1 of 1
Total Records: 3 Records 1 to 3
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | 0 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Downpour) | Cu.Mtrs | 46.32 | 4400 | 203808 | 9 | 4400 | 39600 | 0 | 4400 | 0 | 9 | 5442 | 48977.9964 | 0 | 0 | 0 | 46.32 | 46.32 | 203808 | 203808
2 | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | 0 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Pumpable) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | 0 | Started | Material | (M)Sand-Metal Mix M35 (Downpour) | Cu.Mtrs | 24 | 2125 | 51000 | 24 | 2125 | 51000 | 0 | 2125 | 0 | 24 | 3600 | 86399.988 | 0 | 0 | 0 | 24 | 24 | 51000 | 51000