## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : UGWT-RCC Pardi Concrete M25
Page 1 of 1
Total Records: 2 Records 1 to 2
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | UGWT-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 45.25 | 3150 | 142537.5 | 0 | 0 | 0 | 5 | 3150 | 15750 | 0 | 0 | 0 | 7 | 4670.56 | 32693.89 | 40.25 | 38.25 | 126787.5 | 109843.61
2 | UGWT-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0