## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : D-Stilt to 24th Floor-Main Line Wiring
Page 1 of 1
Total Records: 11 Records 1 to 11
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)2 Pair telephone cable | Mtrs | 6000 | 50 | 300000 | 6000 | 50 | 300000 | 600 | 50 | 30000 | 6000 | 12.29 | 73745.4 | 0 | 0 | 0 | 5400 | 6000 | 270000 | 300000
2 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 10 Sqmm black | Mtrs | 12500 | 60 | 750000 | 12500 | 60 | 750000 | 1250 | 60 | 75000 | 12500 | 103.86 | 1298242.5 | 0 | 0 | 0 | 11250 | 12500 | 675000 | 750000
3 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 10 Sqmm blue | Mtrs | 8700 | 60 | 522000 | 8700 | 60 | 522000 | 870 | 60 | 52200 | 8700 | 103.86 | 903576.78 | 0 | 0 | 0 | 7830 | 8700 | 469800 | 522000
4 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 10 Sqmm red | Mtrs | 8700 | 60 | 522000 | 8700 | 60 | 522000 | 870 | 60 | 52200 | 8700 | 103.86 | 903576.78 | 0 | 0 | 0 | 7830 | 8700 | 469800 | 522000
5 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 10 Sqmm yellow | Mtrs | 8700 | 60 | 522000 | 8700 | 60 | 522000 | 870 | 60 | 52200 | 8700 | 103.86 | 903576.78 | 0 | 0 | 0 | 7830 | 8700 | 469800 | 522000
6 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 2.5 Sqmm green | Mtrs | 8500 | 14.28 | 121380 | 8500 | 14.28 | 121380 | 850 | 14.28 | 12138 | 8500 | 25.87 | 219893.3 | 0 | 0 | 0 | 7650 | 8500 | 109242 | 121380
7 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm black | Mtrs | 12800 | 31.33 | 401024 | 12800 | 31.33 | 401024 | 1280 | 31.33 | 40102.4 | 12800 | 59.15 | 757140.48 | 0 | 0 | 0 | 11520 | 12800 | 360921.6 | 401024
8 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm blue | Mtrs | 8400 | 31.33 | 263172 | 8400 | 31.33 | 263172 | 840 | 31.33 | 26317.2 | 8400 | 59.15 | 496873.44 | 0 | 0 | 0 | 7560 | 8400 | 236854.8 | 263172
9 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm red | Mtrs | 8400 | 31.33 | 263172 | 8400 | 31.33 | 263172 | 840 | 31.33 | 26317.2 | 8400 | 59.15 | 496873.44 | 0 | 0 | 0 | 7560 | 8400 | 236854.8 | 263172
10 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm yellow | Mtrs | 8400 | 31.33 | 263172 | 8400 | 31.33 | 263172 | 840 | 31.33 | 26317.2 | 8400 | 59.15 | 496873.44 | 0 | 0 | 0 | 7560 | 8400 | 236854.8 | 263172
11 | D-Stilt to 24th Floor-Main Line Wiring | 10 | Started | Material | (M)RG-6 Co-Axial Cable-- Mtr | Mtrs | 6000 | 15 | 90000 | 6000 | 15 | 90000 | 600 | 15 | 9000 | 6000 | 18.85 | 113119.8 | 0 | 0 | 0 | 5400 | 6000 | 81000 | 90000