## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : RCC Work RCC Pardi Concrete Work M25
Page 1 of 1
Total Records: 3 Records 1 to 3
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | RCC Work RCC Pardi Concrete Work M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Pumpable | Cu.Mtrs | 31.8883 | 3150 | 100448.15 | 30 | 3150 | 94500 | 3 | 3150 | 9450 | 30 | 4830 | 144899.979 | 31 | 4830 | 149730 | 28.8883 | 0.8883 | 90998.145 | -49281.855
2 | RCC Work RCC Pardi Concrete Work M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 61.895 | 2000 | 123790 | 61.895 | 2000 | 123790 | 6 | 2000 | 12000 | 61.895 | 3925 | 242937.8675 | 61.895 | 3763.84 | 232962.96 | 55.895 | 0 | 111790 | -109172.96
3 | RCC Work RCC Pardi Concrete Work M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 29.9572 | 2500 | 74893 | 0 | 0 | 0 | 3 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 877.8 | 26.9572 | 29.9572 | 67393 | 74015.2