## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : D-P2 Fl Parapet Wall RCC Work Concrete
Page 1 of 1
Total Records: 1 Records 1 to 1
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | D-P2 Fl Parapet Wall RCC Work Concrete | 10 | Started | Material | (M)Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 16.55 | 2000 | 33100 | 14.315 | 2000 | 28630 | 2 | 2000 | 4000 | 14.315 | 3925 | 56186.3736 | 0 | 0 | 0 | 14.55 | 16.55 | 29100 | 33100