## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : E-Bldg-2nd Slab RCC P1 Fl -Parapet Wall Concrete Work-M25
Page 1 of 1
Total Records: 2 Records 1 to 2
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | E-Bldg-2nd Slab RCC P1 Fl -Parapet Wall Concrete Work-M25 | 0 | Tentative | Material | (M)Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | E-Bldg-2nd Slab RCC P1 Fl -Parapet Wall Concrete Work-M25 | 0 | Tentative | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 10.83 | 2500 | 27075 | 10.83 | 2500 | 27075 | 0 | 2500 | 0 | 10.83 | 4125 | 44673.7143 | 0 | 0 | 0 | 10.83 | 10.83 | 27075 | 27075