## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : RCC Work Pump Room-RCC Pardi Concrete-M25
Page 1 of 1
Total Records: 2 Records 1 to 2
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | RCC Work Pump Room-RCC Pardi Concrete-M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 55.3027 | 2000 | 110605.4 | 51.0227 | 2000 | 102045.4 | 6 | 2000 | 12000 | 51.0227 | 3819.29 | 194870.5561 | 51 | 3801.73 | 193888.14 | 49.3027 | 4.3027 | 98605.4 | -83282.74
2 | RCC Work Pump Room-RCC Pardi Concrete-M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 59.9958 | 2500 | 149989.5 | 59.9958 | 2500 | 149989.5 | 6 | 2500 | 15000 | 59.9958 | 3883.64 | 233001.8417 | 59.99 | 4091.18 | 245429.96 | 53.9958 | 0.0058 | 134989.5 | -95440.46