## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : RCC Work Plum Concrete Work
Page 1 of 1
Total Records: 2 Records 1 to 2
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | RCC Work Plum Concrete Work | 10 | Started | Material | (M)Rubble | Cu.Ft | 359.203 | 10 | 3592.03 | 0 | 0 | 0 | 36 | 10 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 323.203 | 359.203 | 3232.03 | 3592.03
2 | RCC Work Plum Concrete Work | 10 | Started | Material | (M)Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 15.26 | 2125 | 32427.5 | 0 | 0 | 0 | 2 | 2125 | 4250 | 0 | 0 | 0 | 0 | 0 | -0.04 | 13.26 | 15.26 | 28177.5 | 32427.54