## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : D-Shops Electrical main line work
Page 1 of 1
Total Records: 6 Records 1 to 6
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | D-Shops Electrical main line work | 10 | Started | Material | (M)PVC Copper Wire 2.5 Sqmm green | Mtrs | 383.615 | 14.28 | 5478.02 | 0 | 0 | 0 | 38 | 14.28 | 542.64 | 0 | 0 | 0 | 0 | 0 | 0 | 345.615 | 383.615 | 4935.382 | 5478.0222
2 | D-Shops Electrical main line work | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm black | Mtrs | 383.615 | 31.33 | 12018.66 | 383.615 | 31.33 | 12018.66 | 38 | 31.33 | 1190.54 | 383.615 | 69.67 | 26728.3368 | 316 | 59.58 | 18825.7 | 345.615 | 67.615 | 10828.118 | -6807.042
3 | D-Shops Electrical main line work | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm blue | Mtrs | 383.615 | 31.33 | 12018.66 | 383.615 | 31.33 | 12018.66 | 38 | 31.33 | 1190.54 | 383.615 | 69.67 | 26728.3368 | 0 | 0 | 0 | 345.615 | 383.615 | 10828.118 | 12018.658
4 | D-Shops Electrical main line work | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm red | Mtrs | 383.615 | 31.33 | 12018.66 | 383.615 | 31.33 | 12018.66 | 38 | 31.33 | 1190.54 | 383.615 | 69.67 | 26728.3368 | 0 | 0 | 0 | 345.615 | 383.615 | 10828.118 | 12018.658
5 | D-Shops Electrical main line work | 10 | Started | Material | (M)PVC Copper Wire 6 Sqmm yellow | Mtrs | 383.615 | 31.33 | 12018.66 | 383.615 | 31.33 | 12018.66 | 38 | 31.33 | 1190.54 | 383.615 | 69.67 | 26728.3368 | 0 | 0 | 0 | 345.615 | 383.615 | 10828.118 | 12018.658
6 | D-Shops Electrical main line work | 10 | Started | Labour | (L)Main Line Electrical work (L) | No. | 8 | 167687 | 1341496 | 0 | 0 | 0 | 1 | 167687 | 167687 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 1173809 | 1341496