## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : D-Internal Plumbing -(PPR-C,PVC,ASTM)
Page 1 of 1
Total Records: 90 Records 1 to 90
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Ball Valve 1-1/4" | No. | 400 | 1055 | 422000 | 400 | 1055 | 422000 | 40 | 1055 | 42200 | 400 | 144.6 | 57840.5264 | 337 | 149.2 | 50281.03 | 360 | 63 | 379800 | 371718.97
2 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Brass FTA 1 1/2" | No. | 400 | 100 | 40000 | 400 | 100 | 40000 | 40 | 100 | 4000 | 400 | 306.44 | 122577.88 | 400 | 300.02 | 120008.77 | 360 | 0 | 36000 | -80008.77
3 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Brass FTA 1-1/4" | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Brass FTA 1/2" | No. | 54 | 56.31 | 3040.74 | 54 | 56.31 | 3040.74 | 5 | 56.31 | 281.55 | 54 | 66.7 | 3601.9998 | 0 | 0 | 0 | 49 | 54 | 2759.19 | 3040.74
5 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Brass MTA 1-1/4" | No. | 400 | 113.46 | 45384 | 400 | 113.46 | 45384 | 40 | 113.46 | 4538.4 | 400 | 247.18 | 98872.4736 | 400 | 246.01 | 98404.37 | 360 | 0 | 40845.6 | -53020.37
6 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Elbow 11/4" | No. | 2000 | 26.31 | 52620 | 2000 | 26.31 | 52620 | 200 | 26.31 | 5262 | 2000 | 35.62 | 71246.656 | 1771 | 35.24 | 62417.68 | 1800 | 229 | 47358 | -9797.68
7 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM End Cap 1/2" | No. | 54 | 15 | 810 | 54 | 15 | 810 | 5 | 15 | 75 | 54 | 4.83 | 261.0162 | 2 | 4.75 | 9.5 | 49 | 52 | 735 | 800.5
8 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM End Cap 11/4" | No. | 400 | 10 | 4000 | 400 | 10 | 4000 | 40 | 10 | 400 | 400 | 15.84 | 6336.2608 | 200 | 15.69 | 3138.86 | 360 | 200 | 3600 | 861.14
9 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Pipe 1/2" x 10 fts | No. | 9 | 110.56 | 995.04 | 9 | 110.56 | 995.04 | 1 | 110.56 | 110.56 | 9 | 184.11 | 1656.9951 | 0 | 0 | 0 | 8 | 9 | 884.48 | 995.04
10 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Pipe 11/4" x 10 fts | No. | 600 | 197.84 | 118704 | 600 | 197.84 | 118704 | 60 | 197.84 | 11870.4 | 600 | 446.94 | 268166.9712 | 532.1 | 455.73 | 242495.64 | 540 | 67.9 | 106833.6 | -123791.64
11 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Reducer Bushing 1 1/4" x 1 1/2" | No. | 400 | 72 | 28800 | 400 | 72 | 28800 | 40 | 72 | 2880 | 400 | 10.06 | 4022.8912 | 400 | 9.89 | 3954.22 | 360 | 0 | 25920 | 24845.78
12 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Astm Reducer Socket 11/4"x1/2" | No. | 54 | 100 | 5400 | 54 | 100 | 5400 | 5 | 100 | 500 | 54 | 22.64 | 1222.5474 | 3 | 20.66 | 61.97 | 49 | 51 | 4900 | 5338.03
13 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Shoe Bend 1 1/4" (32mm) | No. | 800 | 70 | 56000 | 800 | 70 | 56000 | 80 | 70 | 5600 | 800 | 27.75 | 22202.0608 | 475 | 28.17 | 13379.2 | 720 | 325 | 50400 | 42620.8
14 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Socket 11/4" | No. | 400 | 23.55 | 9420 | 400 | 23.55 | 9420 | 40 | 23.55 | 942 | 400 | 19.95 | 7978.6144 | 153 | 20.57 | 3146.47 | 360 | 247 | 8478 | 6273.53
15 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Solvent Cement 472ml | No. | 84.75 | 484.2 | 41035.95 | 84.75 | 484.2 | 41035.95 | 8 | 484.2 | 3873.6 | 84.75 | 386.76 | 32777.7909 | 61 | 385.79 | 23533.14 | 76.75 | 23.75 | 37162.35 | 17502.81
16 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)ASTM Tee 11/4" | No. | 36 | 47 | 1692 | 36 | 47 | 1692 | 4 | 47 | 188 | 36 | 64.24 | 2312.6736 | 9 | 36.66 | 329.98 | 32 | 27 | 1504 | 1362.02
17 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Bullet Fastner 8mm | No. | 2400 | 8 | 19200 | 2100 | 8 | 16800 | 240 | 8 | 1920 | 2100 | 5.93 | 12442.896 | 2369 | 5.72 | 13546.52 | 2160 | 31 | 17280 | 5653.48
18 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Chair Bracket for W H | No. | 400 | 673 | 269200 | 400 | 673 | 269200 | 40 | 673 | 26920 | 400 | 686.58 | 274633.64 | 450 | 677.09 | 304690.48 | 360 | -50 | 242280 | -35490.48
19 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Floor Trap Jali with cover 150mmx150mm (Grey Colour) | No. | 32 | 100 | 3200 | 0 | 0 | 0 | 3 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 32 | 2900 | 3200
20 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI Bracket 3"x6" | No. | 400 | 100 | 40000 | 400 | 100 | 40000 | 40 | 100 | 4000 | 400 | 43.6 | 17440.96 | 290 | 41.4 | 12007.37 | 360 | 110 | 36000 | 27992.63
21 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI Bracket 6"X2" | No. | 576 | 50 | 28800 | 576 | 50 | 28800 | 58 | 50 | 2900 | 576 | 39.21 | 22586.88 | 301 | 38.18 | 11492.77 | 518 | 275 | 25900 | 17307.23
22 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI Bracket 6"X4" | No. | 400 | 53.53 | 21412 | 400 | 53.53 | 21412 | 40 | 53.53 | 2141.2 | 400 | 50.25 | 20100.16 | 400 | 48.66 | 19465.54 | 360 | 0 | 19270.8 | 1946.46
23 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI Clamps 4" | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI Clips 1 1/4" | No. | 425 | 1.5 | 637.5 | 425 | 1.5 | 637.5 | 43 | 1.5 | 64.5 | 425 | 3.86 | 1638.8 | 20 | 5.36 | 107.28 | 382 | 405 | 573 | 530.22
25 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI Clips 1/2" | No. | 2400 | 0.5 | 1200 | 2400 | 0.5 | 1200 | 240 | 0.5 | 120 | 2400 | 2.31 | 5540.128 | 1580 | 2.57 | 4057.38 | 2160 | 820 | 1080 | -2857.38
26 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI D Clamps 11/4" | No. | 800 | 8 | 6400 | 800 | 8 | 6400 | 80 | 8 | 640 | 800 | 11.74 | 9394.88 | 684 | 9.16 | 6268.17 | 720 | 116 | 5760 | 131.83
27 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI D Clamps 3" | No. | 800 | 12 | 9600 | 796 | 12 | 9552 | 80 | 12 | 960 | 796 | 17.14 | 13642.4 | 797 | 17.15 | 13666.21 | 720 | 3 | 8640 | -4066.21
28 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI D Clamps 3/4" | No. | 333 | 19 | 6327 | 173 | 19 | 3287 | 33 | 19 | 627 | 173 | 7.15 | 1236.15 | 0 | 0 | 0 | 300 | 333 | 5700 | 6327
29 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI D Clamps 4" | No. | 800 | 19 | 15200 | 796 | 19 | 15124 | 80 | 19 | 1520 | 796 | 26.94 | 21445.44 | 718 | 24.74 | 17766.75 | 720 | 82 | 13680 | -2566.75
30 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)GI U Clamps 4" | No. | 800 | 8 | 6400 | 796 | 8 | 6368 | 80 | 8 | 640 | 796 | 19.57 | 15575.36 | 775 | 19.77 | 15324.34 | 720 | 25 | 5760 | -8924.34
31 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Habak (200 gm ) | Pack | 50 | 15 | 750 | 26 | 15 | 390 | 5 | 15 | 75 | 26 | 49.68 | 1291.72 | 1 | 46.7 | 46.7 | 45 | 49 | 675 | 703.3
32 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Hold Tite (1 Kgs) | Kgs | 40 | 206.4 | 8256 | 40 | 206.4 | 8256 | 4 | 206.4 | 825.6 | 40 | 285.35 | 11413.8869 | 17 | 288.81 | 4909.71 | 36 | 23 | 7430.4 | 3346.29
33 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Nut 8mm | No. | 4800 | 1 | 4800 | 4764 | 1 | 4764 | 480 | 1 | 480 | 4764 | 1.52 | 7258.26 | 5148 | 1.61 | 8264.87 | 4320 | -348 | 4320 | -3464.87
34 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Plumbing Nails 11/2" | Kgs | 250 | 50 | 12500 | 250 | 50 | 12500 | 25 | 50 | 1250 | 250 | 88.22 | 22055.62 | 151 | 90.43 | 13654.19 | 225 | 99 | 11250 | -1154.19
35 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Plumbing Nails 2" | Kgs | 50 | 45 | 2250 | 50 | 45 | 2250 | 5 | 45 | 225 | 50 | 92.17 | 4608.3 | 0 | 0 | 0 | 45 | 50 | 2025 | 2250
36 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Ballvalve 20mm (Plas-Bo | No. | 600 | 60.4 | 36240 | 600 | 60.4 | 36240 | 60 | 60.4 | 3624 | 600 | 91.05 | 54630.4176 | 563 | 90.4 | 50895.46 | 540 | 37 | 32616 | -14655.46
37 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Brass Elbow 20mm | No. | 2400 | 14.5 | 34800 | 2400 | 14.5 | 34800 | 240 | 14.5 | 3480 | 2400 | 35.1 | 84237.84 | 2281 | 35.04 | 79915.55 | 2160 | 119 | 31320 | -45115.55
38 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Brass FTA 1/2" | No. | 600 | 32.6 | 19560 | 600 | 32.6 | 19560 | 60 | 32.6 | 1956 | 600 | 36.83 | 22098.6624 | 479 | 36.76 | 17606.82 | 540 | 121 | 17604 | 1953.18
39 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Brass MTA 1/2" | No. | 1600 | 54.77 | 87632 | 1600 | 54.77 | 87632 | 160 | 54.77 | 8763.2 | 1600 | 51.06 | 81697.536 | 1621 | 51.06 | 82768.07 | 1440 | -21 | 78868.8 | 4863.93
40 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Brass Tee 20mm | No. | 600 | 25 | 15000 | 600 | 25 | 15000 | 60 | 25 | 1500 | 600 | 37.59 | 22556.88 | 592 | 37.59 | 22255.91 | 540 | 8 | 13500 | -7255.91
41 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Elbow 20mm | No. | 4400 | 14.5 | 63800 | 4400 | 14.5 | 63800 | 440 | 14.5 | 6380 | 4400 | 6.81 | 29942.1696 | 4262 | 6.81 | 29004.95 | 3960 | 138 | 57420 | 34795.05
42 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C End Cap 20mm | No. | 684 | 12.42 | 8495.28 | 684 | 12.42 | 8495.28 | 68 | 12.42 | 844.56 | 684 | 6.59 | 4507.6944 | 571 | 6.6 | 3767.31 | 616 | 113 | 7650.72 | 4727.97
43 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C End Plug 1/2" | No. | 2800 | 7.06 | 19768 | 2800 | 7.06 | 19768 | 280 | 7.06 | 1976.8 | 2800 | 5.54 | 15517.0944 | 2800 | 5.54 | 15515.48 | 2520 | 0 | 17791.2 | 4252.52
44 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C End Plug 20mm | No. | 200 | 321 | 64200 | 200 | 321 | 64200 | 20 | 321 | 6420 | 200 | 7.65 | 1529.28 | 200 | 7.65 | 1529.29 | 180 | 0 | 57780 | 62670.71
45 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Pipe 20mm(PN16) 3Layer | R.Ft | 17500 | 22.28 | 389900 | 17500 | 22.28 | 389900 | 1750 | 22.28 | 38990 | 17500 | 9.98 | 174569.272 | 15969 | 9.98 | 159347.86 | 15750 | 1531 | 350910 | 230552.14
46 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Socket 20mm | No. | 800 | 6.05 | 4840 | 800 | 6.05 | 4840 | 80 | 6.05 | 484 | 800 | 5.94 | 4753.2288 | 415 | 5.96 | 2471.91 | 720 | 385 | 4356 | 2368.09
47 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PPR-C Tee 20mm | No. | 1000 | 18.6 | 18600 | 1000 | 18.6 | 18600 | 100 | 18.6 | 1860 | 1000 | 10.24 | 10235.976 | 1048 | 10.23 | 10724.57 | 900 | -48 | 16740 | 7875.43
48 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC bushing 40mm x 50mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Elbow 1 1/2 " | No. | 800 | 21 | 16800 | 800 | 21 | 16800 | 80 | 21 | 1680 | 800 | 27.67 | 22138.976 | 621 | 27.95 | 17357.64 | 720 | 179 | 15120 | -557.64
50 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Elbow 11/4" - No. | No. | 800 | 9.04 | 7232 | 800 | 9.04 | 7232 | 80 | 9.04 | 723.2 | 800 | 17.34 | 13874.336 | 516 | 18.78 | 9688.47 | 720 | 284 | 6508.8 | -2456.47
51 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Elbow 4" | No. | 300 | 84.92 | 25476 | 300 | 84.92 | 25476 | 30 | 84.92 | 2547.6 | 300 | 130.65 | 39195.948 | 227 | 146.67 | 33294.05 | 270 | 73 | 22928.4 | -7818.05
52 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Elbow 50mm | No. | 216 | 27 | 5832 | 216 | 27 | 5832 | 22 | 27 | 594 | 216 | 40.24 | 8692.8336 | 212 | 40.36 | 8555.76 | 194 | 4 | 5238 | -2723.76
53 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC End Cap 1-1/4" | No. | 400 | 6.89 | 2756 | 400 | 6.89 | 2756 | 40 | 6.89 | 275.6 | 400 | 9.01 | 3602.4752 | 262 | 9.87 | 2586.68 | 360 | 138 | 2480.4 | 169.32
54 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC End Cap 50mm | No. | 600 | 100 | 60000 | 600 | 100 | 60000 | 60 | 100 | 6000 | 600 | 19.28 | 11565.4752 | 492 | 21.24 | 10451.59 | 540 | 108 | 54000 | 49548.41
55 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Multifloor Trap 4" | No. | 200 | 108.42 | 21684 | 200 | 108.42 | 21684 | 20 | 108.42 | 2168.4 | 200 | 184.19 | 36837.668 | 200 | 184.86 | 36971.34 | 180 | 0 | 19515.6 | -15287.34
56 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Nahani Trap 4"X 3" | No. | 200 | 99 | 19800 | 200 | 99 | 19800 | 20 | 99 | 1980 | 200 | 127.17 | 25433.5288 | 135 | 152.26 | 20554.51 | 180 | 65 | 17820 | -754.51
57 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Nahani Trap 4"X3" with Jali (Hanging) | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Nahani Trap 4"X3" without Jali | No. | 432 | 100 | 43200 | 432 | 100 | 43200 | 43 | 100 | 4300 | 432 | 91.82 | 39668.1696 | 432 | 89.99 | 38875.68 | 389 | 0 | 38900 | 4324.32
59 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 11/2"x 10 ft | No. | 120 | 180 | 21600 | 120 | 180 | 21600 | 12 | 180 | 2160 | 120 | 260.46 | 31254.6944 | 102 | 259.99 | 26519.24 | 108 | 18 | 19440 | -4919.24
60 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 11/4"x10 ft | No. | 360 | 91.46 | 32925.6 | 360 | 91.46 | 32925.6 | 36 | 91.46 | 3292.56 | 360 | 202.01 | 72725.3623 | 291 | 190.35 | 55392.41 | 324 | 69 | 29633.04 | -22466.81
61 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 2" x 10 ft S/S | No. | 120 | 156.98 | 18837.6 | 120 | 156.98 | 18837.6 | 12 | 156.98 | 1883.76 | 120 | 329.83 | 39579.971 | 27 | 499.04 | 13474.1 | 108 | 93 | 16953.84 | 5363.5
62 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 3" 2Ft Long D/S | No. | 700 | 38.28 | 26796 | 700 | 38.28 | 26796 | 70 | 38.28 | 2679.6 | 700 | 126.76 | 88732.224 | 163 | 130.59 | 21286.19 | 630 | 537 | 24116.4 | 5509.81
63 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 3" 6Ft Long D/S | No. | 600 | 95.48 | 57288 | 600 | 95.48 | 57288 | 60 | 95.48 | 5728.8 | 600 | 396.52 | 237912.9024 | 593 | 401.06 | 237830.97 | 540 | 7 | 51559.2 | -180542.97
64 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 3"x10 ft D/S | No. | 115.5 | 210.89 | 24357.8 | 86.5 | 210.89 | 18241.99 | 12 | 210.89 | 2530.68 | 86.5 | 483.65 | 41835.4523 | 28 | 525.89 | 14724.81 | 103.5 | 87.5 | 21827.115 | 9632.985
65 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 4" 4 Ft Long D/S | No. | 200 | 199.97 | 39994 | 200 | 199.97 | 39994 | 20 | 199.97 | 3999.4 | 200 | 524.69 | 104938.6224 | 10 | 522.26 | 5222.63 | 180 | 190 | 35994.6 | 34771.37
66 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 4" 6 FT Long D/S | No. | 200 | 282.56 | 56512 | 200 | 282.56 | 56512 | 20 | 282.56 | 5651.2 | 200 | 679.57 | 135913.9472 | 142 | 757.56 | 107573.18 | 180 | 58 | 50860.8 | -51061.18
67 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 4" x 10 Ft S/S | No. | 400 | 489.3 | 195720 | 400 | 489.3 | 195720 | 40 | 489.3 | 19572 | 400 | 1017.81 | 407123.32 | 375 | 1083.31 | 406241.54 | 360 | 25 | 176148 | -210521.54
68 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Pipe 4" x 10 fts D/S | No. | 400 | 393.8 | 157520 | 400 | 393.8 | 157520 | 40 | 393.8 | 15752 | 400 | 967.62 | 387047.9168 | 290 | 998.56 | 289583.19 | 360 | 110 | 141768 | -132063.19
69 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Plain Bend 3" | No. | 400 | 37.16 | 14864 | 400 | 37.16 | 14864 | 40 | 37.16 | 1486.4 | 400 | 77.34 | 30937.2832 | 275 | 76.28 | 20975.72 | 360 | 125 | 13377.6 | -6111.72
70 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Plain Bend 4" | No. | 800 | 146.48 | 117184 | 800 | 146.48 | 117184 | 80 | 146.48 | 11718.4 | 800 | 120.13 | 96105.3359 | 425 | 121.83 | 51777.96 | 720 | 375 | 105465.6 | 65406.04
71 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Plain Tee 2" | No. | 200 | 35 | 7000 | 200 | 35 | 7000 | 20 | 35 | 700 | 200 | 40.14 | 8028.02 | 0 | 0 | 0 | 180 | 200 | 6300 | 7000
72 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Plain Tee 4" | No. | 225 | 100.98 | 22720.5 | 225 | 100.98 | 22720.5 | 23 | 100.98 | 2322.54 | 225 | 174.62 | 39290.1885 | 19 | 230.29 | 4375.45 | 202 | 206 | 20397.96 | 18345.05
73 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Reducer Socket 4" x 3" | No. | 300 | 88.2 | 26460 | 300 | 88.2 | 26460 | 30 | 88.2 | 2646 | 300 | 98.31 | 29493.864 | 4 | 137.86 | 551.44 | 270 | 296 | 23814 | 25908.56
74 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Reducer Tee 3"x4" | No. | 400 | 523 | 209200 | 400 | 523 | 209200 | 40 | 523 | 20920 | 400 | 158.62 | 63446.3232 | 400 | 158.87 | 63547.5 | 360 | 0 | 188280 | 145652.5
75 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Shoe Bend 1-1/4" | No. | 800 | 80 | 64000 | 800 | 80 | 64000 | 80 | 80 | 6400 | 800 | 21.1 | 16876.8512 | 608 | 21.5 | 13069.73 | 720 | 192 | 57600 | 50930.27
76 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Shoe Bend 3" | No. | 1400 | 33.14 | 46396 | 576 | 33.14 | 19088.64 | 140 | 33.14 | 4639.6 | 576 | 88.77 | 51129.4416 | 782 | 74.1 | 57943.27 | 1260 | 618 | 41756.4 | -11547.27
77 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Shoe Bend 4" | No. | 400 | 120.02 | 48008 | 400 | 120.02 | 48008 | 40 | 120.02 | 4800.8 | 400 | 100.28 | 40111.5488 | 351 | 100.41 | 35244.34 | 360 | 49 | 43207.2 | 12763.66
78 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Shoe Bend 50mm | No. | 67 | 192 | 12864 | 67 | 192 | 12864 | 7 | 192 | 1344 | 67 | 34.96 | 2342.6042 | 54 | 30.9 | 1668.72 | 60 | 13 | 11520 | 11195.28
79 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Single Y 3" | No. | 100 | 60.95 | 6095 | 72 | 60.95 | 4388.4 | 10 | 60.95 | 609.5 | 72 | 174.86 | 12589.56 | 1 | 151.07 | 151.07 | 90 | 99 | 5485.5 | 5943.93
80 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Single Y 4" | No. | 75 | 114.76 | 8607 | 36 | 114.76 | 4131.36 | 8 | 114.76 | 918.08 | 36 | 302.13 | 10876.5612 | 0 | 0 | 0 | 67 | 75 | 7688.92 | 8607
81 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Socket 4" | No. | 400 | 30 | 12000 | 384 | 30 | 11520 | 40 | 30 | 1200 | 384 | 84.62 | 32492.2056 | 314 | 86.98 | 27311.39 | 360 | 86 | 10800 | -15311.39
82 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Solvent (500 ml.) - | No. | 40 | 180 | 7200 | 40 | 180 | 7200 | 4 | 180 | 720 | 39.4 | 290.86 | 11459.9953 | 35 | 292.45 | 10235.76 | 36 | 5 | 6480 | -3035.76
83 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)PVC Tee 11/4" | No. | 67 | 18.9 | 1266.3 | 35 | 18.9 | 661.5 | 7 | 18.9 | 132.3 | 35 | 40.52 | 1418.1563 | 16 | 39.72 | 635.56 | 60 | 51 | 1134 | 630.74
84 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Pvc Tee 50mm | No. | 200 | 100 | 20000 | 200 | 100 | 20000 | 20 | 100 | 2000 | 200 | 42.59 | 8517.9728 | 201 | 42.51 | 8543.83 | 180 | -1 | 18000 | 11456.17
85 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Rubber Lubricant (500 ml) | No. | 36 | 67 | 2412 | 36 | 67 | 2412 | 4 | 67 | 268 | 36 | 123.84 | 4458.2748 | 34 | 113.48 | 3858.2 | 32 | 2 | 2144 | -1446.2
86 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Saddle 1 1/4" | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Tag | Kgs | 20 | 84 | 1680 | 20 | 84 | 1680 | 2 | 84 | 168 | 19.9 | 242.07 | 4817.2106 | 5.8 | 260.78 | 1512.5 | 18 | 14.2 | 1512 | 167.5
88 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Teflon Tape | No. | 2400 | 6.24 | 14976 | 2400 | 6.24 | 14976 | 240 | 6.24 | 1497.6 | 2400 | 20.32 | 48774 | 1588 | 19.31 | 30670.02 | 2160 | 812 | 13478.4 | -15694.02
89 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Threaded Rod 8mm x 1mtr | No. | 400 | 25 | 10000 | 400 | 25 | 10000 | 40 | 25 | 1000 | 400 | 37.26 | 14902.08 | 365 | 39.51 | 14421.34 | 360 | 35 | 9000 | -4421.34
90 | D-Internal Plumbing -(PPR-C,PVC,ASTM) | 10 | Started | Material | (M)Washer 8mm | No. | 4800 | 1 | 4800 | 4764 | 1 | 4764 | 480 | 1 | 480 | 4764 | 1.15 | 5493.984 | 4318 | 1.16 | 5005.3 | 4320 | 482 | 4320 | -205.3