## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ALTUS
Task Name : Club House-Plinth Beam Steel Work
Page 1 of 1
Total Records: 6 Records 1 to 6
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | Club House-Plinth Beam Steel Work | 0 | Started | Material | (M)Binding Wire | Kgs | 11 | 62.85 | 691.35 | 0 | 0 | 0 | 0 | 62.85 | 0 | 0 | 0 | 0 | 11 | 78.02 | 858.22 | 11 | 0 | 691.35 | -166.87
2 | Club House-Plinth Beam Steel Work | 0 | Started | Material | (M)Steel Bars 10mm | Kgs | 33.04 | 50.85 | 1680.08 | 0 | 0 | 0 | 0 | 50.85 | 0 | 0 | 0 | 0 | 33 | 60.55 | 1998.15 | 33.04 | 0.04 | 1680.084 | -318.066
3 | Club House-Plinth Beam Steel Work | 0 | Started | Material | (M)Steel Bars 12mm | Kgs | 246.85 | 50.85 | 12552.32 | 0 | 0 | 0 | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246.85 | 246.85 | 12552.323 | 12552.3225
4 | Club House-Plinth Beam Steel Work | 0 | Started | Material | (M)Steel Bars 16mm | Kgs | 280.02 | 50.85 | 14239.02 | 0 | 0 | 0 | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280.02 | 280.02 | 14239.017 | 14239.017
5 | Club House-Plinth Beam Steel Work | 0 | Started | Material | (M)Steel Bars 20mm | Kgs | 40.99 | 50.85 | 2084.34 | 0 | 0 | 0 | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.99 | 40.99 | 2084.342 | 2084.3415
6 | Club House-Plinth Beam Steel Work | 0 | Started | Material | (M)Steel Bars 8mm | Kgs | 328.88 | 50.85 | 16723.55 | 0 | 0 | 0 | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328.88 | 328.88 | 16723.548 | 16723.548