## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : Ground Floor RCC - 1st Slab (parking)
Page 1 of 1
Total Records: 25 Records 1 to 25
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | A - Ground Floor RCC - 1st Slab BUA (L) | 7.09 | Started | Labour | (L)Hacking Work | Sq.Ft | 18375.172 | 0 | 0 | 0 | 0 | 0 | 1303 | 0 | 0 | 18375.172 | 2.95 | 54206.75 | 0 | 0 | 0 | 17072.172 | 18375.172 | 0 | 0
2 | A - Ground Floor RCC - 1st Slab BUA (L) | 7.09 | Started | Labour | (L)RCC Superstructure (B-up area) | Sq.Ft | 18375.172 | 0 | 0 | 0 | 0 | 0 | 1303 | 0 | 0 | 18375.172 | 159.3 | 2927164.9 | 15560 | 159.3 | 2478708 | 17072.172 | 2815.172 | 0 | -2478708
3 | A - Ground Floor RCC - 1st Slab BUA (L) | 7.09 | Started | Labour | (L)Schedule & Quality | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | A - Ground Floor RCC - 1st Slab BUA (L) | 7.09 | Started | Labour | (L)Schedule- BC | Sq.Ft | 18375.172 | 10 | 183751.72 | 0 | 0 | 0 | 1303 | 10 | 13030 | 18375.172 | 11.8 | 216827.02 | 0 | 0 | 0 | 17072.172 | 18375.172 | 170721.72 | 183751.72
5 | 1st Slab Column- Grid to 1st Slab RCC Steel Work New | 10 | Started | Material | (M)Binding Wire | Kgs | 286 | 61.9 | 17703.4 | 286 | 61.9 | 17703.4 | 29 | 61.9 | 1795.1 | 286 | 76.94 | 22004.84 | 285.61 | 75.09 | 21445.22 | 257 | 0.39 | 15908.3 | -3741.82
6 | 1st Slab Column- Grid to 1st Slab RCC Steel Work New | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 3459 | 100 | 345900 | 3459 | 100 | 345900 | 346 | 100 | 34600 | 3449 | 63.22 | 218028.535 | 0 | 0 | 0 | 3113 | 3459 | 311300 | 345900
7 | 1st Slab Column- Grid to 1st Slab RCC Steel Work New | 10 | Started | Material | (M)Steel Bars 12mm | Kgs | 274 | 43 | 11782 | 274 | 43 | 11782 | 27 | 43 | 1161 | 274 | 63.22 | 17320.91 | 0 | 0 | 0 | 247 | 274 | 10621 | 11782
8 | 1st Slab Column- Grid to 1st Slab RCC Steel Work New | 10 | Started | Material | (M)Steel Bars 16mm | Kgs | 4352 | 51 | 221952 | 4206.26 | 51 | 214519.26 | 435 | 51 | 22185 | 766.26 | 63.22 | 48439.1259 | 3034.08 | 60.86 | 184654.11 | 3917 | 1317.92 | 199767 | 37297.89
9 | 1st Slab Column- Grid to 1st Slab RCC Steel Work New | 10 | Started | Material | (M)Steel Bars 20mm | Kgs | 11007 | 1000 | 11007000 | 11007 | 1000 | 11007000 | 1101 | 1000 | 1101000 | 11007 | 63.22 | 695807.505 | 10666.68 | 61.38 | 654747.4842 | 9906 | 340.32 | 9906000 | 10352252.5158
10 | 1st Slab Column- Grid to 1st Slab RCC Steel Work New | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 4758 | 100 | 475800 | 4553 | 100 | 455300 | 476 | 100 | 47600 | 4553 | 64.4 | 293190.435 | 4758 | 61.88 | 294447.97 | 4282 | 0 | 428200 | 181352.03
11 | 1st Slab Column- Plinth to 1st Slab Concrete Work | 10 | Started | Material | (M)Cement Loose 53 Grade | Metric Tonnes | 7 | 3880 | 27160 | 7 | 3880 | 27160 | 1 | 3880 | 3880 | 5.05 | 7400 | 37370.0005 | 0 | 0 | 0 | 6 | 7 | 23280 | 27160
12 | 1st Slab Column- Plinth to 1st Slab Concrete Work | 10 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Downpour) | Cu.Mtrs | 55 | 4400 | 242000 | 55 | 4400 | 242000 | 6 | 4400 | 26400 | 55 | 5000 | 275000 | 36 | 5046.74 | 181682.64 | 49 | 19 | 215600 | 60317.36
13 | 1st Slab Column- Plinth to 1st Slab Concrete Work | 10 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Pumpable) | Cu.Mtrs | 29.93 | 100 | 2993 | 29.93 | 100 | 2993 | 3 | 100 | 300 | 29.93 | 5294.9 | 158476.491 | 25.88 | 5261.99 | 136180.3012 | 26.93 | 4.05 | 2693 | -133187.3012
14 | 1st Slab Column- Plinth to 1st Slab Concrete Work | 10 | Started | Material | (M)Sand-Metal Mix M35 (Pumpable) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | A-1st Slab RCC-Slab, Beam,Staircase | 10 | Started | Material | (M)Binding Wire | Kgs | 470 | 62.85 | 29539.5 | 470 | 62.85 | 29539.5 | 47 | 62.85 | 2953.95 | 470 | 79.06 | 37158.2 | 431.44 | 75.08 | 32394.38 | 423 | 38.56 | 26585.55 | -2854.88
16 | A-1st Slab RCC-Slab, Beam,Staircase | 10 | Started | Material | (M)Steel Bar 25mm | Kgs | 2562.18 | 50.85 | 130286.85 | 0 | 0 | 0 | 256 | 50.85 | 13017.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2306.18 | 2562.18 | 117269.253 | 130286.853
17 | A-1st Slab RCC-Slab, Beam,Staircase | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 17530.24 | 50.85 | 891412.7 | 0 | 0 | 0 | 1753 | 50.85 | 89140.05 | 0 | 0 | 0 | 15722.865 | 61.18 | 961984.9316 | 15777.24 | 1807.375 | 802272.654 | -70572.2276
18 | A-1st Slab RCC-Slab, Beam,Staircase | 10 | Started | Material | (M)Steel Bars 12mm | Kgs | 1183.12 | 50.85 | 60161.65 | 0 | 0 | 0 | 118 | 50.85 | 6000.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1065.12 | 1183.12 | 54161.352 | 60161.652
19 | A-1st Slab RCC-Slab, Beam,Staircase | 10 | Started | Material | (M)Steel Bars 16mm | Kgs | 5847.41 | 50.85 | 297340.8 | 0 | 0 | 0 | 585 | 50.85 | 29747.25 | 0 | 0 | 0 | 4550.56 | 60.89 | 277083.54 | 5262.41 | 1296.85 | 267593.549 | 20257.2585
20 | A-1st Slab RCC-Slab, Beam,Staircase | 10 | Started | Material | (M)Steel Bars 20mm | Kgs | 5280.44 | 50.85 | 268510.37 | 0 | 0 | 0 | 528 | 50.85 | 26848.8 | 0 | 0 | 0 | 4444.45 | 61.75 | 274444.79 | 4752.44 | 835.99 | 241661.574 | -5934.416
21 | A-1st Slab RCC-Slab, Beam,Staircase | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 6789.85 | 50.85 | 345263.87 | 0 | 0 | 0 | 679 | 50.85 | 34527.15 | 0 | 0 | 0 | 6789.85 | 61.9 | 420285.628 | 6110.85 | 0 | 310736.723 | -75021.7555
22 | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | 10 | Started | Material | (M)Cement Loose 53 Grade | Metric Tonnes | 140 | 3880 | 543200 | 140 | 3880 | 543200 | 14 | 3880 | 54320 | 140 | 7500 | 1050000 | 0 | 0 | 0 | 126 | 140 | 488880 | 543200
23 | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | 10 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Downpour) | Cu.Mtrs | 124 | 4400 | 545600 | 124 | 4400 | 545600 | 12 | 4400 | 52800 | 124 | 5071.19 | 628827.2977 | 25.5 | 5057.29 | 128960.79 | 112 | 98.5 | 492800 | 416639.21
24 | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | 10 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Pumpable) | Cu.Mtrs | 240.12 | 100 | 24012 | 240.12 | 100 | 24012 | 24 | 100 | 2400 | 238.4745 | 5253.83 | 1252904.7534 | 240.12 | 5261.99 | 1263509.0388 | 216.12 | 0 | 21612 | -1239497.0388
25 | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | 10 | Started | Material | (M)Sand-Metal Mix M35 (Downpour) | Cu.Mtrs | 10 | 2125 | 21250 | 10 | 2125 | 21250 | 1 | 2125 | 2125 | 10 | 3400 | 34000 | 0 | 0 | 0 | 9 | 10 | 19125 | 21250