## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : RCC Work
Page 1 of 1
Total Records: 9 Records 1 to 9
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | Pumproom-PCC Work | 10 | Started | Material | (M)Ready Mix Concrete M-15 Downpour | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Pumproom-PCC Work | 10 | Started | Material | (M)Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 26.18 | 2125 | 55632.5 | 26.18 | 2125 | 55632.5 | 3 | 2125 | 6375 | 26.18 | 3275 | 85739.4817 | 0 | 0 | 0 | 23.18 | 26.18 | 49257.5 | 55632.5
3 | Pumproom-Raft Concrete M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33.08 | 0 | 0 | 0 | 33.08
4 | Pumproom-Raft Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 50.79 | 3355.93 | 170447.68 | 50.79 | 3355.93 | 170447.68 | 5 | 3355.93 | 16779.65 | 50.79 | 3400 | 172686.0102 | 0 | 0 | 0 | 45.79 | 50.79 | 153668.035 | 170447.6847
5 | Pumproom-Raft Steel | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 3047.1 | 50.85 | 154945.04 | 0 | 0 | 0 | 305 | 50.85 | 15509.25 | 0 | 0 | 0 | 2444.43 | 60.55 | 148010.2365 | 2742.1 | 602.67 | 139435.785 | 6934.7985
6 | Pumproom-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pumproom-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 32.15 | 3355.93 | 107893.15 | 32.15 | 3355.93 | 107893.15 | 3 | 3355.93 | 10067.79 | 32.15 | 3400 | 109310.0064 | 0 | 0 | 0 | 29.15 | 32.15 | 97825.36 | 107893.1495
8 | Pumproom-RCC Pardi Steel | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 3732.79 | 50.85 | 189812.37 | 0 | 0 | 0 | 373 | 50.85 | 18967.05 | 0 | 0 | 0 | 2444.43 | 60.55 | 148010.2365 | 3359.79 | 1288.36 | 170845.322 | 41802.135
9 | Pumproom-RCC Column Steel | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 62.38 | 50.85 | 3172.02 | 0 | 0 | 0 | 6 | 50.85 | 305.1 | 0 | 0 | 0 | 62.38 | 62 | 3867.56 | 56.38 | 0 | 2866.923 | -695.537