## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : RCC WORK
Page 1 of 1
Total Records: 12 Records 1 to 12
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | UGWT- RCC Work (L) | 10 | Started | Labour | (L)UGWT Labour | Ltrs | 267772 | 0 | 0 | 0 | 0 | 0 | 26777 | 0 | 0 | 267772 | 5.02 | 1342876.58 | 160663.2 | 5.02 | 805725.96 | 240995 | 107108.8 | 0 | -805725.96
2 | UGWT-PCC Work-M15 | 10 | Started | Material | (M)Ready Mix Concrete M-15 Grade( D/P) - | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | -0.06
3 | UGWT-PCC Work-M15 | 10 | Started | Material | (M)Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 20.46 | 2125 | 43477.5 | 2 | 2125 | 4250 | 2 | 2125 | 4250 | 2 | 3275 | 6549.9986 | 0 | 0 | 0 | 18.46 | 20.46 | 39227.5 | 43477.5
4 | UGWT-Raft Steel | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 2247.7 | 50.85 | 114295.55 | 0 | 0 | 0 | 225 | 50.85 | 11441.25 | 0 | 0 | 0 | 0 | 0 | 0 | 2022.7 | 2247.7 | 102854.295 | 114295.545
5 | UGWT-Raft Concrete M25 | 10 | Started | Material | (M)Cement Loose 53 Grade | Metric Tonnes | 2.392 | 3880 | 9280.96 | 2.392 | 3880 | 9280.96 | 0 | 3880 | 0 | 1.543 | 7300 | 11263.8998 | 0 | 0 | 0 | 2.392 | 2.392 | 9280.96 | 9280.96
6 | UGWT-Raft Concrete M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | UGWT-Raft Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 8.86 | 2000 | 17720 | 8.86 | 2000 | 17720 | 1 | 2000 | 2000 | 8.86 | 3400 | 30123.9938 | 0 | 0 | 0 | 7.86 | 8.86 | 15720 | 17720
8 | UGWT-Raft Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 30.09 | 3355.93 | 100979.93 | 30.09 | 3355.93 | 100979.93 | 3 | 3355.93 | 10067.79 | 30.09 | 3400 | 102306.003 | 0 | 0 | 0 | 27.09 | 30.09 | 90912.144 | 100979.9337
9 | UGWT-RCC Column Steel | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 208.24 | 50.85 | 10589 | 0 | 0 | 0 | 21 | 50.85 | 1067.85 | 0 | 0 | 0 | 208.24 | 62 | 12910.88 | 187.24 | 0 | 9521.154 | -2321.876
10 | UGWT-RCC Pardi Steel | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 5873.83 | 50.85 | 298684.26 | 0 | 0 | 0 | 587 | 50.85 | 29848.95 | 0 | 0 | 0 | 2444.43 | 62.84 | 153607.9812 | 5286.83 | 3429.4 | 268835.306 | 145076.2743
11 | UGWT-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -131 | 0 | 0 | 0 | 131
12 | UGWT-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 45.25 | 3355.93 | 151855.83 | 45.25 | 3355.93 | 151855.83 | 5 | 3355.93 | 16779.65 | 45.25 | 3400 | 153850.0091 | 0 | 0 | 0 | 40.25 | 45.25 | 135076.183 | 151855.8325