## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : RCC WORK
Page 1 of 1
Total Records: 10 Records 1 to 10
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | STP-170KLD-RCC Work (L) | 10 | Started | Labour | (L)RCC Work STP | Ltrs | 221129.68 | 0 | 0 | 0 | 0 | 0 | 22113 | 0 | 0 | 221129.68 | 5.01 | 1108965.34 | 210073.196 | 5.02 | 1053517.1 | 199016.68 | 11056.484 | 0 | -1053517.1
2 | STP-170KLD-PCC Work | 10 | Started | Material | (M)Ready Mix Concrete M-15 Grade | Cu.Mtrs | 23.02 | 2914 | 67080.28 | 0 | 0 | 0 | 2 | 2914 | 5828 | 0 | 0 | 0 | 0 | 0 | 0 | 21.02 | 23.02 | 61252.28 | 67080.28
3 | STP-170KLD-Raft Steel | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 2560.36 | 50.85 | 130194.31 | 0 | 0 | 0 | 256 | 50.85 | 13017.6 | 0 | 0 | 0 | 2560.36 | 62.84 | 160893.0224 | 2304.36 | 0 | 117176.706 | -30698.7164
4 | STP-170KLD-Raft Concrete M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33.08 | 0 | 0 | 0 | 33.08
5 | STP-170KLD-Raft Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 44.47 | 6000 | 266820 | 20 | 6000 | 120000 | 4 | 6000 | 24000 | 20 | 3400 | 68000 | 0 | 0 | 0 | 40.47 | 44.47 | 242820 | 266820
6 | STP-170KLD-RCC Pardi Steel | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 7310.11 | 50.85 | 371719.09 | 0 | 0 | 0 | 731 | 50.85 | 37171.35 | 0 | 0 | 0 | 4888.86 | 60.55 | 296020.473 | 6579.11 | 2421.25 | 334547.744 | 75698.6205
7 | STP-170KLD-RCC Pardi Steel | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 91.5 | 50.85 | 4652.78 | 0 | 0 | 0 | 9 | 50.85 | 457.65 | 0 | 0 | 0 | 91.5 | 62 | 5673 | 82.5 | 0 | 4195.125 | -1020.225
8 | STP-170KLD-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | STP-170KLD-RCC Pardi Concrete M25 | 10 | Started | Material | (M)Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 59.91 | 3355.93 | 201053.77 | 59.91 | 3355.93 | 201053.77 | 6 | 3355.93 | 20135.58 | 59.91 | 3400 | 203694.006 | 0 | 0 | 0 | 53.91 | 59.91 | 180918.186 | 201053.7663
10 | STP-170KLD-RCC Column Steel | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 270.35 | 50.85 | 13747.3 | 0 | 0 | 0 | 27 | 50.85 | 1372.95 | 0 | 0 | 0 | 270.35 | 62 | 16761.7 | 243.35 | 0 | 12374.348 | -3014.4025