## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA ARCADIA - A BUILDING
Task Name : 1st Floor RCC 2nd Slab (Parking)
Page 1 of 1
Total Records: 26 Records 1 to 26
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | A - 1st Floor RCC 2nd Slab BUA (L) | 10.24 | Started | Labour | (L)Hacking Work | Sq.Ft | 12655.012 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 12655.012 | 2.95 | 37332.29 | 0 | 0 | 0 | 11359.012 | 12655.012 | 0 | 0
2 | A - 1st Floor RCC 2nd Slab BUA (L) | 10.24 | Started | Labour | (L)RCC Superstructure (B-up area) | Sq.Ft | 12655.012 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 12655.012 | 159.3 | 2015943.42 | 0 | 0 | 0 | 11359.012 | 12655.012 | 0 | 0
3 | A - 1st Floor RCC 2nd Slab BUA (L) | 10.24 | Started | Labour | (L)Schedule & Quality | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | A - 1st Floor RCC 2nd Slab BUA (L) | 10.24 | Started | Labour | (L)Schedule- BC | Sq.Ft | 12655.012 | 10 | 126550.12 | 0 | 0 | 0 | 1296 | 10 | 12960 | 12655.012 | 11.8 | 149329.14 | 0 | 0 | 0 | 11359.012 | 12655.012 | 113590.12 | 126550.12
5 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Binding Wire | Kgs | 226.64 | 62.85 | 14244.32 | 3.84 | 62.85 | 241.34 | 23 | 62.85 | 1445.55 | 3.84 | 79.06 | 303.5904 | 187.13 | 78.71 | 14729.0023 | 203.64 | 39.51 | 12798.774 | -484.6783
6 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Steel Bar 25mm | Kgs | 3606 | 1000 | 3606000 | 20 | 1000 | 20000 | 361 | 1000 | 361000 | 20 | 68.32 | 1366.3 | 20 | 68.31 | 1366.2 | 3245 | 3586 | 3245000 | 3604633.8
7 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 1541 | 50.85 | 78359.85 | 0 | 0 | 0 | 154 | 50.85 | 7830.9 | 0 | 0 | 0 | 0 | 0 | 0 | 1387 | 1541 | 70528.95 | 78359.85
8 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Steel Bars 12mm | Kgs | 289 | 50.85 | 14695.65 | 200 | 50.85 | 10170 | 29 | 50.85 | 1474.65 | 200 | 63.22 | 12643 | 0 | 0 | 0 | 260 | 289 | 13221 | 14695.65
9 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Steel Bars 16mm | Kgs | 2112 | 51 | 107712 | 90 | 51 | 4590 | 211 | 51 | 10761 | 90 | 68.31 | 6148.341 | 2112 | 62.34 | 131662.08 | 1901 | 0 | 96951 | -23950.08
10 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Steel Bars 20mm | Kgs | 6912 | 50.85 | 351475.2 | 0 | 0 | 0 | 691 | 50.85 | 35137.35 | 0 | 0 | 0 | 5866.674 | 62.27 | 365300.0122 | 6221 | 1045.326 | 316337.85 | -13824.8122
11 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Steel Bars 32mm | Kgs | 424 | 100 | 42400 | 0 | 0 | 0 | 42 | 100 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 382 | 424 | 38200 | 42400
12 | Column Steel - 1st Slab to 2nd Slab | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 3992 | 100 | 399200 | 10 | 100 | 1000 | 399 | 100 | 39900 | 10 | 69.49 | 694.94 | 3992 | 63.67 | 254153.94 | 3593 | 0 | 359300 | 145046.06
13 | 1st Floor RCC 2nd Slab (Parking) Slab,Beam,Staircase Steel | 10 | Started | Material | (M)Binding Wire | Kgs | 135.99 | 62.85 | 8546.97 | 50 | 62.85 | 3142.5 | 14 | 62.85 | 879.9 | 50 | 79.06 | 3953 | 108.2 | 78.71 | 8516.422 | 121.99 | 27.79 | 7667.072 | 30.5495
14 | 1st Floor RCC 2nd Slab (Parking) Slab,Beam,Staircase Steel | 10 | Started | Material | (M)Steel Bar 25mm | Kgs | 1245 | 50.85 | 63308.25 | 0 | 0 | 0 | 125 | 50.85 | 6356.25 | 0 | 0 | 0 | 916.31 | 68.32 | 62602.2992 | 1120 | 328.69 | 56952 | 705.9508
15 | 1st Floor RCC 2nd Slab (Parking) Slab,Beam,Staircase Steel | 10 | Started | Material | (M)Steel Bars 10mm | Kgs | 9925.33 | 50.85 | 504703.03 | 0 | 0 | 0 | 993 | 50.85 | 50494.05 | 0 | 0 | 0 | 448.88 | 62.84 | 28207.6192 | 8932.33 | 9476.45 | 454208.981 | 476495.4113
16 | 1st Floor RCC 2nd Slab (Parking) Slab,Beam,Staircase Steel | 10 | Started | Material | (M)Steel Bars 12mm | Kgs | 6111.44 | 50.85 | 310766.72 | 0 | 0 | 0 | 611 | 50.85 | 31069.35 | 0 | 0 | 0 | 0 | 0 | 0 | 5500.44 | 6111.44 | 279697.374 | 310766.724
17 | 1st Floor RCC 2nd Slab (Parking) Slab,Beam,Staircase Steel | 10 | Started | Material | (M)Steel Bars 16mm | Kgs | 4185.41 | 50.85 | 212828.1 | 0 | 0 | 0 | 419 | 50.85 | 21306.15 | 0 | 0 | 0 | 0 | 0 | 0 | 3766.41 | 4185.41 | 191521.949 | 212828.0985
18 | 1st Floor RCC 2nd Slab (Parking) Slab,Beam,Staircase Steel | 10 | Started | Material | (M)Steel Bars 20mm | Kgs | 2360 | 50.85 | 120006 | 52 | 50.85 | 2644.2 | 236 | 50.85 | 12000.6 | 52 | 63.21 | 3287.1748 | 0 | 0 | 0 | 2124 | 2360 | 108005.4 | 120006
19 | 1st Floor RCC 2nd Slab (Parking) Slab,Beam,Staircase Steel | 10 | Started | Material | (M)Steel Bars 8mm | Kgs | 3739.05 | 50.85 | 190130.69 | 0 | 0 | 0 | 374 | 50.85 | 19017.9 | 0 | 0 | 0 | 1659.35 | 63.67 | 105650.8145 | 3365.05 | 2079.7 | 171112.793 | 84479.878
20 | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | 0 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Downpour) | Cu.Mtrs | 23 | 4400 | 101200 | 23 | 4400 | 101200 | 0 | 4400 | 0 | 23 | 5442 | 125165.9922 | 0 | 0 | 0 | 23 | 23 | 101200 | 101200
21 | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | 0 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Pumpable) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | 0 | Started | Material | (M)Sand-Metal Mix M35 (Downpour) | Cu.Mtrs | 24 | 2125 | 51000 | 24 | 2125 | 51000 | 0 | 2125 | 0 | 24 | 3600 | 86399.988 | 0 | 0 | 0 | 24 | 24 | 51000 | 51000
23 | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | 0 | Started | Material | (M)Sand-Metal Mix M35 (Pumpable) | Cu.Mtrs | 23.32 | 2175 | 50721 | 23.32 | 2175 | 50721 | 0 | 2175 | 0 | 23.32 | 3600 | 83951.986 | 0 | 0 | 0 | 23.32 | 23.32 | 50721 | 50721
24 | A 2nd Slab (Parking) RCC-Slab,Beam,Staircase M35 | 0 | Started | Material | (M)Cement Loose 53 Grade | Metric Tonnes | 23.872 | 3880 | 92623.36 | 23.872 | 3880 | 92623.36 | 0 | 3880 | 0 | 23.872 | 7300 | 174265.5976 | 0 | 0 | 0 | 23.872 | 23.872 | 92623.36 | 92623.36
25 | A 2nd Slab (Parking) RCC-Slab,Beam,Staircase M35 | 0 | Started | Material | (M)Ready Mix Concrete M-35 Grade (Pumpable) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | A 2nd Slab (Parking) RCC-Slab,Beam,Staircase M35 | 0 | Started | Material | (M)Sand-Metal Mix M35 (Pumpable) | Cu.Mtrs | 240.39 | 2175 | 522848.25 | 94.6 | 2175 | 205755 | 0 | 2175 | 0 | 94.6 | 3600 | 340559.9507 | 0 | 0 | 0 | 240.39 | 240.39 | 522848.25 | 522848.25