## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : GANGA ASMI
Task Name : 1st Floor
Page 1 of 1
Total Records: 18 Records 1 to 18
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | CEMENT | (M)Cement 43 Grade | Bags | 8 | 375 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 3000 | 3000 | 1st Flr Fire Staircase Flooring | 1 | Units
2 | CONSUMABLE/MISC MATERIAL | (M)Araldite | Kgs | 2 | 1400 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2800 | 2800 | 1st Flr Fire Staircase Flooring | 1 | Units
3 | CONSUMABLE/MISC MATERIAL | (M)HCL Acid | Ltrs | 8 | 6 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 48 | 48 | 1st Flr Fire Staircase Flooring | 1 | Units
4 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (20kg bag) | Kgs | 158 | 12.5 | 1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 158 | 1975 | 1975 | 1st Flr Fire Staircase Flooring | 1 | Units
5 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 2 | 100 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 200 | 200 | 1st Flr Fire Staircase Flooring | 1 | Units
6 | SAND & METAL | (M)Crush Sand | Cu.Ft | 31 | 33 | 1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 1023 | 1023 | 1st Flr Fire Staircase Flooring | 1 | Units
7 | SAND & METAL | (M)M Sand | Cu.Ft | 31 | 65 | 2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 2015 | 2015 | 1st Flr Fire Staircase Flooring | 1 | Units
8 | TILES & NATURAL STONE | (M)Kota Tappa 48"x12" (47"x11") - Sq.Ft | Sq.Ft | 80 | 150 | 12000 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 12000 | 12000 | 1st Flr Fire Staircase Flooring | 1 | Units
9 | TILES & NATURAL STONE | (M)Kota Tappa 54" x 12" (53"x11") | Sq.Ft | 163 | 100 | 16300 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 163 | 16300 | 16300 | 1st Flr Fire Staircase Flooring | 1 | Units
10 | 11 TILING WORK | (L)Sadarali Granite Flooring (M) | Sq.Ft | 227.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227.34 | 227.34 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units
11 | B.C. Building Common Items | (L)S. Halli Edge Polish- BCo | R.Ft | 177.12 | 6 | 1062.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 177.12 | 1062.72 | 1062.72 | 1st Flr Fire Staircase Flooring | 1 | Units
12 | No category | (L)Sadarali Granite Flooring (L) | Sq.Ft | 227.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227.34 | 227.34 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units
13 | No category | (L)Sadarali Granite Riser (L) | R.Ft | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 167 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units
14 | No category | (L)Sadarali Granite Riser (M) | Sq.Ft | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units
15 | No category | (L)Sadarali Granite Skirting (L) | R.Ft | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units
16 | No category | (L)Sadarali Granite Skirting (M) | Sq.Ft | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units
17 | No category | (L)Sadarali Granite Tread (L) | R.Ft | 177.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 177.12 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units
18 | No category | (L)sadarali Granite Tread (M) | Sq.Ft | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 163 | 0 | 0 | 1st Flr Fire Staircase Flooring | 1 | Units