## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : GANGA ASMI
Task Name : Wing-1 2nd Floor
Page 1 of 1
Total Records: 218 Records 1 to 218
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 203 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
2 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.0988 | 190 | 208.77 | 1.0988 | 1.0988 | 224.98 | 247.21 | 1.0988 | 0 | 0 | 0 | 0 | 1.0988 | -38.44 | 208.77 | Wing -1 (2BHK) Flat 203 Common Toilet Dado(Light) | 140.87 | Sq.Ft
3 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2328 | 190 | 44.23 | 0.2328 | 0.2328 | 224.98 | 52.38 | 0.2328 | 0 | 0 | 0 | 0 | 0.2328 | -8.14 | 44.23 | Wing -1 (2BHK) Flat 203 Kitchen Dado (M) | 29.84 | Sq.Ft
4 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 203 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
5 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.2688 | 190 | 241.07 | 1.2688 | 1.2688 | 224.98 | 285.46 | 1.2688 | 0 | 0 | 0 | 0 | 1.2688 | -44.38 | 241.07 | Wing -1 (2BHK) Flat 203 Master Toilet Dado(Light) | 162.67 | Sq.Ft
6 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 204 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
7 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.061 | 190 | 201.59 | 1.061 | 1.061 | 224.98 | 238.7 | 1.061 | 0 | 0 | 0 | 0 | 1.061 | -37.11 | 201.59 | Wing -1 (2BHK) Flat 204 Common Toilet Dado(Light) | 136.03 | Sq.Ft
8 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2476 | 190 | 47.04 | 0.2476 | 0.2476 | 224.98 | 55.71 | 0.2476 | 0 | 0 | 0 | 0 | 0.2476 | -8.66 | 47.04 | Wing -1 (2BHK) Flat 204 Kitchen Dado (M) | 31.74 | Sq.Ft
9 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 204 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
10 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.2122 | 190 | 230.32 | 1.2122 | 1.2122 | 224.98 | 272.72 | 1.2122 | 0 | 0 | 0 | 0 | 1.2122 | -42.4 | 230.32 | Wing -1 (2BHK) Flat 204 Master Toilet Dado(Light) | 155.41 | Sq.Ft
11 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 205 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
12 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.061 | 190 | 201.59 | 1.061 | 1.061 | 224.98 | 238.7 | 1.061 | 0 | 0 | 0 | 0 | 1.061 | -37.11 | 201.59 | Wing -1 (2BHK) Flat 205 Common Toilet Dado(Light) | 136.03 | Sq.Ft
13 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2476 | 190 | 47.04 | 0.2476 | 0.2476 | 224.98 | 55.71 | 0.2476 | 0 | 0 | 0 | 0 | 0.2476 | -8.66 | 47.04 | Wing -1 (2BHK) Flat 205 Kitchen Dado (M) | 31.74 | Sq.Ft
14 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 205 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
15 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.2122 | 190 | 230.32 | 1.2122 | 1.2122 | 224.98 | 272.72 | 1.2122 | 0 | 0 | 0 | 0 | 1.2122 | -42.4 | 230.32 | Wing -1 (2BHK) Flat 205 Master Toilet Dado(Light) | 155.41 | Sq.Ft
16 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 208 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
17 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.061 | 190 | 201.59 | 1.061 | 1.061 | 224.98 | 238.7 | 0.2501 | 0 | 0 | 0 | 0 | 1.061 | -37.11 | 201.59 | Wing -1 (2BHK) Flat 208 Common Toilet Dado(Light) | 136.03 | Sq.Ft
18 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2476 | 190 | 47.04 | 0.2476 | 0.2476 | 224.98 | 55.71 | 0.2476 | 0 | 0 | 0 | 0 | 0.2476 | -8.66 | 47.04 | Wing -1 (2BHK) Flat 208 Kitchen Dado (M) | 31.74 | Sq.Ft
19 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing -1 (2BHK) Flat 208 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
20 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.212 | 190 | 230.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.212 | 1.212 | 230.28 | 230.28 | Wing -1 (2BHK) Flat 208 Master Toilet Dado(Light) | 155.38 | Sq.Ft
21 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0567 | 0.0567 | 10.77 | 10.77 | Wing -1 (2BHK) Flat 209 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
22 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.0988 | 190 | 208.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0988 | 1.0988 | 208.77 | 208.77 | Wing -1 (2BHK) Flat 209 Common Toilet Dado(Light) | 140.87 | Sq.Ft
23 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2475 | 190 | 47.03 | 0.2475 | 0.2475 | 224.98 | 55.68 | 0.2475 | 0 | 0 | 0 | 0 | 0.2475 | -8.66 | 47.03 | Wing -1 (2BHK) Flat 209 Kitchen Dado (M) | 31.73 | Sq.Ft
24 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0567 | 0.0567 | 10.77 | 10.77 | Wing -1 (2BHK) Flat 209 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
25 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.2688 | 190 | 241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2688 | 1.2688 | 241.07 | 241.07 | Wing -1 (2BHK) Flat 209 Master Toilet Dado(Light) | 162.67 | Sq.Ft
26 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8606 | 190 | 163.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8606 | 0.8606 | 163.51 | 163.51 | Wing .1 (2BHK) Flat 203 Utility .Dado (M) | 110.33 | Sq.Ft
27 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.1284 | 190 | 24.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1284 | 0.1284 | 24.4 | 24.4 | Wing .1 (2BHK).203 WB Dado (M) | 16.46 | Sq.Ft
28 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.1284 | 190 | 24.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1284 | 0.1284 | 24.4 | 24.4 | Wing .1 (2BHK).204 WB Dado (M) | 16.46 | Sq.Ft
29 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.1284 | 190 | 24.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1284 | 0.1284 | 24.4 | 24.4 | Wing .1 (2BHK).205 WB Dado (M) | 16.46 | Sq.Ft
30 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.1284 | 190 | 24.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1284 | 0.1284 | 24.4 | 24.4 | Wing .1 (2BHK).208 WB Dado (M) | 16.46 | Sq.Ft
31 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.1284 | 190 | 24.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1284 | 0.1284 | 24.4 | 24.4 | Wing .1 (2BHK).209 WB Dado (M) | 16.46 | Sq.Ft
32 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.1366 | 190 | 215.95 | 1.1366 | 1.1366 | 224.98 | 255.71 | 1.1366 | 1.1366 | 234.84 | 266.92 | 0 | 0 | -39.76 | -50.97 | Wing .1 (3BHK) 201 Common Toilet Dado(Light) | 145.72 | Sq.Ft
33 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing .1 (3BHK) 201 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
34 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0 | 0 | 0 | 0 | 0.0567 | -1.98 | 10.77 | Wing .1 (3BHK) 201 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
35 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.1649 | 190 | 221.33 | 1.1649 | 1.1649 | 224.98 | 262.08 | 1.1649 | 0.8634 | 234.84 | 202.76 | 0 | 0.3015 | -40.75 | 18.57 | Wing .1 (3BHK) 201 Master Toilet Dado(Light) | 149.35 | Sq.Ft
36 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0.0567 | 234.92 | 13.32 | 0 | 0 | -1.98 | -2.55 | Wing .1 (3BHK) 202 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
37 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.1364 | 190 | 215.92 | 1.1364 | 1.1364 | 224.98 | 255.67 | 1.1364 | 1.1364 | 234.84 | 266.87 | 0 | 0 | -39.75 | -50.95 | Wing .1 (3BHK) 202 Common Toilet Dado(Light) | 145.69 | Sq.Ft
38 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2583 | 190 | 49.08 | 0.2583 | 0.2583 | 224.98 | 58.11 | 0.2583 | 0.2583 | 234.84 | 60.66 | 0 | 0 | -9.04 | -11.58 | Wing .1 (3BHK) 202 Kitchen Dado (M) | 33.11 | Sq.Ft
39 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0.0567 | 234.84 | 13.32 | 0 | 0 | -1.98 | -2.54 | Wing .1 (3BHK) 202 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
40 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.3633 | 190 | 259.03 | 1.3633 | 1.3633 | 224.98 | 306.72 | 1.3633 | 1.3633 | 234.84 | 320.16 | 0 | 0 | -47.69 | -61.13 | Wing .1 (3BHK) 202 Master Toilet Dado(Light) | 174.78 | Sq.Ft
41 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0.0567 | 234.84 | 13.32 | 0 | 0 | -1.98 | -2.54 | Wing .1 (3BHK) 206 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
42 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.0988 | 190 | 208.77 | 1.0988 | 1.0988 | 224.98 | 247.21 | 1.0988 | 1.0988 | 234.84 | 258.04 | 0 | 0 | -38.44 | -49.27 | Wing .1 (3BHK) 206 Common Toilet Dado(Light) | 140.87 | Sq.Ft
43 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2598 | 190 | 49.36 | 0.2598 | 0.2598 | 224.98 | 58.45 | 0.2598 | 0.2598 | 234.84 | 61.01 | 0 | 0 | -9.09 | -11.65 | Wing .1 (3BHK) 206 Kitchen Dado (M) | 33.31 | Sq.Ft
44 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0.0567 | 234.84 | 13.32 | 0 | 0 | -1.98 | -2.54 | Wing .1 (3BHK) 206 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
45 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.3255 | 190 | 251.85 | 1.3255 | 1.3255 | 224.98 | 298.21 | 1.3255 | 1.3255 | 234.84 | 311.28 | 0 | 0 | -46.37 | -59.44 | Wing .1 (3BHK) 206 Master Toilet Dado(Light) | 169.94 | Sq.Ft
46 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0.0567 | 234.84 | 13.32 | 0 | 0 | -1.98 | -2.54 | Wing .1 (3BHK) 207 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
47 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.1366 | 190 | 215.95 | 1.1366 | 1.1366 | 224.98 | 255.71 | 1.1366 | 1.1366 | 234.84 | 266.92 | 0 | 0 | -39.76 | -50.97 | Wing .1 (3BHK) 207 Common Toilet Dado(Light) | 145.72 | Sq.Ft
48 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2598 | 190 | 49.36 | 0.2598 | 0.2598 | 224.98 | 58.45 | 0.2598 | 0.2598 | 234.84 | 61.01 | 0 | 0 | -9.09 | -11.65 | Wing .1 (3BHK) 207 Kitchen Dado (M) | 33.31 | Sq.Ft
49 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0567 | 190 | 10.77 | 0.0567 | 0.0567 | 224.98 | 12.76 | 0.0567 | 0.0567 | 234.84 | 13.32 | 0 | 0 | -1.98 | -2.54 | Wing .1 (3BHK) 207 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
50 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 1.364 | 190 | 259.16 | 1.364 | 1.364 | 224.98 | 306.87 | 1.364 | 1.364 | 234.84 | 320.32 | 0 | 0 | -47.71 | -61.16 | Wing .1 (3BHK) 207 Master Toilet Dado(Light) | 174.87 | Sq.Ft
51 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8424 | 190 | 160.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8424 | 0.8424 | 160.06 | 160.06 | Wing .1 (3BHK)- 201 Utility Dado (M) | 108 | Sq.Ft
52 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.2583 | 190 | 49.08 | 0.2583 | 0.2583 | 224.98 | 58.11 | 0.2583 | 0 | 0 | 0 | 0 | 0.2583 | -9.04 | 49.08 | Wing .1 (3BHK)-201 Kitchen Dado (M) | 33.11 | Sq.Ft
53 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.1051 | 190 | 19.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1051 | 0.1051 | 19.97 | 19.97 | Wing .1 (3BHK).201 WB Dado (M) | 13.47 | Sq.Ft
54 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.0875 | 190 | 16.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0875 | 0.0875 | 16.63 | 16.63 | Wing .1 (3BHK).202 WB Dado (M) | 11.22 | Sq.Ft
55 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8312 | 190 | 157.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8312 | 0.8312 | 157.93 | 157.93 | Wing .1 (3BHK)202 Utility .Dado (M) | 106.56 | Sq.Ft
56 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8576 | 190 | 162.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8576 | 0.8576 | 162.94 | 162.94 | Wing.1 (2BHK) Flat 204 Utility Dado (M) | 109.95 | Sq.Ft
57 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8576 | 190 | 162.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8576 | 0.8576 | 162.94 | 162.94 | Wing.1 (2BHK) Flat 205 Utility Dado (M) | 109.95 | Sq.Ft
58 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8576 | 190 | 162.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8576 | 0.8576 | 162.94 | 162.94 | Wing.1 (2BHK) Flat 208 Utility Dado (M) | 109.95 | Sq.Ft
59 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.9521 | 190 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9521 | 0.9521 | 180.9 | 180.9 | Wing.1 (2BHK) Flat 209 Utility Dado (M) | 122.06 | Sq.Ft
60 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8312 | 190 | 157.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8312 | 0.8312 | 157.93 | 157.93 | Wing.1 (3BHK) Flat 206 Utility Dado (M) | 106.56 | Sq.Ft
61 | CONSUMABLE/MISC MATERIAL | (M)Hackad Plast Chemical | Ltrs | 0.8312 | 190 | 157.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8312 | 0.8312 | 157.93 | 157.93 | Wing.1 (3BHK) Flat 207 Utility Dado (M) | 106.56 | Sq.Ft
62 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 203 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
63 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.4372 | 590 | 2027.95 | 3.4372 | 3.4372 | 907.03 | 3117.64 | 3.4372 | 3.4372 | 906.95 | 3117.37 | 0 | 0 | -1089.7 | -1089.42 | Wing -1 (2BHK) Flat 203 Common Toilet Dado(Light) | 140.87 | Sq.Ft
64 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.7281 | 589.99 | 429.57 | 0.7281 | 0.7281 | 907.03 | 660.41 | 0.7281 | 0.7281 | 906.95 | 660.35 | 0 | 0 | -230.84 | -230.78 | Wing -1 (2BHK) Flat 203 Kitchen Dado (M) | 29.84 | Sq.Ft
65 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 203 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
66 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.9691 | 590 | 2341.77 | 3.9691 | 3.9691 | 907.03 | 3600.09 | 3.9691 | 3.9691 | 906.95 | 3599.78 | 0 | 0 | -1258.32 | -1258.01 | Wing -1 (2BHK) Flat 203 Master Toilet Dado(Light) | 162.67 | Sq.Ft
67 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 204 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
68 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.3191 | 590 | 1958.27 | 3.3191 | 3.3191 | 907.03 | 3010.52 | 3.3191 | 3.3191 | 906.95 | 3010.26 | 0 | 0 | -1052.25 | -1051.99 | Wing -1 (2BHK) Flat 204 Common Toilet Dado(Light) | 136.03 | Sq.Ft
69 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.7745 | 589.99 | 456.95 | 0.7745 | 0.7745 | 907.03 | 702.49 | 0.7745 | 0.7745 | 906.95 | 702.43 | 0 | 0 | -245.55 | -245.49 | Wing -1 (2BHK) Flat 204 Kitchen Dado (M) | 31.74 | Sq.Ft
70 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 204 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
71 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.792 | 590 | 2237.28 | 3.792 | 3.792 | 907.03 | 3439.46 | 3.792 | 3.792 | 906.95 | 3439.15 | 0 | 0 | -1202.18 | -1201.87 | Wing -1 (2BHK) Flat 204 Master Toilet Dado(Light) | 155.41 | Sq.Ft
72 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 205 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
73 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.3191 | 590 | 1958.27 | 3.3191 | 3.3191 | 907.03 | 3010.52 | 3.3191 | 3.3191 | 906.95 | 3010.26 | 0 | 0 | -1052.25 | -1051.99 | Wing -1 (2BHK) Flat 205 Common Toilet Dado(Light) | 136.03 | Sq.Ft
74 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.7745 | 589.99 | 456.95 | 0.7745 | 0.7745 | 907.03 | 702.49 | 0.7745 | 0.7745 | 906.95 | 702.43 | 0 | 0 | -245.55 | -245.49 | Wing -1 (2BHK) Flat 205 Kitchen Dado (M) | 31.74 | Sq.Ft
75 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 205 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
76 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.792 | 590 | 2237.28 | 3.792 | 3.792 | 907.03 | 3439.46 | 3.792 | 3.792 | 906.95 | 3439.15 | 0 | 0 | -1202.18 | -1201.87 | Wing -1 (2BHK) Flat 205 Master Toilet Dado(Light) | 155.41 | Sq.Ft
77 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 208 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
78 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.3191 | 590 | 1958.27 | 3.3191 | 3.3191 | 907.03 | 3010.52 | 3.3191 | 3.3191 | 906.95 | 3010.26 | 0 | 0 | -1052.25 | -1051.99 | Wing -1 (2BHK) Flat 208 Common Toilet Dado(Light) | 136.03 | Sq.Ft
79 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.7745 | 589.99 | 456.95 | 0.7745 | 0.7745 | 907.03 | 702.49 | 0.7745 | 0.7745 | 906.95 | 702.43 | 0 | 0 | -245.55 | -245.49 | Wing -1 (2BHK) Flat 208 Kitchen Dado (M) | 31.74 | Sq.Ft
80 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 208 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
81 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.7913 | 590 | 2236.87 | 3.7913 | 3.7913 | 907.03 | 3438.82 | 3.7913 | 3.7913 | 906.95 | 3438.52 | 0 | 0 | -1201.96 | -1201.66 | Wing -1 (2BHK) Flat 208 Master Toilet Dado(Light) | 155.38 | Sq.Ft
82 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 209 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
83 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.4372 | 590 | 2027.95 | 3.4372 | 3.4372 | 907.03 | 3117.64 | 3.4372 | 3.4372 | 906.95 | 3117.37 | 0 | 0 | -1089.7 | -1089.42 | Wing -1 (2BHK) Flat 209 Common Toilet Dado(Light) | 140.87 | Sq.Ft
84 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.7742 | 590 | 456.78 | 0.7742 | 0.7742 | 907.03 | 702.22 | 0.7742 | 0.7742 | 906.95 | 702.16 | 0 | 0 | -245.44 | -245.38 | Wing -1 (2BHK) Flat 209 Kitchen Dado (M) | 31.73 | Sq.Ft
85 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing -1 (2BHK) Flat 209 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
86 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.9691 | 590 | 2341.77 | 3.9691 | 3.9691 | 907.03 | 3600.09 | 3.9691 | 3.9691 | 906.95 | 3599.78 | 0 | 0 | -1258.32 | -1258.01 | Wing -1 (2BHK) Flat 209 Master Toilet Dado(Light) | 162.67 | Sq.Ft
87 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6921 | 590 | 1588.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6921 | 2.6921 | 1588.34 | 1588.34 | Wing .1 (2BHK) Flat 203 Utility .Dado (M) | 110.33 | Sq.Ft
88 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.4016 | 589.99 | 236.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4016 | 0.4016 | 236.94 | 236.94 | Wing .1 (2BHK).203 WB Dado (M) | 16.46 | Sq.Ft
89 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.4016 | 589.99 | 236.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4016 | 0.4016 | 236.94 | 236.94 | Wing .1 (2BHK).204 WB Dado (M) | 16.46 | Sq.Ft
90 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.4016 | 589.99 | 236.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4016 | 0.4016 | 236.94 | 236.94 | Wing .1 (2BHK).205 WB Dado (M) | 16.46 | Sq.Ft
91 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.4016 | 589.99 | 236.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4016 | 0.4016 | 236.94 | 236.94 | Wing .1 (2BHK).208 WB Dado (M) | 16.46 | Sq.Ft
92 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.4016 | 589.99 | 236.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4016 | 0.4016 | 236.94 | 236.94 | Wing .1 (2BHK).209 WB Dado (M) | 16.46 | Sq.Ft
93 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.5556 | 590 | 2097.8 | 3.5556 | 3.5556 | 907.03 | 3225.04 | 3.5556 | 3.5556 | 906.95 | 3224.75 | 0 | 0 | -1127.23 | -1126.95 | Wing .1 (3BHK) 201 Common Toilet Dado(Light) | 145.72 | Sq.Ft
94 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 201 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
95 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 201 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
96 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.6441 | 590 | 2150.02 | 3.6441 | 3.6441 | 907.03 | 3305.31 | 3.6441 | 3.5521 | 906.96 | 3221.6 | 0 | 0.092 | -1155.29 | -1071.59 | Wing .1 (3BHK) 201 Master Toilet Dado(Light) | 149.35 | Sq.Ft
97 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 202 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
98 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.5548 | 590 | 2097.33 | 3.5548 | 3.5548 | 907.03 | 3224.31 | 3.5548 | 3.5548 | 906.95 | 3224.03 | 0 | 0 | -1126.98 | -1126.69 | Wing .1 (3BHK) 202 Common Toilet Dado(Light) | 145.69 | Sq.Ft
99 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.8079 | 590.01 | 476.67 | 0.8079 | 0.8079 | 907.03 | 732.79 | 0.8079 | 0.8079 | 906.95 | 732.72 | 0 | 0 | -256.12 | -256.06 | Wing .1 (3BHK) 202 Kitchen Dado (M) | 33.11 | Sq.Ft
100 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 202 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
101 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 4.2646 | 590 | 2516.11 | 4.2646 | 4.2646 | 907.03 | 3868.12 | 4.2646 | 4.2646 | 906.95 | 3867.78 | 0 | 0 | -1352.01 | -1351.67 | Wing .1 (3BHK) 202 Master Toilet Dado(Light) | 174.78 | Sq.Ft
102 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 206 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
103 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.4372 | 590 | 2027.95 | 3.4372 | 3.4372 | 907.03 | 3117.64 | 3.4372 | 3.4372 | 906.96 | 3117.4 | 0 | 0 | -1089.7 | -1089.45 | Wing .1 (3BHK) 206 Common Toilet Dado(Light) | 140.87 | Sq.Ft
104 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.8128 | 590.01 | 479.56 | 0.8128 | 0.8128 | 907.03 | 737.23 | 0.8128 | 0.8128 | 906.95 | 737.17 | 0 | 0 | -257.67 | -257.61 | Wing .1 (3BHK) 206 Kitchen Dado (M) | 33.31 | Sq.Ft
105 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 206 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
106 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 4.1465 | 590 | 2446.44 | 4.1465 | 4.1465 | 907.03 | 3761 | 4.1465 | 4.1465 | 906.95 | 3760.67 | 0 | 0 | -1314.56 | -1314.23 | Wing .1 (3BHK) 206 Master Toilet Dado(Light) | 169.94 | Sq.Ft
107 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 207 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
108 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 3.5556 | 590 | 2097.8 | 3.5556 | 3.5556 | 907.03 | 3225.04 | 3.5556 | 3.5556 | 906.95 | 3224.75 | 0 | 0 | -1127.23 | -1126.95 | Wing .1 (3BHK) 207 Common Toilet Dado(Light) | 145.72 | Sq.Ft
109 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.8128 | 590.01 | 479.56 | 0.8128 | 0.8128 | 907.03 | 737.23 | 0.8128 | 0.8128 | 906.95 | 737.17 | 0 | 0 | -257.67 | -257.61 | Wing .1 (3BHK) 207 Kitchen Dado (M) | 33.31 | Sq.Ft
110 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.1774 | 589.97 | 104.66 | 0.1774 | 0.1774 | 907.03 | 160.91 | 0.1774 | 0.1774 | 906.95 | 160.89 | 0 | 0 | -56.25 | -56.23 | Wing .1 (3BHK) 207 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
111 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 4.2668 | 590 | 2517.41 | 4.2668 | 4.2668 | 907.03 | 3870.12 | 4.2668 | 4.2668 | 906.95 | 3869.77 | 0 | 0 | -1352.7 | -1352.36 | Wing .1 (3BHK) 207 Master Toilet Dado(Light) | 174.87 | Sq.Ft
112 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6352 | 590 | 1554.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6352 | 2.6352 | 1554.77 | 1554.77 | Wing .1 (3BHK)- 201 Utility Dado (M) | 108 | Sq.Ft
113 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.8079 | 590.01 | 476.67 | 0.8079 | 0.8079 | 907.03 | 732.79 | 0.8079 | 0.8079 | 906.95 | 732.72 | 0 | 0 | -256.12 | -256.06 | Wing .1 (3BHK)-201 Kitchen Dado (M) | 33.11 | Sq.Ft
114 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.3287 | 589.99 | 193.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3287 | 0.3287 | 193.93 | 193.93 | Wing .1 (3BHK).201 WB Dado (M) | 13.47 | Sq.Ft
115 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 0.2738 | 589.99 | 161.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2738 | 0.2738 | 161.54 | 161.54 | Wing .1 (3BHK).202 WB Dado (M) | 11.22 | Sq.Ft
116 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6001 | 590 | 1534.06 | 0 | 0 | 0 | 0 | 0 | 2.6001 | 906.96 | 2358.19 | 2.6001 | 0 | 1534.06 | -824.13 | Wing .1 (3BHK)202 Utility .Dado (M) | 106.56 | Sq.Ft
117 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6828 | 590 | 1582.85 | 0 | 0 | 0 | 0 | 0 | 2.5 | 906.96 | 2267.4 | 2.6828 | 0.1828 | 1582.85 | -684.55 | Wing.1 (2BHK) Flat 204 Utility Dado (M) | 109.95 | Sq.Ft
118 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6828 | 590 | 1582.85 | 0 | 0 | 0 | 0 | 0 | 2.5 | 906.96 | 2267.4 | 2.6828 | 0.1828 | 1582.85 | -684.55 | Wing.1 (2BHK) Flat 205 Utility Dado (M) | 109.95 | Sq.Ft
119 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6828 | 590 | 1582.85 | 0 | 0 | 0 | 0 | 0 | 2.6828 | 906.96 | 2433.19 | 2.6828 | 0 | 1582.85 | -850.34 | Wing.1 (2BHK) Flat 208 Utility Dado (M) | 109.95 | Sq.Ft
120 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.9783 | 590 | 1757.2 | 0 | 0 | 0 | 0 | 0 | 2.9783 | 906.96 | 2701.2 | 2.9783 | 0 | 1757.2 | -944 | Wing.1 (2BHK) Flat 209 Utility Dado (M) | 122.06 | Sq.Ft
121 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6001 | 590 | 1534.06 | 0 | 0 | 0 | 0 | 0 | 2.5 | 906.96 | 2267.4 | 2.6001 | 0.1001 | 1534.06 | -733.34 | Wing.1 (3BHK) Flat 206 Utility Dado (M) | 106.56 | Sq.Ft
122 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (Gold) 50kg | Bags | 2.6001 | 590 | 1534.06 | 0 | 0 | 0 | 0 | 0 | 2.5 | 906.96 | 2267.4 | 2.6001 | 0.1001 | 1534.06 | -733.34 | Wing.1 (3BHK) Flat 207 Utility Dado (M) | 106.56 | Sq.Ft
123 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.1033 | 100 | 110.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1033 | 1.1033 | 110.33 | 110.33 | Wing .1 (2BHK) Flat 203 Utility .Dado (M) | 110.33 | Sq.Ft
124 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 16.46 | 100 | 1646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.46 | 16.46 | 1646 | 1646 | Wing .1 (2BHK).203 WB Dado (M) | 16.46 | Sq.Ft
125 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 16.46 | 100 | 1646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.46 | 16.46 | 1646 | 1646 | Wing .1 (2BHK).204 WB Dado (M) | 16.46 | Sq.Ft
126 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 16.46 | 100 | 1646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.46 | 16.46 | 1646 | 1646 | Wing .1 (2BHK).205 WB Dado (M) | 16.46 | Sq.Ft
127 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 16.46 | 100 | 1646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.46 | 16.46 | 1646 | 1646 | Wing .1 (2BHK).208 WB Dado (M) | 16.46 | Sq.Ft
128 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 16.46 | 100 | 1646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.46 | 16.46 | 1646 | 1646 | Wing .1 (2BHK).209 WB Dado (M) | 16.46 | Sq.Ft
129 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.08 | 100 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.08 | 1.08 | 108 | 108 | Wing .1 (3BHK)- 201 Utility Dado (M) | 108 | Sq.Ft
130 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 0.331 | 100 | 33.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.331 | 0.331 | 33.1 | 33.1 | Wing .1 (3BHK)-201 Kitchen Dado (M) | 33.11 | Sq.Ft
131 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 13.47 | 100 | 1347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.47 | 13.47 | 1347 | 1347 | Wing .1 (3BHK).201 WB Dado (M) | 13.47 | Sq.Ft
132 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 11.22 | 100 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.22 | 11.22 | 1122 | 1122 | Wing .1 (3BHK).202 WB Dado (M) | 11.22 | Sq.Ft
133 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.0656 | 100 | 106.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0656 | 1.0656 | 106.56 | 106.56 | Wing .1 (3BHK)202 Utility .Dado (M) | 106.56 | Sq.Ft
134 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.0995 | 100 | 109.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0995 | 1.0995 | 109.95 | 109.95 | Wing.1 (2BHK) Flat 204 Utility Dado (M) | 109.95 | Sq.Ft
135 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.0995 | 100 | 109.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0995 | 1.0995 | 109.95 | 109.95 | Wing.1 (2BHK) Flat 205 Utility Dado (M) | 109.95 | Sq.Ft
136 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.0995 | 100 | 109.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0995 | 1.0995 | 109.95 | 109.95 | Wing.1 (2BHK) Flat 208 Utility Dado (M) | 109.95 | Sq.Ft
137 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.2206 | 100 | 122.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2206 | 1.2206 | 122.06 | 122.06 | Wing.1 (2BHK) Flat 209 Utility Dado (M) | 122.06 | Sq.Ft
138 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.0656 | 100 | 106.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0656 | 1.0656 | 106.56 | 106.56 | Wing.1 (3BHK) Flat 206 Utility Dado (M) | 106.56 | Sq.Ft
139 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 1.0656 | 100 | 106.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0656 | 1.0656 | 106.56 | 106.56 | Wing.1 (3BHK) Flat 207 Utility Dado (M) | 106.56 | Sq.Ft
140 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 29.84 | 100 | 2984 | 29.84 | 29.84 | 39 | 1163.73 | 0 | 29.84 | 39 | 1163.76 | 0 | 0 | 1820.27 | 1820.24 | Wing -1 (2BHK) Flat 203 Kitchen Dado (M) | 29.84 | Sq.Ft
141 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.74 | 100 | 3174 | 31.74 | 31.74 | 39 | 1237.83 | 0 | 31.74 | 39 | 1237.86 | 0 | 0 | 1936.17 | 1936.14 | Wing -1 (2BHK) Flat 204 Kitchen Dado (M) | 31.74 | Sq.Ft
142 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.74 | 100 | 3174 | 31.74 | 31.74 | 39 | 1237.83 | 0 | 31.74 | 39 | 1237.86 | 0 | 0 | 1936.17 | 1936.14 | Wing -1 (2BHK) Flat 205 Kitchen Dado (M) | 31.74 | Sq.Ft
143 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.74 | 100 | 3174 | 31.74 | 31.74 | 39 | 1237.83 | 0 | 31.74 | 39 | 1237.86 | 0 | 0 | 1936.17 | 1936.14 | Wing -1 (2BHK) Flat 208 Kitchen Dado (M) | 31.74 | Sq.Ft
144 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.73 | 100 | 3173 | 31.73 | 31.73 | 39 | 1237.44 | 0 | 23.51 | 39 | 916.89 | 0 | 8.22 | 1935.56 | 2256.11 | Wing -1 (2BHK) Flat 209 Kitchen Dado (M) | 31.73 | Sq.Ft
145 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 110.33 | 100 | 11033 | 110.33 | 110.33 | 39 | 4302.76 | 0 | 0 | 0 | 0 | 0 | 110.33 | 6730.24 | 11033 | Wing .1 (2BHK) Flat 203 Utility .Dado (M) | 110.33 | Sq.Ft
146 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 16.46 | 100 | 1646 | 16.46 | 16.46 | 39 | 641.92 | 0 | 0 | 0 | 0 | 0 | 16.46 | 1004.08 | 1646 | Wing .1 (2BHK).203 WB Dado (M) | 16.46 | Sq.Ft
147 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 16.46 | 100 | 1646 | 16.46 | 16.46 | 39 | 641.92 | 0 | 0 | 0 | 0 | 0 | 16.46 | 1004.08 | 1646 | Wing .1 (2BHK).204 WB Dado (M) | 16.46 | Sq.Ft
148 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 16.46 | 100 | 1646 | 16.46 | 16.46 | 39 | 641.92 | 0 | 0 | 0 | 0 | 0 | 16.46 | 1004.08 | 1646 | Wing .1 (2BHK).205 WB Dado (M) | 16.46 | Sq.Ft
149 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 16.46 | 100 | 1646 | 16.46 | 16.46 | 39 | 641.92 | 0 | 0 | 0 | 0 | 0 | 16.46 | 1004.08 | 1646 | Wing .1 (2BHK).208 WB Dado (M) | 16.46 | Sq.Ft
150 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 16.46 | 100 | 1646 | 16.46 | 16.46 | 39 | 641.92 | 0 | 0 | 0 | 0 | 0 | 16.46 | 1004.08 | 1646 | Wing .1 (2BHK).209 WB Dado (M) | 16.46 | Sq.Ft
151 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.11 | 100 | 3311 | 33.11 | 33.11 | 39 | 1291.26 | 0 | 33.11 | 39 | 1291.29 | 0 | 0 | 2019.74 | 2019.71 | Wing .1 (3BHK) 202 Kitchen Dado (M) | 33.11 | Sq.Ft
152 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.31 | 100 | 3331 | 33.31 | 33.31 | 39 | 1299.06 | 0 | 33.11 | 39 | 1291.29 | 0 | 0.2 | 2031.94 | 2039.71 | Wing .1 (3BHK) 206 Kitchen Dado (M) | 33.31 | Sq.Ft
153 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.31 | 100 | 3331 | 33.31 | 33.31 | 39 | 1299.06 | 0 | 33.11 | 39 | 1291.29 | 0 | 0.2 | 2031.94 | 2039.71 | Wing .1 (3BHK) 207 Kitchen Dado (M) | 33.31 | Sq.Ft
154 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 108 | 100 | 10800 | 108 | 108 | 39 | 4211.89 | 0 | 0 | 0 | 0 | 0 | 108 | 6588.11 | 10800 | Wing .1 (3BHK)- 201 Utility Dado (M) | 108 | Sq.Ft
155 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.11 | 100 | 3311 | 33.11 | 33.11 | 39 | 1291.26 | 0 | 33.11 | 39 | 1291.29 | 0 | 0 | 2019.74 | 2019.71 | Wing .1 (3BHK)-201 Kitchen Dado (M) | 33.11 | Sq.Ft
156 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 13.47 | 100 | 1347 | 13.47 | 13.47 | 39 | 525.32 | 0 | 0 | 0 | 0 | 0 | 13.47 | 821.68 | 1347 | Wing .1 (3BHK).201 WB Dado (M) | 13.47 | Sq.Ft
157 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 11.22 | 100 | 1122 | 11.22 | 11.22 | 39 | 437.57 | 0 | 0 | 0 | 0 | 0 | 11.22 | 684.43 | 1122 | Wing .1 (3BHK).202 WB Dado (M) | 11.22 | Sq.Ft
158 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 106.56 | 100 | 10656 | 106.56 | 106.56 | 39 | 4155.73 | 0 | 0 | 0 | 0 | 0 | 106.56 | 6500.27 | 10656 | Wing .1 (3BHK)202 Utility .Dado (M) | 106.56 | Sq.Ft
159 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 109.95 | 100 | 10995 | 109.95 | 109.95 | 39 | 4287.94 | 0 | 0 | 0 | 0 | 0 | 109.95 | 6707.06 | 10995 | Wing.1 (2BHK) Flat 204 Utility Dado (M) | 109.95 | Sq.Ft
160 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 109.95 | 100 | 10995 | 109.95 | 109.95 | 39 | 4287.94 | 0 | 0 | 0 | 0 | 0 | 109.95 | 6707.06 | 10995 | Wing.1 (2BHK) Flat 205 Utility Dado (M) | 109.95 | Sq.Ft
161 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 109.95 | 100 | 10995 | 109.95 | 109.95 | 39 | 4287.94 | 0 | 0 | 0 | 0 | 0 | 109.95 | 6707.06 | 10995 | Wing.1 (2BHK) Flat 208 Utility Dado (M) | 109.95 | Sq.Ft
162 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 122.06 | 100 | 12206 | 122.06 | 122.06 | 39 | 4760.22 | 0 | 0 | 0 | 0 | 0 | 122.06 | 7445.78 | 12206 | Wing.1 (2BHK) Flat 209 Utility Dado (M) | 122.06 | Sq.Ft
163 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 106.56 | 100 | 10656 | 106.56 | 106.56 | 39 | 4155.73 | 0 | 0 | 0 | 0 | 0 | 106.56 | 6500.27 | 10656 | Wing.1 (3BHK) Flat 206 Utility Dado (M) | 106.56 | Sq.Ft
164 | TILES & NATURAL STONE | (M)Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 106.56 | 100 | 10656 | 106.56 | 106.56 | 39 | 4155.73 | 0 | 0 | 0 | 0 | 0 | 106.56 | 6500.27 | 10656 | Wing.1 (3BHK) Flat 207 Utility Dado (M) | 106.56 | Sq.Ft
165 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 162.67 | 100 | 16267 | 162.67 | 162.67 | 39 | 6343.97 | 162.67 | 162.67 | 39 | 6344.13 | 0 | 0 | 9923.03 | 9922.87 | Wing -1 (2BHK) Flat 203 Master Toilet Dado(Light) | 162.67 | Sq.Ft
166 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 155.41 | 100 | 15541 | 155.41 | 155.41 | 39 | 6060.83 | 155.41 | 155.41 | 39 | 6060.99 | 0 | 0 | 9480.17 | 9480.01 | Wing -1 (2BHK) Flat 204 Master Toilet Dado(Light) | 155.41 | Sq.Ft
167 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 155.41 | 100 | 15541 | 155.41 | 155.41 | 39 | 6060.83 | 155.41 | 155.41 | 39 | 6060.99 | 0 | 0 | 9480.17 | 9480.01 | Wing -1 (2BHK) Flat 205 Master Toilet Dado(Light) | 155.41 | Sq.Ft
168 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 155.38 | 100 | 15538 | 155.38 | 155.38 | 39 | 6059.66 | 155.38 | 155.38 | 39 | 6059.82 | 0 | 0 | 9478.34 | 9478.18 | Wing -1 (2BHK) Flat 208 Master Toilet Dado(Light) | 155.38 | Sq.Ft
169 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 162.67 | 100 | 16267 | 162.67 | 162.67 | 39 | 6343.97 | 162.67 | 156.05 | 39 | 6085.95 | 0 | 6.62 | 9923.03 | 10181.05 | Wing -1 (2BHK) Flat 209 Master Toilet Dado(Light) | 162.67 | Sq.Ft
170 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 149.35 | 100 | 14935 | 149.35 | 149.35 | 39 | 5824.5 | 149.35 | 149.35 | 39 | 5824.65 | 0 | 0 | 9110.5 | 9110.35 | Wing .1 (3BHK) 201 Master Toilet Dado(Light) | 149.35 | Sq.Ft
171 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 174.78 | 100 | 17478 | 174.78 | 174.78 | 39 | 6816.25 | 174.78 | 174.42 | 39 | 6802.38 | 0 | 0.36 | 10661.75 | 10675.62 | Wing .1 (3BHK) 202 Master Toilet Dado(Light) | 174.78 | Sq.Ft
172 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 169.94 | 100 | 16994 | 169.94 | 169.94 | 39 | 6627.49 | 169.94 | 169.94 | 39 | 6627.66 | 0 | 0 | 10366.51 | 10366.34 | Wing .1 (3BHK) 206 Master Toilet Dado(Light) | 169.94 | Sq.Ft
173 | TILES & NATURAL STONE | (M)Artific Gris-Light Tile 300 X 600 (AGL) | Sq.Ft | 174.87 | 100 | 17487 | 174.87 | 174.87 | 39 | 6819.76 | 174.87 | 174.87 | 39 | 6819.93 | 0 | 0 | 10667.24 | 10667.07 | Wing .1 (3BHK) 207 Master Toilet Dado(Light) | 174.87 | Sq.Ft
174 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 203 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
175 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 204 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
176 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 205 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
177 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 5.382 | 39 | 209.9 | 0 | 1.888 | 443.48 | 517.1 | Wing -1 (2BHK) Flat 208 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
178 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 0 | 0 | 0 | 0 | 7.27 | 443.48 | 727 | Wing -1 (2BHK) Flat 209 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
179 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing .1 (3BHK) 201 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
180 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing .1 (3BHK) 202 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
181 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.2 | 39 | 280.8 | 0 | 0.07 | 443.48 | 446.2 | Wing .1 (3BHK) 206 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
182 | TILES & NATURAL STONE | (M)Calleva Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing .1 (3BHK) 207 Master Toilet Dado(Dark) | 7.27 | Sq.Ft
183 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 140.87 | 100 | 14087 | 140.87 | 140.87 | 39 | 5493.79 | 140.87 | 140.87 | 39 | 5493.93 | 0 | 0 | 8593.21 | 8593.07 | Wing -1 (2BHK) Flat 203 Common Toilet Dado(Light) | 140.87 | Sq.Ft
184 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 136.03 | 100 | 13603 | 136.03 | 136.03 | 39 | 5305.03 | 136.03 | 136.03 | 39 | 5305.17 | 0 | 0 | 8297.97 | 8297.83 | Wing -1 (2BHK) Flat 204 Common Toilet Dado(Light) | 136.03 | Sq.Ft
185 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 136.03 | 100 | 13603 | 136.03 | 136.03 | 39 | 5305.03 | 136.03 | 136.03 | 39 | 5305.17 | 0 | 0 | 8297.97 | 8297.83 | Wing -1 (2BHK) Flat 205 Common Toilet Dado(Light) | 136.03 | Sq.Ft
186 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 136.03 | 100 | 13603 | 136.03 | 136.03 | 39 | 5305.03 | 136.03 | 136.03 | 39 | 5305.17 | 0 | 0 | 8297.97 | 8297.83 | Wing -1 (2BHK) Flat 208 Common Toilet Dado(Light) | 136.03 | Sq.Ft
187 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 140.87 | 100 | 14087 | 140.87 | 140.87 | 39 | 5493.79 | 140.87 | 133.08 | 39 | 5190.12 | 0 | 7.79 | 8593.21 | 8896.88 | Wing -1 (2BHK) Flat 209 Common Toilet Dado(Light) | 140.87 | Sq.Ft
188 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 145.72 | 100 | 14572 | 145.72 | 145.72 | 39 | 5682.93 | 145.72 | 145.72 | 39 | 5683.08 | 0 | 0 | 8889.07 | 8888.92 | Wing .1 (3BHK) 201 Common Toilet Dado(Light) | 145.72 | Sq.Ft
189 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 145.69 | 100 | 14569 | 145.69 | 145.69 | 39 | 5681.76 | 145.69 | 145.35 | 39 | 5668.65 | 0 | 0.34 | 8887.24 | 8900.35 | Wing .1 (3BHK) 202 Common Toilet Dado(Light) | 145.69 | Sq.Ft
190 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 140.87 | 100 | 14087 | 140.87 | 140.87 | 39 | 5493.79 | 140.87 | 140.87 | 39 | 5493.93 | 0 | 0 | 8593.21 | 8593.07 | Wing .1 (3BHK) 206 Common Toilet Dado(Light) | 140.87 | Sq.Ft
191 | TILES & NATURAL STONE | (M)Caron Ivory-Light Tile 300 X 600 (AGL) | Sq.Ft | 145.72 | 100 | 14572 | 145.72 | 145.72 | 39 | 5682.93 | 145.72 | 145.72 | 39 | 5683.08 | 0 | 0 | 8889.07 | 8888.92 | Wing .1 (3BHK) 207 Common Toilet Dado(Light) | 145.72 | Sq.Ft
192 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 203 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
193 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 204 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
194 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 205 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
195 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 208 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
196 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing -1 (2BHK) Flat 209 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
197 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing .1 (3BHK) 201 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
198 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing .1 (3BHK) 202 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
199 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.27 | 39 | 283.53 | 0 | 0 | 443.48 | 443.47 | Wing .1 (3BHK) 206 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
200 | TILES & NATURAL STONE | (M)Caron Tan-Dark Tile 300 X 600 (AGL) | Sq.Ft | 7.27 | 100 | 727 | 7.27 | 7.27 | 39 | 283.52 | 7.27 | 7.26 | 39 | 283.14 | 0 | 0.01 | 443.48 | 443.86 | Wing .1 (3BHK) 207 Common Toilet Dado(Dark) | 7.27 | Sq.Ft
201 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 465.34 | 18 | 8376.12 | 0 | 465.34 | 23 | 10702.82 | 0 | 0 | 0 | 0 | 0 | 465.34 | -2326.7 | 8376.12 | Wing -1 (2BHK) Flat 203 Kitchen, Toilet, Utility, WB Counter | 465.34 | Sq.Ft
202 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 454.77 | 18 | 8185.86 | 0 | 454.77 | 23 | 10459.71 | 0 | 0 | 0 | 0 | 0 | 454.77 | -2273.85 | 8185.86 | Wing -1 (2BHK) Flat 204 Kitchen, Toilet, Utility, WB Counter | 454.77 | Sq.Ft
203 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 454.77 | 18 | 8185.86 | 0 | 454.77 | 23 | 10459.71 | 0 | 0 | 0 | 0 | 0 | 454.77 | -2273.85 | 8185.86 | Wing -1 (2BHK) Flat 205 Kitchen, Toilet, Utility, WB Counter | 454.77 | Sq.Ft
204 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 454.74 | 18 | 8185.32 | 0 | 454.74 | 23 | 10459.02 | 0 | 0 | 0 | 0 | 0 | 454.74 | -2273.7 | 8185.32 | Wing -1 (2BHK) Flat 208 Kitchen, Toilet, Utility, WB Counter | 454.74 | Sq.Ft
205 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 478.97 | 18 | 8621.46 | 0 | 478.97 | 23 | 11016.31 | 0 | 0 | 0 | 0 | 0 | 478.97 | -2394.85 | 8621.46 | Wing -1 (2BHK) Flat 209 Kitchen, Toilet, Utility, WB Counter | 478.97 | Sq.Ft
206 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 456.52 | 18 | 8217.36 | 0 | 456.52 | 23 | 10499.96 | 0 | 0 | 0 | 0 | 0 | 456.52 | -2282.6 | 8217.36 | Wing -1 (3BHK)- 201 Kitchen, Toilet, Utility, WB Counter - D | 456.52 | Sq.Ft
207 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 474.91 | 18 | 8548.38 | 0 | 474.91 | 23 | 10922.93 | 0 | 0 | 0 | 0 | 0 | 474.91 | -2374.55 | 8548.38 | Wing 1 (3BHK)207 Kit, Toi, Utility, WB Count Dado | 474.91 | Sq.Ft
208 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 479.52 | 18 | 8631.36 | 0 | 479.52 | 23 | 11028.96 | 0 | 0 | 0 | 0 | 0 | 479.52 | -2397.6 | 8631.36 | Wing 1 3BHK 202 Kit, Toil, Utility, WB Count Dado | 479.52 | Sq.Ft
209 | 11 TILING WORK | (L)Dado Fixing | Sq.Ft | 465.22 | 18 | 8373.96 | 0 | 465.22 | 23 | 10700.06 | 0 | 0 | 0 | 0 | 0 | 465.22 | -2326.1 | 8373.96 | Wing1 3BHK 206 Kit, Toil, Utility, WB Count Dado | 465.22 | Sq.Ft
210 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 465.34 | 1000 | 465340 | 0 | 465.34 | 2 | 930.68 | 0 | 0 | 0 | 0 | 0 | 465.34 | 464409.32 | 465340 | Wing -1 (2BHK) Flat 203 Kitchen, Toilet, Utility, WB Counter | 465.34 | Sq.Ft
211 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 454.77 | 1000 | 454770 | 0 | 454.77 | 2 | 909.54 | 0 | 0 | 0 | 0 | 0 | 454.77 | 453860.46 | 454770 | Wing -1 (2BHK) Flat 204 Kitchen, Toilet, Utility, WB Counter | 454.77 | Sq.Ft
212 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 454.77 | 1000 | 454770 | 0 | 454.77 | 2 | 909.54 | 0 | 0 | 0 | 0 | 0 | 454.77 | 453860.46 | 454770 | Wing -1 (2BHK) Flat 205 Kitchen, Toilet, Utility, WB Counter | 454.77 | Sq.Ft
213 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 454.74 | 1000 | 454740 | 0 | 454.74 | 2 | 909.48 | 0 | 0 | 0 | 0 | 0 | 454.74 | 453830.52 | 454740 | Wing -1 (2BHK) Flat 208 Kitchen, Toilet, Utility, WB Counter | 454.74 | Sq.Ft
214 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 478.97 | 1000 | 478970 | 0 | 478.97 | 2 | 957.94 | 0 | 0 | 0 | 0 | 0 | 478.97 | 478012.06 | 478970 | Wing -1 (2BHK) Flat 209 Kitchen, Toilet, Utility, WB Counter | 478.97 | Sq.Ft
215 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 456.52 | 1000 | 456520 | 0 | 456.52 | 2 | 913.04 | 0 | 0 | 0 | 0 | 0 | 456.52 | 455606.96 | 456520 | Wing -1 (3BHK)- 201 Kitchen, Toilet, Utility, WB Counter - D | 456.52 | Sq.Ft
216 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 474.91 | 1000 | 474910 | 0 | 474.91 | 2 | 949.82 | 0 | 0 | 0 | 0 | 0 | 474.91 | 473960.18 | 474910 | Wing 1 (3BHK)207 Kit, Toi, Utility, WB Count Dado | 474.91 | Sq.Ft
217 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 479.52 | 1000 | 479520 | 0 | 479.52 | 2 | 959.04 | 0 | 0 | 0 | 0 | 0 | 479.52 | 478560.96 | 479520 | Wing 1 3BHK 202 Kit, Toil, Utility, WB Count Dado | 479.52 | Sq.Ft
218 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 465.22 | 1000 | 465220 | 0 | 465.22 | 2 | 930.44 | 0 | 0 | 0 | 0 | 0 | 465.22 | 464289.56 | 465220 | Wing1 3BHK 206 Kit, Toil, Utility, WB Count Dado | 465.22 | Sq.Ft