## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : GANGA ASMI
Task Name : 2nd Floor
Page 1 of 1
Total Records: 15 Records 1 to 15
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | CEMENT | (M)Cement 43 grade (PPC) | Bags | 25.5946 | 100 | 2559.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.5946 | 25.5946 | 2559.46 | 2559.46 | Lobby Flooring | 1279.731 | Sq.Ft
2 | CONSUMABLE/MISC MATERIAL | (M)HCL Acid | Ltrs | 1246.458 | 6 | 7478.75 | 1246.458 | 1246.458 | 9.22 | 11492.34 | 1232.8468 | 0 | 0 | 0 | 0 | 1246.458 | -4013.59 | 7478.75 | Lobby Flooring | 1279.731 | Sq.Ft
3 | CONSUMABLE/MISC MATERIAL | (M)Mcon NSA Grey (20kg bag) | Kgs | 117.8471 | 12.5 | 1473.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.8471 | 117.8471 | 1473.09 | 1473.09 | 2nd Floor lobby Skirting (M) | 96.596 | Sq.Ft
4 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 0.966 | 100 | 96.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.966 | 0.966 | 96.6 | 96.6 | 2nd Floor lobby Skirting (M) | 96.596 | Sq.Ft
5 | CONSUMABLE/MISC MATERIAL | (M)Tile Grout | Kgs | 12.79 | 100 | 1279 | 12.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.79 | 12.79 | 1279 | 1279 | Lobby Flooring | 1279.731 | Sq.Ft
6 | SAND & METAL | (M)Crush Sand | Cu.Ft | 10.23 | 33 | 337.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.23 | 10.23 | 337.59 | 337.59 | Lobby Flooring | 1279.731 | Sq.Ft
7 | SAND & METAL | (M)M Sand | Cu.Ft | 10.23 | 65 | 664.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.23 | 10.23 | 664.95 | 664.95 | Lobby Flooring | 1279.731 | Sq.Ft
8 | TILES & NATURAL STONE | (M)Altus Beige Tile 600 X 600 | Sq.Ft | 96.596 | 100 | 9659.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.596 | 96.596 | 9659.6 | 9659.6 | 2nd Floor lobby Skirting (M) | 96.596 | Sq.Ft
9 | TILES & NATURAL STONE | (M)Altus Beige Tile 600 X 600 | Sq.Ft | 1279.371 | 100 | 127937.1 | 1279.371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279.371 | 1279.371 | 127937.1 | 127937.1 | Lobby Flooring | 1279.731 | Sq.Ft
10 | TILES & NATURAL STONE | (M)Vitrified Flooring 600 x 600 | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Lobby Flooring | 1279.731 | Sq.Ft
11 | 11 TILING WORK | (L)Floor Guard Removing & Acid Wash | Sq.Ft | 1279.731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279.731 | 1279.731 | 0 | 0 | Lobby Flooring | 1279.731 | Sq.Ft
12 | 11 TILING WORK | (L)Vitrified Flooring & Floor Guard Laying | Sq.Ft | 1279.731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279.731 | 1279.731 | 0 | 0 | Lobby Flooring | 1279.731 | Sq.Ft
13 | 11 TILING WORK | (L)Vitrified Flooring work | Sq.Ft | 1279.731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279.731 | 1279.731 | 0 | 0 | Lobby Flooring | 1279.731 | Sq.Ft
14 | B.C. RCC Superstructure | (L)Schedule & Quality | Sq.Ft | 1279.731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279.731 | 1279.731 | 0 | 0 | Lobby Flooring | 1279.731 | Sq.Ft
15 | B.C. Rework/Extrawork | (L)Vitrified Skirting - BRE | R.Ft | 386.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386.38 | 386.38 | 0 | 0 | Lobby Skirting | 386.38 | R.Ft