## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : SRA MORWADI
Task Name : A Bldg 4th Slab
Page 1 of 1
Total Records: 30 Records 1 to 30
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | CEMENT | (M)Cement 43 Grade | Bags | 4 | 375 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1500 | 1500 | A-4th Slab Cement For Cement Slurry | 1 | No.
2 | CEMENT | (M)Cement 43 Grade | Bags | 1 | 375 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 375 | 375 | A-4th Slab Material On Debit Basis | 1 | No.
3 | CEMENT | (M)Cement 43 grade (PPC) | Bags | 5 | 100 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 500 | 500 | A Bldg 4th Slab Curing & Other Material | 1 | No.
4 | CEMENT | (M)Cement Loose 53 Grade | Metric Tonnes | 38.9 | 3880 | 150932 | 38.9 | 19.45 | 7400 | 143930 | 19.45 | 35.0262 | 7480.41 | 262010.34 | 19.45 | 3.8738 | 7002 | -111078.34 | A Bldg 3rd To 4th Slab column & non str. wall concrete | 1 | Cu.Mtrs
5 | CEMENT | (M)Cement Loose 53 Grade | Metric Tonnes | 40.84 | 3880 | 158459.2 | 40.84 | 40.84 | 7530.36 | 307540 | 40.84 | 34.108 | 7480.41 | 255141.82 | 0 | 6.732 | -149080.8 | -96682.62 | A Bldg 4th Slab,Beam,Staircase Concrete | 1 | Cu.Mtrs
6 | CONSUMABLE/MISC MATERIAL | (M)GP2 Waterproofing Chemical | Kgs | 125 | 150 | 18750 | 0 | 0 | 0 | 0 | 0 | 90 | 20.65 | 1858.5 | 125 | 35 | 18750 | 16891.5 | A Bldg 4th Slab Curing & Other Material | 1 | No.
7 | CONSUMABLE/MISC MATERIAL | (M)GP2 Waterproofing Chemical | Kgs | 30 | 150 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 4500 | 4500 | A-4th Slab Material On Debit Basis | 1 | No.
8 | RMC | (M)Sand-Metal Mix M30 (Downpour) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A Bldg 4th Slab,Beam,Staircase Concrete | 1 | Cu.Mtrs
9 | RMC | (M)Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A Bldg 3rd To 4th Slab column & non str. wall concrete | 1 | Cu.Mtrs
10 | RMC | (M)Sand-Metal Mix M30 hi-flow (Pumpable) | Cu.Mtrs | 167.99 | 3150 | 529168.5 | 167.99 | 158.36 | 3956 | 626472.1 | 158.36 | 159.21 | 3956 | 629834.76 | 9.63 | 8.78 | -97303.6 | -100666.26 | A Bldg 3rd To 4th Slab column & non str. wall concrete | 1 | Cu.Mtrs
11 | RMC | (M)Sand-Metal Mix M30 hi-flow (Pumpable) | Cu.Mtrs | 160.33 | 3150 | 505039.5 | 160.33 | 155.89 | 3956 | 616700.78 | 155.89 | 155.04 | 3956 | 613338.24 | 4.44 | 5.29 | -111661.28 | -108298.74 | A Bldg 4th Slab,Beam,Staircase Concrete | 1 | Cu.Mtrs
12 | SAND & METAL | (M)Crush Sand | Cu.Ft | 100 | 33 | 3300 | 100 | 100 | 39.38 | 3937.5 | 100 | 0 | 0 | 0 | 0 | 100 | -637.5 | 3300 | A Bldg 4th Slab Curing & Other Material | 1 | No.
13 | STEEL | (M)Binding Wire | Kgs | 162.44 | 62.85 | 10209.35 | 162.44 | 162.44 | 80.88 | 13138.15 | 162.44 | 161 | 80.43 | 12949.23 | 0 | 1.44 | -2928.79 | -2739.88 | A Bldg 4th Slab,Beam & Staircase Steel Work | 1 | Kgs
14 | STEEL | (M)Binding Wire | Kgs | 182.02 | 62.85 | 11439.96 | 182.02 | 182.02 | 80.88 | 14721.78 | 182.02 | 182 | 79.33 | 14438.06 | 0 | 0.02 | -3281.82 | -2998.1 | A BldgThird to Fourth slab Column,lift Steel | 1 | Kgs
15 | STEEL | (M)Binding Wire | Kgs | 4.35 | 62.85 | 273.4 | 4.35 | 4.35 | 80.88 | 351.83 | 4.35 | 4.35 | 79.33 | 345.09 | 0 | 0 | -78.43 | -71.69 | A Building 4th Slab Non Str. wall steel | 1 | Kgs
16 | STEEL | (M)GFRP Bars 6mm | Kgs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A Building 4th Slab Non Str. wall steel | 1 | Kgs
17 | STEEL | (M)GFRP Bars 8mm | Kgs | 768.73 | 100 | 76873 | 768.73 | 768.73 | 174.64 | 134251.01 | 768.73 | 768.73 | 174.64 | 134251.01 | 0 | 0 | -57378.01 | -57378.01 | A Building 4th Slab Non Str. wall steel | 1 | Kgs
18 | STEEL | (M)Steel Bar 25mm | Kgs | 111.28 | 50.85 | 5658.59 | 0 | 0 | 0 | 0 | 0 | 92.592 | 60.66 | 5616.63 | 111.28 | 18.688 | 5658.59 | 41.96 | A Bldg 4th Slab,Beam & Staircase Steel Work | 1 | Kgs
19 | STEEL | (M)Steel Bar 25mm | Kgs | 939.81 | 50.85 | 47789.34 | 0 | 0 | 0 | 0 | 0 | 909.256 | 60.6 | 55099.91 | 939.81 | 30.554 | 47789.34 | -7310.58 | A BldgThird to Fourth slab Column,lift Steel | 1 | Kgs
20 | STEEL | (M)Steel Bars 10mm | Kgs | 500.23 | 50.85 | 25436.7 | 0 | 0 | 0 | 0 | 0 | 383.87 | 62.37 | 23941.74 | 500.23 | 116.36 | 25436.7 | 1494.96 | A Bldg 4th Slab,Beam & Staircase Steel Work | 1 | Kgs
21 | STEEL | (M)Steel Bars 10mm | Kgs | 732.44 | 50.85 | 37244.57 | 0 | 0 | 0 | 0 | 0 | 732.44 | 62.12 | 45501.72 | 732.44 | 0 | 37244.57 | -8257.15 | A BldgThird to Fourth slab Column,lift Steel | 1 | Kgs
22 | STEEL | (M)Steel Bars 12mm | Kgs | 2905.47 | 50.85 | 147743.15 | 0 | 0 | 0 | 0 | 0 | 2351.69 | 60.2 | 141571.74 | 2905.47 | 553.78 | 147743.15 | 6171.41 | A Bldg 4th Slab,Beam & Staircase Steel Work | 1 | Kgs
23 | STEEL | (M)Steel Bars 12mm | Kgs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A BldgThird to Fourth slab Column,lift Steel | 1 | Kgs
24 | STEEL | (M)Steel Bars 16mm | Kgs | 3100 | 50.85 | 157635 | 0 | 0 | 0 | 0 | 0 | 3033.6 | 63.19 | 191693.18 | 3100 | 66.4 | 157635 | -34058.18 | A Bldg 4th Slab,Beam & Staircase Steel Work | 1 | Kgs
25 | STEEL | (M)Steel Bars 16mm | Kgs | 4350.48 | 50.85 | 221221.91 | 0 | 0 | 0 | 0 | 0 | 4322.99 | 61.84 | 267331.42 | 4350.48 | 27.49 | 221221.91 | -46109.51 | A BldgThird to Fourth slab Column,lift Steel | 1 | Kgs
26 | STEEL | (M)Steel Bars 20mm | Kgs | 558.47 | 50.85 | 28398.2 | 0 | 0 | 0 | 0 | 0 | 444.42 | 61.62 | 27385.16 | 558.47 | 114.05 | 28398.2 | 1013.04 | A Bldg 4th Slab,Beam & Staircase Steel Work | 1 | Kgs
27 | STEEL | (M)Steel Bars 20mm | Kgs | 4938.86 | 50.85 | 251141.03 | 0 | 0 | 0 | 0 | 0 | 2844.378 | 60.94 | 173350.58 | 4938.86 | 2094.482 | 251141.03 | 77790.45 | A BldgThird to Fourth slab Column,lift Steel | 1 | Kgs
28 | STEEL | (M)Steel Bars 8mm | Kgs | 7481.67 | 50.85 | 380442.92 | 0 | 0 | 0 | 0 | 0 | 7481.67 | 63.63 | 476022 | 7481.67 | 0 | 380442.92 | -95579.08 | A Bldg 4th Slab,Beam & Staircase Steel Work | 1 | Kgs
29 | STEEL | (M)Steel Bars 8mm | Kgs | 2938.5 | 50.85 | 149422.73 | 0 | 0 | 0 | 0 | 0 | 2901.32 | 63.19 | 183324.74 | 2938.5 | 37.18 | 149422.73 | -33902.02 | A BldgThird to Fourth slab Column,lift Steel | 1 | Kgs
30 | STEEL | (M)Steel Bars 8mm | Kgs | 991.88 | 50.85 | 50437.1 | 0 | 0 | 0 | 0 | 0 | 979.23 | 62.65 | 61349.9 | 991.88 | 12.65 | 50437.1 | -10912.81 | A Building 4th Slab Non Str. wall steel | 1 | Kgs