## Material Receipt Details6385819
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 53 Records 1 to 53
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Binding Wire - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 838.745 | 61.9 | 51918.3155 | 838.745 | 61.9 | 51918.3155 | 838.745 | 0 | 0 | 838.745 | 0 | 838.745 | 0 | 88.6715 | 74372.8099 | 827.669 | 11.076 | -11.076 | 838.745 | 2576.001 | 204268.0176 | Kgs | 62285.713 | 84084.8 | 0 | 0 | -32166.4845
Binding Wire - Kgs | UGWT RCC Bottom Slab | STEEL | 82.66 | 61.9 | 5116.654 | 82.66 | 61.9 | 5116.654 | 82.66 | 0 | 0 | 82.66 | 0 | 82.66 | 0 | 94.4 | 7803.104 | 82.66 | 0 | 0.255 | 82.405 | 2576.001 | 204268.0176 | Kgs | 6612.8 | 13225.6 | 0 | 0 | -8108.946
Binding Wire - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 120.55 | 62.85 | 7576.5675 | 0 | 0 | 0 | 0 | 120.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50 | 50 | 2576.001 | 204268.0176 | Kgs | 0 | 0 | 0 | 120.55 | 7576.5675
Binding Wire - Kgs | UGWT RCC Grid Slab Reinforcement Work | STEEL | 41.1 | 62.85 | 2583.135 | 41.1 | 62.85 | 2583.135 | 41.1 | 0 | 0 | 41.1 | 0 | 41.1 | 0 | 79.06 | 3249.366 | 41.1 | 0 | 41.1 | 0 | 2576.001 | 204268.0176 | Kgs | 2753.7 | 0 | 0 | 0 | 2583.135
Binding Wire - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 7.03 | 62.85 | 441.8355 | 0 | 0 | 0 | 0 | 7.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2576.001 | 204268.0176 | Kgs | 0 | 0 | 0 | 7.03 | 441.8355
Cement 43 Grade - Bags | UGWT RCC Misc. Material for RCC Work | CEMENT | 28 | 375 | 10500 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20 | 20 | 20 | 6804.1654 | Bags | 0 | 0 | 0 | 28 | 10500
Cement Loose 53 Grade - Metric Tonnes | UGWT RCC Plum Concrete Below Raft (C60-R40) | CEMENT | 15.516 | 3880 | 60202.08 | 0 | 0 | 0 | 0 | 15.516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259.5366 | 1978730.8697 | Metric Tonnes | 0 | 0 | 0 | 15.516 | 60202.08
Cement Loose 53 Grade - Metric Tonnes | UGWT Raft PCC M-15 | CEMENT | 11.6116 | 3880 | 45053.008 | 11.6116 | 3880 | 45053.008 | 11.6116 | 0 | 0 | 11.6116 | 0 | 11.6116 | 0 | 7400.0001 | 85925.8412 | 0 | 11.6116 | -10.64 | 10.64 | 259.5366 | 1978730.8697 | Metric Tonnes | 0 | 0 | 0 | 0 | 45053.008
Cement Loose 53 Grade - Metric Tonnes | UGWT Raft RS1 Concrete M-30 | CEMENT | 57.4 | 3880 | 222712 | 57.4 | 3880 | 222712 | 57.4 | 0 | 0 | 57.4 | 0 | 57.4 | 0 | 6729.6876 | 386284.0682 | 0 | 57.4 | 0 | 0 | 259.5366 | 1978730.8697 | Metric Tonnes | 0 | 0 | 0 | 0 | 222712
Cement Loose 53 Grade - Metric Tonnes | UGWT RCC Wall/Pardi Concrete M-30 | CEMENT | 124.642 | 3880 | 483610.96 | 123.392 | 3880 | 478760.96 | 123.392 | 1.25 | 0 | 123.392 | 0 | 123.392 | 0 | 7400.0001 | 913100.8123 | 0 | 123.392 | -73.025 | 73.025 | 259.5366 | 1978730.8697 | Metric Tonnes | 0 | 0 | 0 | 1.25 | 483610.96
Cement Loose 53 Grade - Metric Tonnes | UGWT RCC Plum Concrete Above Raft (C60-R40) | CEMENT | 64.469 | 3880 | 250139.72 | 0 | 0 | 0 | 0 | 64.469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10.01 | 10.01 | 259.5366 | 1978730.8697 | Metric Tonnes | 0 | 0 | 0 | 64.469 | 250139.72
Cement Loose 53 Grade - Metric Tonnes | UGWT RCC Footing Concrete M-30 | CEMENT | 11.563 | 3880 | 44864.44 | 0 | 0 | 0 | 0 | 11.563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.8 | 5.8 | 259.5366 | 1978730.8697 | Metric Tonnes | 0 | 0 | 0 | 11.563 | 44864.44
Cement Loose 53 Grade - Metric Tonnes | UGWT RCC Top Slab & Beam Concrete | CEMENT | 28.957 | 3880 | 112353.16 | 0 | 0 | 0 | 0 | 28.957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259.5366 | 1978730.8697 | Metric Tonnes | 0 | 0 | 0 | 28.957 | 112353.16
Cement Loose 53 Grade - Metric Tonnes | UGWT RCC Grid Slab Concrete | CEMENT | 12.76 | 3880 | 49508.8 | 12.76 | 3880 | 49508.8 | 12.76 | 0 | 0 | 12.76 | 0 | 12.76 | 0 | 7500 | 95700 | 12.76 | 0 | 12.76 | 0 | 259.5366 | 1978730.8697 | Metric Tonnes | 74765.625 | 0 | 0 | 0 | 49508.8
GP2 Waterproofing Chemical - Kgs | UGWT RCC Misc. Material for RCC Work | CONSUMABLE/MISC MATERIAL | 300 | 150 | 45000 | 150 | 150 | 22500 | 150 | 150 | 0 | 150 | 0 | 150 | 0 | 20.65 | 3097.5 | 150 | 0 | -140 | 290 | 975 | 20133.75 | Kgs | 2625 | 0 | 0 | 150 | 45000
Nitobond SBR (Latex) - Ltrs | UGWT RCC Misc. Material for RCC Work | CONSUMABLE/MISC MATERIAL | 60 | 265 | 15900 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60 | 60 | 250 | 56050 | Ltrs | 0 | 0 | 0 | 60 | 15900
Ready Mix Concrete M-10 Grade (D/P) - Cu.Mtrs | UGWT RCC Plum Concrete Below Raft (C60-R40) | RMC | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-10 Grade (D/P) - Cu.Mtrs | UGWT RCC Plum Concrete Above Raft (C60-R40) | RMC | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-15 Grade( D/P) - - Cu.Mtrs | UGWT RCC Plum Concrete Below Raft (C60-R40) | RMC | 10 | 3500 | 35000 | 10 | 3500 | 35000 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 4547.0001 | 45470.001 | 10 | 0 | 0 | 10 | 0 | 0 | Cu.Mtrs | 38533.9 | 0 | 0 | 0 | 35000
Ready Mix Concrete M-15 Grade( D/P) - - Cu.Mtrs | UGWT RCC Plum Concrete Above Raft (C60-R40) | RMC | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-15 Grade( PUMPABLE) - Cu.Mtrs | UGWT RCC Plum Concrete Below Raft (C60-R40) | RMC | 74.94 | 20 | 1498.8 | 74.94 | 20 | 1498.8 | 74.94 | 0 | 0 | 74.94 | 0 | 74.94 | 0 | 4728.9915 | 354390.623 | 74.94 | 0 | 0 | 74.94 | 0 | 0 | Cu.Mtrs | 300331.0428 | 0 | 0 | 0 | 1498.8
Ready Mix Concrete M-15 Grade( PUMPABLE) - Cu.Mtrs | UGWT RCC Plum Concrete Above Raft (C60-R40) | RMC | 57.06 | 20 | 1141.2 | 57.06 | 20 | 1141.2 | 57.06 | 0 | 0 | 57.06 | 0 | 57.06 | 0 | 4728.9915 | 269836.2567 | 57.06 | 0 | 0 | 57.06 | 0 | 0 | Cu.Mtrs | 228674.7972 | 0 | 0 | 0 | 1141.2
Ready Mix Concrete M-30 Grade (Pumpable) - Cu.Mtrs | UGWT Raft RS1 Concrete M-30 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-30 Grade (Pumpable) - Cu.Mtrs | UGWT RCC Wall/Pardi Concrete M-30 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Rubble - Cu.Ft | UGWT RCC Plum Concrete Below Raft (C60-R40) | SAND & METAL | 2762.74 | 10 | 27627.4 | 2194.763 | 10 | 21947.63 | 2194.763 | 567.977 | 0 | 2194.763 | 0 | 2194.763 | 0 | 23.0996 | 50698.2242 | 2194 | 0.763 | -203.4738 | 2397.4738 | 316 | 6967.82 | Cu.Ft | 48268 | 0 | 0 | 567.977 | 27627.4
Rubble - Cu.Ft | UGWT RCC Plum Concrete Above Raft (C60-R40) | SAND & METAL | 14607.8754 | 10 | 146078.754 | 14607.8754 | 10 | 146078.754 | 14607.8754 | 0 | 0 | 14607.8754 | 0 | 14607.8754 | 0 | 22.2093 | 324430.4526 | 6619.19 | 7988.6854 | -3265.3362 | 9884.5262 | 316 | 6967.82 | Cu.Ft | 141218.99 | 0 | 0 | 0 | 146078.754
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | UGWT RCC Plum Concrete Above Raft (C60-R40) | RMC | 6 | 3165.25 | 18991.5 | 6 | 3165.25 | 18991.5 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 3734.9967 | 22409.9802 | 6 | 0 | 0 | 6 | 0 | 0 | Cu.Mtrs | 18991.5 | 18991.5 | 0 | 0 | 0
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | UGWT RCC Plum Concrete Below Raft (C60-R40) | RMC | 110.83 | 2125 | 235513.75 | 110.83 | 2125 | 235513.75 | 110.83 | 0 | 0 | 110.83 | 0 | 87.88 | 22.95 | 3959.9974 | 348004.5707 | 86.88 | 1 | -1 | 87.88 | 0 | 0 | Cu.Mtrs | 291563.1984 | 0 | 22.95 | 0 | 235513.75
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | UGWT Raft PCC M-15 | RMC | 82.94 | 2125 | 176247.5 | 82.94 | 2125 | 176247.5 | 82.94 | 0 | 0 | 82.94 | 0 | 81.94 | 1 | 3959.9991 | 324482.3252 | 81.62 | 0.32 | 1.004 | 80.616 | 0 | 0 | Cu.Mtrs | 273911.1346 | 214779.648 | 1 | 0 | -38532.148
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | UGWT RCC Plum Concrete Above Raft (C60-R40) | RMC | 454.494 | 2125 | 965799.75 | 454.494 | 2125 | 965799.75 | 454.494 | 0 | 0 | 454.494 | 0 | 454.494 | 0 | 3959.9996 | 1799796.0407 | 454.49 | 0.004 | -0.004 | 454.494 | 0 | 0 | Cu.Mtrs | 1525237.4707 | 959796.552 | 0 | 0 | 6003.198
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | UGWT RCC Wall/Pardi Concrete M-30 | RMC | 25 | 3165.25 | 79131.25 | 25 | 3165.25 | 79131.25 | 25 | 0 | 0 | 25 | 0 | 25 | 0 | 3173.02 | 79325.5 | 6 | 19 | 0 | 6 | 0 | 0 | Cu.Mtrs | 16134 | 0 | 0 | 0 | 79131.25
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | UGWT Raft RS1 Concrete M-30 | RMC | 287 | 4012 | 1151444 | 287 | 4012 | 1151444 | 287 | 0 | 0 | 287 | 0 | 287 | 0 | 3959.9998 | 1136519.9426 | 287 | 0 | 0 | 287 | 0 | 0 | Cu.Mtrs | 963152.484 | 884288.082 | 0 | 0 | 267155.918
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | UGWT RCC Wall/Pardi Concrete M-30 | RMC | 591.96 | 4012 | 2374943.52 | 591.96 | 4012 | 2374943.52 | 591.96 | 0 | 0 | 591.96 | 0 | 591.96 | 0 | 3641.6829 | 2155730.6028 | 444.483 | 147.477 | -7.517 | 452 | 0 | 0 | Cu.Mtrs | 1426887.7402 | 474833.952 | 0 | 0 | 1900109.568
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | UGWT RCC Footing Concrete M-30 | RMC | 57.817 | 4012 | 231961.804 | 57.817 | 4012 | 231961.804 | 57.817 | 0 | 0 | 57.817 | 0 | 57.817 | 0 | 3959.9985 | 228955.235 | 57.817 | 0 | 28.817 | 29 | 0 | 0 | Cu.Mtrs | 194029.8628 | 97322.028 | 0 | 0 | 134639.776
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | UGWT RCC Top Slab & Beam Concrete | RMC | 144.79 | 4012 | 580897.48 | 0 | 0 | 0 | 0 | 144.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 144.79 | 580897.48
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | UGWT RCC Grid Slab Concrete | RMC | 63.8 | 4012 | 255965.6 | 63.8 | 4012 | 255965.6 | 63.8 | 0 | 0 | 63.8 | 0 | 63.8 | 0 | 3959.9982 | 252647.8864 | 26 | 37.8 | -28 | 54 | 0 | 0 | Cu.Mtrs | 87254.232 | 40271.184 | 0 | 0 | 215694.416
Steel Bar 25mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 668.84 | 50.85 | 34010.514 | 0 | 0 | 0 | 0 | 668.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -556 | 556 | 23262 | 1407220.6223 | Kgs | 0 | 0 | 0 | 668.84 | 34010.514
Steel Bars 10mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 17337.88 | 43 | 745528.84 | 9297.41 | 43 | 399788.63 | 9297.41 | 8040.47 | 0 | 9297.41 | 0 | 9297.41 | 0 | 78.361 | 728554.345 | 9297.41 | 0 | -8039.59 | 17337 | 17170 | 1038059.2409 | Kgs | 617418.6843 | 0 | 0 | 8040.47 | 745528.84
Steel Bars 10mm - Kgs | UGWT RCC Bottom Slab | STEEL | 6041.73 | 50.85 | 307221.9705 | 0 | 0 | 0 | 0 | 6041.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6024 | 6024 | 17170 | 1038059.2409 | Kgs | 0 | 0 | 0 | 6041.73 | 307221.9705
Steel Bars 10mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 2450.13 | 50.85 | 124589.1105 | 0 | 0 | 0 | 0 | 2450.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2442 | 2442 | 17170 | 1038059.2409 | Kgs | 0 | 0 | 0 | 2450.13 | 124589.1105
Steel Bars 10mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 6.43 | 50.85 | 326.9655 | 0 | 0 | 0 | 0 | 6.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17170 | 1038059.2409 | Kgs | 0 | 0 | 0 | 6.43 | 326.9655
Steel Bars 12mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 9437.35 | 43 | 405806.05 | 9437.35 | 43 | 405806.05 | 9437.35 | 0 | 0 | 9437.35 | 0 | 9437.35 | 0 | 76.4003 | 721015.9815 | 9437.35 | 0 | 4060.35 | 5377 | 18174 | 1081668.8622 | Kgs | 611030.2767 | 160035.4576 | 0 | 0 | 245770.5924
Steel Bars 12mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 1428.14 | 50.85 | 72620.919 | 0 | 0 | 0 | 0 | 1428.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -427 | 427 | 18174 | 1081668.8622 | Kgs | 0 | 0 | 0 | 1428.14 | 72620.919
Steel Bars 12mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 21.09 | 50.85 | 1072.4265 | 0 | 0 | 0 | 0 | 21.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18174 | 1081668.8622 | Kgs | 0 | 0 | 0 | 21.09 | 1072.4265
Steel Bars 16mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 41360 | 51 | 2109360 | 20799.89 | 51 | 1060794.39 | 20799.89 | 20560.11 | 0 | 20799.89 | 0 | 20799.89 | 0 | 73.4375 | 1527491.6016 | 20799.89 | 0 | -20181.11 | 40981 | 14385 | 855252.4386 | Kgs | 1294484.063 | 868907.746 | 0 | 20560.11 | 1240452.254
Steel Bars 16mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 1182.28 | 50.85 | 60118.938 | 0 | 0 | 0 | 0 | 1182.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1149 | 1149 | 14385 | 855252.4386 | Kgs | 0 | 0 | 0 | 1182.28 | 60118.938
Steel Bars 16mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 478.16 | 50.85 | 24314.436 | 0 | 0 | 0 | 0 | 478.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -455 | 455 | 14385 | 855252.4386 | Kgs | 0 | 0 | 0 | 478.16 | 24314.436
Steel Bars 20mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 821.82 | 50.85 | 41789.547 | 0 | 0 | 0 | 0 | 821.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29200.66 | 1761541.4524 | Kgs | 0 | 0 | 0 | 821.82 | 41789.547
Steel Bars 8mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 4259.18 | 53 | 225736.54 | 4259.18 | 53 | 225736.54 | 4259.18 | 0 | 0 | 4259.18 | 0 | 4259.18 | 0 | 69.9782 | 298049.8994 | 4259.18 | 0 | 68.336 | 4190.844 | 57790.88 | 3561377.8938 | Kgs | 252584.6685 | 366013.242 | 0 | 0 | -140276.702
Steel Bars 8mm - Kgs | UGWT RCC Bottom Slab | STEEL | 6888.27 | 53 | 365078.31 | 6888.27 | 53 | 365078.31 | 6888.27 | 0 | 0 | 6888.27 | 0 | 6888.27 | 0 | 79.591 | 548244.2976 | 6888.27 | 0 | 6082.27 | 806 | 57790.88 | 3561377.8938 | Kgs | 464613.8115 | 0 | 0 | 0 | 365078.31
Steel Bars 8mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 3494.57 | 50.85 | 177698.8845 | 0 | 0 | 0 | 0 | 3494.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -886 | 886 | 57790.88 | 3561377.8938 | Kgs | 0 | 0 | 0 | 3494.57 | 177698.8845
Steel Bars 8mm - Kgs | UGWT RCC Grid Slab Reinforcement Work | STEEL | 3425.02 | 50.85 | 174162.267 | 0 | 0 | 0 | 0 | 3425.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57790.88 | 3561377.8938 | Kgs | 0 | 0 | 0 | 3425.02 | 174162.267
Steel Bars 8mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 80.31 | 50.85 | 4083.7635 | 0 | 0 | 0 | 0 | 80.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57790.88 | 3561377.8938 | Kgs | 0 | 0 | 0 | 80.31 | 4083.7635