## Material Receipt Details6385820
Material Receipt Details
GANGA ALTUS
Page 1 of 1
Total Records: 397 Records 1 to 397
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Ready Mix Concrete M-15 Grade - Cu.Mtrs | Tower E PCC Footing PCC RMC M-15 | RMC | 6 | 2914 | 17484 | 6 | 2914 | 17484 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 3499.998 | 20999.988 | 6 | 0 | 0 | 6 | 0 | 0 | Cu.Mtrs | 17796.6 | 17796.6 | 0 | 0 | -312.6
Ready Mix Concrete M-20 Grade - Cu.Mtrs | Tower D Grade Slab RMC Grade Slab-(Cu.Mtrs) | RMC | 0 | 3961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-20 Grade Pump - Cu.Mtrs | Tower D Grade Slab RMC Grade Slab-(Cu.Mtrs) | RMC | 0 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-20 Grade Pump - Cu.Mtrs | F-Bldg LG Floor Trimix Work- Material | RMC | 56.38 | 3050 | 171959 | 56.38 | 3050 | 171959 | 56.38 | 0 | 0 | 56.38 | 0 | 56.38 | 0 | 4629.999 | 261039.3436 | 56.38 | 0 | 0 | 56.38 | 0 | 0 | Cu.Mtrs | 221219.7846 | 0 | 0 | 0 | 171959
Ready Mix Concrete M-20 Grade Pump - Cu.Mtrs | D-Bldg Parking Grade Slab D-Parking Grid Slab- Concrete Work | RMC | 6.76 | 3050 | 20618 | 6.76 | 3050 | 20618 | 6.76 | 0 | 0 | 6.76 | 0 | 6.76 | 0 | 4630.0002 | 31298.8014 | 5.12 | 1.64 | 0 | 5.12 | 0 | 0 | Cu.Mtrs | 20089.4874 | 0 | 0 | 0 | 20618
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | D-Bldg Parking Ret Wall RMC M-25-(Cu.Mtrs) | RMC | 48 | 3150 | 151200 | 48 | 3150 | 151200 | 48 | 0 | 0 | 48 | 0 | 48 | 0 | 4151.4219 | 199268.2506 | 48 | 0 | 0 | 48 | 119.5 | 571329.4771 | Cu.Mtrs | 168871.395 | 0 | 0 | 0 | 151200
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | RW-at UGWT side (Plinth to 1st Slab) Concrete Work M25 | RMC | 21.76 | 3150 | 68544 | 21.76 | 3150 | 68544 | 21.76 | 0 | 0 | 21.76 | 0 | 21.76 | 0 | 4649.9906 | 101183.7955 | 21.76 | 0 | 17.76 | 4 | 119.5 | 571329.4771 | Cu.Mtrs | 85748.9792 | 0 | 0 | 0 | 68544
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | Ret Wall E-Bldg-at Well side Concrete work-6m Raft+Pardi (Fo | RMC | 10.5 | 3150 | 33075 | 10.5 | 3150 | 33075 | 10.5 | 0 | 0 | 10.5 | 0 | 10.5 | 0 | 4649.9906 | 48824.9013 | 10.5 | 0 | 10.5 | 0 | 119.5 | 571329.4771 | Cu.Mtrs | 41377.035 | 0 | 0 | 0 | 33075
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | E-Bldg-3rd Slab RCC P2 Fl -Parapet Wall Concrete Work-M25 | RMC | 10.83 | 3150 | 34114.5 | 10.83 | 3150 | 34114.5 | 10.83 | 0 | 0 | 10.83 | 0 | 10.83 | 0 | 4649.9906 | 50359.3982 | 10.83 | 0 | 10.83 | 0 | 119.5 | 571329.4771 | Cu.Mtrs | 42677.4561 | 0 | 0 | 0 | 34114.5
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | E-Bldg-4th Slab RCC P3 Fl -Parapet Wall Concrete Work-M25 | RMC | 10.83 | 3150 | 34114.5 | 10.83 | 3150 | 34114.5 | 10.83 | 0 | 0 | 10.83 | 0 | 10.83 | 0 | 4649.9906 | 50359.3982 | 10.83 | 0 | 10.83 | 0 | 119.5 | 571329.4771 | Cu.Mtrs | 42677.4561 | 0 | 0 | 0 | 34114.5
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | E-Bldg-5th Slab RCC P5 Fl -Parapet Wall Concrete Work-M25 | RMC | 10.83 | 3150 | 34114.5 | 10.83 | 3150 | 34114.5 | 10.83 | 0 | 0 | 10.83 | 0 | 10.83 | 0 | 4649.9906 | 50359.3982 | 10.83 | 0 | 10.83 | 0 | 119.5 | 571329.4771 | Cu.Mtrs | 42677.4561 | 0 | 0 | 0 | 34114.5
Ready Mix Concrete M-30 Grade - Cu.Mtrs | D-31st to above Column Concrete | RMC | 8.768 | 3945 | 34589.76 | 8.768 | 3945 | 34589.76 | 8.768 | 0 | 0 | 8.768 | 0 | 8.768 | 0 | 4800.0035 | 42086.4307 | 8.768 | 0 | 0.008 | 8.76 | 0 | 0 | Cu.Mtrs | 35666.4704 | 24406.8 | 0 | 0 | 10182.96
Ready Mix Concrete M-30 Grade - Cu.Mtrs | Top Terrace LMR ,OHWT Concrete | RMC | 6.16 | 3945 | 24301.2 | 3.232 | 3945 | 12750.24 | 3.232 | 2.928 | 0 | 3.232 | 0 | 3.232 | 0 | 4800.0045 | 15513.6145 | 3.232 | 0 | -0.008 | 3.24 | 0 | 0 | Cu.Mtrs | 13147.1296 | 0 | 0 | 2.928 | 24301.2
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | Top Terrace LMR ,OHWT Concrete | RMC | 24 | 100 | 2400 | 24 | 100 | 2400 | 24 | 0 | 0 | 24 | 0 | 24 | 0 | 4949.9936 | 118799.8464 | 24 | 0 | 0 | 24 | 25.75 | 132020.4074 | Cu.Mtrs | 100677.84 | 0 | 0 | 0 | 2400
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | D-25th RCC Slab,Beam,ST Concrete | RMC | 18.56 | 100 | 1856 | 18.56 | 100 | 1856 | 18.56 | 0 | 0 | 18.56 | 0 | 18.56 | 0 | 4949.9937 | 91871.8831 | 18.56 | 0 | 0.56 | 18 | 25.75 | 132020.4074 | Cu.Mtrs | 77857.5296 | 0 | 0 | 0 | 1856
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | D-31st to above Column Concrete | RMC | 40.842 | 100 | 4084.2 | 40.69 | 100 | 4069 | 40.69 | 0.152 | 0 | 40.69 | 0 | 40.69 | 0 | 4949.9979 | 201415.414 | 40.69 | 0 | 0.69 | 40 | 25.75 | 132020.4074 | Cu.Mtrs | 170691.0264 | 54533.83 | 0 | 0.152 | -50449.63
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | 29th Slab 29th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.75 | 132020.4074 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | 30th Slab 30th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.75 | 132020.4074 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | 31st Slab- 30th to 31st Column Concrete- M30 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.75 | 132020.4074 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | E-OHWT LMR PARAPIT PARGOLA-M30 | RMC | 23 | 100 | 2300 | 23 | 100 | 2300 | 23 | 0 | 0 | 23 | 0 | 23 | 0 | 5127.0056 | 117921.1288 | 23 | 0 | 23 | 0 | 25.75 | 132020.4074 | Cu.Mtrs | 99933.16 | 0 | 0 | 0 | 2300
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | 24th Slab 24th Slab Concrete M30 | RMC | 2.75 | 100 | 275 | 2.75 | 100 | 275 | 2.75 | 0 | 0 | 2.75 | 0 | 2.75 | 0 | 4949.9937 | 13612.4827 | 2.75 | 0 | 1.5 | 1.25 | 25.75 | 132020.4074 | Cu.Mtrs | 11536.0025 | 0 | 0 | 0 | 275
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | 26th Slab 26th Slab,Beam,SW,ST Concrete M30 | RMC | 4.02 | 100 | 402 | 4.02 | 100 | 402 | 4.02 | 0 | 0 | 4.02 | 0 | 4.02 | 0 | 4949.9946 | 19898.9783 | 3 | 1.02 | 0 | 3 | 25.75 | 132020.4074 | Cu.Mtrs | 12584.73 | 0 | 0 | 0 | 402
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | 27th Slab 27th Slab Concrete M30 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.75 | 132020.4074 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-30 Grade FF (Downpour) - Cu.Mtrs | 28th Slab (Refuge) 28th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.75 | 132020.4074 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 28th Slab (Refuge) 28th Slab,Beam,SW,ST Concrete M30 | RMC | 290.27 | 100 | 29027 | 290.27 | 100 | 29027 | 290.27 | 0 | 0 | 290.27 | 0 | 290.27 | 0 | 5132.1395 | 1489706.1385 | 290.27 | 0 | 3.51 | 286.76 | 314.01 | 1682350.9636 | Cu.Mtrs | 1262462.8434 | 0 | 0 | 0 | 29027
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 28th Slab (Refuge) 28th Slab Concrete M30 | RMC | 80.74 | 100 | 8074 | 80.74 | 100 | 8074 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 5129.9992 | 414196.1354 | 80.74 | 0 | 0 | 80.74 | 314.01 | 1682350.9636 | Cu.Mtrs | 351013.6782 | 0 | 0 | 0 | 8074
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 27th Slab 27th Slab Concrete M30 | RMC | 80.74 | 100 | 8074 | 80.74 | 100 | 8074 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 5140.9822 | 415082.9064 | 80.74 | 0 | 5.01 | 75.73 | 314.01 | 1682350.9636 | Cu.Mtrs | 351765.1782 | 329232.9186 | 0 | 0 | -321158.9186
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 27th Slab 27th Slab,Beam,SW,ST Concrete M30 | RMC | 290.27 | 100 | 29027 | 290.27 | 100 | 29027 | 290.27 | 0 | 0 | 290.27 | 0 | 290.27 | 0 | 5129.9992 | 1489084.8678 | 290.27 | 0 | 0 | 290.27 | 314.01 | 1682350.9636 | Cu.Mtrs | 1261936.3434 | 1261936.3434 | 0 | 0 | -1232909.3434
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 26th Slab 26th Slab,Beam,SW,ST Concrete M30 | RMC | 286.25 | 100 | 28625 | 286.25 | 100 | 28625 | 286.25 | 0 | 0 | 286.25 | 0 | 286.25 | 0 | 5129.9992 | 1468462.271 | 286.25 | 0 | 0 | 286.25 | 314.01 | 1682350.9636 | Cu.Mtrs | 1244459.5663 | 1244459.5663 | 0 | 0 | -1215834.5663
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 26th Slab 26th Slab Concrete M30 | RMC | 80.74 | 100 | 8074 | 80.74 | 100 | 8074 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 5129.9992 | 414196.1354 | 80.74 | 0 | 0 | 80.74 | 314.01 | 1682350.9636 | Cu.Mtrs | 351013.6782 | 346709.6958 | 0 | 0 | -338635.6958
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 25th Slab 25th Slab Concrete M30 | RMC | 80.74 | 100 | 8074 | 80.74 | 100 | 8074 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 5129.9992 | 414196.1354 | 80.74 | 0 | 0 | 80.74 | 314.01 | 1682350.9636 | Cu.Mtrs | 351013.6782 | 0 | 0 | 0 | 8074
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 25th Slab 25th Slab,Beam,SW,ST Concrete M30 | RMC | 290.27 | 100 | 29027 | 290.27 | 100 | 29027 | 290.27 | 0 | 0 | 290.27 | 0 | 290.27 | 0 | 5129.9992 | 1489084.8678 | 290.27 | 0 | 0 | 290.27 | 314.01 | 1682350.9636 | Cu.Mtrs | 1261936.3434 | 0 | 0 | 0 | 29027
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | E-OHWT LMR PARAPIT PARGOLA-M30 | RMC | 176.5 | 100 | 17650 | 176.5 | 100 | 17650 | 176.5 | 0 | 0 | 176.5 | 0 | 176.5 | 0 | 5483.3254 | 967806.9379 | 119.06 | 57.44 | 67.06 | 52 | 314.01 | 1682350.9636 | Cu.Mtrs | 548941.7904 | 0 | 0 | 0 | 17650
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 31st Slab- 30th to 31st Column Concrete- M30 | RMC | 213.8 | 100 | 21380 | 213.8 | 100 | 21380 | 213.8 | 0 | 0 | 213.8 | 0 | 213.8 | 0 | 5306.9993 | 1134636.452 | 213.8 | 0 | 213.8 | 0 | 314.01 | 1682350.9636 | Cu.Mtrs | 961556.3066 | 0 | 0 | 0 | 21380
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 31st Slab- 31st Slab,Beam ST Concrete- M30 | RMC | 173.6 | 100 | 17360 | 173.6 | 100 | 17360 | 173.6 | 0 | 0 | 173.6 | 0 | 173.6 | 0 | 5306.9993 | 921295.0785 | 173.6 | 0 | 19.6 | 154 | 314.01 | 1682350.9636 | Cu.Mtrs | 780758.5352 | 0 | 0 | 0 | 17360
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 30th Slab 30th Slab,Beam,SW,ST Concrete M30 | RMC | 290.27 | 100 | 29027 | 290.27 | 100 | 29027 | 290.27 | 0 | 0 | 290.27 | 0 | 290.27 | 0 | 5131.8346 | 1489617.6384 | 290.27 | 0 | 3.01 | 287.26 | 314.01 | 1682350.9636 | Cu.Mtrs | 1262387.8434 | 0 | 0 | 0 | 29027
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 30th Slab 30th Slab Concrete M30 | RMC | 80.74 | 100 | 8074 | 80.74 | 100 | 8074 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 5129.9992 | 414196.1354 | 80.74 | 0 | 0 | 80.74 | 314.01 | 1682350.9636 | Cu.Mtrs | 351013.6782 | 0 | 0 | 0 | 8074
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 29th Slab 29th Slab,Beam,SW,ST Concrete M30 | RMC | 290.27 | 100 | 29027 | 290.27 | 100 | 29027 | 290.27 | 0 | 0 | 290.27 | 0 | 290.27 | 0 | 5130.6151 | 1489263.638 | 290.27 | 0 | 1.01 | 289.26 | 314.01 | 1682350.9636 | Cu.Mtrs | 1262087.8434 | 0 | 0 | 0 | 29027
Ready Mix Concrete M-30 Grade FF (Pumpable) - Cu.Mtrs | 29th Slab 29th Slab Concrete M30 | RMC | 80.74 | 100 | 8074 | 80.74 | 100 | 8074 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 5129.9992 | 414196.1354 | 80.74 | 0 | 1.01 | 79.73 | 314.01 | 1682350.9636 | Cu.Mtrs | 351013.6782 | 0 | 0 | 0 | 8074
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | D-Bldg Parking Substructure Footing-RMC-M35 | RMC | 13.55 | 4400 | 59620 | 13.55 | 4400 | 59620 | 13.55 | 0 | 0 | 13.55 | 0 | 13.55 | 0 | 5085.5565 | 68909.2909 | 13.55 | 0 | 6.55 | 7 | 10.5 | 54358.3999 | Cu.Mtrs | 58397.7 | 0 | 0 | 0 | 59620
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | Tower E Footing M-35 Concrete | RMC | 170.5 | 4400 | 750200 | 170.5 | 4400 | 750200 | 170.5 | 0 | 0 | 170.5 | 0 | 170.5 | 0 | 4324.0038 | 737242.6479 | 170.5 | 0 | 0 | 170.5 | 10.5 | 54358.3999 | Cu.Mtrs | 624781.905 | 588137.805 | 0 | 0 | 162062.195
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | Tower D Footing RMC M-35 | RMC | 7.29 | 4400 | 32076 | 7.29 | 4400 | 32076 | 7.29 | 0 | 0 | 7.29 | 0 | 7.29 | 0 | 4999.9986 | 36449.9898 | 7 | 0.29 | 0 | 7 | 10.5 | 54358.3999 | Cu.Mtrs | 29661.016 | 0 | 0 | 0 | 32076
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | D&E Bldg Between-P3-4th Slab RCC- Slab,Beam Concrete - 1 | RMC | 7 | 4400 | 30800 | 7 | 4400 | 30800 | 7 | 0 | 0 | 7 | 0 | 7 | 0 | 4999.9994 | 34999.9958 | 7 | 0 | 0 | 7 | 10.5 | 54358.3999 | Cu.Mtrs | 29661.016 | 0 | 0 | 0 | 30800
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | 1st PT Slab,Beam Concrete | RMC | 4 | 4400 | 17600 | 4 | 4400 | 17600 | 4 | 0 | 0 | 4 | 0 | 3.95 | 0.05 | 5176.99 | 20449.1105 | 3.95 | 0 | 3.95 | 0 | 10.5 | 54358.3999 | Cu.Mtrs | 17329.756 | 0 | 0.05 | 0 | 17600
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | D&E Bldg Between-P2-3rd Slab RCC 3rd Slab,Beam Concrete - | RMC | 0.01 | 100 | 1 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0.01 | 1
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | Tower D Footing RMC M-35 | RMC | 6 | 100 | 600 | 6 | 100 | 600 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 5180.0001 | 31080.0006 | 6 | 0 | 0.5 | 5.5 | 0 | 0 | Cu.Mtrs | 26338.98 | 0 | 0 | 0 | 600
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | D-Bldg Parking Substructure Footing-RMC-M35 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | 2nd Slab RCC 2nd Slab,Beam Concrete | RMC | 53 | 100 | 5300 | 53 | 100 | 5300 | 53 | 0 | 0 | 53 | 0 | 53 | 0 | 5179.9994 | 274539.9682 | 52.5 | 0.5 | -0.5 | 53 | 0 | 0 | Cu.Mtrs | 230466.075 | 0 | 0 | 0 | 5300
Ready Mix Concrete M-40 Grade (Downpour) - Cu.Mtrs | E-P4-5th Slab RCC 5th Slab,Beam,ST Concrete | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-40 Grade (Downpour) - Cu.Mtrs | D-P4-5th Slab RCC P4-Parking 5th Slab Concrete | RMC | 57 | 100 | 5700 | 57 | 100 | 5700 | 57 | 0 | 0 | 57 | 0 | 57 | 0 | 5199.9888 | 296399.3598 | 57 | 0 | 0 | 57 | 0 | 0 | Cu.Mtrs | 251185.89 | 202711.42 | 0 | 0 | -197011.42
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-P4-5th Slab RCC P4-Parking 5th Slab Concrete | RMC | 111.06 | 100 | 11106 | 111.06 | 100 | 11106 | 111.06 | 0 | 0 | 111.06 | 0 | 111.06 | 0 | 5386.213 | 598192.8172 | 111.06 | 0 | 1.56 | 109.5 | 159.5 | 886119.7639 | Cu.Mtrs | 506943.0792 | 248482.94 | 0 | 0 | -237376.94
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | E-P4-5th Slab RCC 5th Slab,Beam,ST Concrete | RMC | 93.8 | 100 | 9380 | 93.8 | 100 | 9380 | 93.8 | 0 | 0 | 93.8 | 0 | 93.8 | 0 | 5379.9976 | 504643.7761 | 93.72 | 0.08 | 2.21 | 91.51 | 159.5 | 886119.7639 | Cu.Mtrs | 427299.4704 | 0 | 0 | 0 | 9380
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | E-UGF-1st Slab RCC Slab Beam Concrete | RMC | 6.25 | 100 | 625 | 6.25 | 100 | 625 | 6.25 | 0 | 0 | 6.25 | 0 | 6.25 | 0 | 5556.9973 | 34731.2331 | 6.25 | 0 | 6.25 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 29433.25 | 0 | 0 | 0 | 625
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | 24th Slab 24th Slab Concrete M30 | RMC | 1.26 | 100 | 126 | 1.26 | 100 | 126 | 1.26 | 0 | 0 | 1.26 | 0 | 1.26 | 0 | 5822.4977 | 7336.3471 | 1.26 | 0 | 1.26 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 6217.2432 | 0 | 0 | 0 | 126
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | 20th Slab 20th Slab,Beam,SW,ST Concrete M40 | RMC | 33.47 | 100 | 3347 | 33.47 | 100 | 3347 | 33.47 | 0 | 0 | 33.47 | 0 | 33.47 | 0 | 5379.9976 | 180068.5209 | 33.47 | 0 | 8.48 | 24.99 | 159.5 | 886119.7639 | Cu.Mtrs | 152600.4404 | 2279.66 | 0 | 0 | 1067.34
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | Top Terrace LMR ,OHWT Concrete | RMC | 81.65 | 100 | 8165 | 81.65 | 100 | 8165 | 81.65 | 0 | 0 | 81.65 | 0 | 81.65 | 0 | 5640.4033 | 460538.9316 | 81.65 | 0 | 81.65 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 390287.228 | 0 | 0 | 0 | 8165
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-27th Slab RCC 26th to 27th Column Concrete | RMC | 8.51 | 100 | 851 | 8.51 | 100 | 851 | 8.51 | 0 | 0 | 8.51 | 0 | 8.51 | 0 | 5822.4977 | 49549.4554 | 0.09 | 8.42 | 0.09 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 444.0888 | 0 | 0 | 0 | 851
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-29th Slab RCC 29th Slab,Beam,ST Concrete | RMC | 3.41 | 100 | 341 | 3.41 | 100 | 341 | 3.41 | 0 | 0 | 3.41 | 0 | 3.41 | 0 | 5822.4977 | 19854.7172 | 3.41 | 0 | 3.41 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 16826.0312 | 0 | 0 | 0 | 341
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-26th Slab RCC 25th to 26th Column Concrete | RMC | 8.56 | 100 | 856 | 8.56 | 100 | 856 | 8.56 | 0 | 0 | 8.56 | 0 | 8.56 | 0 | 5822.4977 | 49840.5803 | 0 | 8.56 | 0 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 0 | 0 | 0 | 0 | 856
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-21st Slab RCC 20th to 21st Column Concrete-(Cu.Mtrs) | RMC | 2.1 | 100 | 210 | 2.1 | 100 | 210 | 2.1 | 0 | 0 | 2.1 | 0 | 2.1 | 0 | 5822.4977 | 12227.2452 | 0 | 2.1 | 0 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 0 | 0 | 0 | 0 | 210
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | 16th Slab,Beam,SW,ST Concrete M40 | RMC | 9.86 | 100 | 986 | 9.86 | 100 | 986 | 9.86 | 0 | 0 | 9.86 | 0 | 9.86 | 0 | 5379.9976 | 53046.7763 | 9.86 | 0 | 9.86 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 44954.8952 | 0 | 0 | 0 | 986
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D&E Bldg Between-P5-5th Slab RCC 4th to 5th column concrete | RMC | 22.61 | 100 | 2261 | 22.61 | 100 | 2261 | 22.61 | 0 | 0 | 22.61 | 0 | 22.61 | 0 | 5465.9142 | 123584.3196 | 22.61 | 0 | 22.61 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 104732.4752 | 0 | 0 | 0 | 2261
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-7th Slab RCC 1st Floor slab,beam,ST Concrete | RMC | 5.1 | 100 | 510 | 5.1 | 100 | 510 | 5.1 | 0 | 0 | 5.1 | 0 | 5.1 | 0 | 5556.9973 | 28340.6862 | 5.1 | 0 | 5.1 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 24017.532 | 0 | 0 | 0 | 510
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-8th Slab Concrete-M40 | RMC | 2.46 | 100 | 246 | 2.46 | 100 | 246 | 2.46 | 0 | 0 | 2.46 | 0 | 2.46 | 0 | 5379.9975 | 13234.7939 | 2.46 | 0 | 2.46 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 11215.9272 | 0 | 0 | 0 | 246
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-11th Slab RCC Concrete | RMC | 4.5 | 100 | 450 | 4.5 | 100 | 450 | 4.5 | 0 | 0 | 4.5 | 0 | 4.5 | 0 | 5379.9982 | 24209.9919 | 4.5 | 0 | 4.5 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 20516.94 | 0 | 0 | 0 | 450
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-13th Slab RCC Concrete | RMC | 4.93 | 100 | 493 | 4.93 | 100 | 493 | 4.93 | 0 | 0 | 4.93 | 0 | 4.93 | 0 | 5379.9976 | 26523.3882 | 4.93 | 0 | 4.93 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 22477.4476 | 0 | 0 | 0 | 493
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-17th Slab RCC 16th to 17th Slab Concrete | RMC | 2.3 | 100 | 230 | 2.3 | 100 | 230 | 2.3 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 5379.9976 | 12373.9945 | 2.3 | 0 | 2.3 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 10486.436 | 0 | 0 | 0 | 230
Ready Mix Concrete M-40 Grade (Pumpable) - Cu.Mtrs | D-18th Slab RCC 18th Slab,Beam,ST Concrete | RMC | 2.83 | 100 | 283 | 2.83 | 100 | 283 | 2.83 | 0 | 0 | 2.83 | 0 | 2.83 | 0 | 5379.9982 | 15225.3949 | 2.83 | 0 | 2.83 | 0 | 159.5 | 886119.7639 | Cu.Mtrs | 12902.8756 | 0 | 0 | 0 | 283
Ready Mix Concrete M50 Easycrete (Downpour) - Cu.Mtrs | Tower D Column Upto Grid Readymix Concrete RMC M-50 | RMC | 9.79 | 3150 | 30838.5 | 9.79 | 3150 | 30838.5 | 9.79 | 0 | 0 | 9.79 | 0 | 9.79 | 0 | 5321.4801 | 52097.2902 | 9.79 | 0 | 0 | 9.79 | 0 | 0 | Cu.Mtrs | 44150.2469 | 0 | 0 | 0 | 30838.5
Ready Mix Concrete M50 Easycrete (Downpour) - Cu.Mtrs | D-UGF-1st Column Grid to 1st Slab RCC RMC M-50 | RMC | 33.64 | 3150 | 105966 | 33.64 | 3150 | 105966 | 33.64 | 0 | 0 | 33.64 | 0 | 33.64 | 0 | 5321.4803 | 179014.598 | 33.64 | 0 | 0 | 33.64 | 0 | 0 | Cu.Mtrs | 151707.2836 | 0 | 0 | 0 | 105966
Ready Mix Concrete M50 Easycrete (Downpour) - Cu.Mtrs | D-P1-2nd Slab RCC Column 1st Slab To 2nd Slab Concrete | RMC | 42 | 3150 | 132300 | 51.94 | 3150 | 163611 | 42 | -9.94 | 9.94 | 42 | 9.94 | 42 | 0 | 5321.4803 | 223502.1726 | 42 | 0 | 0 | 42 | 0 | 0 | Cu.Mtrs | 189408.618 | 0 | 9.94 | -9.94 | 132300
Ready Mix Concrete M50 Easycrete (Downpour) - Cu.Mtrs | D&EBldg Between-LGF-1st Slab Shear Wall RCC RMC M-50 | RMC | 30.07 | 3150 | 94720.5 | 30.07 | 3150 | 94720.5 | 30.07 | 0 | 0 | 30.07 | 0 | 30.07 | 0 | 5321.4801 | 160016.9066 | 30.07 | 0 | 0 | 30.07 | 0 | 0 | Cu.Mtrs | 135607.551 | 0 | 0 | 0 | 94720.5
Ready Mix Concrete M50 Regular Downpour - Cu.Mtrs | D-Bldg Parking Tie Beam Readymix Concrete RMC M50 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M50 Regular Pumpable - Cu.Mtrs | D,E,Podium- Parking Superstructure Adjusted Concrete Qty-M50 | RMC | 6.258 | 3950 | 24719.1 | 6.258 | 3950 | 24719.1 | 6.258 | 0 | 0 | 6.258 | 0 | 6.258 | 0 | 5957.0058 | 37278.9423 | 6.258 | 0 | 6.258 | 0 | 16 | 95312.1 | Cu.Mtrs | 31592.324 | 0 | 0 | 0 | 24719.1
Ready Mix Concrete M50 Regular Pumpable - Cu.Mtrs | E-UGF-1st Slab RCC Slab Beam Concrete | RMC | 0.75 | 3950 | 2962.5 | 0.75 | 3950 | 2962.5 | 0.75 | 0 | 0 | 0.75 | 0 | 0.75 | 0 | 5957.0058 | 4467.7544 | 0 | 0.75 | 0 | 0 | 16 | 95312.1 | Cu.Mtrs | 0 | 0 | 0 | 0 | 2962.5
Ready Mix Concrete M50 Regular Pumpable - Cu.Mtrs | E-P2-3rd Slab RCC Column 2nd to 3rd concrete-(Cu.Mtrs) - 1 | RMC | 35.27 | 3950 | 139316.5 | 35.27 | 3950 | 139316.5 | 35.27 | 0 | 0 | 35.27 | 0 | 35.27 | 0 | 5957.0058 | 210103.5946 | 9.742 | 25.528 | 9.742 | 0 | 16 | 95312.1 | Cu.Mtrs | 49180.636 | 0 | 0 | 0 | 139316.5
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | E-Bldg Parking Ret Wall PCC RMC M15(Downpour)-(Cu.Mtrs) | RMC | 5.75 | 2125 | 12218.75 | 5.75 | 2125 | 12218.75 | 5.75 | 0 | 0 | 5.75 | 0 | 5.75 | 0 | 3199.9949 | 18399.9707 | 5.75 | 0 | 5.75 | 0 | 23.5 | 79900.026 | Cu.Mtrs | 15593.195 | 0 | 0 | 0 | 12218.75
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | E-Bldg Parking Substructure PCC RMC M15(Downpour)-(Cu.Mtrs) | RMC | 7.03 | 2125 | 14938.75 | 7.03 | 2125 | 14938.75 | 7.03 | 0 | 0 | 7.03 | 0 | 7.03 | 0 | 3212.9984 | 22587.3788 | 7.03 | 0 | 7.03 | 0 | 23.5 | 79900.026 | Cu.Mtrs | 19141.8464 | 19141.8464 | 0 | 0 | -4203.0964
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | D&E -Bldg Between Parking Substructure PCC RMC M15(Downpour) | RMC | 14.38 | 2125 | 30557.5 | 14.38 | 2125 | 30557.5 | 14.38 | 0 | 0 | 14.38 | 0 | 14.38 | 0 | 3212.9984 | 46202.917 | 14.38 | 0 | 0.38 | 14 | 23.5 | 79900.026 | Cu.Mtrs | 39155.0144 | 39155.0144 | 0 | 0 | -8597.5144
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | Between D&E-Bldg Parking Ret Wall PCC RMC M15(Downpour)-(Cu. | RMC | 3.7 | 2125 | 7862.5 | 3.7 | 2125 | 7862.5 | 3.7 | 0 | 0 | 3.7 | 0 | 3.7 | 0 | 3199.9948 | 11839.9808 | 3.7 | 0 | 0 | 3.7 | 23.5 | 79900.026 | Cu.Mtrs | 10033.882 | 0 | 0 | 0 | 7862.5
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | Footing PCC work-M15 | RMC | 19.46 | 2125 | 41352.5 | 19.46 | 2125 | 41352.5 | 19.46 | 0 | 0 | 19.46 | 0 | 19.46 | 0 | 2200.5999 | 42823.6734 | 19.46 | 0 | 0 | 19.46 | 23.5 | 79900.026 | Cu.Mtrs | 36291.2459 | 36291.2459 | 0 | 0 | 5061.2541
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | PCC Below Strap Beam | RMC | 1.95 | 2125 | 4143.75 | 1.95 | 2125 | 4143.75 | 1.95 | 0 | 0 | 1.95 | 0 | 1.95 | 0 | 2200.5997 | 4291.1694 | 1.95 | 0 | 0 | 1.95 | 23.5 | 79900.026 | Cu.Mtrs | 3636.5843 | 3636.5843 | 0 | 0 | 507.1657
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | PCC Below Tie Beam | RMC | 6.75 | 2125 | 14343.75 | 6.75 | 2125 | 14343.75 | 6.75 | 0 | 0 | 6.75 | 0 | 6.75 | 0 | 2200.5997 | 14854.048 | 6.75 | 0 | 2.77 | 3.98 | 23.5 | 79900.026 | Cu.Mtrs | 12588.1763 | 12588.1763 | 0 | 0 | 1755.5737
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | Tower D PCC Footing PCC RMC M15(Downpour)-(Cu.Mtrs) | RMC | 180 | 2125 | 382500 | 180 | 2125 | 382500 | 180 | 0 | 0 | 180 | 0 | 180 | 0 | 3213.3932 | 578410.7828 | 180 | 0 | 17 | 163 | 23.5 | 79900.026 | Cu.Mtrs | 490178.6209 | 489742.9601 | 0 | 0 | -107242.9601
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | F-Bldg Shop Stairacse Tappa PCC Work | RMC | 13.21 | 2125 | 28071.25 | 13.21 | 2125 | 28071.25 | 13.21 | 0 | 0 | 13.21 | 0 | 13.21 | 0 | 3228.9991 | 42655.0781 | 13.21 | 0 | 0.21 | 13 | 23.5 | 79900.026 | Cu.Mtrs | 36148.3724 | 36148.3724 | 0 | 0 | -8077.1224
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | Extra work F-Bldg Extra PCC | RMC | 40.11 | 2125 | 85233.75 | 40.11 | 2125 | 85233.75 | 40.11 | 0 | 0 | 40.11 | 0 | 40.11 | 0 | 3226.8723 | 129429.8493 | 40.11 | 0 | 0 | 40.11 | 23.5 | 79900.026 | Cu.Mtrs | 109686.3073 | 42937.0086 | 0 | 0 | 42296.7414
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | D-Bldg Parking Substructure PCC RMC M15(Downpour)-(Cu.Mtrs) | RMC | 7.03 | 2125 | 14938.75 | 7.03 | 2125 | 14938.75 | 7.03 | 0 | 0 | 7.03 | 0 | 7.03 | 0 | 3212.9984 | 22587.3788 | 7.03 | 0 | 7.03 | 0 | 23.5 | 79900.026 | Cu.Mtrs | 19141.8464 | 19141.8464 | 0 | 0 | -4203.0964
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | D-Bldg Parking Ret Wall Raft PCC RMC M15(Downpour)-(Cu.Mtrs) | RMC | 12.57 | 2125 | 26711.25 | 12.57 | 2125 | 26711.25 | 12.57 | 0 | 0 | 12.57 | 0 | 12.57 | 0 | 3212.9985 | 40387.3911 | 12.57 | 0 | -142 | 154.57 | 23.5 | 79900.026 | Cu.Mtrs | 34226.6016 | 34226.6016 | 0 | 0 | -7515.3516
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | Tower E PCC Footing PCC RMC M15(Downpour)-(Cu.Mtrs) | RMC | 175.47 | 2125 | 372873.75 | 175.47 | 2125 | 372873.75 | 175.47 | 0 | 0 | 175.47 | 0 | 175.47 | 0 | 3206.2076 | 562593.2517 | 175.47 | 0 | 52.47 | 123 | 23.5 | 79900.026 | Cu.Mtrs | 476773.928 | 15139.2128 | 0 | 0 | 357734.5372
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | Retaining Wall Raft PCC M15 | RMC | 2.74 | 2125 | 5822.5 | 0 | 0 | 0 | 0 | 2.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.74 | 2.74 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 2.74 | 5822.5
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | 2nd PT sunk slab filling- PCC | RMC | 20 | 2125 | 42500 | 20 | 2125 | 42500 | 20 | 0 | 0 | 20 | 0 | 20 | 0 | 3869.9976 | 77399.9514 | 14 | 6 | 14 | 0 | 0 | 0 | Cu.Mtrs | 48940.64 | 48940.64 | 0 | 0 | -6440.64
Sand-Metal Mix M20 (Downpour) - Cu.Mtrs | Grid Slab Grid Slab Concrete M20 | RMC | 103.26 | 1948 | 201150.48 | 130 | 1948 | 253240 | 103.26 | -26.74 | 26.74 | 103.26 | 26.74 | 92.41 | 10.85 | 3734.995 | 345150.8907 | 92.41 | 0 | 17.16 | 75.25 | 0 | 0 | Cu.Mtrs | 292500.7525 | 66470.25 | 37.59 | -26.74 | 134680.23
Sand-Metal Mix M20 (Downpour) - Cu.Mtrs | Tower D Grade Slab RMC Grade Slab-(Cu.Mtrs) | RMC | 134.5 | 1948 | 262006 | 134.5 | 1948 | 262006 | 134.5 | 0 | 0 | 134.5 | 0 | 109 | 25.5 | 3258.7245 | 355200.9666 | 109 | 0 | -25.5 | 134.5 | 0 | 0 | Cu.Mtrs | 301017.759 | 301017.759 | 25.5 | 0 | -39011.759
Sand-Metal Mix M20 (Downpour) - Cu.Mtrs | Tower E Grade Slab Concrete-M20 | RMC | 137.01 | 1948 | 266895.48 | 137.01 | 1948 | 266895.48 | 137.01 | 0 | 0 | 137.01 | 0 | 128 | 9.01 | 3566.5741 | 456521.4827 | 128 | 0 | 18.82 | 109.18 | 0 | 0 | Cu.Mtrs | 386882.6065 | 320134.742 | 9.01 | 0 | -53239.262
Sand-Metal Mix M20 (Downpour) - Cu.Mtrs | D&E Podium Grid Slab Concrete-M20 | RMC | 28 | 1948 | 54544 | 28 | 1948 | 54544 | 28 | 0 | 0 | 28 | 0 | 28 | 0 | 3924.9996 | 109899.9888 | 28 | 0 | 28 | 0 | 0 | 0 | Cu.Mtrs | 93135.588 | 93135.588 | 0 | 0 | -38591.588
Sand-Metal Mix M20 (Downpour) - Cu.Mtrs | E-Bldg Parking Grade Slab Concrete-M20 | RMC | 19.39 | 1948 | 37771.72 | 17 | 1948 | 33116 | 17 | 2.39 | 0 | 17 | 0 | 17 | 0 | 2817.2427 | 47893.126 | 17 | 0 | -1 | 18 | 0 | 0 | Cu.Mtrs | 40587.386 | 21432.306 | 0 | 2.39 | 16339.414
Sand-Metal Mix M20 (Pumpable) - Cu.Mtrs | E-Bldg Parking Grade Slab Concrete-M20 | RMC | 40 | 2125 | 85000 | 40 | 2125 | 85000 | 40 | 0 | 0 | 40 | 0 | 40 | 0 | 3960 | 158400 | 40 | 0 | 15 | 25 | 0 | 0 | Cu.Mtrs | 134237.28 | 0 | 0 | 0 | 85000
Sand-Metal Mix M20 (Pumpable) - Cu.Mtrs | D&E Podium Grid Slab Concrete-M20 | RMC | 100.75 | 2125 | 214093.75 | 100.75 | 2125 | 214093.75 | 100.75 | 0 | 0 | 100.75 | 0 | 82 | 18.75 | 4112.9237 | 337259.7474 | 82 | 0 | 50 | 32 | 0 | 0 | Cu.Mtrs | 285813.352 | 265677.76 | 18.75 | 0 | -51584.01
Sand-Metal Mix M20 (Pumpable) - Cu.Mtrs | D-Bldg Parking Grade Slab D-Parking Grid Slab- Concrete Work | RMC | 50 | 2125 | 106250 | 20 | 2125 | 42500 | 20 | 30 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | -50 | 50 | 0 | 0 | Cu.Mtrs | 0 | 0 | 20 | 30 | 106250
Sand-Metal Mix M20 (Pumpable) - Cu.Mtrs | Tower D Grade Slab RMC Grade Slab-(Cu.Mtrs) | RMC | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M20 (Pumpable) - Cu.Mtrs | F-Bldg LG Floor Trimix Work- Material | RMC | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | P5-Fl Parapet Wall RCC Concrete Work M25 | RMC | 6.95 | 2000 | 13900 | 6.95 | 2000 | 13900 | 6.95 | 0 | 0 | 6.95 | 0 | 6.95 | 0 | 3400.0001 | 23630.0007 | 0.41 | 6.54 | -6.54 | 6.95 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 13900
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | P3-Fl Parapet Wall RCC Concrete Work M25 | RMC | 6.95 | 2000 | 13900 | 6.95 | 2000 | 13900 | 6.95 | 0 | 0 | 6.95 | 0 | 6.95 | 0 | 3400.0001 | 23630.0007 | 0 | 6.95 | -6.95 | 6.95 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 13900
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | P2-Fl Parapet Wall RCC Concrete Work M25 | RMC | 6.95 | 2000 | 13900 | 6.95 | 2000 | 13900 | 6.95 | 0 | 0 | 6.95 | 0 | 6.95 | 0 | 3400.0001 | 23630.0007 | 0 | 6.95 | -6.95 | 6.95 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 13900
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | P1-Fl Parapet Wall RCC Concrete Work M25 | RMC | 6.95 | 2000 | 13900 | 6.95 | 2000 | 13900 | 6.95 | 0 | 0 | 6.95 | 0 | 0 | 6.95 | 0 | 0 | 0 | 0 | -6.95 | 6.95 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 6.95 | 0 | 13900
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | Retaining Wall Raft Concrete-M25 | RMC | 11.08 | 2000 | 22160 | 11.08 | 2000 | 22160 | 11.08 | 0 | 0 | 11.08 | 0 | 11.08 | 0 | 3750.0013 | 41550.0144 | 11.08 | 0 | -1.29 | 12.37 | 19 | 64600.0038 | Cu.Mtrs | 35211.8744 | 35211.8744 | 0 | 0 | -13051.8744
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | Retaining Wall Concrete M-25 | RMC | 27.66 | 2000 | 55320 | 27.66 | 2000 | 55320 | 27.66 | 0 | 0 | 27.66 | 0 | 27.66 | 0 | 3197.6546 | 88447.1268 | 27.66 | 0 | -10.5 | 38.16 | 19 | 64600.0038 | Cu.Mtrs | 74955.1929 | 69965.7864 | 0 | 0 | -14645.7864
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | Footing Concrete-M25 | RMC | 47.47 | 2000 | 94940 | 47.47 | 2000 | 94940 | 47.47 | 0 | 0 | 47.47 | 0 | 47.47 | 0 | 3659.5716 | 173719.8632 | 47.47 | 0 | -15 | 62.47 | 19 | 64600.0038 | Cu.Mtrs | 147220.2167 | 147220.2167 | 0 | 0 | -52280.2167
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | D-Bldg Parking Ret Wall RMC M-25 | RMC | 66.01 | 2000 | 132020 | 68.01 | 2000 | 136020 | 66.01 | -2 | 2 | 66.01 | 2 | 66.01 | 0 | 3186.2803 | 210326.3617 | 66.01 | 0 | 29.01 | 37 | 19 | 64600.0038 | Cu.Mtrs | 178242.6845 | 131752.3651 | 2 | -2 | 267.6349
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | Ground Fl Parapet Wall RCC Concrete Work M25 | RMC | 4.46 | 2000 | 8920 | 4.46 | 2000 | 8920 | 4.46 | 0 | 0 | 4.46 | 0 | 4 | 0.46 | 3925.0002 | 15700.0008 | 4 | 0 | 4 | 0 | 19 | 64600.0038 | Cu.Mtrs | 13305.084 | 13305.084 | 0.46 | 0 | -4385.084
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | E-Bldg-2nd Slab RCC P1 Fl -Parapet Wall Concrete Work-M25 | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | E-Bldg-1st Slab RCC G.Fl -Parapet Wall Concrete Work-M25 | RMC | 7.07 | 2000 | 14140 | 7.07 | 2000 | 14140 | 7.07 | 0 | 0 | 7.07 | 0 | 4.1473 | 2.9227 | 3734.9944 | 15490.1423 | 4.1473 | 0 | 4.1473 | 0 | 19 | 64600.0038 | Cu.Mtrs | 13127.2413 | 13127.2413 | 2.9227 | 0 | 1012.7587
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | E-Bldg-5th Slab RCC P5 Fl -Parapet Wall Concrete Work-M25 | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | E-Bldg-3rd Slab RCC P2 Fl -Parapet Wall Concrete Work-M25 | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | E-Bldg-4th Slab RCC P3 Fl -Parapet Wall Concrete Work-M25 | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | RW-at UGWT side (Plinth to 1st Slab) Concrete Work M25 | RMC | 13 | 2000 | 26000 | 13 | 2000 | 26000 | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 3808.074 | 49504.9624 | 13 | 0 | 0 | 13 | 19 | 64600.0038 | Cu.Mtrs | 41953.355 | 41953.355 | 0 | 0 | -15953.355
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | E-Bldg Parking Ret Wall-Grid to 1st Concrete-M25 | RMC | 19.22 | 2000 | 38440 | 19.22 | 2000 | 38440 | 19.22 | 0 | 0 | 19.22 | 0 | 19.22 | 0 | 3434.6253 | 66013.4979 | 19.22 | 0 | 19.22 | 0 | 19 | 64600.0038 | Cu.Mtrs | 55943.6376 | 61864.4 | 0 | 0 | -23424.4
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | Ret Wall E-Bldg-at Well side Concrete work-6m Raft+Pardi (Fo | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | D-P5 Fl Parapet Wall RCC Work Concrete | RMC | 14.6 | 2000 | 29200 | 14.6 | 2000 | 29200 | 14.6 | 0 | 0 | 14.6 | 0 | 14.6 | 0 | 3400.0001 | 49640.0015 | 0 | 14.6 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 29200
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | D-Ground Fl Parapet Wall RCC Work Concrete | RMC | 6.55 | 2000 | 13100 | 6.55 | 2000 | 13100 | 6.55 | 0 | 0 | 6.55 | 0 | 6.55 | 0 | 3734.9944 | 24464.2133 | 6.55 | 0 | 6.55 | 0 | 19 | 64600.0038 | Cu.Mtrs | 20732.3875 | 20732.3875 | 0 | 0 | -7632.3875
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | D-P1 Fl Parapet Wall RCC Work Concrete | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | D-P2 Fl Parapet Wall RCC Work Concrete | RMC | 16.55 | 2000 | 33100 | 16.55 | 2000 | 33100 | 16.55 | 0 | 0 | 16.55 | 0 | 14.315 | 2.235 | 3924.9999 | 56186.3736 | 14.315 | 0 | 14.315 | 0 | 19 | 64600.0038 | Cu.Mtrs | 47615.5694 | 47615.5694 | 2.235 | 0 | -14515.5694
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | D-P3 Fl Parapet Wall RCC Work Concrete | RMC | 17.36 | 2000 | 34720 | 17.36 | 2000 | 34720 | 17.36 | 0 | 0 | 17.36 | 0 | 17.36 | 0 | 3400.0001 | 59024.0017 | 0 | 17.36 | 0 | 0 | 19 | 64600.0038 | Cu.Mtrs | 0 | 0 | 0 | 0 | 34720
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | D-P1 Fl Parapet Wall RCC Work Concrete | RMC | 16.55 | 2500 | 41375 | 16.55 | 2500 | 41375 | 16.55 | 0 | 0 | 16.55 | 0 | 16.55 | 0 | 4124.9967 | 68268.6954 | 16.55 | 0 | 16.55 | 0 | 33 | 112199.968 | Cu.Mtrs | 57854.828 | 57854.828 | 0 | 0 | -16479.828
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | E-Bldg-2nd Slab RCC P1 Fl -Parapet Wall Concrete Work-M25 | RMC | 10.83 | 2500 | 27075 | 10.83 | 2500 | 27075 | 10.83 | 0 | 0 | 10.83 | 0 | 10.83 | 0 | 4124.9967 | 44673.7143 | 10.83 | 0 | 10.83 | 0 | 33 | 112199.968 | Cu.Mtrs | 37859.0808 | 37859.0808 | 0 | 0 | -10784.0808
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | Footing Concrete-M25 | RMC | 107 | 2500 | 267500 | 125.57 | 2500 | 313925 | 107 | -18.57 | 18.57 | 107 | 18.57 | 107 | 0 | 2239.0146 | 239574.5587 | 107 | 0 | 0 | 107 | 33 | 112199.968 | Cu.Mtrs | 203029.29 | 203029.29 | 18.57 | -18.57 | 64470.71
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | Retaining Wall Raft Concrete-M25 | RMC | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 112199.968 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | Retaining Wall Concrete M-25 | RMC | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 112199.968 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | Tie Beam Tie Beam Concrete M-30 | RMC | 36 | 2100 | 75600 | 36 | 2100 | 75600 | 36 | 0 | 0 | 36 | 0 | 36 | 0 | 3314.6417 | 119327.1005 | 36 | 0 | -0.5 | 36.5 | 0 | 0 | Cu.Mtrs | 101124.6538 | 83775.6242 | 0 | 0 | -8175.6242
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 1st Slab RCC Grid to 1st slab column concrete | RMC | 66.14 | 2100 | 138894 | 66.14 | 2100 | 138894 | 66.14 | 0 | 0 | 66.14 | 0 | 66.14 | 0 | 3613.1134 | 238971.321 | 66.14 | 0 | 0 | 66.14 | 0 | 0 | Cu.Mtrs | 202518.0769 | 199637.6994 | 0 | 0 | -60743.6994
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | Strap Beam Concrete M30 | RMC | 26.62 | 2100 | 55902 | 26.62 | 2100 | 55902 | 26.62 | 0 | 0 | 26.62 | 0 | 26.62 | 0 | 3750.0013 | 99825.0346 | 26.62 | 0 | 0 | 26.62 | 0 | 0 | Cu.Mtrs | 84597.4815 | 84597.4815 | 0 | 0 | -28695.4815
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | Column Upto Grid Footing To Grid Slab Column M30 Concrete | RMC | 63.35 | 2100 | 133035 | 63.35 | 2100 | 133035 | 63.35 | 0 | 0 | 63.35 | 0 | 63.35 | 0 | 3288.4193 | 208321.3654 | 63.35 | 0 | 0 | 63.35 | 0 | 0 | Cu.Mtrs | 176543.5358 | 155462.9708 | 0 | 0 | -22427.9708
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 3rd Slab RCC 2nd to 3rd Column Concrete | RMC | 10.5 | 2100 | 22050 | 10.5 | 2100 | 22050 | 10.5 | 0 | 0 | 10.5 | 0 | 10.5 | 0 | 3229 | 33904.5 | 10.5 | 0 | 0 | 10.5 | 0 | 0 | Cu.Mtrs | 28732.62 | 28732.62 | 0 | 0 | -6682.62
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 3rd RCC Slab,Beam,ST Concrete | RMC | 19.63 | 2100 | 41223 | 19.63 | 2100 | 41223 | 19.63 | 0 | 0 | 19.63 | 0 | 19.63 | 0 | 3660.2426 | 71850.5615 | 19.63 | 0 | 0 | 19.63 | 0 | 0 | Cu.Mtrs | 60890.3085 | 0 | 0 | 0 | 41223
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 1st RCC Slab,Beam,Staircase Concrete | RMC | 38.68 | 2100 | 81228 | 38.68 | 2100 | 81228 | 38.68 | 0 | 0 | 38.68 | 0 | 38.68 | 0 | 3709.1065 | 143468.2407 | 38.68 | 0 | 1.53 | 37.15 | 0 | 0 | Cu.Mtrs | 121583.2587 | 0 | 0 | 0 | 81228
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 2nd Slab RCC Column 1st to 2nd slab concrete | RMC | 32.9 | 2100 | 69090 | 32.9 | 2100 | 69090 | 32.9 | 0 | 0 | 32.9 | 0 | 32.9 | 0 | 3678.0898 | 121009.1558 | 32.9 | 0 | 0 | 32.9 | 0 | 0 | Cu.Mtrs | 102550.128 | 92425.3 | 0 | 0 | -23335.3
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | F-Bldg Shops RCC Pardi Wall Concrete | RMC | 14.08 | 2100 | 29568 | 14.08 | 2100 | 29568 | 14.08 | 0 | 0 | 14.08 | 0 | 14.08 | 0 | 3734.9957 | 52588.7394 | 14.08 | 0 | 0 | 14.08 | 0 | 0 | Cu.Mtrs | 44566.72 | 43933.67 | 0 | 0 | -14365.67
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | F-Mezzanine Slab,Beam Concrete | RMC | 23.19 | 2100 | 48699 | 23.19 | 2100 | 48699 | 23.19 | 0 | 0 | 23.19 | 0 | 23.19 | 0 | 3734.9949 | 86614.5312 | 23.19 | 0 | 0 | 23.19 | 0 | 0 | Cu.Mtrs | 73402.1475 | 66185.3775 | 0 | 0 | -17486.3775
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | LG to Terrace(Roof Slab)Starircase RCC Pardi-Concrete | RMC | 7.57 | 2100 | 15897 | 7.5 | 2100 | 15750 | 7.5 | 0.07 | 0 | 7.5 | 0 | 7.5 | 0 | 3229 | 24217.5 | 7.5 | 0 | -0.07 | 7.57 | 0 | 0 | Cu.Mtrs | 20523.3 | 20523.3 | 0 | 0.07 | -4626.3
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | OHWT RCC Work- Slab,Beam,Pardi Concrete-M30 | RMC | 2 | 2100 | 4200 | 2 | 2100 | 4200 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 3229 | 3229 | 1 | 0 | -1 | 2 | 0 | 0 | Cu.Mtrs | 2736.44 | 2736.44 | 1 | 0 | 1463.56
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 2nd Slab RCC 2nd RCC Slab,Beam,ST Concrete | RMC | 21.44 | 2100 | 45024 | 21.44 | 2100 | 45024 | 21.44 | 0 | 0 | 21.44 | 0 | 21.44 | 0 | 3680.0056 | 78899.32 | 21.44 | 0 | 0.04 | 21.4 | 0 | 0 | Cu.Mtrs | 66863.8327 | 41496.4275 | 0 | 0 | 3527.5725
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 4th Slab RCC 3rd to 4th Column Concrete | RMC | 15 | 2100 | 31500 | 15 | 2100 | 31500 | 15 | 0 | 0 | 15 | 0 | 15 | 0 | 3228.9993 | 48434.9895 | 15 | 0 | 0 | 15 | 0 | 0 | Cu.Mtrs | 41046.6 | 41046.6 | 0 | 0 | -9546.6
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 4th Slab RCC 4th Slab,Beam,ST Concrete | RMC | 13.27 | 2100 | 27867 | 13.27 | 2100 | 27867 | 13.27 | 0 | 0 | 13.27 | 0 | 13.27 | 0 | 3734.9949 | 49563.383 | 13.27 | 0 | 0 | 13.27 | 0 | 0 | Cu.Mtrs | 42002.8675 | 0 | 0 | 0 | 27867
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 31st Slab- 31st Slab,Beam ST Concrete- M30 | RMC | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | 31st Slab- 30th to 31st Column Concrete- M30 | RMC | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Downpour) - Cu.Mtrs | Top Terrace LMR ,OHWT Concrete | RMC | 14 | 2100 | 29400 | 14 | 2100 | 29400 | 14 | 0 | 0 | 14 | 0 | 14 | 0 | 3924.9984 | 54949.9776 | 14 | 0 | 0 | 14 | 0 | 0 | Cu.Mtrs | 46567.78 | 46567.78 | 0 | 0 | -17167.78
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | D-31st to above Column Concrete | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | D-22nd RCC Slab,Beam,ST Concrete | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | D-21st Slab RCC 20th to 21st Column Concrete-(Cu.Mtrs) | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | D-22nd Slab RCC 21st to 22nd Column Concrete | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 32nd Above Roof Column Concrete- M30 | RMC | 21.92 | 4012 | 87943.04 | 0 | 0 | 0 | 0 | 21.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 21.92 | 87943.04
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 5th Slab RCC 4th to 5th Column Concrete-M30 | RMC | 37.27 | 4012 | 149527.24 | 37.27 | 4012 | 149527.24 | 37.27 | 0 | 0 | 37.27 | 0 | 37.27 | 0 | 3523.9994 | 131339.4584 | 37.27 | 0 | -0.73 | 38 | 0 | 0 | Cu.Mtrs | 111304.6188 | 111304.6188 | 0 | 0 | 38222.6212
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 4th Slab RCC 4th Slab,Beam,ST Concrete | RMC | 15.69 | 4012 | 62948.28 | 15.69 | 4012 | 62948.28 | 15.69 | 0 | 0 | 15.69 | 0 | 15.69 | 0 | 3523.9994 | 55291.5505 | 15.69 | 0 | 0 | 15.69 | 0 | 0 | Cu.Mtrs | 46857.2436 | 46857.2436 | 0 | 0 | 16091.0364
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 4th Slab RCC 3rd to 4th Column Concrete | RMC | 19.75 | 4012 | 79237 | 19.75 | 4012 | 79237 | 19.75 | 0 | 0 | 19.75 | 0 | 19.75 | 0 | 3523.9991 | 69598.9822 | 19.75 | 0 | 0 | 19.75 | 0 | 0 | Cu.Mtrs | 58982.19 | 58982.19 | 0 | 0 | 20254.81
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | F-Mezzanine Slab,Beam Concrete | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 5th RCC Slab,Beam,ST M30-concrete | RMC | 17.17 | 4012 | 68886.04 | 17.17 | 4012 | 68886.04 | 17.17 | 0 | 0 | 17.17 | 0 | 17.17 | 0 | 3523.9985 | 60507.0544 | 17.17 | 0 | 1.29 | 15.88 | 0 | 0 | Cu.Mtrs | 51277.1748 | 51277.1748 | 0 | 0 | 17608.8652
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | Terrace Parapet-Ext Column Concrete-M30 | RMC | 3.7 | 4012 | 14844.4 | 3.7 | 4012 | 14844.4 | 3.7 | 0 | 0 | 3.7 | 0 | 3.7 | 0 | 3523.9996 | 13038.7985 | 2.94 | 0.76 | -0.56 | 3.5 | 0 | 0 | Cu.Mtrs | 8780.1336 | 8780.1336 | 0 | 0 | 6064.2664
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | OHWT RCC Work- Slab,Beam,Pardi Concrete-M30 | RMC | 43.5 | 4012 | 174522 | 43.5 | 4012 | 174522 | 43.5 | 0 | 0 | 43.5 | 0 | 43.5 | 0 | 3814.1361 | 165914.9185 | 43.5 | 0 | 0 | 43.5 | 0 | 0 | Cu.Mtrs | 140605.86 | 140605.86 | 0 | 0 | 33916.14
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | D-21st Slab RCC 21st Slab,Beam,ST Concrete | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 3rd Slab RCC 2nd to 3rd Column Concrete | RMC | 27.6 | 4012 | 110731.2 | 27.6 | 4012 | 110731.2 | 27.6 | 0 | 0 | 27.6 | 0 | 27.6 | 0 | 3745.1586 | 103366.378 | 27.6 | 0 | 0 | 27.6 | 0 | 0 | Cu.Mtrs | 87598.632 | 40615.584 | 0 | 0 | 70115.616
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 1st RCC Slab,Beam,Staircase Concrete | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | 2nd Slab RCC 2nd RCC Slab,Beam,ST Concrete | RMC | 14.08 | 4012 | 56488.96 | 14.08 | 4012 | 56488.96 | 14.08 | 0 | 0 | 14.08 | 0 | 14.08 | 0 | 3523.9991 | 49617.9069 | 14.08 | 0 | 0 | 14.08 | 0 | 0 | Cu.Mtrs | 42049.0752 | 42049.0752 | 0 | 0 | 14439.8848
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | Tie Beam Tie Beam Concrete M-30 | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 (Pumpable) - Cu.Mtrs | Column Upto Grid Footing To Grid Slab Column M30 Concrete | RMC | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Downpour) - Cu.Mtrs | 21st Slab 21st Slab,Beam,SW,ST Concrete M30 | RMC | 8.51 | 3150 | 26806.5 | 8.51 | 3150 | 26806.5 | 8.51 | 0 | 0 | 8.51 | 0 | 8.51 | 0 | 4124.9997 | 35103.7474 | 8.51 | 0 | 0.01 | 8.5 | 0 | 0 | Cu.Mtrs | 29748.9346 | 0 | 0 | 0 | 26806.5
Sand-Metal Mix M30 hi-flow (Downpour) - Cu.Mtrs | 22nd Slab 22nd Slab,Beam,SW,ST Concrete M30 | RMC | 1.01 | 3150 | 3181.5 | 1.01 | 3150 | 3181.5 | 1.01 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 4124.9997 | 4166.2497 | 1.01 | 0 | 0.01 | 1 | 0 | 0 | Cu.Mtrs | 3530.7196 | 0 | 0 | 0 | 3181.5
Sand-Metal Mix M30 hi-flow (Downpour) - Cu.Mtrs | 23rd Slab (Refuge) 23rd Slab,Beam,SW,ST Concrete M30 | RMC | 6.51 | 3150 | 20506.5 | 6.51 | 3150 | 20506.5 | 6.51 | 0 | 0 | 6.51 | 0 | 6.51 | 0 | 4124.9997 | 26853.748 | 6.48 | 0.03 | -0.02 | 6.5 | 0 | 0 | Cu.Mtrs | 22652.5378 | 0 | 0 | 0 | 20506.5
Sand-Metal Mix M30 hi-flow (Downpour) - Cu.Mtrs | D-31st to above Column Concrete | RMC | 12 | 3150 | 37800 | 12 | 3150 | 37800 | 12 | 0 | 0 | 12 | 0 | 12 | 0 | 4124.9987 | 49499.9844 | 12 | 0 | 0 | 12 | 0 | 0 | Cu.Mtrs | 41949.144 | 0 | 0 | 0 | 37800
Sand-Metal Mix M30 hi-flow (Downpour) - Cu.Mtrs | Top Terrace LMR ,OHWT Concrete | RMC | 34 | 3150 | 107100 | 34 | 3150 | 107100 | 34 | 0 | 0 | 34 | 0 | 34 | 0 | 4124.9991 | 140249.9694 | 34 | 0 | 0 | 34 | 0 | 0 | Cu.Mtrs | 118855.908 | 76906.764 | 0 | 0 | 30193.236
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-29th Slab RCC 28th to 29th Column Concrete | RMC | 290.57 | 3150 | 915295.5 | 290.57 | 3150 | 915295.5 | 290.57 | 0 | 0 | 290.57 | 0 | 290.57 | 0 | 4325.0068 | 1256717.2259 | 290.57 | 0 | 1.62 | 288.95 | 80.74 | 343605.3391 | Cu.Mtrs | 1065014.5982 | 1090671.4182 | 0 | 0 | -175375.9182
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-30th Slab RCC 30th Slab,Beam,ST Concrete | RMC | 80.84 | 3150 | 254646 | 80.84 | 3150 | 254646 | 80.84 | 0 | 0 | 80.84 | 0 | 80.84 | 0 | 4325.0068 | 349633.5497 | 80.43 | 0.41 | -0.41 | 80.84 | 80.74 | 343605.3391 | Cu.Mtrs | 294796.8618 | 294796.8618 | 0 | 0 | -40150.8618
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-30th Slab RCC 29th to 30th Column Concrete | RMC | 290.57 | 3150 | 915295.5 | 290.57 | 3150 | 915295.5 | 290.57 | 0 | 0 | 290.57 | 0 | 290.57 | 0 | 4325.0068 | 1256717.2259 | 290.57 | 0 | 0 | 290.57 | 80.74 | 343605.3391 | Cu.Mtrs | 1065014.5982 | 1065014.5982 | 0 | 0 | -149719.0982
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-31st Slab RCC Terrace Slab,Beam Concrete Work -M30 | RMC | 173.6 | 3150 | 546840 | 173.6 | 3150 | 546840 | 173.6 | 0 | 0 | 173.6 | 0 | 173.6 | 0 | 4325.0068 | 750821.1805 | 173.6 | 0 | 0.6 | 173 | 80.74 | 343605.3391 | Cu.Mtrs | 636289.136 | 636289.136 | 0 | 0 | -89449.136
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-31st Slab RCC 30th to 31st Column Concrete-M30 | RMC | 213.8 | 3150 | 673470 | 213.8 | 3150 | 673470 | 213.8 | 0 | 0 | 213.8 | 0 | 213.8 | 0 | 4325.0068 | 924686.4538 | 213.8 | 0 | 0 | 213.8 | 80.74 | 343605.3391 | Cu.Mtrs | 783632.588 | 783632.588 | 0 | 0 | -110162.588
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-28th Slab RCC 28th Slab,Beam,ST Concrete | RMC | 80.84 | 3150 | 254646 | 80.84 | 3150 | 254646 | 80.84 | 0 | 0 | 80.84 | 0 | 80.52 | 0.32 | 4089.9992 | 329326.7356 | 80.52 | 0 | 8.09 | 72.43 | 80.74 | 343605.3391 | Cu.Mtrs | 279090.4525 | 279090.4525 | 0.32 | 0 | -24444.4525
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-28th Slab RCC 27th to 28th Column Concrete | RMC | 290.57 | 3150 | 915295.5 | 290.57 | 3150 | 915295.5 | 290.57 | 0 | 0 | 290.57 | 0 | 290.57 | 0 | 4089.9992 | 1188431.0675 | 290.57 | 0 | 0 | 290.57 | 80.74 | 343605.3391 | Cu.Mtrs | 1007144.9676 | 1007144.9676 | 0 | 0 | -91849.4676
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-29th Slab RCC 29th Slab,Beam,ST Concrete | RMC | 77.43 | 3150 | 243904.5 | 77.43 | 3150 | 243904.5 | 77.43 | 0 | 0 | 77.43 | 0 | 77.43 | 0 | 4325.0068 | 334885.2765 | 77.43 | 0 | 0 | 77.43 | 80.74 | 343605.3391 | Cu.Mtrs | 283801.0818 | 283801.0818 | 0 | 0 | -39896.5818
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-22nd Slab RCC 21st to 22nd Column Concrete | RMC | 213.8 | 3150 | 673470 | 213.8 | 3150 | 673470 | 213.8 | 0 | 0 | 213.8 | 0 | 213.8 | 0 | 4325.0068 | 924686.4538 | 213.8 | 0 | 0 | 213.8 | 80.74 | 343605.3391 | Cu.Mtrs | 783632.588 | 783632.588 | 0 | 0 | -110162.588
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-23rd Slab RCC 22nd to 23rd Column Concrete | RMC | 213.8 | 3150 | 673470 | 213.8 | 3150 | 673470 | 213.8 | 0 | 0 | 213.8 | 0 | 213.8 | 0 | 4028.5725 | 861308.7926 | 213.8 | 0 | 2.56 | 211.24 | 80.74 | 343605.3391 | Cu.Mtrs | 729922.7056 | 729922.7056 | 0 | 0 | -56452.7056
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-23rd RCC Slab,Beam,ST Concrete | RMC | 157.76 | 3150 | 496944 | 157.76 | 3150 | 496944 | 157.76 | 0 | 0 | 157.76 | 0 | 157.76 | 0 | 4325.0068 | 682313.0728 | 157.76 | 0 | 0 | 157.76 | 80.74 | 343605.3391 | Cu.Mtrs | 578231.4176 | 578231.4176 | 0 | 0 | -81287.4176
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-24th Slab RCC 23rd to 24th Column Concrete | RMC | 213.8 | 3150 | 673470 | 213.8 | 3150 | 673470 | 213.8 | 0 | 0 | 213.8 | 0 | 213.8 | 0 | 4325.0068 | 924686.4538 | 213.04 | 0.76 | 3.3 | 209.74 | 80.74 | 343605.3391 | Cu.Mtrs | 780846.9904 | 801005.9204 | 0 | 0 | -127535.9204
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-24th RCC Slab,Beam,ST Concrete | RMC | 157.76 | 3150 | 496944 | 157.76 | 3150 | 496944 | 157.76 | 0 | 0 | 157.76 | 0 | 157.76 | 0 | 4024.98 | 634980.8448 | 157.76 | 0 | 0 | 157.76 | 80.74 | 343605.3391 | Cu.Mtrs | 538119.36 | 538119.36 | 0 | 0 | -41175.36
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-25th Slab RCC 24th to 25th Column Concrete | RMC | 213.8 | 3150 | 673470 | 213.8 | 3150 | 673470 | 213.8 | 0 | 0 | 213.8 | 0 | 213.8 | 0 | 4077.8955 | 871854.0648 | 213.8 | 0 | 7.86 | 205.94 | 80.74 | 343605.3391 | Cu.Mtrs | 738859.374 | 1945062.522 | 0 | 0 | -1271592.522
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-25th RCC Slab,Beam,ST Concrete | RMC | 139.2 | 3150 | 438480 | 139.2 | 3150 | 438480 | 139.2 | 0 | 0 | 139.2 | 0 | 139.2 | 0 | 4024.98 | 560277.216 | 139.2 | 0 | 0 | 139.2 | 80.74 | 343605.3391 | Cu.Mtrs | 474811.2 | 474811.2 | 0 | 0 | -36331.2
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-21st Slab RCC 20th to 21st Column Concrete-(Cu.Mtrs) | RMC | 211.7 | 3150 | 666855 | 211.7 | 3150 | 666855 | 211.7 | 0 | 0 | 211.7 | 0 | 211.7 | 0 | 4127.4095 | 873772.5901 | 211.7 | 0 | 0.8 | 210.9 | 80.74 | 343605.3391 | Cu.Mtrs | 740485.24 | 1357451.218 | 0 | 0 | -690596.218
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-22nd RCC Slab,Beam,ST Concrete | RMC | 157.76 | 3150 | 496944 | 157.76 | 3150 | 496944 | 157.76 | 0 | 0 | 157.76 | 0 | 157.76 | 0 | 4325.0068 | 682313.0728 | 155.74 | 2.02 | -2.02 | 157.76 | 80.74 | 343605.3391 | Cu.Mtrs | 570827.5924 | 570827.5924 | 0 | 0 | -73883.5924
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-27th Slab RCC 27th Slab,Beam,ST Concrete | RMC | 80.84 | 3150 | 254646 | 80.84 | 3150 | 254646 | 80.84 | 0 | 0 | 80.84 | 0 | 80.84 | 0 | 4325.0068 | 349633.5497 | 80.84 | 0 | 0 | 80.84 | 80.74 | 343605.3391 | Cu.Mtrs | 296299.6184 | 296299.6184 | 0 | 0 | -41653.6184
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-27th Slab RCC 26th to 27th Column Concrete | RMC | 281.9 | 3150 | 887985 | 281.9 | 3150 | 887985 | 281.9 | 0 | 0 | 281.9 | 0 | 281.9 | 0 | 4325.0068 | 1219219.4169 | 281.9 | 0 | 0.16 | 281.74 | 80.74 | 343605.3391 | Cu.Mtrs | 1033236.794 | 1033236.794 | 0 | 0 | -145251.794
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-26th Slab RCC 26th Slab,Beam,ST Concrete | RMC | 80.84 | 3150 | 254646 | 80.84 | 3150 | 254646 | 80.84 | 0 | 0 | 80.84 | 0 | 80.84 | 0 | 4325.0068 | 349633.5497 | 80.84 | 0 | 0 | 80.84 | 80.74 | 343605.3391 | Cu.Mtrs | 296299.6184 | 296299.6184 | 0 | 0 | -41653.6184
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-26th Slab RCC 25th to 26th Column Concrete | RMC | 282.16 | 3150 | 888804 | 282.16 | 3150 | 888804 | 282.16 | 0 | 0 | 282.16 | 0 | 282.16 | 0 | 4139.9889 | 1168139.2555 | 282.16 | 0 | 0 | 282.16 | 80.74 | 343605.3391 | Cu.Mtrs | 989948.5216 | 989948.5216 | 0 | 0 | -101144.5216
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 23rd Slab (Refuge) 23rd Slab,Beam,SW,ST Concrete M30 | RMC | 283.76 | 3150 | 893844 | 283.76 | 3150 | 893844 | 283.76 | 0 | 0 | 283.76 | 0 | 283.76 | 0 | 4210.8201 | 1194862.3163 | 283.76 | 0 | 0 | 283.76 | 80.74 | 343605.3391 | Cu.Mtrs | 1012595.1776 | 30275.0476 | 0 | 0 | 863568.9524
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 24th Slab 24th Slab Concrete M30 | RMC | 76.73 | 3150 | 241699.5 | 76.73 | 3150 | 241699.5 | 76.73 | 0 | 0 | 76.73 | 0 | 76.73 | 0 | 4325.0068 | 331857.7718 | 76.73 | 0 | 0 | 76.73 | 80.74 | 343605.3391 | Cu.Mtrs | 281235.3998 | 281235.3998 | 0 | 0 | -39535.8998
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 22nd Slab 22nd Slab,Beam,SW,ST Concrete M30 | RMC | 289.26 | 3150 | 911169 | 289.26 | 3150 | 911169 | 289.26 | 0 | 0 | 289.26 | 0 | 289.26 | 0 | 4174.9993 | 1207660.2975 | 289.26 | 0 | 21.24 | 268.02 | 80.74 | 343605.3391 | Cu.Mtrs | 1023440.9301 | 867762.9901 | 0 | 0 | 43406.0099
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 23rd Slab (Refuge) 23rd Slab Concrete M30 | RMC | 80.74 | 3150 | 254331 | 80.74 | 3150 | 254331 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4325.0069 | 349201.0571 | 80.74 | 0 | 0 | 80.74 | 80.74 | 343605.3391 | Cu.Mtrs | 295933.0924 | 246452.0824 | 0 | 0 | 7878.9176
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 24th Slab 24th Slab,Beam,SW,ST Concrete M30 | RMC | 290.27 | 3150 | 914350.5 | 290.27 | 3150 | 914350.5 | 290.27 | 0 | 0 | 290.27 | 0 | 290.27 | 0 | 4325.0068 | 1255419.7238 | 290.27 | 0 | 6.01 | 284.26 | 80.74 | 343605.3391 | Cu.Mtrs | 1063915.0202 | 726711.1002 | 0 | 0 | 187639.3998
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 25th Slab 25th Slab Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 21st Slab 21st Slab,Beam,SW,ST Concrete M30 | RMC | 281.76 | 3150 | 887544 | 281.76 | 3150 | 887544 | 281.76 | 0 | 0 | 281.76 | 0 | 281.76 | 0 | 4174.9993 | 1176347.8028 | 281.76 | 0 | 30.61 | 251.15 | 80.74 | 343605.3391 | Cu.Mtrs | 996904.9176 | 630707.9451 | 0 | 0 | 256836.0549
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 22nd Slab 22nd Slab Concrete M30 | RMC | 80.74 | 3150 | 254331 | 80.74 | 3150 | 254331 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 80.74 | 343605.3391 | Cu.Mtrs | 285669.0199 | 285669.0199 | 0 | 0 | -31338.0199
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 21st Slab 21st Slab Concrete M30 | RMC | 80.74 | 3150 | 254331 | 80.74 | 3150 | 254331 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0.32 | 80.42 | 80.74 | 343605.3391 | Cu.Mtrs | 285669.0199 | 285669.0199 | 0 | 0 | -31338.0199
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 26th Slab 26th Slab Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 25th Slab 25th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 26th Slab 26th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 27th Slab 27th Slab Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 28th Slab (Refuge) 28th Slab Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 27th Slab 27th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 28th Slab (Refuge) 28th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 29th Slab 29th Slab Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 22nd Slab 22nd Slab Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 30th Slab 30th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 29th Slab 29th Slab,Beam,SW,ST Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | 30th Slab 30th Slab Concrete M30 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.74 | 343605.3391 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | D-21st Slab RCC 21st Slab,Beam,ST Concrete | RMC | 157.76 | 3150 | 496944 | 157.76 | 3150 | 496944 | 157.76 | 0 | 0 | 157.76 | 0 | 157.76 | 0 | 4325.0068 | 682313.0728 | 157.76 | 0 | 0 | 157.76 | 80.74 | 343605.3391 | Cu.Mtrs | 578231.4176 | 578231.4176 | 0 | 0 | -81287.4176
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D&E Bldg Between-P5-5th Slab RCC 5th Slab,Beam Concrete - | RMC | 30 | 2125 | 63750 | 30 | 2125 | 63750 | 30 | 0 | 0 | 30 | 0 | 28.9724 | 1.0276 | 3755.7654 | 108813.5383 | 28.9724 | 0 | -1.0276 | 30 | 4 | 13600.004 | Cu.Mtrs | 92214.8616 | 78909.7776 | 1.0276 | 0 | -15159.7776
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D&E Bldg Between-P2-3rd Slab RCC 3rd Slab,Beam Concrete - | RMC | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13600.004 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D&E Bldg Between-P3-4th Slab RCC- Slab,Beam Concrete - 1 | RMC | 34.14 | 2125 | 72547.5 | 34.14 | 2125 | 72547.5 | 34.14 | 0 | 0 | 34.14 | 0 | 33.64 | 0.5 | 3868.6549 | 130141.5492 | 33.64 | 0 | 1.64 | 32 | 4 | 13600.004 | Cu.Mtrs | 110289.4404 | 110289.4404 | 0.5 | 0 | -37741.9404
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | Tower D Footing RMC M-35 | RMC | 74.8952 | 2125 | 159152.3 | 74.8952 | 2125 | 159152.3 | 74.8952 | 0 | 0 | 74.8952 | 0 | 74.8952 | 0 | 3289.8275 | 246392.2866 | 74.8952 | 0 | 0 | 74.8952 | 4 | 13600.004 | Cu.Mtrs | 208807.0225 | 208807.0225 | 0 | 0 | -49654.7225
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D-Bldg Parking Ret Wall Raft RMC M-35 | RMC | 31.82 | 2125 | 67617.5 | 31.82 | 2125 | 67617.5 | 31.82 | 0 | 0 | 31.82 | 0 | 31.82 | 0 | 3212.9984 | 102237.6091 | 31.82 | 0 | 0 | 31.82 | 4 | 13600.004 | Cu.Mtrs | 86642.0416 | 86642.0416 | 0 | 0 | -19024.5416
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D-Bldg Parking Retaining Wall RMC M-35 | RMC | 25 | 2125 | 53125 | 25 | 2125 | 53125 | 25 | 0 | 0 | 25 | 0 | 25 | 0 | 3212.9984 | 80324.96 | 25 | 0 | 17.1852 | 7.8148 | 4 | 13600.004 | Cu.Mtrs | 68072 | 27228.8 | 0 | 0 | 25896.2
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D-Bldg Parking Substructure Footing-RMC-M35 | RMC | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13600.004 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | Tower E Footing M-35 Concrete | RMC | 767.55 | 2125 | 1631043.75 | 767.55 | 2125 | 1631043.75 | 767.55 | 0 | 0 | 767.55 | 0 | 767.55 | 0 | 3204.9157 | 2459933.0669 | 767.55 | 0 | -35.95 | 803.5 | 4 | 13600.004 | Cu.Mtrs | 2084689.0478 | 334264.3566 | 0 | 0 | 1296779.3934
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | E-RCC Ret wall Concrete M35 | RMC | 101.3 | 2125 | 215262.5 | 101.3 | 2125 | 215262.5 | 101.3 | 0 | 0 | 101.3 | 0 | 101.3 | 0 | 3212.9984 | 325476.7379 | 101.3 | 0 | 14.8 | 86.5 | 4 | 13600.004 | Cu.Mtrs | 275827.744 | 116457.5776 | 0 | 0 | 98804.9224
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | E-Bldg Parking Footing RMC-M35 | RMC | 28.64 | 2125 | 60860 | 28.64 | 2125 | 60860 | 28.64 | 0 | 0 | 28.64 | 0 | 28.64 | 0 | 3750.0046 | 107400.1317 | 28.64 | 0 | 0 | 28.64 | 4 | 13600.004 | Cu.Mtrs | 91017.0608 | 91017.0608 | 0 | 0 | -30157.0608
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | 2nd Slab RCC 2nd Slab,Beam Concrete | RMC | 36 | 2125 | 76500 | 36 | 2125 | 76500 | 36 | 0 | 0 | 36 | 0 | 36 | 0 | 3851.1892 | 138642.8127 | 36 | 0 | 0 | 36 | 4 | 13600.004 | Cu.Mtrs | 117493.9095 | 36156.4773 | 0 | 0 | 40343.5227
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D&EBldg Between-LGF-RCC 1st Slab,Beam Concrete-M35 | RMC | 205.48 | 2125 | 436645 | 205.48 | 2125 | 436645 | 205.48 | 0 | 0 | 205.48 | 0 | 205.48 | 0 | 3552.8299 | 730035.4971 | 205.48 | 0 | 5.98 | 199.5 | 4 | 13600.004 | Cu.Mtrs | 618674.156 | 422380.5442 | 0 | 0 | 14264.4558
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | D&E-Bldg Between Footing Concrete M35 | RMC | 85.68 | 2125 | 182070 | 85.68 | 2125 | 182070 | 85.68 | 0 | 0 | 85.68 | 0 | 85.68 | 0 | 3212.9984 | 275289.7029 | 85.68 | 0 | 0 | 85.68 | 4 | 13600.004 | Cu.Mtrs | 233296.3584 | 2722.88 | 0 | 0 | 179347.12
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | Between D&E-Bldg Parking Ret Wall Concrete | RMC | 26.15 | 2125 | 55568.75 | 26.15 | 2125 | 55568.75 | 26.15 | 0 | 0 | 26.15 | 0 | 26.15 | 0 | 3199.9994 | 83679.9843 | 26.15 | 0 | 0 | 26.15 | 4 | 13600.004 | Cu.Mtrs | 70915.2436 | 70915.2436 | 0 | 0 | -15346.4936
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | Between D&E-Bldg Parking Ret Wall Raft Concrete M35 | RMC | 9.22 | 2175 | 20053.5 | 9.22 | 2175 | 20053.5 | 9.22 | 0 | 0 | 9.22 | 0 | 9.22 | 0 | 4124.9994 | 38032.4945 | 9.22 | 0 | 9.22 | 0 | 0 | 0 | Cu.Mtrs | 32230.9256 | 32230.9256 | 0 | 0 | -12177.4256
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | 2nd Slab RCC 2nd Slab,Beam Concrete | RMC | 123 | 2175 | 267525 | 123 | 2175 | 267525 | 123 | 0 | 0 | 123 | 0 | 123 | 0 | 4124.9992 | 507374.9016 | 123 | 0 | 0 | 123 | 0 | 0 | Cu.Mtrs | 429978.726 | 429978.726 | 0 | 0 | -162453.726
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | D-Bldg Parking Substructure Footing-RMC-M35 | RMC | 15.49 | 2175 | 33690.75 | 15.49 | 2175 | 33690.75 | 15.49 | 0 | 0 | 15.49 | 0 | 15.49 | 0 | 3387.9993 | 52480.1092 | 15.49 | 0 | 0 | 15.49 | 0 | 0 | Cu.Mtrs | 44474.6711 | 44474.6711 | 0 | 0 | -10783.9211
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | Tower D Footing RMC M-35 | RMC | 848 | 2175 | 1844400 | 848 | 2175 | 1844400 | 848 | 0 | 0 | 848 | 0 | 848 | 0 | 3387.9995 | 2873023.5616 | 848 | 0 | 0 | 848 | 0 | 0 | Cu.Mtrs | 2434765.728 | 2434765.728 | 0 | 0 | -590365.728
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | D&E Bldg Between-P5-5th Slab RCC 5th Slab,Beam Concrete - | RMC | 179.14 | 2175 | 389629.5 | 179.14 | 2175 | 389629.5 | 179.14 | 0 | 0 | 179.14 | 0 | 171.28 | 7.86 | 3971.3561 | 680213.8707 | 171.28 | 0 | -3.8424 | 175.1224 | 0 | 0 | Cu.Mtrs | 576452.4234 | 576452.4234 | 7.86 | 0 | -186822.9234
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | D&E Bldg Between-P2-3rd Slab RCC 3rd Slab,Beam Concrete - | RMC | 209.14 | 2175 | 454879.5 | 209.14 | 2175 | 454879.5 | 209.14 | 0 | 0 | 209.14 | 0 | 204.2624 | 4.8776 | 3880.8132 | 792704.2256 | 204.2624 | 0 | -4.8776 | 209.14 | 0 | 0 | Cu.Mtrs | 671783.2499 | 215761.7349 | 4.8776 | 0 | 239117.7651
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | D&E Bldg Between-P3-4th Slab RCC- Slab,Beam Concrete - 1 | RMC | 175 | 2175 | 380625 | 175 | 2175 | 380625 | 175 | 0 | 0 | 175 | 0 | 175 | 0 | 4124.9991 | 721874.8449 | 175 | 0 | -0.5 | 175.5 | 0 | 0 | Cu.Mtrs | 611758.35 | 611758.35 | 0 | 0 | -231133.35
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | 2nd PT Slab,Beam Concrete | RMC | 0 | 2175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | 1st PT Slab,Beam Concrete | RMC | 0 | 2175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 PT (Downpour) Without Flyash - Cu.Mtrs | 1st PT Slab,Beam Concrete | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 PT (Downpour) Without Flyash - Cu.Mtrs | 3rd PT Slab,Beam Concrete | RMC | 157.3997 | 2000 | 314799.4 | 157.3997 | 2000 | 314799.4 | 157.3997 | 0 | 0 | 157.3997 | 0 | 157.3997 | 0 | 3523.9992 | 554676.4169 | 157.3997 | 0 | 0.3997 | 157 | 0 | 0 | Cu.Mtrs | 470064.7601 | 0 | 0 | 0 | 314799.4
Sand-Metal Mix M35 PT (Downpour) Without Flyash - Cu.Mtrs | 4th Slab RCC 4th PT Slab,Beam Concrete | RMC | 20.0035 | 2000 | 40007 | 20 | 2000 | 40000 | 18.6003 | 0.0035 | 1.3997 | 18.6003 | 1.3997 | 18.6003 | 0 | 3523.999 | 65547.4386 | 18.6003 | 0 | -0.3997 | 19 | 0 | 0 | Cu.Mtrs | 55548.6799 | 0 | 1.3997 | 0.0035 | 40007
Sand-Metal Mix M35 PT (Pumpable) Without Flyash - Cu.Mtrs | 4th Slab RCC 4th PT Slab,Beam Concrete | RMC | 149.3596 | 2000 | 298719.2 | 149.3596 | 2000 | 298719.2 | 149.3596 | 0 | 0 | 149.3596 | 0 | 149.3596 | 0 | 3818.9992 | 570404.1937 | 149.3596 | 0 | 0.3596 | 149 | 0 | 0 | Cu.Mtrs | 483393.3838 | 902057.9676 | 0 | 0 | -603338.7676
Sand-Metal Mix M35 PT (Pumpable) Without Flyash - Cu.Mtrs | 5th PT Slab,Beam Concrete | RMC | 170.42 | 2000 | 340840 | 170.42 | 2000 | 340840 | 170.42 | 0 | 0 | 170.42 | 0 | 170 | 0.42 | 3818.9992 | 649229.86 | 170 | 0 | 0 | 170 | 0 | 0 | Cu.Mtrs | 550194.8 | 614923.6 | 0.42 | 0 | -274083.6
Sand-Metal Mix M35 PT (Pumpable) Without Flyash - Cu.Mtrs | 3rd PT Slab,Beam Concrete | RMC | 15.0615 | 2000 | 30123 | 15.0615 | 2000 | 30123 | 15.0615 | 0 | 0 | 15.0615 | 0 | 15.0604 | 0.0011 | 3818.9999 | 57515.666 | 15.0604 | 0 | -0.3596 | 15.42 | 0 | 0 | Cu.Mtrs | 48742.081 | 17090.9924 | 0.0011 | 0 | 13032.0076
Sand-Metal Mix M35 PT (Pumpable) Without Flyash - Cu.Mtrs | 1st PT Slab,Beam Concrete | RMC | 117.93 | 2000 | 235860 | 117.93 | 2000 | 235860 | 117.93 | 0 | 0 | 117.93 | 0 | 117.93 | 0 | 4124.9968 | 486460.8726 | 117.93 | 0 | 0 | 117.93 | 0 | 0 | Cu.Mtrs | 412254.9768 | 412254.9768 | 0 | 0 | -176394.9768
Sand-Metal Mix M35 PT (Pumpable) Without Flyash - Cu.Mtrs | 2nd PT Slab,Beam Concrete | RMC | 181.15 | 2000 | 362300 | 181.15 | 2000 | 362300 | 181.15 | 0 | 0 | 181.15 | 0 | 181.15 | 0 | 3926.3813 | 711263.9756 | 181.15 | 0 | 0 | 181.15 | 0 | 0 | Cu.Mtrs | 602766.0784 | 63878.9832 | 0 | 0 | 298421.0168
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | D-7th Slab RCC 1st Floor slab,beam,ST Concrete | RMC | 78.9 | 2200 | 173580 | 78.9 | 2200 | 173580 | 78.9 | 0 | 0 | 78.9 | 0 | 78.9 | 0 | 3763.0861 | 296907.4957 | 78.9 | 0 | 0 | 78.9 | 0 | 0 | Cu.Mtrs | 251616.5169 | 251616.5169 | 0 | 0 | -78036.5169
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | D-8th Slab Concrete-M40 | RMC | 77 | 2200 | 169400 | 77 | 2200 | 169400 | 77 | 0 | 0 | 77 | 0 | 77 | 0 | 3658.6333 | 281714.7638 | 77 | 0 | 0 | 77 | 0 | 0 | Cu.Mtrs | 238741.3247 | 230290.0965 | 0 | 0 | -60890.0965
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | D-9th Slab Concrete | RMC | 80.84 | 2200 | 177848 | 80.84 | 2200 | 177848 | 80.84 | 0 | 0 | 80.84 | 0 | 80.84 | 0 | 3734.995 | 301936.9958 | 80.84 | 0 | 0 | 80.84 | 0 | 0 | Cu.Mtrs | 255878.81 | 233722.06 | 0 | 0 | -55874.06
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | D-P4-5th Slab RCC P4-Parking 5th Slab Concrete | RMC | 50.94 | 2200 | 112068 | 50.94 | 2200 | 112068 | 50.94 | 0 | 0 | 50.94 | 0 | 50.94 | 0 | 3272.8237 | 166717.6381 | 50.94 | 0 | 1 | 49.94 | 0 | 0 | Cu.Mtrs | 141286.1278 | 141286.1278 | 0 | 0 | -29218.1278
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | D-P1 Parking Floor 2nd Slab Concrete M40. | RMC | 322.24 | 2200 | 708928 | 322.24 | 2200 | 708928 | 322.24 | 0 | 0 | 322.24 | 0 | 322.24 | 0 | 3212.1558 | 1035085.0768 | 322.24 | 0 | 0 | 322.24 | 0 | 0 | Cu.Mtrs | 877190.757 | 0 | 0 | 0 | 708928
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | D-P2-Parking 3rd Slab Concrete-M40 | RMC | 310.19 | 2200 | 682418 | 310.19 | 2200 | 682418 | 310.19 | 0 | 0 | 310.19 | 0 | 310.19 | 0 | 3212.9996 | 996640.3459 | 310.19 | 0 | 0.1 | 310.09 | 0 | 0 | Cu.Mtrs | 844610.4574 | 0 | 0 | 0 | 682418
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | D-P3-4th Slab RCC P3-Parking Slab Concrete | RMC | 310.19 | 2200 | 682418 | 310.19 | 2200 | 682418 | 310.19 | 0 | 0 | 310.19 | 0 | 310.19 | 0 | 3206.4996 | 994624.0954 | 310.19 | 0 | 0 | 310.19 | 0 | 0 | Cu.Mtrs | 842901.7758 | 567103.1793 | 0 | 0 | 115314.8207
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | E-P2-3rd Slab RCC 3rd Slab,Beam,ST Concrete - 1 Cu.Mtrs | RMC | 306.9 | 2200 | 675180 | 306.9 | 2200 | 675180 | 306.9 | 0 | 0 | 306.9 | 0 | 306.9 | 0 | 3789.1705 | 1162896.4117 | 306.9 | 0 | 0.27 | 306.63 | 0 | 0 | Cu.Mtrs | 985505.4401 | 601243.6045 | 0 | 0 | 73936.3955
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | E-P3-4th Slab RCC 4th Slab,Beam,ST Concrete - 1 Cu.Mtrs | RMC | 84 | 2200 | 184800 | 84 | 2200 | 184800 | 84 | 0 | 0 | 84 | 0 | 84 | 0 | 3734.9997 | 313739.9748 | 84 | 0 | 1.21 | 82.79 | 0 | 0 | Cu.Mtrs | 265881.336 | 265881.336 | 0 | 0 | -81081.336
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | E-P4-5th Slab RCC 5th Slab,Beam,ST Concrete | RMC | 57.6 | 2200 | 126720 | 57.6 | 2200 | 126720 | 57.6 | 0 | 0 | 57.6 | 0 | 57.6 | 0 | 3734.9997 | 215135.9827 | 57.6 | 0 | 0 | 57.6 | 0 | 0 | Cu.Mtrs | 182318.6304 | 0 | 0 | 0 | 126720
Sand-Metal Mix M40 (Downpour) - Cu.Mtrs | E-P1-2nd Slab RCC 2nd Slab,Beam,ST Concrete - 1 Cu.Mtrs | RMC | 156.61 | 2200 | 344542 | 156.61 | 2200 | 344542 | 154.03 | 0 | 2.58 | 154.03 | 2.58 | 154.03 | 0 | 3734.9952 | 575301.308 | 154.03 | 0 | -2.58 | 156.61 | 0 | 0 | Cu.Mtrs | 487543.481 | 402493.19 | 2.58 | 0 | -57951.19
Sand-Metal Mix M40 (Pumpable) - Cu.Mtrs | E-P2-3rd Slab RCC 3rd Slab,Beam,ST Concrete - 1 Cu.Mtrs | RMC | 0 | 2815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4 | 55275 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 (Pumpable) - Cu.Mtrs | E-P4-5th Slab RCC 5th Slab,Beam,ST Concrete | RMC | 144.1 | 2815 | 405641.5 | 144.1 | 2815 | 405641.5 | 144.1 | 0 | 0 | 144.1 | 0 | 144.1 | 0 | 4124.9985 | 594412.2792 | 144.1 | 0 | 0 | 144.1 | 13.4 | 55275 | Cu.Mtrs | 503739.226 | 120953.311 | 0 | 0 | 284688.189
Sand-Metal Mix M40 (Pumpable) - Cu.Mtrs | E-P3-4th Slab RCC 4th Slab,Beam,ST Concrete - 1 Cu.Mtrs | RMC | 222.9 | 2815 | 627463.5 | 222.9 | 2815 | 627463.5 | 222.9 | 0 | 0 | 222.9 | 0 | 222.9 | 0 | 3979.9119 | 887122.3581 | 222.9 | 0 | 0 | 222.9 | 13.4 | 55275 | Cu.Mtrs | 751798.616 | 194713.904 | 0 | 0 | 432749.596
Sand-Metal Mix M40 (Pumpable) - Cu.Mtrs | D-P4-5th Slab RCC P4-Parking 5th Slab Concrete | RMC | 76.5 | 2815 | 215347.5 | 76.5 | 2815 | 215347.5 | 76.5 | 0 | 0 | 76.5 | 0 | 76.5 | 0 | 4124.9968 | 315562.2527 | 76.5 | 0 | 13.4 | 63.1 | 13.4 | 55275 | Cu.Mtrs | 267425.64 | 0 | 0 | 0 | 215347.5
Sand-Metal Mix M40 (Pumpable) - Cu.Mtrs | 20th Slab 20th Slab,Beam,SW,ST Concrete M40 | RMC | 87.5 | 2815 | 246312.5 | 87.5 | 2815 | 246312.5 | 87.5 | 0 | 0 | 87.5 | 0 | 87.5 | 0 | 4065.5979 | 355739.8152 | 87.5 | 0 | 0 | 87.5 | 13.4 | 55275 | Cu.Mtrs | 301474.418 | 105711.858 | 0 | 0 | 140600.642
Sand-Metal Mix M40 (Pumpable) - Cu.Mtrs | 7th Slab Concrete-M40 | RMC | 0 | 2815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4 | 55275 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-10th Slab Column,ST,NSW Concrete | RMC | 288.41 | 3150 | 908491.5 | 288.41 | 3150 | 908491.5 | 288.41 | 0 | 0 | 288.41 | 0 | 288.41 | 0 | 3987.6216 | 1150069.9355 | 288.41 | 0 | 0 | 288.41 | 493 | 2033575.7 | Cu.Mtrs | 974635.5386 | 904338.8786 | 0 | 0 | 4152.6214
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-10th Slab Concrete | RMC | 80.84 | 3150 | 254646 | 80.84 | 3150 | 254646 | 80.84 | 0 | 0 | 80.84 | 0 | 80.84 | 0 | 3950.0028 | 319318.2264 | 80.84 | 0 | 0 | 80.84 | 493 | 2033575.7 | Cu.Mtrs | 270608.6664 | 270608.6664 | 0 | 0 | -15962.6664
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-11th Slab RCC Column,ST,NSW Concrete | RMC | 184.75 | 3150 | 581962.5 | 184.75 | 3150 | 581962.5 | 184.75 | 0 | 0 | 184.75 | 0 | 184.75 | 0 | 3950.0028 | 729763.0173 | 184.75 | 0 | 0 | 184.75 | 493 | 2033575.7 | Cu.Mtrs | 618443.235 | 618443.235 | 0 | 0 | -36480.735
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-11th Slab RCC Concrete | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-20th Slab RCC 19th to 20th Column Concrete | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-19th Slab RCC 18th to 19th Column Concrete | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-20th Slab RCC 20th Slab,Beam,ST Concrete | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-18th Slab RCC 17th to 18th Column Concrete | RMC | 20.86 | 3150 | 65709 | 20.86 | 3150 | 65709 | 20.86 | 0 | 0 | 20.86 | 0 | 20.86 | 0 | 4124.9988 | 86047.475 | 20.86 | 0 | 0 | 20.86 | 493 | 2033575.7 | Cu.Mtrs | 72921.5953 | 72921.5953 | 0 | 0 | -7212.5953
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-19th Slab RCC 19th Slab,Beam,ST Concrete - 157.75 Cu.Mt | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-18th Slab RCC 18th Slab,Beam,ST Concrete | RMC | 6 | 3150 | 18900 | 6 | 3150 | 18900 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 3950.0033 | 23700.0198 | 6 | 0 | 0 | 6 | 493 | 2033575.7 | Cu.Mtrs | 20084.76 | 0 | 0 | 0 | 18900
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-17th Slab RCC 16th to 17th Slab Concrete | RMC | 200.0182 | 3150 | 630057.33 | 199.75 | 3150 | 629212.5 | 199.75 | 0.2682 | 0 | 199.75 | 0 | 199.75 | 0 | 3950.0028 | 789013.0593 | 199.75 | 0 | -0.3229 | 200.0729 | 493 | 2033575.7 | Cu.Mtrs | 668655.135 | 0 | 0 | 0.2682 | 630057.33
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-14th Slab RCC 14th Slab,Beam,ST Concrete | RMC | 156.56 | 3150 | 493164 | 156.56 | 3150 | 493164 | 156.56 | 0 | 0 | 156.56 | 0 | 156.56 | 0 | 3950.0028 | 618412.4384 | 156.56 | 0 | 0 | 156.56 | 493 | 2033575.7 | Cu.Mtrs | 524078.3376 | 0 | 0 | 0 | 493164
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-14th Slab RCC 14th Slab SW,NSW Concrete | RMC | 213.8 | 3150 | 673470 | 213.6129 | 3150 | 672880.635 | 213.6129 | 0.1871 | 0 | 213.6129 | 0 | 213.6129 | 0 | 3950.0028 | 843771.5531 | 213.6129 | 0 | -0.1871 | 213.8 | 493 | 2033575.7 | Cu.Mtrs | 715060.6382 | 0 | 0 | 0.1871 | 673470
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-15th Slab RCC 14th to 15th SW,NSW Concrete | RMC | 213.8 | 3150 | 673470 | 213.8 | 3150 | 673470 | 213.8 | 0 | 0 | 213.8 | 0 | 213.8 | 0 | 3950.0028 | 844510.5986 | 213.8 | 0 | 0 | 213.8 | 493 | 2033575.7 | Cu.Mtrs | 715686.948 | 0 | 0 | 0 | 673470
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-15th Slab RCC 15th Slab,Beam Concrete | RMC | 142.4696 | 3150 | 448779.24 | 142.46 | 3150 | 448749 | 142.46 | 0.0096 | 0 | 142.46 | 0 | 142.46 | 0 | 3950.0028 | 562717.3989 | 142.46 | 0 | 0.37 | 142.09 | 493 | 2033575.7 | Cu.Mtrs | 476879.1516 | 0 | 0 | 0.0096 | 448779.24
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-12th Slab RCC Column,ST,NSW Concrete | RMC | 288.41 | 3150 | 908491.5 | 288.41 | 3150 | 908491.5 | 288.41 | 0 | 0 | 288.41 | 0 | 288.41 | 0 | 3950.0028 | 1139220.3075 | 288.41 | 0 | 0.25 | 288.16 | 493 | 2033575.7 | Cu.Mtrs | 965440.9386 | 0 | 0 | 0 | 908491.5
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-12th Slab RCC Concrete | RMC | 80.84 | 3150 | 254646 | 80.73 | 3150 | 254299.5 | 80.73 | 0.11 | 0 | 80.73 | 0 | 80.73 | 0 | 3950.3062 | 318908.2203 | 80.73 | 0 | -0.11 | 80.84 | 493 | 2033575.7 | Cu.Mtrs | 270261.2081 | 489.4067 | 0 | 0.11 | 254156.5933
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-13th Slab RCC Column,ST,NSW Concrete | RMC | 112 | 3150 | 352800 | 112 | 3150 | 352800 | 112 | 0 | 0 | 112 | 0 | 112 | 0 | 3950.0028 | 442400.3136 | 112 | 0 | 0 | 112 | 493 | 2033575.7 | Cu.Mtrs | 374915.52 | 0 | 0 | 0 | 352800
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-13th Slab RCC Concrete | RMC | 67.25 | 3150 | 211837.5 | 67.25 | 3150 | 211837.5 | 67.25 | 0 | 0 | 67.25 | 0 | 67.25 | 0 | 3950.0028 | 265637.6883 | 67.25 | 0 | 493 | -425.75 | 493 | 2033575.7 | Cu.Mtrs | 225116.685 | 0 | 0 | 0 | 211837.5
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-16th Slab RCC 16th Slab,Beam,ST Concrete | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-16th Slab RCC 15th to 16th SW,NSW Concrete | RMC | 187.4171 | 3150 | 590363.865 | 187.4171 | 3150 | 590363.865 | 187.4171 | 0 | 0 | 187.4171 | 0 | 187.4171 | 0 | 3950.0028 | 740298.0698 | 187.4171 | 0 | 0 | 187.4171 | 493 | 2033575.7 | Cu.Mtrs | 627371.2456 | 0 | 0 | 0 | 590363.865
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-17th Slab RCC 17th Slab,Beam,ST Concrete | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | D-P1 Parking Floor 2nd Slab Concrete M40. | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 2033575.7 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-17th Slab RCC 17th Slab,Beam,ST Concrete | RMC | 157.75 | 4500 | 709875 | 157.75 | 4500 | 709875 | 157.75 | 0 | 0 | 157.75 | 0 | 157.75 | 0 | 4324.9998 | 682268.7185 | 157.75 | 0 | 0 | 157.75 | 0.3456 | 1442.8795 | Cu.Mtrs | 578193.8185 | 0 | 0 | 0 | 709875
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-16th Slab RCC 15th to 16th SW,NSW Concrete | RMC | 26.3829 | 4500 | 118723.05 | 26.3796 | 4500 | 118708.2 | 26.3796 | 0.0033 | 0 | 26.3796 | 0 | 26.3796 | 0 | 4174.9993 | 110134.8115 | 26.3796 | 0 | -0.0033 | 26.3829 | 0.3456 | 1442.8795 | Cu.Mtrs | 93334.586 | 0 | 0 | 0.0033 | 118723.05
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-16th Slab RCC 16th Slab,Beam,ST Concrete | RMC | 157.03 | 4500 | 706635 | 157.03 | 4500 | 706635 | 157.03 | 0 | 0 | 157.03 | 0 | 157.03 | 0 | 4174.9993 | 655600.1401 | 157.03 | 0 | 0 | 157.03 | 0.3456 | 1442.8795 | Cu.Mtrs | 555593.3391 | 0 | 0 | 0 | 706635
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-13th Slab RCC Concrete | RMC | 12.59 | 4500 | 56655 | 12.59 | 4500 | 56655 | 12.59 | 0 | 0 | 12.59 | 0 | 12.59 | 0 | 4175.0005 | 52563.2563 | 12.59 | 0 | 0 | 12.59 | 0.3456 | 1442.8795 | Cu.Mtrs | 44545.1322 | 0 | 0 | 0 | 56655
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-13th Slab RCC Column,ST,NSW Concrete | RMC | 176.41 | 4500 | 793845 | 176.41 | 4500 | 793845 | 176.41 | 0 | 0 | 176.41 | 0 | 176.41 | 0 | 4175.0005 | 736511.8382 | 176.41 | 0 | 0 | 176.41 | 0.3456 | 1442.8795 | Cu.Mtrs | 624162.5718 | 0 | 0 | 0 | 793845
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-15th Slab RCC 15th Slab,Beam Concrete | RMC | 14.0904 | 4500 | 63406.8 | 14.0904 | 4500 | 63406.8 | 14.0904 | 0 | 0 | 14.0904 | 0 | 14.0904 | 0 | 4174.9993 | 58827.4101 | 14.0904 | 0 | 0 | 14.0904 | 0.3456 | 1442.8795 | Cu.Mtrs | 49853.7374 | 0 | 0 | 0 | 63406.8
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-17th Slab RCC 16th to 17th Slab Concrete | RMC | 10.7618 | 4500 | 48428.1 | 10.75 | 4500 | 48375 | 10.75 | 0.0118 | 0 | 10.75 | 0 | 10.75 | 0 | 4324.9998 | 46493.7479 | 10.75 | 0 | -0.011 | 10.761 | 0.3456 | 1442.8795 | Cu.Mtrs | 39401.4805 | 0 | 0 | 0.0118 | 48428.1
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-18th Slab RCC 18th Slab,Beam,ST Concrete | RMC | 151.7501 | 4500 | 682875.45 | 151.7501 | 4500 | 682875.45 | 151.7501 | 0 | 0 | 151.7501 | 0 | 151.7501 | 0 | 4324.9929 | 656318.1068 | 151.7501 | 0 | 0 | 151.7501 | 0.3456 | 1442.8795 | Cu.Mtrs | 556201.7839 | 541540.7679 | 0 | 0 | 141334.6821
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-19th Slab RCC 19th Slab,Beam,ST Concrete - 157.75 Cu.Mt | RMC | 157.75 | 4500 | 709875 | 157.75 | 4500 | 709875 | 157.75 | 0 | 0 | 157.75 | 0 | 157.75 | 0 | 3839.5129 | 605683.1647 | 157.75 | 0 | 0 | 157.75 | 0.3456 | 1442.8795 | Cu.Mtrs | 513290.8176 | 513290.8176 | 0 | 0 | 196584.1824
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-18th Slab RCC 17th to 18th Column Concrete | RMC | 192.48 | 4500 | 866160 | 192.48 | 4500 | 866160 | 192.48 | 0 | 0 | 192.48 | 0 | 192.48 | 0 | 4324.9997 | 832475.9465 | 192.48 | 0 | 0 | 192.48 | 0.3456 | 1442.8795 | Cu.Mtrs | 705488.0899 | 705488.0899 | 0 | 0 | 160671.9101
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-20th Slab RCC 20th Slab,Beam,ST Concrete | RMC | 157.75 | 4500 | 709875 | 157.75 | 4500 | 709875 | 157.75 | 0 | 0 | 157.75 | 0 | 157.75 | 0 | 3830.486 | 604259.1643 | 157.75 | 0 | 0 | 157.75 | 0.3456 | 1442.8795 | Cu.Mtrs | 512084.0376 | 512084.0376 | 0 | 0 | 197790.9624
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-19th Slab RCC 18th to 19th Column Concrete | RMC | 213.34 | 4500 | 960030 | 213.34 | 4500 | 960030 | 213.34 | 0 | 0 | 213.34 | 0 | 213.34 | 0 | 4224.5776 | 901271.3919 | 213.34 | 0 | 0 | 213.34 | 0.3456 | 1442.8795 | Cu.Mtrs | 763789.3036 | 763789.3036 | 0 | 0 | 196240.6964
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-20th Slab RCC 19th to 20th Column Concrete | RMC | 213.34 | 4500 | 960030 | 213.34 | 4500 | 960030 | 213.34 | 0 | 0 | 213.34 | 0 | 213.34 | 0 | 4235.2507 | 903548.3946 | 213.34 | 0 | 0 | 213.34 | 0.3456 | 1442.8795 | Cu.Mtrs | 765718.9666 | 767551.5936 | 0 | 0 | 192478.4064
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-11th Slab RCC Concrete | RMC | 76.34 | 4500 | 343530 | 76.34 | 4500 | 343530 | 76.34 | 0 | 0 | 76.34 | 0 | 76.34 | 0 | 4175.0005 | 318719.5382 | 76.34 | 0 | 0 | 76.34 | 0.3456 | 1442.8795 | Cu.Mtrs | 270101.3022 | 270101.3022 | 0 | 0 | 73428.6978
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-11th Slab RCC Column,ST,NSW Concrete | RMC | 103.66 | 4500 | 466470 | 103.66 | 4500 | 466470 | 103.66 | 0 | 0 | 103.66 | 0 | 103.66 | 0 | 4175.0005 | 432780.5518 | 103.66 | 0 | 0 | 103.66 | 0.3456 | 1442.8795 | Cu.Mtrs | 366763.1778 | 366763.1778 | 0 | 0 | 99706.8222
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | D-8th Slab Concrete-M40 | RMC | 3.84 | 4500 | 17280 | 3.84 | 4500 | 17280 | 3.84 | 0 | 0 | 3.84 | 0 | 3.84 | 0 | 4324.9997 | 16607.9988 | 3.84 | 0 | 0 | 3.84 | 0.3456 | 1442.8795 | Cu.Mtrs | 14074.5754 | 14074.5754 | 0 | 0 | 3205.4246
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 7th Slab Concrete-M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4316.1935 | 348489.4663 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 295330.0639 | 295330.0639 | 0 | 0 | 67999.9361
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 8th Slab Concrete- M40 | RMC | 83.41 | 4500 | 375345 | 83.41 | 4500 | 375345 | 83.41 | 0 | 0 | 83.41 | 0 | 83.41 | 0 | 4320.6658 | 360386.7321 | 83.41 | 0 | 0 | 83.41 | 0.3456 | 1442.8795 | Cu.Mtrs | 305412.4794 | 305412.4794 | 0 | 0 | 69932.5206
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 17th Slab 17th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 285669.0199 | 285669.0199 | 0 | 0 | 77660.9801
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 17th Slab 17th Slab,Beam,SW,ST Concrete M40 | RMC | 289.62 | 4500 | 1303290 | 289.62 | 4500 | 1303290 | 289.62 | 0 | 0 | 289.62 | 0 | 289.62 | 0 | 4174.9993 | 1209163.2973 | 289.62 | 0 | 0 | 289.62 | 0.3456 | 1442.8795 | Cu.Mtrs | 1024714.6587 | 1012331.1862 | 0 | 0 | 290958.8138
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 18th Slab (Refuge) 18th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 285669.0199 | 264440.2099 | 0 | 0 | 98889.7901
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 18th Slab (Refuge) 18th Slab,Beam,SW,ST Concrete M40 | RMC | 289.62 | 4500 | 1303290 | 289.62 | 4500 | 1303290 | 289.62 | 0 | 0 | 289.62 | 0 | 289.62 | 0 | 4174.9993 | 1209163.2973 | 289.62 | 0 | 0 | 289.62 | 0.3456 | 1442.8795 | Cu.Mtrs | 1024714.6587 | 985795.1737 | 0 | 0 | 317494.8263
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 19th Slab 19th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 285669.0199 | 285669.0199 | 0 | 0 | 77660.9801
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 19th Slab 19th Slab,Beam,SW,ST Concrete M40 | RMC | 289.62 | 4500 | 1303290 | 289.62 | 4500 | 1303290 | 289.62 | 0 | 0 | 289.62 | 0 | 289.62 | 0 | 4174.9993 | 1209163.2973 | 289.62 | 0 | 0 | 289.62 | 0.3456 | 1442.8795 | Cu.Mtrs | 1024714.6587 | 1003485.8487 | 0 | 0 | 299804.1513
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 20th Slab 20th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 285669.0199 | 285669.0199 | 0 | 0 | 77660.9801
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 10th Slab Concrete M40 | RMC | 83.41 | 4500 | 375345 | 83.41 | 4500 | 375345 | 83.41 | 0 | 0 | 83.41 | 0 | 83.41 | 0 | 4324.9997 | 360748.225 | 83.41 | 0 | 0 | 83.41 | 0.3456 | 1442.8795 | Cu.Mtrs | 305718.8361 | 305718.8361 | 0 | 0 | 69626.1639
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 10th Slab,Beam,SW,ST Concrete M40 | RMC | 288.48 | 4500 | 1298160 | 288.48 | 4500 | 1298160 | 288.48 | 0 | 0 | 288.48 | 0 | 288.48 | 0 | 4321.6442 | 1246707.9309 | 288.48 | 0 | 0 | 288.48 | 0.3456 | 1442.8795 | Cu.Mtrs | 1056532.1496 | 1073025.7926 | 0 | 0 | 225134.2074
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 11th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4324.9997 | 349200.4758 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 295932.608 | 295932.608 | 0 | 0 | 67397.392
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 11th Slab,Beam,SW,ST Concrete M40 | RMC | 288.64 | 4500 | 1298880 | 288.64 | 4500 | 1298880 | 288.64 | 0 | 0 | 288.64 | 0 | 288.64 | 0 | 4318.7012 | 1246549.9086 | 288.64 | 0 | 0 | 288.64 | 0.3456 | 1442.8795 | Cu.Mtrs | 1056398.2323 | 1030741.4543 | 0 | 0 | 268138.5457
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 12th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4324.9997 | 349200.4758 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 295932.608 | 295932.608 | 0 | 0 | 67397.392
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 12th Slab,Beam,SW,ST Concrete M40 | RMC | 289 | 4500 | 1300500 | 289 | 4500 | 1300500 | 289 | 0 | 0 | 289 | 0 | 289 | 0 | 4324.9997 | 1249924.9133 | 289 | 0 | 0 | 289 | 0.3456 | 1442.8795 | Cu.Mtrs | 1059258.406 | 1059258.406 | 0 | 0 | 241241.594
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 13th Slab (Refuge) 13th Slab Concrete M40 | RMC | 83.41 | 4500 | 375345 | 83.41 | 4500 | 375345 | 83.41 | 0 | 0 | 83.41 | 0 | 83.41 | 0 | 4324.9997 | 360748.225 | 83.41 | 0 | 0 | 83.41 | 0.3456 | 1442.8795 | Cu.Mtrs | 305718.8361 | 305718.8361 | 0 | 0 | 69626.1639
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 13th Slab (Refuge) 13th Slab,Beam,SW,ST Concrete M40 | RMC | 289.78 | 4500 | 1304010 | 289.78 | 4500 | 1304010 | 289.78 | 0 | 0 | 289.78 | 0 | 289.78 | 0 | 4246.3243 | 1230499.8523 | 289.78 | 0 | 0 | 289.78 | 0.3456 | 1442.8795 | Cu.Mtrs | 1042796.4873 | 1042796.4873 | 0 | 0 | 261213.5127
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 14th Slab 14th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 285669.0199 | 262671.1424 | 0 | 0 | 100658.8576
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 14th Slab 14th Slab,Beam,SW,ST Concrete M40 | RMC | 289.62 | 4500 | 1303290 | 289.62 | 4500 | 1303290 | 289.62 | 0 | 0 | 289.62 | 0 | 289.62 | 0 | 4099.3828 | 1187263.2389 | 289.62 | 0 | 0 | 289.62 | 0.3456 | 1442.8795 | Cu.Mtrs | 1006155.2847 | 1006155.2847 | 0 | 0 | 297134.7153
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 15th Slab 15th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 285669.0199 | 285669.0199 | 0 | 0 | 77660.9801
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 15th Slab 15th Slab,Beam,SW,ST Concrete M40 | RMC | 289.62 | 4500 | 1303290 | 289.62 | 4500 | 1303290 | 289.62 | 0 | 0 | 289.62 | 0 | 289.62 | 0 | 4174.9993 | 1209163.2973 | 289.62 | 0 | 0.36 | 289.26 | 0.3456 | 1442.8795 | Cu.Mtrs | 1024714.6587 | 1024714.6587 | 0 | 0 | 278575.3413
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 16th Slab Concrete M40 | RMC | 80.74 | 4500 | 363330 | 80.74 | 4500 | 363330 | 80.74 | 0 | 0 | 80.74 | 0 | 80.74 | 0 | 4174.9993 | 337089.4435 | 80.74 | 0 | 0 | 80.74 | 0.3456 | 1442.8795 | Cu.Mtrs | 285669.0199 | 285669.0199 | 0 | 0 | 77660.9801
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 16th Slab,Beam,SW,ST Concrete M40 | RMC | 279.76 | 4500 | 1258920 | 279.76 | 4500 | 1258920 | 279.76 | 0 | 0 | 279.76 | 0 | 279.76 | 0 | 4174.9993 | 1167997.8042 | 279.76 | 0 | 0 | 279.76 | 0.3456 | 1442.8795 | Cu.Mtrs | 989828.6476 | 989828.6476 | 0 | 0 | 269091.3524
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 20th Slab 20th Slab,Beam,SW,ST Concrete M40 | RMC | 168.65 | 4500 | 758925 | 168.6499 | 4500 | 758924.55 | 168.6499 | 0.0001 | 0 | 168.6499 | 0 | 168.6499 | 0 | 4174.9993 | 704113.211 | 168.6499 | 0 | -0.0001 | 168.65 | 0.3456 | 1442.8795 | Cu.Mtrs | 596706.1139 | 596706.1139 | 0 | 0.0001 | 162218.8861
Sand-Metal Mix M40 Easycrete (Pumpable) - Cu.Mtrs | 9th Slab Concrete M40 | RMC | 83.41 | 4500 | 375345 | 83.41 | 4500 | 375345 | 83.41 | 0 | 0 | 83.41 | 0 | 83.41 | 0 | 4280.1429 | 357006.7202 | 83.41 | 0 | 0 | 83.41 | 0.3456 | 1442.8795 | Cu.Mtrs | 302548.0684 | 302548.0684 | 0 | 0 | 72796.9316
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-UGF-1st Column Grid to 1st Slab RCC RMC M-50 | RMC | 22.47 | 2200 | 49434 | 22.47 | 2200 | 49434 | 22.47 | 0 | 0 | 22.47 | 0 | 22.47 | 0 | 3199.9995 | 71903.9888 | 22.47 | 0 | 0 | 22.47 | 0 | 0 | Cu.Mtrs | 60935.5841 | 30128.809 | 0 | 0 | 19305.191
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-Upper Ground Floor-1st Slab RCC 1st Slab Concrete M50. | RMC | 73.63 | 2200 | 161986 | 73.63 | 2200 | 161986 | 73.63 | 0 | 0 | 73.63 | 0 | 73.63 | 0 | 3225.6963 | 237508.0201 | 73.63 | 0 | 0 | 73.63 | 0 | 0 | Cu.Mtrs | 201277.9723 | 29649.1487 | 0 | 0 | 132336.8513
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-Bldg Tie Beam Concrete M50 | RMC | 29.31 | 2200 | 64482 | 29.31 | 2200 | 64482 | 29.31 | 0 | 0 | 29.31 | 0 | 29.31 | 0 | 3199.9994 | 93791.9824 | 29.31 | 0 | 29.31 | 0 | 0 | 0 | Cu.Mtrs | 79484.7338 | 79484.7338 | 0 | 0 | -15002.7338
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | Podium Floor-6th Slab,Beam,NSW Concre | RMC | 153.88 | 2200 | 338536 | 153.88 | 2200 | 338536 | 153.88 | 0 | 0 | 153.88 | 0 | 153.88 | 0 | 3924.9986 | 603978.7789 | 153.88 | 0 | -59.38 | 213.26 | 0 | 0 | Cu.Mtrs | 511846.4276 | 280670.6626 | 0 | 0 | 57865.3374
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | Podium Floor- 6th Slab 5th To 6th Column Concrete-M50 | RMC | 56.9992 | 2200 | 125398.24 | 56.9992 | 2200 | 125398.24 | 56.9992 | 0 | 0 | 56.9992 | 0 | 56.67 | 0.3292 | 3924.9985 | 222429.665 | 56.67 | 0 | -7.57 | 64.24 | 0 | 0 | Cu.Mtrs | 188499.7209 | 82059.0809 | 0.3292 | 0 | 43339.1591
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | Column Footing To Grid Concrete M50 | RMC | 205.27 | 2200 | 451594 | 205.27 | 2200 | 451594 | 205.27 | 0 | 0 | 205.27 | 0 | 205.27 | 0 | 3354.9275 | 688665.9773 | 205.27 | 0 | 0 | 205.27 | 0 | 0 | Cu.Mtrs | 583615.2291 | 332076.2838 | 0 | 0 | 119517.7162
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-7th Slab RCC 6th to 7th slab Column Concrete | RMC | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-7th Slab RCC 1st Floor slab,beam,ST Concrete | RMC | 7 | 2200 | 15400 | 7 | 2200 | 15400 | 7 | 0 | 0 | 7 | 0 | 7 | 0 | 3924.9993 | 27474.9951 | 7 | 0 | 0 | 7 | 0 | 0 | Cu.Mtrs | 23283.897 | 23283.897 | 0 | 0 | -7883.897
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-Podium Floor-RCC 6th Slab,Beam,ST Concrete | RMC | 104.805 | 2200 | 230571 | 104.805 | 2200 | 230571 | 104.805 | 0 | 0 | 104.805 | 0 | 104.805 | 0 | 3199.9996 | 335375.9581 | 104.805 | 0 | 27.55 | 77.255 | 0 | 0 | Cu.Mtrs | 284216.9065 | 284216.9065 | 0 | 0 | -53645.9065
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-Podium Floor-6th Slab RCC 5th to 6th Column Concrete | RMC | 102.86 | 2200 | 226292 | 102.86 | 2200 | 226292 | 102.86 | 0 | 0 | 102.86 | 0 | 102.85 | 0.01 | 3220.0895 | 331186.2086 | 102.85 | 0 | 2.85 | 100 | 0 | 0 | Cu.Mtrs | 280666.2724 | 280666.2724 | 0.01 | 0 | -54374.2724
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | Tower D Tie Beam RMC M-50 | RMC | 28 | 2200 | 61600 | 28 | 2200 | 61600 | 28 | 0 | 0 | 28 | 0 | 28 | 0 | 3213.0008 | 89964.0219 | 28 | 0 | 0 | 28 | 0 | 0 | Cu.Mtrs | 76240.696 | 54457.64 | 0 | 0 | 7142.36
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D&E Bldg Between-P3-4th Slab RCC 3rd to 4th column concrete | RMC | 2.34 | 2200 | 5148 | 2.34 | 2200 | 5148 | 2.34 | 0 | 0 | 2.34 | 0 | 2.34 | 0 | 3924.9985 | 9184.4965 | 2.34 | 0 | 0.61 | 1.73 | 0 | 0 | Cu.Mtrs | 7783.4718 | 7783.4718 | 0 | 0 | -2635.4718
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D&E Bldg Between-P2-3rd Slab RCC 2nd to 3rd column concrete | RMC | 22.61 | 2200 | 49742 | 22.61 | 2200 | 49742 | 22.61 | 0 | 0 | 22.61 | 0 | 22.61 | 0 | 3924.9985 | 88744.2161 | 22.61 | 0 | -0.39 | 23 | 0 | 0 | Cu.Mtrs | 75206.9647 | 75206.9647 | 0 | 0 | -25464.9647
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D&E Podium Shops Shop RCC Pardi Concrete | RMC | 20.67 | 2200 | 45474 | 20.67 | 2200 | 45474 | 20.67 | 0 | 0 | 20.67 | 0 | 20.67 | 0 | 3199.9998 | 66143.9959 | 20.67 | 0 | 0 | 20.67 | 0 | 0 | Cu.Mtrs | 56054.2289 | 56054.2289 | 0 | 0 | -10580.2289
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D&E Bldg Between-P5-5th Slab RCC 4th to 5th column concrete | RMC | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-Upper Ground Floor-1st Slab RCC 1-lift pardi concrete grid | RMC | 3.42 | 2200 | 7524 | 3.42 | 2200 | 7524 | 3.42 | 0 | 0 | 3.42 | 0 | 3.42 | 0 | 3199.9994 | 10943.9979 | 3.42 | 0 | 0.42 | 3 | 0 | 0 | Cu.Mtrs | 9274.5749 | 0 | 0 | 0 | 7524
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-P1-2nd Slab RCC Column 1st Slab To 2nd Slab Concrete | RMC | 8.2 | 2200 | 18040 | 8.2 | 2200 | 18040 | 8.2 | 0 | 0 | 8.2 | 0 | 8.2 | 0 | 3199.9994 | 26239.9951 | 8.2 | 0 | 0 | 8.2 | 0 | 0 | Cu.Mtrs | 22237.2848 | 22237.2848 | 0 | 0 | -4197.2848
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-P4-5th Slab RCC Column 4th To 5th Concrete-M50 | RMC | 107.875 | 2200 | 237325 | 107.875 | 2200 | 237325 | 107.875 | 0 | 0 | 107.875 | 0 | 107.875 | 0 | 3199.9994 | 345199.9353 | 107.875 | 0 | 0 | 107.875 | 0 | 0 | Cu.Mtrs | 292542.329 | 29911.8599 | 0 | 0 | 207413.1401
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-P3-4th Slab RCC Column 3rd To 4th Slab Concrete | RMC | 94.47 | 2200 | 207834 | 94.47 | 2200 | 207834 | 94.47 | 0 | 0 | 94.47 | 0 | 94.47 | 0 | 3199.9996 | 302303.9595 | 94.47 | 0 | 0 | 94.47 | 0 | 0 | Cu.Mtrs | 256189.7921 | 36528.8081 | 0 | 0 | 171305.1919
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D-P2-RCC Column 2nd Slab To 3rd Slab Concrete | RMC | 78.31 | 2200 | 172282 | 78.31 | 2200 | 172282 | 78.31 | 0 | 0 | 78.31 | 0 | 78.31 | 0 | 3199.9994 | 250591.953 | 78.31 | 0 | 0 | 78.31 | 0 | 0 | Cu.Mtrs | 212366.0698 | 22535.5898 | 0 | 0 | 149746.4102
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | Shops RCC Work Non Structural wall Concrete | RMC | 22.47 | 2200 | 49434 | 22.47 | 2200 | 49434 | 22.47 | 0 | 0 | 22.47 | 0 | 22.47 | 0 | 3199.9993 | 71903.9843 | 22.47 | 0 | 0.47 | 22 | 0 | 0 | Cu.Mtrs | 60935.5841 | 0 | 0 | 0 | 49434
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-Parking Tie Beam Concrete M50 | RMC | 9.9 | 2200 | 21780 | 9.9 | 2200 | 21780 | 9.9 | 0 | 0 | 9.9 | 0 | 9.9 | 0 | 3199.9994 | 31679.9941 | 9.9 | 0 | 0 | 9.9 | 0 | 0 | Cu.Mtrs | 26847.4536 | 26847.4536 | 0 | 0 | -5067.4536
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-Bldg Parking Column Upto Grid RMC-M-50 | RMC | 10.43 | 2200 | 22946 | 10.43 | 2200 | 22946 | 10.43 | 0 | 0 | 10.43 | 0 | 10.43 | 0 | 3199.9995 | 33375.9948 | 10.43 | 0 | 0 | 10.43 | 0 | 0 | Cu.Mtrs | 28284.7415 | 28284.7415 | 0 | 0 | -5338.7415
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-P3-4th Slab RCC Column 3rd to 4th slab concrete-(Cu.Mtrs) | RMC | 4.89 | 2200 | 10758 | 4.89 | 2200 | 10758 | 4.89 | 0 | 0 | 4.89 | 0 | 4.89 | 0 | 3924.9992 | 19193.2462 | 4.89 | 0 | 1.89 | 3 | 0 | 0 | Cu.Mtrs | 16265.4652 | 16265.4652 | 0 | 0 | -5507.4652
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-Bldg Shops Shop RCC Pardi Concrete | RMC | 8.33 | 2200 | 18326 | 8.33 | 2200 | 18326 | 8.33 | 0 | 0 | 8.33 | 0 | 8.33 | 0 | 3635.1737 | 30280.9968 | 8.33 | 0 | 0.07 | 8.26 | 0 | 0 | Cu.Mtrs | 25661.8621 | 25661.8621 | 0 | 0 | -7335.8621
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-P2-3rd Slab RCC Column 2nd to 3rd concrete-(Cu.Mtrs) - 1 | RMC | 0.73 | 2200 | 1606 | 0.73 | 2200 | 1606 | 0.73 | 0 | 0 | 0.73 | 0 | 0.73 | 0 | 3735.0074 | 2726.5554 | 0.73 | 0 | 0 | 0.73 | 0 | 0 | Cu.Mtrs | 2310.6354 | 0 | 0 | 0 | 1606
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-P1-2nd Slab RCC 2nd Slab,Beam,ST Concrete - 1 Cu.Mtrs | RMC | 156.61 | 2200 | 344542 | 156.61 | 2200 | 344542 | 156.61 | 0 | 0 | 156.61 | 0 | 156.61 | 0 | 3738.3618 | 585464.8414 | 156.61 | 0 | 0.84 | 155.77 | 0 | 0 | Cu.Mtrs | 496156.6495 | 496156.6495 | 0 | 0 | -151614.6495
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-P1-2nd Slab RCC 1st to 2nd slab Column Concrete - 1 Cu. | RMC | 171.74 | 2200 | 377828 | 171.74 | 2200 | 377828 | 171.74 | 0 | 0 | 171.74 | 0 | 171.74 | 0 | 3780.5174 | 649266.0571 | 171.74 | 0 | 0 | 171.74 | 0 | 0 | Cu.Mtrs | 550225.4774 | 495561.5408 | 0 | 0 | -117733.5408
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-UGF-1st Slab RCC Column Grid to 1st concrete | RMC | 100 | 2200 | 220000 | 100 | 2200 | 220000 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 3199.9995 | 319999.95 | 100 | 0 | 0 | 100 | 0 | 0 | Cu.Mtrs | 271186.4 | 271186.4 | 0 | 0 | -51186.4
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D&E Podium Tie Beam Concrete-M50 | RMC | 29.77 | 2200 | 65494 | 29.77 | 2200 | 65494 | 29.77 | 0 | 0 | 29.77 | 0 | 29.77 | 0 | 3199.9994 | 95263.9821 | 29.77 | 0 | 0.71 | 29.06 | 0 | 0 | Cu.Mtrs | 80732.1913 | 80732.1913 | 0 | 0 | -15238.1913
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D&EBldg Between-LGF-1st Slab Shear Wall RCC RMC M-50 | RMC | 3.9 | 2200 | 8580 | 3.9 | 2200 | 8580 | 3.9 | 0 | 0 | 3.9 | 0 | 3.9 | 0 | 3199.9994 | 12479.9977 | 3.9 | 0 | 0 | 3.9 | 0 | 0 | Cu.Mtrs | 10576.2696 | 10576.2696 | 0 | 0 | -1996.2696
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | E-Bldg Shops Mezzanine Slab,Beam Concrete | RMC | 23.76 | 2200 | 52272 | 23.76 | 2200 | 52272 | 23.76 | 0 | 0 | 23.76 | 0 | 23.76 | 0 | 3750.0011 | 89100.0261 | 23.76 | 0 | 0.47 | 23.29 | 0 | 0 | Cu.Mtrs | 75508.4959 | 75508.4959 | 0 | 0 | -23236.4959
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | D&E -Bldg Between Parking Colm upto Grid RMC-M50 | RMC | 12.54 | 2200 | 27588 | 12.54 | 2200 | 27588 | 12.54 | 0 | 0 | 12.54 | 0 | 12.54 | 0 | 3199.9994 | 40127.9925 | 12.54 | 0 | 0 | 12.54 | 0 | 0 | Cu.Mtrs | 34006.7746 | 34006.7746 | 0 | 0 | -6418.7746
Sand-Metal Mix M50 (Downpour) - Cu.Mtrs | 2nd Slab RCC column 1st to 2nd slab concrete | RMC | 21 | 2200 | 46200 | 21 | 2200 | 46200 | 21 | 0 | 0 | 21 | 0 | 21 | 0 | 3924.9996 | 82424.9916 | 21 | 0 | 0 | 21 | 0 | 0 | Cu.Mtrs | 69851.691 | 69851.691 | 0 | 0 | -23651.691
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | E-UGF-1st Slab RCC Slab Beam Concrete | RMC | 63 | 2200 | 138600 | 63 | 2200 | 138600 | 63 | 0 | 0 | 63 | 0 | 63 | 0 | 3813.0321 | 240221.0223 | 63 | 0 | 0 | 63 | 0 | 0 | Cu.Mtrs | 203577.138 | 203577.138 | 0 | 0 | -64977.138
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | E-P1-2nd Slab RCC 1st to 2nd slab Column Concrete - 1 Cu. | RMC | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | E-P1-2nd Slab RCC 2nd Slab,Beam,ST Concrete - 1 Cu.Mtrs | RMC | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | E-Bldg Shops Shop RCC Pardi Concrete | RMC | 14.73 | 2200 | 32406 | 14.635 | 2200 | 32197 | 14.635 | 0.095 | 0 | 14.635 | 0 | 14.635 | 0 | 3996.6236 | 58490.5869 | 14.635 | 0 | 0 | 14.635 | 0 | 0 | Cu.Mtrs | 49568.2921 | 49568.2921 | 0 | 0.095 | -17162.2921
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | D-Bldg Ramp Work- Concrete Qty | RMC | 30 | 2200 | 66000 | 30 | 2200 | 66000 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 4124.9967 | 123749.901 | 30 | 0 | 0 | 30 | 0 | 0 | Cu.Mtrs | 104872.8 | 104872.8 | 0 | 0 | -38872.8
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | D,E,Podium- Parking Superstructure Adjusted Concrete Qty-M50 | RMC | 100.87 | 2200 | 221914 | 100.87 | 2200 | 221914 | 100.87 | 0 | 0 | 100.87 | 0 | 100.87 | 0 | 4028.4868 | 406353.4668 | 100.87 | 0 | 0 | 100.87 | 0 | 0 | Cu.Mtrs | 344367.3412 | 344367.3412 | 0 | 0 | -122453.3412
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | 2nd Slab RCC column 1st to 2nd slab concrete | RMC | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | D-Podium Floor-6th Slab RCC 5th to 6th Column Concrete | RMC | 29.13 | 2200 | 64086 | 29.13 | 2200 | 64086 | 29.13 | 0 | 0 | 29.13 | 0 | 29.13 | 0 | 3374.9995 | 98313.7354 | 29.13 | 0 | 0 | 29.13 | 0 | 0 | Cu.Mtrs | 83316.723 | 83316.723 | 0 | 0 | -19230.723
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | D-Podium Floor-RCC 6th Slab,Beam,ST Concrete | RMC | 53.365 | 2200 | 117403 | 53.365 | 2200 | 117403 | 53.365 | 0 | 0 | 53.365 | 0 | 53.365 | 0 | 3374.9995 | 180106.8483 | 53.365 | 0 | 0 | 53.365 | 0 | 0 | Cu.Mtrs | 152632.9187 | 152632.9187 | 0 | 0 | -35229.9187
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | Column Footing To Grid Concrete M50 | RMC | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 (Pumpable) - Cu.Mtrs | D-Upper Ground Floor-1st Slab RCC 1st Slab Concrete M50. | RMC | 235.5 | 2200 | 518100 | 235.5 | 2200 | 518100 | 235.5 | 0 | 0 | 235.5 | 0 | 235.5 | 0 | 3384.8532 | 797132.9262 | 235.5 | 0 | 0 | 235.5 | 0 | 0 | Cu.Mtrs | 675536.391 | 0 | 0 | 0 | 518100
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-UGF-1st Column Grid to 1st Slab RCC RMC M-50 | RMC | 200.84 | 3150 | 632646 | 200.84 | 3150 | 632646 | 200.84 | 0 | 0 | 200.84 | 0 | 200.84 | 0 | 3428.9997 | 688680.3036 | 200.84 | 0 | 0 | 200.84 | 0 | 0 | Cu.Mtrs | 583627.3829 | 315293.622 | 0 | 0 | 317352.378
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | Column Footing To Grid Concrete M50 | RMC | 4.5 | 3150 | 14175 | 4.5 | 3150 | 14175 | 4.5 | 0 | 0 | 4.5 | 0 | 4.5 | 0 | 3949.9909 | 17774.9591 | 4.5 | 0 | 0 | 4.5 | 0 | 0 | Cu.Mtrs | 15063.525 | 15063.525 | 0 | 0 | -888.525
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | Podium Floor- 6th Slab 5th To 6th Column Concrete-M50 | RMC | 13 | 3150 | 40950 | 13 | 3150 | 40950 | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 4124.9992 | 53624.9896 | 13 | 0 | 0 | 13 | 0 | 0 | Cu.Mtrs | 45444.906 | 0 | 0 | 0 | 40950
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-7th Slab RCC 1st Floor slab,beam,ST Concrete | RMC | 56 | 3150 | 176400 | 56 | 3150 | 176400 | 56 | 0 | 0 | 56 | 0 | 56 | 0 | 4020.3056 | 225137.1142 | 56 | 0 | 0 | 56 | 0 | 0 | Cu.Mtrs | 190794.175 | 190794.175 | 0 | 0 | -14394.175
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | Tower D Column Upto Grid RMC M-50-(Cu.Mtrs) | RMC | 55.71 | 3150 | 175486.5 | 55.71 | 3150 | 175486.5 | 55.71 | 0 | 0 | 55.71 | 0 | 55.71 | 0 | 3428.9997 | 191029.5721 | 55.71 | 0 | 0 | 55.71 | 0 | 0 | Cu.Mtrs | 161889.4717 | 151108.464 | 0 | 0 | 24378.036
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-7th Slab RCC 6th to 7th slab Column Concrete | RMC | 222.25 | 3150 | 700087.5 | 222.25 | 3150 | 700087.5 | 222.25 | 0 | 0 | 222.25 | 0 | 222.25 | 0 | 3949.991 | 877885.4998 | 222.25 | 0 | 0 | 222.25 | 0 | 0 | Cu.Mtrs | 743970.7625 | 743970.7625 | 0 | 0 | -43883.2625
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-8th Slab Column,Beam,NSW Concrete M50 | RMC | 288.41 | 3150 | 908491.5 | 288.41 | 3150 | 908491.5 | 288.41 | 0 | 0 | 288.41 | 0 | 288.41 | 0 | 3836.4066 | 1106458.0275 | 288.41 | 0 | 0 | 288.41 | 0 | 0 | Cu.Mtrs | 937676.2945 | 915917.8695 | 0 | 0 | -7426.3695
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-9th Slab Column,Beam,NSW,ST concrete | RMC | 288.41 | 3150 | 908491.5 | 288.41 | 3150 | 908491.5 | 288.41 | 0 | 0 | 288.41 | 0 | 288.41 | 0 | 3949.991 | 1139216.9043 | 288.41 | 0 | 0.02 | 288.39 | 0 | 0 | Cu.Mtrs | 965438.0545 | 690947.1545 | 0 | 0 | 217544.3455
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-P2-RCC Column 2nd Slab To 3rd Slab Concrete | RMC | 97.16 | 3150 | 306054 | 97.16 | 3150 | 306054 | 97.16 | 0 | 0 | 97.16 | 0 | 97.16 | 0 | 3428.9999 | 333161.6266 | 97.16 | 0 | -0.01 | 97.17 | 0 | 0 | Cu.Mtrs | 282340.3531 | 464.9491 | 0 | 0 | 305589.0509
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-P3-4th Slab RCC Column 3rd To 4th Slab Concrete | RMC | 81 | 3150 | 255150 | 81 | 3150 | 255150 | 81 | 0 | 0 | 81 | 0 | 81 | 0 | 3473.333 | 281339.974 | 81 | 0 | 0 | 81 | 0 | 0 | Cu.Mtrs | 238423.7106 | 59708.8926 | 0 | 0 | 195441.1074
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-P4-5th Slab RCC Column 4th To 5th Concrete-M50 | RMC | 96.845 | 3150 | 305061.75 | 96.845 | 3150 | 305061.75 | 96.845 | 0 | 0 | 96.845 | 0 | 96.845 | 0 | 3515.6745 | 340475.4999 | 96.845 | 0 | -0.005 | 96.85 | 0 | 0 | Cu.Mtrs | 288538.5635 | 223155.0935 | 0 | 0 | 81906.6565
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D-P1-2nd Slab RCC Column 1st Slab To 2nd Slab Concrete | RMC | 124.28 | 3150 | 391482 | 124.28 | 3150 | 391482 | 124.28 | 0 | 0 | 124.28 | 0 | 124.28 | 0 | 3511.2126 | 436373.497 | 124.28 | 0 | 0 | 124.28 | 0 | 0 | Cu.Mtrs | 369808.0515 | 152008.4481 | 0 | 0 | 239473.5519
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | E-P4-5th Slab RCC 4th to 5th Column Concrete | RMC | 178.35 | 3150 | 561802.5 | 178.35 | 3150 | 561802.5 | 178.35 | 0 | 0 | 178.35 | 0 | 178.345 | 0.005 | 3941.2922 | 702909.7531 | 178.345 | 0 | -0.005 | 178.35 | 0 | 0 | Cu.Mtrs | 595686.2408 | 47223.2955 | 0.005 | 0 | 514579.2045
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | E-P3-4th Slab RCC Column 3rd to 4th slab concrete-(Cu.Mtrs) | RMC | 166.25 | 3150 | 523687.5 | 166.25 | 3150 | 523687.5 | 166.25 | 0 | 0 | 166.25 | 0 | 166.25 | 0 | 3949.991 | 656686.0038 | 166.25 | 0 | 0 | 166.25 | 0 | 0 | Cu.Mtrs | 556513.5625 | 0 | 0 | 0 | 523687.5
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | E-P2-3rd Slab RCC Column 2nd to 3rd concrete-(Cu.Mtrs) - 1 | RMC | 135.14 | 3150 | 425691 | 135.14 | 3150 | 425691 | 135.14 | 0 | 0 | 135.14 | 0 | 135.14 | 0 | 4045.8209 | 546752.2389 | 135.14 | 0 | 0 | 135.14 | 0 | 0 | Cu.Mtrs | 463349.353 | 254735.3508 | 0 | 0 | 170955.6492
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | E-UGF-1st Slab RCC Slab Beam Concrete | RMC | 230.41 | 3150 | 725791.5 | 230.41 | 3150 | 725791.5 | 230.41 | 0 | 0 | 230.41 | 0 | 230.41 | 0 | 3940.7865 | 907996.6132 | 230.41 | 0 | 0 | 230.41 | 0 | 0 | Cu.Mtrs | 769488.6485 | 766141.1985 | 0 | 0 | -40349.6985
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | E-UGF-1st Slab RCC Column Grid to 1st concrete | RMC | 157.15 | 3150 | 495022.5 | 157.15 | 3150 | 495022.5 | 157.15 | 0 | 0 | 157.15 | 0 | 157.15 | 0 | 3948.3326 | 620480.4745 | 157.15 | 0 | 0 | 157.15 | 0 | 0 | Cu.Mtrs | 525830.918 | 525830.918 | 0 | 0 | -30808.418
Sand-Metal Mix M50 Easycrete (Downpour) - Cu.Mtrs | D&E -Bldg Between Parking Colm upto Grid RMC-M50 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | E-P4-5th Slab RCC 4th to 5th Column Concrete | RMC | 20 | 3150 | 63000 | 20 | 3150 | 63000 | 20 | 0 | 0 | 20 | 0 | 20 | 0 | 4174.999 | 83499.98 | 20 | 0 | -0.5 | 20.5 | 0 | 0 | Cu.Mtrs | 70762.7 | 0 | 0 | 0 | 63000
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | D-P1-2nd Slab RCC Column 1st Slab To 2nd Slab Concrete | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | E-Bldg Parking Column Upto Grid RMC-M-50 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | Podium Floor- 6th Slab 5th To 6th Column Concrete-M50 | RMC | 55.2716 | 3150 | 174105.54 | 55.2716 | 3150 | 174105.54 | 55.2716 | 0 | 0 | 55.2716 | 0 | 55.27 | 0.0016 | 4324.9996 | 239042.7274 | 55.27 | 0 | -0.0016 | 55.2716 | 0 | 0 | Cu.Mtrs | 202578.5886 | 54978.81 | 0.0016 | 0 | 119126.73
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | Column Footing To Grid Concrete M50 | RMC | 26 | 3150 | 81900 | 26 | 3150 | 81900 | 26 | 0 | 0 | 26 | 0 | 26 | 0 | 3600.0008 | 93600.0208 | 26 | 0 | 0 | 26 | 0 | 0 | Cu.Mtrs | 79322.048 | 0 | 0 | 0 | 81900
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | 8th Slab- Beam,SW,ST Concrete M50 | RMC | 288.48 | 3150 | 908712 | 288.48 | 3150 | 908712 | 288.48 | 0 | 0 | 288.48 | 0 | 288.48 | 0 | 4324.9997 | 1247675.9135 | 288.48 | 0 | -0.1984 | 288.6784 | 0 | 0 | Cu.Mtrs | 1057352.4739 | 1075678.7439 | 0 | 0 | -166966.7439
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | 7th Slab ST,SW,Beam Concrete M50 | RMC | 288.32 | 3150 | 908208 | 288.32 | 3150 | 908208 | 288.32 | 0 | 0 | 288.32 | 0 | 288.32 | 0 | 4324.9997 | 1246983.9135 | 288.32 | 0 | 0 | 288.32 | 0 | 0 | Cu.Mtrs | 1056766.0333 | 1078757.5573 | 0 | 0 | -170549.5573
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | D-UGF-1st Column Grid to 1st Slab RCC RMC M-50 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | D-Bldg Parking Substructure Column Upto Grid-RMC-M50 | RMC | 4.73 | 3150 | 14899.5 | 4.73 | 3150 | 14899.5 | 4.73 | 0 | 0 | 4.73 | 0 | 4.73 | 0 | 4324.9997 | 20457.2486 | 4.73 | 0 | 0 | 4.73 | 0 | 0 | Cu.Mtrs | 17336.6514 | 0 | 0 | 0 | 14899.5
Sand-Metal Mix M50 Easycrete (Pumpable) - Cu.Mtrs | 9th Slab,Beam,SW,ST Concrete M50 | RMC | 288.48 | 3150 | 908712 | 288.48 | 3150 | 908712 | 288.48 | 0 | 0 | 288.48 | 0 | 286.2 | 2.28 | 4580.7736 | 1311017.4004 | 286.2 | 0 | 0.7 | 285.5 | 0 | 0 | Cu.Mtrs | 1111031.6998 | 1111031.6998 | 2.28 | 0 | -202319.6998