## Material Receipt Details6385828
Material Receipt Details
GANGA ALTUS
Page 1 of 1
Total Records: 10 Records 1 to 10
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
RCC NP2 Class Pipe 12" - Mtrs | Ext storm water line-In Front of shops only | RCC MATERIAL | 16 | 350 | 5600 | 16 | 350 | 5600 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 495.6 | 7929.5997 | 16 | 0 | 0 | 16 | 234 | 102636.4 | Mtrs | 6720 | 0 | 0 | 0 | 5600
RCC NP2 Class Pipe 12" - Mtrs | Electrical Line from shops to transformer- in front of shops | RCC MATERIAL | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234 | 102636.4 | Mtrs | 0 | 0 | 0 | 0 | 0
RCC NP2 Class Pipe 12" - Mtrs | Basement level Elecctrical line pipe laying work | RCC MATERIAL | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234 | 102636.4 | Mtrs | 0 | 0 | 0 | 0 | 0
RCC NP2 Class Pipe 12" - Mtrs | In F-Building Storm Water Line-In F-Bldg | RCC MATERIAL | 31.83 | 350 | 11140.5 | 31.83 | 350 | 11140.5 | 31.83 | 0 | 0 | 31.83 | 0 | 31 | 0.83 | 407.1 | 12620.1 | 31 | 0 | 13 | 18 | 234 | 102636.4 | Mtrs | 10695 | 8625 | 0.83 | 0 | 2515.5
RCC NP2 Class Pipe 12" - Mtrs | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | RCC MATERIAL | 130 | 350 | 45500 | 130 | 350 | 45500 | 130 | 0 | 0 | 130 | 0 | 130 | 0 | 407.1 | 52923 | 130 | 0 | 0 | 130 | 234 | 102636.4 | Mtrs | 44850 | 0 | 0 | 0 | 45500
RCC NP2 Class Pipe 12" - Mtrs | Ele.Line -Transf. R to FBldg.-As per Sit | RCC MATERIAL | 65 | 350 | 22750 | 65 | 350 | 22750 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 480.85 | 31255.25 | 0 | 65 | 0 | 0 | 234 | 102636.4 | Mtrs | 0 | 0 | 0 | 0 | 22750
RCC NP2 Class Pipe 12" - Mtrs | Ele.Line -Transformer R to F Bldg. | RCC MATERIAL | 156 | 350 | 54600 | 156 | 350 | 54600 | 156 | 0 | 0 | 156 | 0 | 156 | 0 | 480.85 | 75012.6 | 0 | 156 | 0 | 0 | 234 | 102636.4 | Mtrs | 0 | 0 | 0 | 0 | 54600
RCC NP2 Class Pipe 12" - Mtrs | Ele.Line-D Bldg.to F Bldg. | RCC MATERIAL | 216 | 350 | 75600 | 216 | 350 | 75600 | 216 | 0 | 0 | 216 | 0 | 216 | 0 | 480.85 | 103863.6 | 0 | 216 | 0 | 0 | 234 | 102636.4 | Mtrs | 0 | 0 | 0 | 0 | 75600
RCC NP2 Class Pipe 12" - Mtrs | Ele.Line-F Bldg. to Club House | RCC MATERIAL | 100 | 350 | 35000 | 100 | 350 | 35000 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 480.85 | 48085 | 0 | 100 | 0 | 0 | 234 | 102636.4 | Mtrs | 0 | 0 | 0 | 0 | 35000
RCC NP2 Class Pipe 12" - Mtrs | Ele.Line-Common Electrical Meter Line | RCC MATERIAL | 360 | 350 | 126000 | 360 | 350 | 126000 | 360 | 0 | 0 | 360 | 0 | 360 | 0 | 456.0618 | 164182.25 | 221 | 139 | 221 | 0 | 234 | 102636.4 | Mtrs | 41745 | 14145 | 0 | 0 | 111855