## Material Receipt Details6385828
Material Receipt Details
GANGA ALTUS
Page 1 of 1
Total Records: 9 Records 1 to 9
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
RCC Chamber Cover with Frame 18"x36" (HD) - No. | LG Floor Drainage line pipe laying From Bldg to Nala | RCC MATERIAL | 10 | 3010 | 30100 | 10 | 3010 | 30100 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 2889.4545 | 28894.5453 | 10 | 0 | 0 | 10 | 0 | 0 | No. | 24486.9 | 16461.9 | 0 | 0 | 13638.1
RCC Chamber Cover with Frame 18"x36" (HD) - No. | Ext storm water line-In Front of shops only | RCC MATERIAL | 9 | 3010 | 27090 | 9 | 3010 | 27090 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 3156.5 | 28408.5 | 9 | 0 | 0 | 9 | 0 | 0 | No. | 24075 | 0 | 0 | 0 | 27090
RCC Chamber Cover with Frame 18"x36" (HD) - No. | Re-work material due to damage | RCC MATERIAL | 5 | 3010 | 15050 | 5 | 3010 | 15050 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 2775.0063 | 13875.0315 | 5 | 0 | 0 | 5 | 0 | 0 | No. | 11758.5 | 11758.5 | 0 | 0 | 3291.5
RCC Chamber Cover with Frame 18"x36" (HD) - No. | In F-Building Storm Water Line-In F-Bldg | RCC MATERIAL | 3 | 3010 | 9030 | 3 | 3010 | 9030 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 2775.0063 | 8325.0189 | 3 | 0 | 0 | 3 | 0 | 0 | No. | 7055.1 | 7055.1 | 0 | 0 | 1974.9
RCC Chamber Cover with Frame 18"x36" (HD) - No. | Drainage L-F Bldg.to ETP-As per Site Con | RCC MATERIAL | 3 | 3010 | 9030 | 3 | 3010 | 9030 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 2775.0063 | 8325.0189 | 3 | 0 | 0 | 3 | 0 | 0 | No. | 7055.1 | 7055.1 | 0 | 0 | 1974.9
RCC Chamber Cover with Frame 18"x36" (HD) - No. | Drainage Line.-Side of F Bldg.-As per Site Condition | RCC MATERIAL | 4 | 3010 | 12040 | 4 | 3010 | 12040 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 2775.0063 | 11100.0252 | 4 | 0 | 0 | 4 | 0 | 0 | No. | 9406.8 | 9406.8 | 0 | 0 | 2633.2
RCC Chamber Cover with Frame 18"x36" (HD) - No. | Ele.Line -Transf. R to FBldg.-As per Sit | RCC MATERIAL | 4 | 3010 | 12040 | 4 | 3010 | 12040 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 2775.0063 | 11100.0252 | 4 | 0 | 0 | 4 | 0 | 0 | No. | 9406.8 | 9406.8 | 0 | 0 | 2633.2
RCC Chamber Cover with Frame 18"x36" (HD) - No. | Ele.Line-D Bldg.to F Bldg. | RCC MATERIAL | 9 | 3010 | 27090 | 9 | 3010 | 27090 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 2775.0063 | 24975.0567 | 9 | 0 | 0 | 9 | 0 | 0 | No. | 21165.3 | 21165.3 | 0 | 0 | 5924.7
RCC Chamber Cover with Frame 18"x36" (HD) - No. | STP Overflow line-265KLD to Nala Line-(L) | RCC MATERIAL | 4 | 3010 | 12040 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No. | 0 | 0 | 0 | 4 | 12040