## Material Receipt Details6385828
Material Receipt Details
GANGA ALTUS
Page 1 of 1
Total Records: 15 Records 1 to 15
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
FlyAsh Bricks 3"x4"x9" - No. | LG Floor Drainage line chamber brickwork | BRICKS/ BLOCKS | 9180.68 | 5 | 45903.4 | 15356 | 5 | 76780 | 5373.415 | -6175.32 | 9982.585 | 5373.415 | 9982.585 | 5373.415 | 0 | 7.875 | 42315.6431 | 5373.415 | 0 | 685.415 | 4688 | 13500 | 110880 | No. | 40300.6125 | 0 | 9982.585 | -6175.32 | 45903.4
FlyAsh Bricks 3"x4"x9" - No. | Storm WL Chamber-Brickwork-In front of shop only | BRICKS/ BLOCKS | 838 | 5 | 4190 | 0 | 0 | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -838 | 838 | 13500 | 110880 | No. | 0 | 0 | 0 | 838 | 4190
FlyAsh Bricks 3"x4"x9" - No. | Basement Level Electrical pipe line chamber 4" brickwork | BRICKS/ BLOCKS | 3313 | 5 | 16565 | 3313 | 5 | 16565 | 3313 | 0 | 0 | 3313 | 0 | 3313 | 0 | 8.3361 | 27617.632 | 3313 | 0 | 0 | 3313 | 13500 | 110880 | No. | 24658.6 | 15000 | 0 | 0 | 1565
FlyAsh Bricks 3"x4"x9" - No. | F-Bldg LG Fl-Electrical Cable pipe line Chamber Brickwork-Li | BRICKS/ BLOCKS | 41.72 | 5 | 208.6 | 41.72 | 5 | 208.6 | 41.72 | 0 | 0 | 41.72 | 0 | 41.72 | 0 | 8.064 | 336.4301 | 41.72 | 0 | 0 | 41.72 | 13500 | 110880 | No. | 300.384 | 0 | 0 | 0 | 208.6
FlyAsh Bricks 3"x4"x9" - No. | Transformer Room- 9" Brickwork above Plinth Beam | BRICKS/ BLOCKS | 4837 | 5 | 24185 | 4837 | 5 | 24185 | 4837 | 0 | 0 | 4837 | 0 | 4837 | 0 | 8.4 | 40630.8 | 4372.8 | 464.2 | 4372.8 | 0 | 13500 | 110880 | No. | 32796 | 0 | 0 | 0 | 24185
FlyAsh Bricks 3"x4"x9" - No. | Transformer Room- Cable Trench 15" Thk Brickwork | BRICKS/ BLOCKS | 10091.64 | 5 | 50458.2 | 10091.64 | 5 | 50458.2 | 10091.64 | 0 | 0 | 10091.64 | 0 | 10091.64 | 0 | 8.4 | 84769.776 | 6000 | 4091.64 | -4000 | 10000 | 13500 | 110880 | No. | 45000 | 45000 | 0 | 0 | 5458.2
FlyAsh Bricks 3"x4"x9" - No. | Drainage L-F Bldg.to ETP-As per Site Con | BRICKS/ BLOCKS | 666 | 5 | 3330 | 666 | 5 | 3330 | 666 | 0 | 0 | 666 | 0 | 666 | 0 | 8.064 | 5370.624 | 666 | 0 | 0 | 666 | 13500 | 110880 | No. | 4795.2 | 0 | 0 | 0 | 3330
FlyAsh Bricks 3"x4"x9" - No. | Drainage Line-Bldg. to STP | BRICKS/ BLOCKS | 1091 | 5 | 5455 | 1091 | 5 | 5455 | 1091 | 0 | 0 | 1091 | 0 | 1091 | 0 | 8.064 | 8797.824 | 1024.28 | 66.72 | -66.72 | 1091 | 13500 | 110880 | No. | 7374.816 | 0 | 0 | 0 | 5455
FlyAsh Bricks 3"x4"x9" - No. | Drainage Line-For Club House Additionall | BRICKS/ BLOCKS | 200 | 5 | 1000 | 200 | 5 | 1000 | 200 | 0 | 0 | 200 | 0 | 200 | 0 | 8.064 | 1612.8 | 0 | 200 | 0 | 0 | 13500 | 110880 | No. | 0 | 0 | 0 | 0 | 1000
FlyAsh Bricks 3"x4"x9" - No. | Drainage Line.-Side of F Bldg.-As per Site Condition | BRICKS/ BLOCKS | 1488 | 5 | 7440 | 1488 | 5 | 7440 | 1488 | 0 | 0 | 1488 | 0 | 1488 | 0 | 8.064 | 11999.232 | 0 | 1488 | -1488 | 1488 | 13500 | 110880 | No. | 0 | 0 | 0 | 0 | 7440
FlyAsh Bricks 3"x4"x9" - No. | Storm Line-As per Site Cond | BRICKS/ BLOCKS | 1222 | 5 | 6110 | 1222 | 5 | 6110 | 1222 | 0 | 0 | 1222 | 0 | 1222 | 0 | 8.064 | 9854.208 | 0 | 1222 | 0 | 0 | 13500 | 110880 | No. | 0 | 0 | 0 | 0 | 6110
FlyAsh Bricks 3"x4"x9" - No. | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | BRICKS/ BLOCKS | 7103 | 5 | 35515 | 7103 | 5 | 35515 | 7103 | 0 | 0 | 7103 | 0 | 7103 | 0 | 8.064 | 57278.592 | 0 | 7103 | 0 | 0 | 13500 | 110880 | No. | 0 | 0 | 0 | 0 | 35515
FlyAsh Bricks 3"x4"x9" - No. | STP Overflow-STP to PMC Gutter | BRICKS/ BLOCKS | 2361 | 5 | 11805 | 2361 | 5 | 11805 | 2361 | 0 | 0 | 2361 | 0 | 2361 | 0 | 8.064 | 19039.104 | 0 | 2361 | 0 | 0 | 13500 | 110880 | No. | 0 | 0 | 0 | 0 | 11805
FlyAsh Bricks 3"x4"x9" - No. | Ele.Line-F Bldg. to Club House | BRICKS/ BLOCKS | 1018 | 5 | 5090 | 1018 | 5 | 5090 | 1018 | 0 | 0 | 1018 | 0 | 1018 | 0 | 8.064 | 8209.152 | 0 | 1018 | 0 | 0 | 13500 | 110880 | No. | 0 | 0 | 0 | 0 | 5090
FlyAsh Bricks 3"x4"x9" - No. | STP Overflow line-265KLD to Nala Line-(L) | BRICKS/ BLOCKS | 2287 | 5 | 11435 | 2287 | 5 | 11435 | 2287 | 0 | 0 | 2287 | 0 | 2287 | 0 | 8.064 | 18442.368 | 0 | 2287 | 0 | 0 | 13500 | 110880 | No. | 0 | 0 | 0 | 0 | 11435