## Material Receipt Details6385864
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 28 Records 1 to 28
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Binding Wire - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 355 | 62.85 | 22311.75 | 355 | 62.85 | 22311.75 | 355 | 0 | 0 | 355 | 0 | 355 | 0 | 73.16 | 25971.8 | 355 | 0 | 0 | 355 | 2428.351 | 192559.3726 | Kgs | 22010 | 0 | 0 | 0 | 22311.75
Binding Wire - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 63 | 62.85 | 3959.55 | 63 | 0 | 0 | 63 | 0 | 63 | 0 | 73.16 | 4609.08 | 63 | 0 | 63 | 0 | 2428.351 | 192559.3726 | Kgs | 3906 | 0 | 0 | 0 | 3959.55
Binding Wire - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 0 | 0 | 0 | 0 | 251.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -125.29 | 125.29 | 2428.351 | 192559.3726 | Kgs | 0 | 0 | 0 | 251.93 | 15833.8005
Cement 43 Grade - Bags | Wing 1-12th Slab (6th Floor) Cement For Misc Work | CEMENT | 35 | 375 | 13125 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 43 | 14621.8654 | Bags | 0 | 0 | 0 | 35 | 13125
Cement 43 Grade - Bags | Wing 1-12th Slab (6th Floor) Cement For Cover Block Making | CEMENT | 12 | 375 | 4500 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 8 | 43 | 14621.8654 | Bags | 0 | 0 | 0 | 12 | 4500
Cement Loose 53 Grade - Metric Tonnes | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | CEMENT | 73.335 | 3880 | 284539.8 | 0 | 0 | 0 | 0 | 73.335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27.04 | 27.04 | 284.7066 | 2148117.02 | Metric Tonnes | 0 | 0 | 0 | 73.335 | 284539.8
Cement Loose 53 Grade - Metric Tonnes | Wing 1.12th Slab (6th Flr) Slab,Beam,Stair Con M30 | CEMENT | 49.049 | 3880 | 190310.12 | 0 | 0 | 0 | 0 | 49.049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10.56 | 10.56 | 284.7066 | 2148117.02 | Metric Tonnes | 0 | 0 | 0 | 49.049 | 190310.12
Crush Sand - Cu.Ft | Wing 1-12th Slab (6th Floor) Cement For Cover Block Making | SAND & METAL | 50 | 33 | 1650 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35 | 35 | 1389.318 | 54348.2432 | Cu.Ft | 0 | 0 | 0 | 50 | 1650
GFRP Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.33 | 0 | 2086.33 | 0 | 6259 | 1144771.1 | Kgs | 323381.15 | 323381.15 | 0 | 0 | -114748.15
GP2 Waterproofing Chemical - Kgs | Wing 1-12th Slab (6th Floor) GP2 For Wall Tie & Rod Hole | CONSUMABLE/MISC MATERIAL | 1035 | 150 | 155250 | 1035 | 150 | 155250 | 1035 | 0 | 0 | 1035 | 0 | 1035 | 0 | 20.65 | 21372.75 | 1035 | 0 | 1035 | 0 | 675 | 13938.75 | Kgs | 18112.5 | 0 | 0 | 0 | 155250
Nitobond SBR (Latex) - Ltrs | Wing 1-12th Slab (6th Floor) Nitobond SBR For Concrete Joint | CONSUMABLE/MISC MATERIAL | 40 | 265 | 10600 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 56050 | Ltrs | 0 | 0 | 0 | 40 | 10600
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | Wing 1.12th Slab (6th Flr) Slab,Beam,Stair Con M30 | RMC | 222.95 | 3150 | 702292.5 | 70 | 3150 | 220500 | 70 | 152.95 | 0 | 70 | 0 | 70 | 0 | 4462.9996 | 312409.972 | 48 | 22 | 0 | 48 | 0 | -0.016 | Cu.Mtrs | 0 | 0 | 0 | 152.95 | 702292.5
Sand-Metal Mix M40 hi-flow (Pumpable) - Cu.Mtrs | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | RMC | 282.06 | 3150 | 888489 | 120 | 3150 | 378000 | 120 | 162.06 | 0 | 120 | 0 | 120 | 0 | 4462.9996 | 535559.952 | 104 | 16 | 0 | 104 | 0 | -0.028 | Cu.Mtrs | 98337.278 | 0 | 0 | 162.06 | 888489
Steel Bar 25mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 4051 | 50.85 | 205993.35 | 0 | 0 | 0 | 0 | 4051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4028 | 4028 | 21317 | 1290754.0223 | Kgs | 0 | 0 | 0 | 4051 | 205993.35
Steel Bar 25mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3287 | 3287 | 21317 | 1290754.0223 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bars 10mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 3220 | 50.85 | 163737 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3175 | 3175 | 16031 | 970789.9009 | Kgs | 0 | 0 | 0 | 3220 | 163737
Steel Bars 10mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3339 | 3339 | 16031 | 970789.9009 | Kgs | 0 | 0 | 0 | 3382.53 | 172001.6505
Steel Bars 12mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 2587 | 50.85 | 131548.95 | 0 | 0 | 0 | 0 | 2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2560 | 2560 | 15443 | 921728.0722 | Kgs | 0 | 0 | 0 | 2587 | 131548.95
Steel Bars 12mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2731 | 2731 | 15443 | 921728.0722 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 16mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 3238 | 50.85 | 164652.3 | 0 | 0 | 0 | 0 | 3238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3185 | 3185 | 11578 | 691267.4986 | Kgs | 0 | 0 | 0 | 3238 | 164652.3
Steel Bars 16mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2806 | 2806 | 11578 | 691267.4986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 20mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 8542 | 50.85 | 434360.7 | 8542 | 50.85 | 434360.7 | 6510 | 0 | 2032 | 6510 | 2032 | 6510 | 0 | 58.646 | 381785.46 | 6510 | 0 | -2024 | 8534 | 25911.66 | 1567556.2324 | Kgs | 323547 | 0 | 2032 | 0 | 434360.7
Steel Bars 20mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3556 | 3556 | 25911.66 | 1567556.2324 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 32mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 5651 | 50.85 | 287353.35 | 5000 | 50.85 | 254250 | 5000 | 651 | 0 | 5000 | 0 | 5000 | 0 | 64.31 | 321550 | 4920 | 80 | -692 | 5612 | 7564 | 477175.91 | Kgs | 268140 | 268140 | 0 | 651 | 19213.35
Steel Bars 32mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -532 | 532 | 7564 | 477175.91 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 8mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 8166 | 50.85 | 415241.1 | 0 | 0 | 0 | 0 | 8166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8140 | 8140 | 52472.88 | 3241970.0038 | Kgs | 0 | 0 | 0 | 8166 | 415241.1
Steel Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52472.88 | 3241970.0038 | Kgs | 0 | 0 | 0 | 0 | 0
Steel Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8220 | 8220 | 52472.88 | 3241970.0038 | Kgs | 0 | 0 | 0 | 8281.07 | 421092.4095