## Material Receipt Details6385864
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 27 Records 1 to 27
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Binding Wire - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 336 | 62.85 | 21117.6 | 336 | 62.85 | 21117.6 | 336 | 0 | 0 | 336 | 0 | 336 | 0 | 73.16 | 24581.76 | 336 | 0 | 336 | 0 | 2428.351 | 192559.3726 | Kgs | 20832 | 0 | 0 | 0 | 21117.6
Binding Wire - Kgs | Wing 1-13th Slab (7th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 65 | 62.85 | 4085.25 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 75.52 | 4908.8 | 0 | 65 | 0 | 0 | 2428.351 | 192559.3726 | Kgs | 0 | 0 | 0 | 0 | 4085.25
Binding Wire - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200.79 | 200.79 | 2428.351 | 192559.3726 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Cement 43 Grade - Bags | Wing 1-13th Slab (7th Floor) Cement For Misc Work | CEMENT | 35 | 375 | 13125 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 14621.8654 | Bags | 0 | 0 | 0 | 35 | 13125
Cement 43 Grade - Bags | Wing 1-13th Slab (7th Floor) Cement For Cover Block Making | CEMENT | 12 | 375 | 4500 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 14621.8654 | Bags | 0 | 0 | 0 | 12 | 4500
Cement Loose 53 Grade - Metric Tonnes | Wing 1.13th Slab (7th Floor) Column,LW,SW M.40 | CEMENT | 73.335 | 3880 | 284539.8 | 0 | 0 | 0 | 0 | 73.335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.7066 | 2148117.02 | Metric Tonnes | 0 | 0 | 0 | 73.335 | 284539.8
Cement Loose 53 Grade - Metric Tonnes | Wing 1 13th Slab Slab,Beam,Stair Con M30 | CEMENT | 49.049 | 3880 | 190310.12 | 0 | 0 | 0 | 0 | 49.049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.7066 | 2148117.02 | Metric Tonnes | 0 | 0 | 0 | 49.049 | 190310.12
Crush Sand - Cu.Ft | Wing 1-13th Slab (7th Floor) Cement For Cover Block Making | SAND & METAL | 50 | 33 | 1650 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1389.318 | 54348.2432 | Cu.Ft | 0 | 0 | 0 | 50 | 1650
GFRP Bars 8mm - Kgs | Wing 1-13th Slab (7th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.33 | 0 | 2086.33 | 0 | 6259 | 1144771.1 | Kgs | 323381.15 | 3512.3 | 0 | 0 | 205120.7
GP2 Waterproofing Chemical - Kgs | Wing 1-13th Slab (7th Floor) GP2 For Wall Tie & Rod Hole | CONSUMABLE/MISC MATERIAL | 1035 | 150 | 155250 | 500 | 150 | 75000 | 500 | 535 | 0 | 500 | 0 | 500 | 0 | 20.65 | 10325 | 500 | 0 | 500 | 0 | 675 | 13938.75 | Kgs | 8750 | 0 | 0 | 535 | 155250
Nitobond SBR (Latex) - Ltrs | Wing 1-12th Slab (7th Floor) Nitobond SBR For Concrete Joint | CONSUMABLE/MISC MATERIAL | 40 | 265 | 10600 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 56050 | Ltrs | 0 | 0 | 0 | 40 | 10600
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | Wing 1 13th Slab Slab,Beam,Stair Con M30 | RMC | 222.95 | 3150 | 702292.5 | 0 | 0 | 0 | 0 | 222.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.016 | Cu.Mtrs | 0 | 0 | 0 | 222.95 | 702292.5
Sand-Metal Mix M40 hi-flow (Pumpable) - Cu.Mtrs | Wing 1.13th Slab (7th Floor) Column,LW,SW M.40 | RMC | 282.06 | 3150 | 888489 | 0 | 0 | 0 | 0 | 282.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.028 | Cu.Mtrs | 0 | 0 | 0 | 282.06 | 888489
Steel Bar 25mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 3380 | 50.85 | 171873 | 0 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2871 | 2871 | 21317 | 1290754.0223 | Kgs | 0 | 0 | 0 | 3380 | 171873
Steel Bar 25mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -926 | 926 | 21317 | 1290754.0223 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bars 10mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 3220 | 50.85 | 163737 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16031 | 970789.9009 | Kgs | 0 | 0 | 0 | 3220 | 163737
Steel Bars 10mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -814 | 814 | 16031 | 970789.9009 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 12mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 2819 | 50.85 | 143346.15 | 0 | 0 | 0 | 0 | 2819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2560 | 2560 | 15443 | 921728.0722 | Kgs | 0 | 0 | 0 | 2819 | 143346.15
Steel Bars 12mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1707 | 1707 | 15443 | 921728.0722 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 16mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 3701 | 50.85 | 188195.85 | 0 | 0 | 0 | 0 | 3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3034 | 3034 | 11578 | 691267.4986 | Kgs | 0 | 0 | 0 | 3701 | 188195.85
Steel Bars 16mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1517 | 1517 | 11578 | 691267.4986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 20mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 8175 | 50.85 | 415698.75 | 0 | 0 | 0 | 0 | 8175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1067 | 1067 | 25911.66 | 1567556.2324 | Kgs | 0 | 0 | 0 | 8175 | 415698.75
Steel Bars 20mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1778 | 1778 | 25911.66 | 1567556.2324 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 32mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 4096 | 50.85 | 208281.6 | 0 | 0 | 0 | 0 | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1896 | 1896 | 7564 | 477175.91 | Kgs | 0 | 0 | 0 | 4096 | 208281.6
Steel Bars 32mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -531 | 531 | 7564 | 477175.91 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 8mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 8166 | 50.85 | 415241.1 | 0 | 0 | 0 | 0 | 8166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1048 | 1048 | 52472.88 | 3241970.0038 | Kgs | 0 | 0 | 0 | 8166 | 415241.1
Steel Bars 8mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3223 | 3223 | 52472.88 | 3241970.0038 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848