## Material Receipt Details6385871
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 28 Records 1 to 28
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Binding Wire - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 325 | 62.85 | 20426.25 | 325 | 62.85 | 20426.25 | 325 | 0 | 0 | 325 | 0 | 325 | 0 | 79.06 | 25694.5 | 325 | 0 | 325 | 0 | 2428.351 | 192559.3726 | Kgs | 21775 | 0 | 0 | 0 | 20426.25
Binding Wire - Kgs | Wing 1-14th Slab (8th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 65 | 62.85 | 4085.25 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 75.52 | 4908.8 | 0 | 65 | 0 | 0 | 2428.351 | 192559.3726 | Kgs | 0 | 0 | 0 | 0 | 4085.25
Binding Wire - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2428.351 | 192559.3726 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Cement 43 Grade - Bags | Wing 1-14th Slab (8th Floor) Cement For Misc Work | CEMENT | 35 | 375 | 13125 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 14621.8654 | Bags | 0 | 0 | 0 | 35 | 13125
Cement 43 Grade - Bags | Wing 1-14th Slab (8th Floor) Cement For Cover Block Making | CEMENT | 12 | 375 | 4500 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 14621.8654 | Bags | 0 | 0 | 0 | 12 | 4500
Cement 53 Grade - Bags | Wing 1.14th Slab (8th Floor) Column,LW,SW M.40 | CEMENT | 37.568 | 360 | 13524.48 | 0 | 0 | 0 | 0 | 37.568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bags | 0 | 0 | 0 | 37.568 | 13524.48
Cement Loose 53 Grade - Metric Tonnes | Wing 1.14th Slab (8th Floor) Column,LW,SW M.40 | CEMENT | 35.767 | 3880 | 138775.96 | 0 | 0 | 0 | 0 | 35.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.7066 | 2148117.02 | Metric Tonnes | 0 | 0 | 0 | 35.767 | 138775.96
Cement Loose 53 Grade - Metric Tonnes | Wing 1 14th Slab Slab,Beam,Stair Con M30 | CEMENT | 49.049 | 3880 | 190310.12 | 0 | 0 | 0 | 0 | 49.049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.7066 | 2148117.02 | Metric Tonnes | 0 | 0 | 0 | 49.049 | 190310.12
Crush Sand - Cu.Ft | Wing 1-14th Slab (8th Floor) Cement For Cover Block Making | SAND & METAL | 50 | 33 | 1650 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1389.318 | 54348.2432 | Cu.Ft | 0 | 0 | 0 | 50 | 1650
GFRP Bars 8mm - Kgs | Wing 1-14th Slab (8th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.33 | 0 | 2086.33 | 0 | 6259 | 1144771.1 | Kgs | 323381.15 | 0 | 0 | 0 | 208633
GP2 Waterproofing Chemical - Kgs | Wing 1-14th Slab (8th Floor) GP2 For Wall Tie & Rod Hole | CONSUMABLE/MISC MATERIAL | 1035 | 150 | 155250 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 13938.75 | Kgs | 0 | 0 | 0 | 1035 | 155250
Nitobond SBR (Latex) - Ltrs | Wing 1-14th Slab (8th Floor) Nitobond SBR For Concrete Joint | CONSUMABLE/MISC MATERIAL | 40 | 265 | 10600 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 56050 | Ltrs | 0 | 0 | 0 | 40 | 10600
Sand-Metal Mix M30 hi-flow (Pumpable) - Cu.Mtrs | Wing 1 14th Slab Slab,Beam,Stair Con M30 | RMC | 222.95 | 3150 | 702292.5 | 0 | 0 | 0 | 0 | 222.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.016 | Cu.Mtrs | 0 | 0 | 0 | 222.95 | 702292.5
Sand-Metal Mix M40 hi-flow (Pumpable) - Cu.Mtrs | Wing 1.14th Slab (8th Floor) Column,LW,SW M.40 | RMC | 282.06 | 3150 | 888489 | 0 | 0 | 0 | 0 | 282.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.028 | Cu.Mtrs | 0 | 0 | 0 | 282.06 | 888489
Steel Bar 25mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3981 | 50.85 | 202433.85 | 0 | 0 | 0 | 0 | 3981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20808 | 1260275.1023 | Kgs | 0 | 0 | 0 | 3981 | 202433.85
Steel Bar 25mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20808 | 1260275.1023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bars 10mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3282 | 50.85 | 166889.7 | 0 | 0 | 0 | 0 | 3282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16031 | 970789.9009 | Kgs | 0 | 0 | 0 | 3282 | 166889.7
Steel Bars 10mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16031 | 970789.9009 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 12mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 2868 | 50.85 | 145837.8 | 0 | 0 | 0 | 0 | 2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15443 | 921728.0722 | Kgs | 0 | 0 | 0 | 2868 | 145837.8
Steel Bars 12mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15443 | 921728.0722 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 16mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3622 | 50.85 | 184178.7 | 0 | 0 | 0 | 0 | 3622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11578 | 691267.4986 | Kgs | 0 | 0 | 0 | 3622 | 184178.7
Steel Bars 16mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11578 | 691267.4986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 20mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 7550 | 50.85 | 383917.5 | 0 | 0 | 0 | 0 | 7550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23510.66 | 1425649.7724 | Kgs | 0 | 0 | 0 | 7550 | 383917.5
Steel Bars 20mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23510.66 | 1425649.7724 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 32mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3034 | 50.85 | 154278.9 | 0 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7564 | 477175.91 | Kgs | 0 | 0 | 0 | 3034 | 154278.9
Steel Bars 32mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7564 | 477175.91 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 8mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 8131 | 50.85 | 413461.35 | 0 | 0 | 0 | 0 | 8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52472.88 | 3241970.0038 | Kgs | 0 | 0 | 0 | 8131 | 413461.35
Steel Bars 8mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52472.88 | 3241970.0038 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848