## Material Receipt Details6385872
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 63 Records 1 to 63
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Cement 43 Grade - Bags | Wing-1 Flat No 101 Int Flat Chemical Grouting Work | CEMENT | 1.1237 | 375 | 421.3875 | 1.1237 | 375 | 421.3875 | 1.1237 | 0 | 0 | 1.1237 | 0 | 1.1237 | 0 | 364.9997 | 410.1502 | 1.1237 | 0 | 1.1237 | 0 | 35 | 11901.5454 | Bags | 320.4298 | 320.4298 | 0 | 0 | 100.9577
Cement 43 Grade - Bags | Wing-1 Flat No 101 C.Toilet Chemical Coat W/P | CEMENT | 0.1085 | 375 | 40.6875 | 0.1085 | 375 | 40.6875 | 0.1085 | 0 | 0 | 0.1085 | 0 | 0.1085 | 0 | 364.9997 | 39.6025 | 0.1085 | 0 | 0.1085 | 0 | 35 | 11901.5454 | Bags | 30.9394 | 30.9394 | 0 | 0 | 9.7481
Cement 43 Grade - Bags | Wing-1 Flat No 101 C.Toilet IPS W/P | CEMENT | 1.1869 | 375 | 445.0875 | 1.1869 | 375 | 445.0875 | 1.1869 | 0 | 0 | 1.1869 | 0 | 1.1869 | 0 | 364.9997 | 433.2181 | 1.1869 | 0 | 1.1869 | 0 | 35 | 11901.5454 | Bags | 338.4517 | 338.4517 | 0 | 0 | 106.6358
Cement 43 Grade - Bags | Wing-1 Flat No 101 M.Toilet Chemical Coat W/P | CEMENT | 0.124 | 375 | 46.5 | 0.124 | 375 | 46.5 | 0.124 | 0 | 0 | 0.124 | 0 | 0.124 | 0 | 364.9997 | 45.26 | 0.124 | 0 | 0.124 | 0 | 35 | 11901.5454 | Bags | 35.3593 | 35.3593 | 0 | 0 | 11.1407
Cement 43 Grade - Bags | Wing-1 Flat No 101 M.Toilet IPS W/P | CEMENT | 1.3563 | 375 | 508.6125 | 1.3563 | 375 | 508.6125 | 1.3563 | 0 | 0 | 1.3563 | 0 | 1.3563 | 0 | 364.9997 | 495.0491 | 1.3563 | 0 | 1.3563 | 0 | 35 | 11901.5454 | Bags | 386.7571 | 386.7571 | 0 | 0 | 121.8554
Cement 43 Grade - Bags | Wing-1 Flat No 101 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.6277 | 375 | 610.3875 | 1.6277 | 375 | 610.3875 | 1.6277 | 0 | 0 | 1.6277 | 0 | 1.6277 | 0 | 364.9997 | 594.11 | 1.6277 | 0 | 1.6277 | 0 | 35 | 11901.5454 | Bags | 464.1484 | 464.1484 | 0 | 0 | 146.2391
Cement 43 Grade - Bags | Wing-1 Flat No 109 M.Toilet IPS W/P | CEMENT | 1.3563 | 375 | 508.6125 | 1.3563 | 375 | 508.6125 | 1.3563 | 0 | 0 | 1.3563 | 0 | 1.3563 | 0 | 364.9997 | 495.0491 | 1.3563 | 0 | 1.3563 | 0 | 35 | 11901.5454 | Bags | 386.7571 | 386.7571 | 0 | 0 | 121.8554
Cement 43 Grade - Bags | Wing-1 Flat No 109 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5696 | 375 | 588.6 | 1.5696 | 375 | 588.6 | 1.5696 | 0 | 0 | 1.5696 | 0 | 1.5696 | 0 | 364.9997 | 572.9035 | 1.5696 | 0 | 1.5696 | 0 | 35 | 11901.5454 | Bags | 447.5809 | 447.5809 | 0 | 0 | 141.0191
Cement 43 Grade - Bags | Wing-1 Flat No 109 Balcony Brickbatt+Finish Coat W/P | CEMENT | 1.8167 | 375 | 681.2625 | 1.8167 | 375 | 681.2625 | 1.8167 | 0 | 0 | 1.8167 | 0 | 1.8167 | 0 | 364.9997 | 663.095 | 1.8167 | 0 | 1.8167 | 0 | 35 | 11901.5454 | Bags | 518.0429 | 518.0429 | 0 | 0 | 163.2196
Cement 43 Grade - Bags | Wing-1 Flat No 108 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5696 | 375 | 588.6 | 1.5696 | 375 | 588.6 | 1.5696 | 0 | 0 | 1.5696 | 0 | 1.5696 | 0 | 364.9997 | 572.9035 | 1.5696 | 0 | 1.5696 | 0 | 35 | 11901.5454 | Bags | 447.5809 | 447.5809 | 0 | 0 | 141.0191
Cement 43 Grade - Bags | Wing-1 Flat No 108 Balcony Brickbatt+Finish Coat W/P | CEMENT | 1.8167 | 375 | 681.2625 | 1.8167 | 375 | 681.2625 | 1.8167 | 0 | 0 | 1.8167 | 0 | 1.8167 | 0 | 364.9997 | 663.095 | 1.8167 | 0 | 1.8167 | 0 | 35 | 11901.5454 | Bags | 518.0429 | 518.0429 | 0 | 0 | 163.2196
Cement 43 Grade - Bags | Wing.1 Flat No 109 Int Flat Chemical Grouting Work | CEMENT | 0.8596 | 375 | 322.35 | 0.8596 | 375 | 322.35 | 0.8596 | 0 | 0 | 0.8596 | 0 | 0.8596 | 0 | 364.9997 | 313.7537 | 0.8596 | 0 | 0.8596 | 0 | 35 | 11901.5454 | Bags | 245.1201 | 245.1201 | 0 | 0 | 77.2299
Cement 43 Grade - Bags | Wing-1 Flat No 109 C.Toilet Chemical Coat W/P | CEMENT | 0.1013 | 375 | 37.9875 | 0.1013 | 375 | 37.9875 | 0.1013 | 0 | 0 | 0.1013 | 0 | 0.1013 | 0 | 364.9997 | 36.9745 | 0.1013 | 0 | 0.1013 | 0 | 35 | 11901.5454 | Bags | 28.8863 | 28.8863 | 0 | 0 | 9.1012
Cement 43 Grade - Bags | Wing-1 Flat No 109 C.Toilet IPS W/P | CEMENT | 1.1078 | 375 | 415.425 | 1.1078 | 375 | 415.425 | 1.1078 | 0 | 0 | 1.1078 | 0 | 1.1078 | 0 | 364.9997 | 404.3467 | 1.1078 | 0 | 1.1078 | 0 | 35 | 11901.5454 | Bags | 315.8958 | 315.8958 | 0 | 0 | 99.5292
Cement 43 Grade - Bags | Wing-1 Flat No 109 M.Toilet Chemical Coat W/P | CEMENT | 0.124 | 375 | 46.5 | 0.124 | 375 | 46.5 | 0.124 | 0 | 0 | 0.124 | 0 | 0.124 | 0 | 364.9997 | 45.26 | 0.124 | 0 | 0.124 | 0 | 35 | 11901.5454 | Bags | 35.3593 | 35.3593 | 0 | 0 | 11.1407
Cement 43 Grade - Bags | Wing-1 Flat No 107 Balcony Brickbatt+Finish Coat W/P | CEMENT | 2.4575 | 375 | 921.5625 | 2.4575 | 375 | 921.5625 | 2.4575 | 0 | 0 | 2.4575 | 0 | 2.4575 | 0 | 364.9997 | 896.9868 | 2.4575 | 0 | 2.4575 | 0 | 35 | 11901.5454 | Bags | 700.7709 | 700.7709 | 0 | 0 | 220.7916
Cement 43 Grade - Bags | Wing-1 Flat No 108 Int Flat Chemical Grouting Work | CEMENT | 0.8596 | 375 | 322.35 | 0.8596 | 375 | 322.35 | 0.8596 | 0 | 0 | 0.8596 | 0 | 0.8596 | 0 | 364.9997 | 313.7537 | 0.8596 | 0 | 0.8596 | 0 | 35 | 11901.5454 | Bags | 245.1201 | 245.1201 | 0 | 0 | 77.2299
Cement 43 Grade - Bags | Wing-1 Flat No 108 C.Toilet Chemical Coat W/P | CEMENT | 0.1013 | 375 | 37.9875 | 0.1013 | 375 | 37.9875 | 0.1013 | 0 | 0 | 0.1013 | 0 | 0.1013 | 0 | 364.9997 | 36.9745 | 0.1013 | 0 | 0.1013 | 0 | 35 | 11901.5454 | Bags | 28.8863 | 28.8863 | 0 | 0 | 9.1012
Cement 43 Grade - Bags | Wing-1 Flat No 108 C.Toilet IPS W/P | CEMENT | 1.1078 | 375 | 415.425 | 1.1078 | 375 | 415.425 | 1.1078 | 0 | 0 | 1.1078 | 0 | 1.1078 | 0 | 364.9997 | 404.3467 | 1.1078 | 0 | 1.1078 | 0 | 35 | 11901.5454 | Bags | 315.8958 | 315.8958 | 0 | 0 | 99.5292
Cement 43 Grade - Bags | Wing-1 Flat No 108 M.Toilet Chemical Coat W/P | CEMENT | 0.124 | 375 | 46.5 | 0.124 | 375 | 46.5 | 0.124 | 0 | 0 | 0.124 | 0 | 0.124 | 0 | 364.9997 | 45.26 | 0.124 | 0 | 0.124 | 0 | 35 | 11901.5454 | Bags | 35.3593 | 35.3593 | 0 | 0 | 11.1407
Cement 43 Grade - Bags | Wing-1 Flat No 108 M.Toilet IPS W/P | CEMENT | 1.3563 | 375 | 508.6125 | 1.3563 | 375 | 508.6125 | 1.3563 | 0 | 0 | 1.3563 | 0 | 1.3563 | 0 | 364.9997 | 495.0491 | 1.3563 | 0 | 1.3563 | 0 | 35 | 11901.5454 | Bags | 386.7571 | 386.7571 | 0 | 0 | 121.8554
Cement 43 Grade - Bags | Wing-1 Flat No 107 Int Flat Chemical Grouting Work | CEMENT | 1.1378 | 375 | 426.675 | 1.1378 | 375 | 426.675 | 1.1378 | 0 | 0 | 1.1378 | 0 | 1.1378 | 0 | 364.9997 | 415.2967 | 1.1378 | 0 | 1.1378 | 0 | 35 | 11901.5454 | Bags | 324.4505 | 324.4505 | 0 | 0 | 102.2245
Cement 43 Grade - Bags | Wing-1 Flat No 107 C.Toilet Chemical Coat W/P | CEMENT | 0.1085 | 375 | 40.6875 | 0.1085 | 375 | 40.6875 | 0.1085 | 0 | 0 | 0.1085 | 0 | 0.1085 | 0 | 364.9997 | 39.6025 | 0.1085 | 0 | 0.1085 | 0 | 35 | 11901.5454 | Bags | 30.9394 | 30.9394 | 0 | 0 | 9.7481
Cement 43 Grade - Bags | Wing-1 Flat No 107 C.Toilet IPS W/P | CEMENT | 1.1869 | 375 | 445.0875 | 1.1869 | 375 | 445.0875 | 1.1869 | 0 | 0 | 1.1869 | 0 | 1.1869 | 0 | 364.9997 | 433.2181 | 1.1869 | 0 | 1.1869 | 0 | 35 | 11901.5454 | Bags | 338.4517 | 338.4517 | 0 | 0 | 106.6358
Cement 43 Grade - Bags | Wing-1 Flat No 107 M.Toilet Chemical Coat W/P | CEMENT | 0.1395 | 375 | 52.3125 | 0.1395 | 375 | 52.3125 | 0.1395 | 0 | 0 | 0.1395 | 0 | 0.1395 | 0 | 364.9997 | 50.9175 | 0.1395 | 0 | 0.1395 | 0 | 35 | 11901.5454 | Bags | 39.7793 | 39.7793 | 0 | 0 | 12.5332
Cement 43 Grade - Bags | Wing-1 Flat No 107 M.Toilet IPS W/P | CEMENT | 1.5257 | 375 | 572.1375 | 1.5257 | 375 | 572.1375 | 1.5257 | 0 | 0 | 1.5257 | 0 | 1.5257 | 0 | 364.9997 | 556.88 | 1.5257 | 0 | 1.5257 | 0 | 35 | 11901.5454 | Bags | 435.0625 | 435.0625 | 0 | 0 | 137.075
Cement 43 Grade - Bags | Wing-1 Flat No 107 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5984 | 375 | 599.4 | 1.5984 | 375 | 599.4 | 1.5984 | 0 | 0 | 1.5984 | 0 | 1.5984 | 0 | 364.9997 | 583.4155 | 1.5984 | 0 | 1.5984 | 0 | 35 | 11901.5454 | Bags | 455.7934 | 455.7934 | 0 | 0 | 143.6066
Cement 43 Grade - Bags | Wing-1 Flat No 106 C.Toilet Chemical Coat W/P | CEMENT | 0.1085 | 375 | 40.6875 | 0.1085 | 375 | 40.6875 | 0.1085 | 0 | 0 | 0.1085 | 0 | 0.1085 | 0 | 364.9997 | 39.6025 | 0.1085 | 0 | 0.1085 | 0 | 35 | 11901.5454 | Bags | 30.9394 | 30.9394 | 0 | 0 | 9.7481
Cement 43 Grade - Bags | Wing-1 Flat No 106 C.Toilet IPS W/P | CEMENT | 1.1869 | 375 | 445.0875 | 1.1869 | 375 | 445.0875 | 1.1869 | 0 | 0 | 1.1869 | 0 | 1.1869 | 0 | 364.9997 | 433.2181 | 1.1869 | 0 | 1.1869 | 0 | 35 | 11901.5454 | Bags | 338.4517 | 338.4517 | 0 | 0 | 106.6358
Cement 43 Grade - Bags | Wing-1 Flat No 106 M.Toilet Chemical Coat W/P | CEMENT | 0.1395 | 375 | 52.3125 | 0.1395 | 375 | 52.3125 | 0.1395 | 0 | 0 | 0.1395 | 0 | 0.1395 | 0 | 364.9997 | 50.9175 | 0.1395 | 0 | 0.1395 | 0 | 35 | 11901.5454 | Bags | 39.7793 | 39.7793 | 0 | 0 | 12.5332
Cement 43 Grade - Bags | Wing-1 Flat No 106 M.Toilet IPS W/P | CEMENT | 1.5257 | 375 | 572.1375 | 1.5257 | 375 | 572.1375 | 1.5257 | 0 | 0 | 1.5257 | 0 | 1.5257 | 0 | 364.9997 | 556.88 | 1.5257 | 0 | 1.5257 | 0 | 35 | 11901.5454 | Bags | 435.0625 | 435.0625 | 0 | 0 | 137.075
Cement 43 Grade - Bags | Wing-1 Flat No 106 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5984 | 375 | 599.4 | 1.5984 | 375 | 599.4 | 1.5984 | 0 | 0 | 1.5984 | 0 | 1.5984 | 0 | 364.9997 | 583.4155 | 1.5984 | 0 | 1.5984 | 0 | 35 | 11901.5454 | Bags | 455.7934 | 455.7934 | 0 | 0 | 143.6066
Cement 43 Grade - Bags | Wing-1 Flat No 106 Balcony Brickbatt+Finish Coat W/P | CEMENT | 2.4575 | 375 | 921.5625 | 2.4575 | 375 | 921.5625 | 2.4575 | 0 | 0 | 2.4575 | 0 | 2.4575 | 0 | 364.9997 | 896.9868 | 2.4575 | 0 | 2.4575 | 0 | 35 | 11901.5454 | Bags | 700.7709 | 700.7709 | 0 | 0 | 220.7916
Cement 43 Grade - Bags | Wing-1 Flat No 105 C.Toilet IPS W/P | CEMENT | 1.1078 | 375 | 415.425 | 1.1078 | 375 | 415.425 | 1.1078 | 0 | 0 | 1.1078 | 0 | 1.1078 | 0 | 364.9997 | 404.3467 | 1.1078 | 0 | 1.1078 | 0 | 35 | 11901.5454 | Bags | 315.8958 | 315.8958 | 0 | 0 | 99.5292
Cement 43 Grade - Bags | Wing-1 Flat No 105 M.Toilet Chemical Coat W/P | CEMENT | 0.124 | 375 | 46.5 | 0.124 | 375 | 46.5 | 0.124 | 0 | 0 | 0.124 | 0 | 0.124 | 0 | 364.9997 | 45.26 | 0.124 | 0 | 0.124 | 0 | 35 | 11901.5454 | Bags | 35.3593 | 35.3593 | 0 | 0 | 11.1407
Cement 43 Grade - Bags | Wing-1 Flat No 105 M.Toilet IPS W/P | CEMENT | 1.3563 | 375 | 508.6125 | 1.3563 | 375 | 508.6125 | 1.3563 | 0 | 0 | 1.3563 | 0 | 1.3563 | 0 | 364.9997 | 495.0491 | 1.3563 | 0 | 1.3563 | 0 | 35 | 11901.5454 | Bags | 386.7571 | 386.7571 | 0 | 0 | 121.8554
Cement 43 Grade - Bags | Wing-1 Flat No 105 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5696 | 375 | 588.6 | 1.5696 | 375 | 588.6 | 1.5696 | 0 | 0 | 1.5696 | 0 | 1.5696 | 0 | 364.9997 | 572.9035 | 1.5696 | 0 | 1.5696 | 0 | 35 | 11901.5454 | Bags | 447.5809 | 447.5809 | 0 | 0 | 141.0191
Cement 43 Grade - Bags | Wing-1 Flat No 105 Balcony Brickbatt+Finish Coat W/P | CEMENT | 1.8167 | 375 | 681.2625 | 1.8167 | 375 | 681.2625 | 1.8167 | 0 | 0 | 1.8167 | 0 | 1.8167 | 0 | 364.9997 | 663.095 | 1.8167 | 0 | 1.8167 | 0 | 35 | 11901.5454 | Bags | 518.0429 | 518.0429 | 0 | 0 | 163.2196
Cement 43 Grade - Bags | Wing-1 Flat No 106 Int Flat Chemical Grouting Work | CEMENT | 1.1378 | 375 | 426.675 | 1.1378 | 375 | 426.675 | 1.1378 | 0 | 0 | 1.1378 | 0 | 1.1378 | 0 | 364.9997 | 415.2967 | 1.1378 | 0 | 1.1378 | 0 | 35 | 11901.5454 | Bags | 324.4505 | 324.4505 | 0 | 0 | 102.2245
Cement 43 Grade - Bags | Wing-1 Flat No 104 M.Toilet Chemical Coat W/P | CEMENT | 0.124 | 375 | 46.5 | 0.124 | 375 | 46.5 | 0.124 | 0 | 0 | 0.124 | 0 | 0.124 | 0 | 364.9997 | 45.26 | 0.124 | 0 | 0.124 | 0 | 35 | 11901.5454 | Bags | 35.3593 | 35.3593 | 0 | 0 | 11.1407
Cement 43 Grade - Bags | Wing-1 Flat No 104 M.Toilet IPS W/P | CEMENT | 1.3563 | 375 | 508.6125 | 1.3563 | 375 | 508.6125 | 1.3563 | 0 | 0 | 1.3563 | 0 | 1.3563 | 0 | 364.9997 | 495.0491 | 1.3563 | 0 | 1.3563 | 0 | 35 | 11901.5454 | Bags | 386.7571 | 386.7571 | 0 | 0 | 121.8554
Cement 43 Grade - Bags | Wing-1 Flat No 104 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5696 | 375 | 588.6 | 1.5696 | 375 | 588.6 | 1.5696 | 0 | 0 | 1.5696 | 0 | 1.5696 | 0 | 364.9997 | 572.9035 | 1.5696 | 0 | 1.5696 | 0 | 35 | 11901.5454 | Bags | 447.5809 | 447.5809 | 0 | 0 | 141.0191
Cement 43 Grade - Bags | Wing-1 Flat No 104 Balcony Brickbatt+Finish Coat W/P | CEMENT | 1.8167 | 375 | 681.2625 | 1.8167 | 375 | 681.2625 | 1.8167 | 0 | 0 | 1.8167 | 0 | 1.8167 | 0 | 364.9997 | 663.095 | 1.8167 | 0 | 1.8167 | 0 | 35 | 11901.5454 | Bags | 518.0429 | 518.0429 | 0 | 0 | 163.2196
Cement 43 Grade - Bags | Wing-1 Flat No 105 Int Flat Chemical Grouting Work | CEMENT | 0.8596 | 375 | 322.35 | 0.8596 | 375 | 322.35 | 0.8596 | 0 | 0 | 0.8596 | 0 | 0.8596 | 0 | 364.9997 | 313.7537 | 0.8596 | 0 | 0.8596 | 0 | 35 | 11901.5454 | Bags | 245.1201 | 245.1201 | 0 | 0 | 77.2299
Cement 43 Grade - Bags | Wing-1 Flat No 105 C.Toilet Chemical Coat W/P | CEMENT | 0.1013 | 375 | 37.9875 | 0.1013 | 375 | 37.9875 | 0.1013 | 0 | 0 | 0.1013 | 0 | 0.1013 | 0 | 364.9997 | 36.9745 | 0.1013 | 0 | 0.1013 | 0 | 35 | 11901.5454 | Bags | 28.8863 | 28.8863 | 0 | 0 | 9.1012
Cement 43 Grade - Bags | Wing-1 Flat No 103 M.Toilet IPS W/P | CEMENT | 1.3563 | 375 | 508.6125 | 1.3563 | 375 | 508.6125 | 1.3563 | 0 | 0 | 1.3563 | 0 | 1.3563 | 0 | 364.9997 | 495.0491 | 1.3563 | 0 | 1.3563 | 0 | 35 | 11901.5454 | Bags | 386.7571 | 386.7571 | 0 | 0 | 121.8554
Cement 43 Grade - Bags | Wing-1 Flat No 103 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5696 | 375 | 588.6 | 1.5696 | 375 | 588.6 | 1.5696 | 0 | 0 | 1.5696 | 0 | 1.5696 | 0 | 364.9997 | 572.9035 | 1.5696 | 0 | 1.5696 | 0 | 35 | 11901.5454 | Bags | 447.5809 | 447.5809 | 0 | 0 | 141.0191
Cement 43 Grade - Bags | Wing-1 Flat No 103 Balcony Brickbatt+Finish Coat W/P | CEMENT | 1.8167 | 375 | 681.2625 | 1.8167 | 375 | 681.2625 | 1.8167 | 0 | 0 | 1.8167 | 0 | 1.8167 | 0 | 364.9997 | 663.095 | 1.8167 | 0 | 1.8167 | 0 | 35 | 11901.5454 | Bags | 518.0429 | 518.0429 | 0 | 0 | 163.2196
Cement 43 Grade - Bags | Wing-1 Flat No 104 Int Flat Chemical Grouting Work | CEMENT | 0.8847 | 375 | 331.7625 | 0.8847 | 375 | 331.7625 | 0.8847 | 0 | 0 | 0.8847 | 0 | 0.8847 | 0 | 364.9997 | 322.9152 | 0.8847 | 0 | 0.8847 | 0 | 35 | 11901.5454 | Bags | 252.2775 | 252.2775 | 0 | 0 | 79.485
Cement 43 Grade - Bags | Wing-1 Flat No 104 C.Toilet Chemical Coat W/P | CEMENT | 0.1013 | 375 | 37.9875 | 0.1013 | 375 | 37.9875 | 0.1013 | 0 | 0 | 0.1013 | 0 | 0.1013 | 0 | 364.9997 | 36.9745 | 0.1013 | 0 | 0.1013 | 0 | 35 | 11901.5454 | Bags | 28.8863 | 28.8863 | 0 | 0 | 9.1012
Cement 43 Grade - Bags | Wing-1 Flat No 104 C.Toilet IPS W/P | CEMENT | 1.1078 | 375 | 415.425 | 1.1078 | 375 | 415.425 | 1.1078 | 0 | 0 | 1.1078 | 0 | 1.1078 | 0 | 364.9997 | 404.3467 | 1.1078 | 0 | 1.1078 | 0 | 35 | 11901.5454 | Bags | 315.8958 | 315.8958 | 0 | 0 | 99.5292
Cement 43 Grade - Bags | Wing-1 Flat No 102 Utility Brickbatt+Finish Coat W/P | CEMENT | 1.5984 | 375 | 599.4 | 1.5984 | 375 | 599.4 | 1.5984 | 0 | 0 | 1.5984 | 0 | 1.5984 | 0 | 364.9997 | 583.4155 | 1.5984 | 0 | 1.5984 | 0 | 35 | 11901.5454 | Bags | 455.7934 | 455.7934 | 0 | 0 | 143.6066
Cement 43 Grade - Bags | Wing-1 Flat No 102 Balcony Brickbatt+Finish Coat W/P | CEMENT | 2.4575 | 375 | 921.5625 | 2.4575 | 375 | 921.5625 | 2.4575 | 0 | 0 | 2.4575 | 0 | 2.4575 | 0 | 364.9997 | 896.9868 | 2.4575 | 0 | 2.4575 | 0 | 35 | 11901.5454 | Bags | 700.7709 | 700.7709 | 0 | 0 | 220.7916
Cement 43 Grade - Bags | Wing-1 Flat No 103 Int Flat Chemical Grouting Work | CEMENT | 0.8596 | 375 | 322.35 | 0.8596 | 375 | 322.35 | 0.8596 | 0 | 0 | 0.8596 | 0 | 0.8596 | 0 | 364.9997 | 313.7537 | 0.8596 | 0 | 0.8596 | 0 | 35 | 11901.5454 | Bags | 245.1201 | 245.1201 | 0 | 0 | 77.2299
Cement 43 Grade - Bags | Wing-1 Flat No 103 C.Toilet Chemical Coat W/P | CEMENT | 0.1013 | 375 | 37.9875 | 0.1013 | 375 | 37.9875 | 0.1013 | 0 | 0 | 0.1013 | 0 | 0.1013 | 0 | 364.9997 | 36.9745 | 0.1013 | 0 | 0.1013 | 0 | 35 | 11901.5454 | Bags | 28.8863 | 28.8863 | 0 | 0 | 9.1012
Cement 43 Grade - Bags | Wing-1 Flat No 103 C.Toilet IPS W/P | CEMENT | 1.1078 | 375 | 415.425 | 1.1078 | 375 | 415.425 | 1.1078 | 0 | 0 | 1.1078 | 0 | 1.1078 | 0 | 364.9997 | 404.3467 | 1.1078 | 0 | 1.1078 | 0 | 35 | 11901.5454 | Bags | 315.8958 | 315.8958 | 0 | 0 | 99.5292
Cement 43 Grade - Bags | Wing-1 Flat No 103 M.Toilet Chemical Coat W/P | CEMENT | 0.124 | 375 | 46.5 | 0.124 | 375 | 46.5 | 0.124 | 0 | 0 | 0.124 | 0 | 0.124 | 0 | 364.9997 | 45.26 | 0.124 | 0 | 0.124 | 0 | 35 | 11901.5454 | Bags | 35.3593 | 35.3593 | 0 | 0 | 11.1407
Cement 43 Grade - Bags | Wing-1 Flat No 101 Balcony Brickbatt+Finish Coat W/P | CEMENT | 2.4575 | 375 | 921.5625 | 2.4575 | 375 | 921.5625 | 2.4575 | 0 | 0 | 2.4575 | 0 | 2.4575 | 0 | 364.9997 | 896.9868 | 2.4575 | 0 | 2.4575 | 0 | 35 | 11901.5454 | Bags | 700.7709 | 700.7709 | 0 | 0 | 220.7916
Cement 43 Grade - Bags | Wing-1 Flat No 102 Int Flat Chemical Grouting Work | CEMENT | 1.1378 | 375 | 426.675 | 1.1378 | 375 | 426.675 | 1.1378 | 0 | 0 | 1.1378 | 0 | 1.1378 | 0 | 364.9997 | 415.2967 | 1.1378 | 0 | 1.1378 | 0 | 35 | 11901.5454 | Bags | 324.4505 | 324.4505 | 0 | 0 | 102.2245
Cement 43 Grade - Bags | Wing-1 Flat No 102 C.Toilet Chemical Coat W/P | CEMENT | 0.1085 | 375 | 40.6875 | 0.1085 | 375 | 40.6875 | 0.1085 | 0 | 0 | 0.1085 | 0 | 0.1085 | 0 | 364.9997 | 39.6025 | 0.1085 | 0 | 0.1085 | 0 | 35 | 11901.5454 | Bags | 30.9394 | 30.9394 | 0 | 0 | 9.7481
Cement 43 Grade - Bags | Wing-1 Flat No 102 C.Toilet IPS W/P | CEMENT | 1.1869 | 375 | 445.0875 | 1.1869 | 375 | 445.0875 | 1.1869 | 0 | 0 | 1.1869 | 0 | 1.1869 | 0 | 364.9997 | 433.2181 | 1.1869 | 0 | 1.1869 | 0 | 35 | 11901.5454 | Bags | 338.4517 | 338.4517 | 0 | 0 | 106.6358
Cement 43 Grade - Bags | Wing-1 Flat No 102 M.Toilet Chemical Coat W/P | CEMENT | 0.1395 | 375 | 52.3125 | 0.1395 | 375 | 52.3125 | 0.1395 | 0 | 0 | 0.1395 | 0 | 0.1395 | 0 | 364.9997 | 50.9175 | 0.1395 | 0 | 0.1395 | 0 | 35 | 11901.5454 | Bags | 39.7793 | 39.7793 | 0 | 0 | 12.5332
Cement 43 Grade - Bags | Wing-1 Flat No 102 M.Toilet IPS W/P | CEMENT | 1.5257 | 375 | 572.1375 | 1.5257 | 375 | 572.1375 | 1.5257 | 0 | 0 | 1.5257 | 0 | 1.5257 | 0 | 364.9997 | 556.88 | 1.5257 | 0 | 1.5257 | 0 | 35 | 11901.5454 | Bags | 435.0625 | 435.0625 | 0 | 0 | 137.075