## Material Receipt Details6385905
Material Receipt Details
GANGA ALTUS
Page 1 of 1
Total Records: 15 Records 1 to 15
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Anchor Fastner 12mmx100mm - No. | D-Bldg Safety Material | HARDWARE/CARPENTARY | 250 | 40 | 10000 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No. | 0 | 0 | 0 | 250 | 10000
Barricating Tape - ROLL | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 5 | 213.75 | 1068.75 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 3 | 19 | 5667.79 | ROLL | 0 | 0 | 0 | 5 | 1068.75
GI Pipe 1-1/2"X 20RFT - No. - No. | D-Bldg Safety Material | ELECTRICAL MATERIAL | 50 | 300 | 15000 | 50 | 300 | 15000 | 50 | 0 | 0 | 50 | 0 | 50 | 0 | 2577.12 | 128856 | 50 | 0 | 0 | 50 | 0 | 0 | No. | 109200 | 0 | 0 | 0 | 15000
M S Square tube 40mm - Mtrs | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 3252 | 300 | 975600 | 3252 | 300 | 975600 | 3252 | 0 | 0 | 3252 | 0 | 1350 | 1902 | 235.3444 | 317715 | 1350 | 0 | 511.83 | 838.17 | 0 | 0 | Mtrs | 269250 | 269250 | 1902 | 0 | 706350
MS Safety Bracket - No. | D-Bldg Safety Material | PLUMBING MATERIALS | 16 | 1200 | 19200 | 16 | 1200 | 19200 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 1239 | 19824 | 16 | 0 | 0 | 16 | 0 | 0 | No. | 16800 | 16800 | 0 | 0 | 2400
MS Sq. Pipe 40mmx40mmx16G- 20ft - No. | D-Bldg Safety Material | FABRICATION MATERIAL | 345 | 1500 | 517500 | 345 | 1500 | 517500 | 345 | 0 | 0 | 345 | 0 | 345 | 0 | 1034.0733 | 356755.3 | 345 | 0 | 45 | 300 | 0 | 0 | No. | 302335 | 302335 | 0 | 0 | 215165
Nylon Rope 12mm - Mtrs | D-Bldg Safety Material | HARDWARE/CARPENTARY | 0 | 18.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mtrs | 0 | 0 | 0 | 0 | 0
Nylon Rope 12mm kg - Kgs - Kgs | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 46.5 | 155 | 7207.5 | 66.5 | 155 | 10307.5 | 46.5 | -20 | 20 | 46.5 | 20 | 46.5 | 0 | 190.4 | 8853.6 | 46.5 | 0 | 0 | 46.5 | 0 | 0 | Kgs | 7905 | 0 | 20 | -20 | 7207.5
Nylon Rope 16mm - Kgs | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 52 | 160 | 8320 | 52 | 160 | 8320 | 52 | 0 | 0 | 52 | 0 | 52 | 0 | 196 | 10192 | 51.2 | 0.8 | 14.7 | 36.5 | 0 | 0 | Kgs | 8960 | 8960 | 0 | 0 | -640
Safety Net 10 x 3 mtr - Sq.m. | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 1500 | 75 | 112500 | 1500 | 75 | 112500 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 0 | 79.254 | 118881 | 1500 | 0 | 30 | 1470 | 30 | 2672.205 | Sq.m. | 113220 | 56100 | 0 | 0 | 56400
Safety Net 2x10 mtr - Sq.m. - Sq.m. | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sq.m. | 0 | 0 | 0 | 0 | 0
Safety net 5x10 mtrs - Sq.m. | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 1000 | 75 | 75000 | 750 | 75 | 56250 | 750 | 250 | 0 | 750 | 0 | 750 | 0 | 89.25 | 66937.5 | 750 | 0 | 50 | 700 | 350 | 31482.345 | Sq.m. | 63750 | 63750 | 0 | 250 | 11250
Safety Net 6x10 mtr - Sq.m. | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 394 | 75 | 29550 | 960 | 75 | 72000 | 394 | -566 | 566 | 394 | 566 | 394 | 0 | 94.08 | 37067.52 | 394 | 0 | 94 | 300 | 0 | 0 | Sq.m. | 33096 | 0 | 566 | -566 | 29550
Shedding Net - Sq.Ft | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 22950 | 2.7 | 61965 | 22950 | 2.7 | 61965 | 22950 | 0 | 0 | 22950 | 0 | 22950 | 0 | 1.5825 | 36318.135 | 22950 | 0 | 49.8 | 22900.2 | 0 | 0 | Sq.Ft | 34588.7 | 16537.4 | 0 | 0 | 45427.6
Vertical Safety Net 6mtr x 8mtr - Sq.m. | D-Bldg Safety Material | CONSUMABLE/MISC MATERIAL | 2159.23 | 150 | 323884.5 | 2159.23 | 150 | 323884.5 | 2159.23 | 0 | 0 | 2159.23 | 0 | 2159.23 | 0 | 89.25 | 192711.2775 | 2159.23 | 0 | 863.23 | 1296 | 240 | 21420 | Sq.m. | 183534.55 | 183534.55 | 0 | 0 | 140349.95