## Material Receipt Details6385986
Material Receipt Details
GANGA ARCADIA - A BUILDING
Page 1 of 1
Total Records: 51 Records 1 to 51
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Ready Mix Concrete M-15 Downpour - Cu.Mtrs | Pumproom-PCC Work | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-15 Grade - Cu.Mtrs | A-Bldg PCC Work-M15 | RMC | 23.9967 | 2914 | 69926.3838 | 23.0003 | 2914 | 67022.8742 | 23.0003 | 0.9964 | 0 | 23.0003 | 0 | 23.0003 | 0 | 4199.9977 | 96601.2075 | 23 | 0.0003 | 0 | 23 | 0 | 0 | Cu.Mtrs | 81864.36 | 21355.92 | 0 | 0.9964 | 48570.4638
Ready Mix Concrete M-15 Grade - Cu.Mtrs | STP-170KLD-PCC Work | RMC | 23.02 | 2914 | 67080.28 | 0 | 0 | 0 | 0 | 23.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 23.02 | 67080.28
Ready Mix Concrete M-15 Grade( D/P) - - Cu.Mtrs | A-Bldg PCC Work-M15 | RMC | 72.18 | 3500 | 252630 | 72.18 | 3500 | 252630 | 72.18 | 0 | 0 | 72.18 | 0 | 72.18 | 0 | 4274.6246 | 308542.4012 | 70 | 2.18 | 34 | 36 | 34 | 146129.632 | Cu.Mtrs | 252900.712 | 71186.4 | 0 | 0 | 181443.6
Ready Mix Concrete M-15 Grade( D/P) - - Cu.Mtrs | UGWT-PCC Work-M15 | RMC | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 146129.632 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-15 Grade( PUMPABLE) - Cu.Mtrs | A-Bldg PCC Work-M15 | RMC | 103.18 | 20 | 2063.6 | 103.18 | 20 | 2063.6 | 103.18 | 0 | 0 | 103.18 | 0 | 103.18 | 0 | 4379.9996 | 451928.3563 | 83 | 20.18 | 83 | 0 | 83 | 363540.052 | Cu.Mtrs | 308084.712 | 89084.736 | 0 | 0 | -87021.136
Ready Mix Concrete M15 with Pump - Cu.Mtrs | A Bldg.-Plum Concrete Work-M15 | RMC | 20.106 | 100 | 2010.6 | 0 | 0 | 0 | 0 | 20.106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 20.106 | 2010.6
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | A-Bldg Footing Concrete Work M25 | RMC | 137 | 3150 | 431550 | 137 | 3150 | 431550 | 137 | 0 | 0 | 137 | 0 | 137 | 0 | 4654.8303 | 637711.7448 | 137 | 0 | 126 | 11 | 164 | 769895.192 | Cu.Mtrs | 540433.666 | 425592.36 | 0 | 0 | 5957.64
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | A Bldg.-Retaining Wall-Concrete-M25(Raft Parking) | RMC | 64.603 | 3150 | 203499.45 | 48.5 | 3150 | 152775 | 48.5 | 16.103 | 0 | 48.5 | 0 | 48.5 | 0 | 4823.2399 | 233927.1346 | 45 | 3.5 | 38 | 7 | 164 | 769895.192 | Cu.Mtrs | 183139.946 | 27584.69 | 0 | 16.103 | 175914.76
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | STP-170KLD-Raft Concrete M25 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 769895.192 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | STP-170KLD-RCC Pardi Concrete M25 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 769895.192 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | UGWT-Raft Concrete M25 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 769895.192 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | UGWT-RCC Pardi Concrete M25 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 769895.192 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | Pumproom-Raft Concrete M25 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 769895.192 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M25 Regular Downpour - Cu.Mtrs | Pumproom-RCC Pardi Concrete M25 | RMC | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 769895.192 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M25 Regular Pumpable - Cu.Mtrs | A-Bldg Footing Concrete Work M25 | RMC | 327 | 3150 | 1030050 | 327 | 3150 | 1030050 | 327 | 0 | 0 | 327 | 0 | 327 | 0 | 4832.9767 | 1580383.3815 | 325 | 2 | 181 | 144 | 243.5 | 1186518.29 | Cu.Mtrs | 1331121.5 | 437974.54 | 0 | 0 | 592075.46
Ready Mix Concrete M25 Regular Pumpable - Cu.Mtrs | A Bldg.-Raft Concrete-M25(Lift Raft+Bldg Raft) | RMC | 376.726 | 3150 | 1186686.9 | 326.5 | 3150 | 1028475 | 326.5 | 50.226 | 0 | 326.5 | 0 | 326.5 | 0 | 4883.3978 | 1594429.3694 | 326.5 | 0 | 62.5 | 264 | 243.5 | 1186518.29 | Cu.Mtrs | 1351211.33 | 331550.82 | 0 | 50.226 | 855136.08
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | Column Footing To Plinth Concrete Work | RMC | 79.8745 | 4400 | 351447.8 | 79.8745 | 4400 | 351447.8 | 79.8745 | 0 | 0 | 79.8745 | 0 | 79.8745 | 0 | 4999.9999 | 399372.4887 | 79.8745 | 0 | 23.3745 | 56.5 | 197 | 1005980.204 | Cu.Mtrs | 338451.2604 | 253705.5004 | 0 | 0 | 97742.2996
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | 1st Slab Column- Plinth to 1st Slab Concrete Work | RMC | 55 | 4400 | 242000 | 55 | 4400 | 242000 | 55 | 0 | 0 | 55 | 0 | 55 | 0 | 5000 | 275000 | 55 | 0 | 19 | 36 | 197 | 1005980.204 | Cu.Mtrs | 233050.84 | 167372.876 | 0 | 0 | 74627.124
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | RMC | 124 | 4400 | 545600 | 124 | 4400 | 545600 | 124 | 0 | 0 | 124 | 0 | 124 | 0 | 5071.1879 | 628827.2977 | 124 | 0 | 98.5 | 25.5 | 197 | 1005980.204 | Cu.Mtrs | 532904.488 | 191265.9796 | 0 | 0 | 354334.0204
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | Shops-Partition Pardi Concrete-M35 | RMC | 33.5 | 4400 | 147400 | 33.5 | 4400 | 147400 | 33.5 | 0 | 0 | 33.5 | 0 | 33.5 | 0 | 5278.8366 | 176841.0277 | 33.1255 | 0.3745 | 33.1255 | 0 | 197 | 1005980.204 | Cu.Mtrs | 148138.1436 | 0 | 0 | 0 | 147400
Ready Mix Concrete M-35 Grade (Downpour) - Cu.Mtrs | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | RMC | 46.32 | 4400 | 203808 | 23 | 4400 | 101200 | 23 | 23.32 | 0 | 23 | 0 | 23 | 0 | 5441.9997 | 125165.9922 | 23 | 0 | 23 | 0 | 197 | 1005980.204 | Cu.Mtrs | 106072.872 | 0 | 0 | 23.32 | 203808
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | Column Footing To Plinth Concrete Work | RMC | 14.0955 | 100 | 1409.55 | 14.0955 | 100 | 1409.55 | 14.0955 | 0 | 0 | 14.0955 | 0 | 14.0955 | 0 | 5269.099 | 74270.585 | 14.0955 | 0 | 3.5955 | 10.5 | 6 | 31572.62 | Cu.Mtrs | 62941.1738 | 30728.81 | 0 | 0 | -29319.26
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | 1st Slab Column- Plinth to 1st Slab Concrete Work | RMC | 29.93 | 100 | 2993 | 29.93 | 100 | 2993 | 29.93 | 0 | 0 | 29.93 | 0 | 29.93 | 0 | 5294.9045 | 158476.491 | 29.93 | 0 | 4.05 | 25.88 | 6 | 31572.62 | Cu.Mtrs | 134302.1119 | 46093.215 | 0 | 0 | -43100.215
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | RMC | 240.12 | 100 | 24012 | 240.12 | 100 | 24012 | 240.12 | 0 | 0 | 240.12 | 0 | 238.4745 | 1.6455 | 5253.8311 | 1252904.7534 | 238.4745 | 0 | -1.6455 | 240.12 | 6 | 31572.62 | Cu.Mtrs | 1061783.6893 | 13169.49 | 1.6455 | 0 | 10842.51
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 31572.62 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Ready Mix Concrete M-35 Grade (Pumpable) - Cu.Mtrs | A 2nd Slab (Parking) RCC-Slab,Beam,Staircase M35 | RMC | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 31572.62 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | PCC Work-M15 | RMC | 73.11 | 2125 | 155358.75 | 125.22 | 2125 | 266092.5 | 73.11 | -52.11 | 52.11 | 73.11 | 52.11 | 69 | 4.11 | 3208.8254 | 221408.955 | 68 | 1 | 16 | 52 | 20 | 64580 | Cu.Mtrs | 184898.272 | 184898.272 | 56.22 | -52.11 | -29539.522
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | PCC for barrication work | RMC | 18 | 2125 | 38250 | 18 | 2125 | 38250 | 6 | 0 | 12 | 6 | 12 | 6 | 0 | 2200.5983 | 13203.5898 | 6 | 0 | 4 | 2 | 20 | 64580 | Cu.Mtrs | 11189.49 | 11189.49 | 12 | 0 | 27060.51
Sand-Metal Mix M15 (Downpour) - Cu.Mtrs | A-Bldg PCC Work-M15 | RMC | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 64580 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | A-Bldg PCC Work-M15 | RMC | 90 | 2125 | 191250 | 90 | 2125 | 191250 | 90 | 0 | 0 | 90 | 0 | 81 | 9 | 3872.2203 | 313649.8461 | 81 | 0 | 39 | 42 | 67 | 232099.977 | Cu.Mtrs | 265804.953 | 265804.953 | 9 | 0 | -74554.953
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | A Bldg.-Plum Concrete Work-M15 | RMC | 33.51 | 2125 | 71208.75 | 33.51 | 2125 | 71208.75 | 33.51 | 0 | 0 | 33.51 | 0 | 33 | 0.51 | 3960 | 130680 | 33 | 0 | 0 | 33 | 67 | 232099.977 | Cu.Mtrs | 110745.756 | 110745.756 | 0.51 | 0 | -39537.006
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | UGWT-PCC Work-M15 | RMC | 20.46 | 2125 | 43477.5 | 2 | 2125 | 4250 | 2 | 18.46 | 0 | 2 | 0 | 2 | 0 | 3274.9993 | 6549.9986 | 2 | 0 | 2 | 0 | 67 | 232099.977 | Cu.Mtrs | 5550.846 | 0 | 0 | 18.46 | 43477.5
Sand-Metal Mix M15 (Pumpable) - Cu.Mtrs | Pumproom-PCC Work | RMC | 26.18 | 2125 | 55632.5 | 26.18 | 2125 | 55632.5 | 26.18 | 0 | 0 | 26.18 | 0 | 26.18 | 0 | 3274.9993 | 85739.4817 | 26 | 0.18 | 26 | 0 | 67 | 232099.977 | Cu.Mtrs | 72160.998 | 0 | 0 | 0 | 55632.5
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | Concrete for Barrication work | RMC | 20 | 2000 | 40000 | 20 | 2000 | 40000 | 20 | 0 | 0 | 20 | 0 | 20 | 0 | 3400 | 68000 | 18.5 | 1.5 | 18.5 | 0 | 30.5 | 103700.018 | Cu.Mtrs | 53305.086 | 53305.086 | 0 | 0 | -13305.086
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | A-Bldg Footing Concrete Work M25 | RMC | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.5 | 103700.018 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | STP-170KLD-Raft Concrete M25 | RMC | 44.47 | 6000 | 266820 | 20 | 6000 | 120000 | 20 | 24.47 | 0 | 20 | 0 | 20 | 0 | 3400 | 68000 | 4 | 16 | 4 | 0 | 30.5 | 103700.018 | Cu.Mtrs | 11525.424 | 0 | 0 | 24.47 | 266820
Sand-Metal Mix M25 (Downpour) - Cu.Mtrs | UGWT-Raft Concrete M25 | RMC | 8.86 | 2000 | 17720 | 8.86 | 2000 | 17720 | 8.86 | 0 | 0 | 8.86 | 0 | 8.86 | 0 | 3399.9993 | 30123.9938 | 8 | 0.86 | 8 | 0 | 30.5 | 103700.018 | Cu.Mtrs | 23050.848 | 0 | 0 | 0 | 17720
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | A-Bldg Footing Concrete Work M25 | RMC | 20 | 2500 | 50000 | 20 | 2500 | 50000 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 601799.812 | Cu.Mtrs | 0 | 0 | 20 | 0 | 50000
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | STP-170KLD-RCC Pardi Concrete M25 | RMC | 59.91 | 3355.93 | 201053.7663 | 59.91 | 3355.93 | 201053.7663 | 59.91 | 0 | 0 | 59.91 | 0 | 59.91 | 0 | 3400.0001 | 203694.006 | 59.91 | 0 | 59.91 | 0 | 177 | 601799.812 | Cu.Mtrs | 172622.038 | 0 | 0 | 0 | 201053.7663
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | UGWT-Raft Concrete M25 | RMC | 30.09 | 3355.93 | 100979.9337 | 30.09 | 3355.93 | 100979.9337 | 30.09 | 0 | 0 | 30.09 | 0 | 30.09 | 0 | 3400.0001 | 102306.003 | 30.09 | 0 | 30.09 | 0 | 177 | 601799.812 | Cu.Mtrs | 86700.002 | 0 | 0 | 0 | 100979.9337
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | UGWT-RCC Pardi Concrete M25 | RMC | 45.25 | 3355.93 | 151855.8325 | 45.25 | 3355.93 | 151855.8325 | 45.25 | 0 | 0 | 45.25 | 0 | 45.25 | 0 | 3400.0002 | 153850.0091 | 19.85 | 25.4 | 19.85 | 0 | 177 | 601799.812 | Cu.Mtrs | 57194.9166 | 0 | 0 | 0 | 151855.8325
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | Pumproom-Raft Concrete M25 | RMC | 50.79 | 3355.93 | 170447.6847 | 50.79 | 3355.93 | 170447.6847 | 50.79 | 0 | 0 | 50.79 | 0 | 50.79 | 0 | 3400.0002 | 172686.0102 | 35 | 15.79 | 35 | 0 | 177 | 601799.812 | Cu.Mtrs | 100847.46 | 0 | 0 | 0 | 170447.6847
Sand-Metal Mix M25 (Pumpable) - Cu.Mtrs | Pumproom-RCC Pardi Concrete M25 | RMC | 32.15 | 3355.93 | 107893.1495 | 32.15 | 3355.93 | 107893.1495 | 32.15 | 0 | 0 | 32.15 | 0 | 32.15 | 0 | 3400.0002 | 109310.0064 | 32.15 | 0 | 32.15 | 0 | 177 | 601799.812 | Cu.Mtrs | 92635.5954 | 0 | 0 | 0 | 107893.1495
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | RMC | 10 | 2125 | 21250 | 10 | 2125 | 21250 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 3400 | 34000 | 10 | 0 | 10 | 0 | 18 | 62800.016 | Cu.Mtrs | 28813.56 | 28813.56 | 0 | 0 | -7563.56
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | Shops-Partition Pardi Concrete-M35 | RMC | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 62800.016 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 (Downpour) - Cu.Mtrs | A 2nd Slab (Parking) Column 1st to 2nd Concrete M35 | RMC | 24 | 2125 | 51000 | 24 | 2125 | 51000 | 24 | 0 | 0 | 24 | 0 | 24 | 0 | 3599.9995 | 86399.988 | 8 | 16 | 8 | 0 | 18 | 62800.016 | Cu.Mtrs | 24406.776 | 0 | 0 | 0 | 51000
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | Column Footing To Plinth Concrete Work | RMC | 0 | 2175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 50399.978 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | 1st Slab Column- Plinth to 1st Slab Concrete Work | RMC | 0 | 2175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 50399.978 | Cu.Mtrs | 0 | 0 | 0 | 0 | 0
Sand-Metal Mix M35 (Pumpable) - Cu.Mtrs | A 2nd Slab (Parking) RCC-Slab,Beam,Staircase M35 | RMC | 74.6 | 2175 | 162255 | 74.6 | 2175 | 162255 | 74.6 | 0 | 0 | 74.6 | 0 | 74.6 | 0 | 3599.9995 | 268559.9627 | 14 | 60.6 | 14 | 0 | 14 | 50399.978 | Cu.Mtrs | 42711.858 | 0 | 0 | 0 | 162255
Sand-Metal Mix M40 Easycrete (Downpour) - Cu.Mtrs | Concrete for Barrication work | RMC | 7 | 3150 | 22050 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cu.Mtrs | 0 | 0 | 0 | 7 | 22050