## Material Receipt Details6386010
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 17 Records 1 to 17
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Binding Wire - Kgs | Wing-1 Parking Column Upto Grid Slab Steel | STEEL | 148.12 | 61.9 | 9168.628 | 148.12 | 61.9 | 9168.628 | 148.12 | 0 | 0 | 148.12 | 0 | 148.12 | 0 | 86.14 | 12759.0568 | 148.12 | 0 | 0 | 148.12 | 3192.591 | 249762.0656 | Kgs | 10812.76 | 0 | 0 | 0 | 9168.628
Binding Wire - Kgs | Wing-1 Parking Footing Steel | STEEL | 25.22 | 61.9 | 1561.118 | 25.22 | 61.9 | 1561.118 | 25.22 | 0 | 0 | 25.22 | 0 | 25.22 | 0 | 86.14 | 2172.4508 | 25.22 | 0 | 25.22 | 0 | 3192.591 | 249762.0656 | Kgs | 1841.06 | 0 | 0 | 0 | 1561.118
Binding Wire - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 16.58 | 61.9 | 1026.302 | 0 | 0 | 0 | 0 | 16.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.47 | 2.47 | 3192.591 | 249762.0656 | Kgs | 0 | 0 | 0 | 16.58 | 1026.302
Binding Wire - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 63.33 | 61.9 | 3920.127 | 5.919 | 61.9 | 366.3861 | 5.919 | 57.411 | 0 | 5.919 | 0 | 5.919 | 0 | 73.1607 | 433.0382 | 5.919 | 0 | -55.201 | 61.12 | 3192.591 | 249762.0656 | Kgs | 366.978 | 0 | 0 | 57.411 | 3920.127
Steel Bars 10mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 24.14 | 50.85 | 1227.519 | 24.14 | 50.85 | 1227.519 | 24.14 | 0 | 0 | 24.14 | 0 | 24.14 | 0 | 81.7315 | 1972.9984 | 24.14 | 0 | 0.7 | 23.44 | 4792 | 304998.2609 | Kgs | 1672.033 | 8360.1648 | 0 | 0 | -7132.6458
Steel Bars 10mm - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 170.34 | 50.85 | 8661.789 | 0 | 0 | 0 | 0 | 170.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -163 | 163 | 4792 | 304998.2609 | Kgs | 0 | 0 | 0 | 170.34 | 8661.789
Steel Bars 12mm - Kgs | Wing-1 Parking Footing Steel | STEEL | 31.64 | 50.85 | 1608.894 | 31.64 | 50.85 | 1608.894 | 31.64 | 0 | 0 | 31.64 | 0 | 31.64 | 0 | 81.7315 | 2585.9847 | 31.64 | 0 | 0 | 31.64 | 8360 | 508762.6022 | Kgs | 2191.513 | 10957.5648 | 0 | 0 | -9348.6708
Steel Bars 12mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 501.01 | 50.85 | 25476.3585 | 501.01 | 50.85 | 25476.3585 | 501.01 | 0 | 0 | 501.01 | 0 | 501.01 | 0 | 69.1086 | 34624.095 | 501.01 | 0 | 0 | 501.01 | 8360 | 508762.6022 | Kgs | 29342.4534 | 30201.327 | 0 | 0 | -4724.9685
Steel Bars 16mm - Kgs | Wing-1 Parking Footing Steel | STEEL | 727.07 | 50.85 | 36971.5095 | 727.07 | 50.85 | 36971.5095 | 727.07 | 0 | 0 | 727.07 | 0 | 727.07 | 0 | 69.03 | 50189.6421 | 727.07 | 0 | 611.07 | 116 | 3767 | 234948.8786 | Kgs | 42533.595 | 42533.595 | 0 | 0 | -5562.0855
Steel Bars 16mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 273.02 | 50.85 | 13883.067 | 273.02 | 50.85 | 13883.067 | 273.02 | 0 | 0 | 273.02 | 0 | 273.02 | 0 | 69.03 | 18846.5706 | 273.02 | 0 | 0.02 | 273 | 3767 | 234948.8786 | Kgs | 15971.67 | 15971.67 | 0 | 0 | -2088.603
Steel Bars 20mm - Kgs | Wing-1 Parking Column Upto Grid Slab Steel | STEEL | 6855.02 | 50.85 | 348577.767 | 6855.02 | 50.85 | 348577.767 | 6855.02 | 0 | 0 | 6855.02 | 0 | 6855.02 | 0 | 81.7315 | 560271.0671 | 6855.02 | 0 | 0.02 | 6855 | 10359.66 | 650003.7924 | Kgs | 474806.1053 | 2374030.5264 | 0 | 0 | -2025452.7594
Steel Bars 20mm - Kgs | Wing-1 Parking Footing Steel | STEEL | 1342.96 | 50.85 | 68289.516 | 1342.96 | 50.85 | 68289.516 | 1342.96 | 0 | 0 | 1342.96 | 0 | 1342.96 | 0 | 62.658 | 84147.1877 | 1342.96 | 0 | 0.96 | 1342 | 10359.66 | 650003.7924 | Kgs | 71311.176 | 142622.352 | 0 | 0 | -74332.836
Steel Bars 20mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 283.85 | 50.85 | 14433.7725 | 283.85 | 50.85 | 14433.7725 | 283.85 | 0 | 0 | 283.85 | 0 | 283.85 | 0 | 81.7315 | 23199.4863 | 283.85 | 0 | 0 | 283.85 | 10359.66 | 650003.7924 | Kgs | 19660.5864 | 98302.932 | 0 | 0 | -83869.1595
Steel Bars 20mm - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 4362 | 50.85 | 221807.7 | 0 | 0 | 0 | 0 | 4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4296 | 4296 | 10359.66 | 650003.7924 | Kgs | 0 | 0 | 0 | 4362 | 221807.7
Steel Bars 8mm - Kgs | Wing-1 Parking Column Upto Grid Slab Steel | STEEL | 5488.28 | 50.85 | 279079.038 | 5488.28 | 50.85 | 279079.038 | 5488.28 | 0 | 0 | 5488.28 | 0 | 5488.28 | 0 | 73.4853 | 403307.8285 | 5488.28 | 0 | 0 | 5488.28 | 30394.88 | 1907862.5138 | Kgs | 341786.3433 | 738955.5763 | 0 | 0 | -459876.5383
Steel Bars 8mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 299.38 | 50.85 | 15223.473 | 299.38 | 50.85 | 15223.473 | 299.38 | 0 | 0 | 299.38 | 0 | 299.38 | 0 | 82.9339 | 24828.751 | 299.38 | 0 | 0 | 299.38 | 30394.88 | 1907862.5138 | Kgs | 21041.3245 | 105206.6227 | 0 | 0 | -89983.1497
Steel Bars 8mm - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 745 | 50.85 | 37883.25 | 0 | 0 | 0 | 0 | 745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -592 | 592 | 30394.88 | 1907862.5138 | Kgs | 0 | 0 | 0 | 745 | 37883.25