## Material Receipt Details6386027
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 19 Records 1 to 19
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Binding Wire - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 355 | 62.85 | 22311.75 | 355 | 62.85 | 22311.75 | 355 | 0 | 0 | 355 | 0 | 355 | 0 | 73.16 | 25971.8 | 355 | 0 | 0 | 355 | 3029.781 | 237025.4392 | Kgs | 22010 | 0 | 0 | 0 | 22311.75
Binding Wire - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 63 | 62.85 | 3959.55 | 63 | 0 | 0 | 63 | 0 | 63 | 0 | 73.16 | 4609.08 | 63 | 0 | 0 | 63 | 3029.781 | 237025.4392 | Kgs | 3906 | 0 | 0 | 0 | 3959.55
Binding Wire - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 0 | 0 | 0 | 0 | 251.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -251.93 | 251.93 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.93 | 15833.8005
GFRP Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.33 | 0 | 2086.33 | 0 | 6259 | 1144771.1 | Kgs | 323381.15 | 323381.15 | 0 | 0 | -114748.15
Steel Bar 25mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3287 | 3287 | 11825 | 721095.1823 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 4051 | 50.85 | 205993.35 | 0 | 0 | 0 | 0 | 4051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4028 | 4028 | 11825 | 721095.1823 | Kgs | 0 | 0 | 0 | 4051 | 205993.35
Steel Bars 10mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 3220 | 50.85 | 163737 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3175 | 3175 | 4222 | 271334.0609 | Kgs | 0 | 0 | 0 | 3220 | 163737
Steel Bars 10mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3339 | 3339 | 4222 | 271334.0609 | Kgs | 0 | 0 | 0 | 3382.53 | 172001.6505
Steel Bars 12mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2731 | 2731 | 8189 | 498863.4122 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 2587 | 50.85 | 131548.95 | 0 | 0 | 0 | 0 | 2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2560 | 2560 | 8189 | 498863.4122 | Kgs | 0 | 0 | 0 | 2587 | 131548.95
Steel Bars 16mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 3238 | 50.85 | 164652.3 | 0 | 0 | 0 | 0 | 3238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3185 | 3185 | 2629 | 168466.9186 | Kgs | 0 | 0 | 0 | 3238 | 164652.3
Steel Bars 16mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2806 | 2806 | 2629 | 168466.9186 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 20mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3912 | 3912 | 9292.66 | 587072.1324 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 8542 | 50.85 | 434360.7 | 8542 | 50.85 | 434360.7 | 6510 | 0 | 2032 | 6510 | 2032 | 6510 | 0 | 58.646 | 381785.46 | 6510 | 0 | -2024 | 8534 | 9292.66 | 587072.1324 | Kgs | 323547 | 0 | 2032 | 0 | 434360.7
Steel Bars 32mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 5651 | 50.85 | 287353.35 | 5000 | 50.85 | 254250 | 5000 | 651 | 0 | 5000 | 0 | 5000 | 0 | 64.31 | 321550 | 4920 | 80 | -692 | 5612 | 4151 | 266491.42 | Kgs | 268140 | 268140 | 0 | 651 | 19213.35
Steel Bars 32mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -532 | 532 | 4151 | 266491.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8220 | 8220 | 28137.88 | 1766190.6238 | Kgs | 0 | 0 | 0 | 8281.07 | 421092.4095
Steel Bars 8mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 8166 | 50.85 | 415241.1 | 0 | 0 | 0 | 0 | 8166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8140 | 8140 | 28137.88 | 1766190.6238 | Kgs | 0 | 0 | 0 | 8166 | 415241.1
Steel Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28137.88 | 1766190.6238 | Kgs | 0 | 0 | 0 | 0 | 0