## Material Receipt Details6386054
Material Receipt Details
GANGA ASMI
Page 1 of 1
Total Records: 989 Records 1 to 989
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
Binding Wire - Kgs | Wing-1 Substructure Footing Steel-(Kgs) | STEEL | 805.83 | 62.85 | 50646.4155 | 805.83 | 62.85 | 50646.4155 | 663.002 | 0 | 142.828 | 663.002 | 142.828 | 663.002 | 0 | 90.6906 | 60128.0399 | 663.002 | 0 | 0.33 | 805.5 | 3029.781 | 237025.4392 | Kgs | 50955.966 | 31012.366 | 142.828 | 0 | 19634.0495
Binding Wire - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 1969.92 | 62.85 | 123809.472 | 1969.92 | 62.85 | 123809.472 | 1969.92 | 0 | 0 | 1969.92 | 0 | 1969.92 | 0 | 88.2953 | 173934.714 | 1969.92 | 0 | 28.38 | 1941.54 | 3029.781 | 237025.4392 | Kgs | 147402.3 | 95359.87 | 0 | 0 | 28449.602
Binding Wire - Kgs | Wing-1 Parking Column Upto Grid Slab Steel | STEEL | 148.12 | 61.9 | 9168.628 | 148.12 | 61.9 | 9168.628 | 148.12 | 0 | 0 | 148.12 | 0 | 148.12 | 0 | 86.14 | 12759.0568 | 148.12 | 0 | 0 | 148.12 | 3029.781 | 237025.4392 | Kgs | 10812.76 | 0 | 0 | 0 | 9168.628
Binding Wire - Kgs | Wing-1 Parking Footing Steel | STEEL | 25.22 | 61.9 | 1561.118 | 25.22 | 61.9 | 1561.118 | 25.22 | 0 | 0 | 25.22 | 0 | 25.22 | 0 | 86.14 | 2172.4508 | 25.22 | 0 | 25.22 | 0 | 3029.781 | 237025.4392 | Kgs | 1841.06 | 0 | 0 | 0 | 1561.118
Binding Wire - Kgs | Weigh Bridge Beam Steel | STEEL | 1.04 | 61.9 | 64.376 | 1.04 | 61.9 | 64.376 | 1.04 | 0 | 0 | 1.04 | 0 | 1.04 | 0 | 86.14 | 89.5856 | 1.04 | 0 | 1.04 | 0 | 3029.781 | 237025.4392 | Kgs | 75.92 | 0 | 0 | 0 | 64.376
Binding Wire - Kgs | Weigh Bridge Column Steel | STEEL | 2.79 | 61.9 | 172.701 | 2.79 | 61.9 | 172.701 | 2.79 | 0 | 0 | 2.79 | 0 | 2.79 | 0 | 86.14 | 240.3306 | 2.79 | 0 | 2.79 | 0 | 3029.781 | 237025.4392 | Kgs | 203.67 | 0 | 0 | 0 | 172.701
Binding Wire - Kgs | Weigh Bridge Footing Steel | STEEL | 3.51 | 61.9 | 217.269 | 3.51 | 61.9 | 217.269 | 3.51 | 0 | 0 | 3.51 | 0 | 3.51 | 0 | 86.14 | 302.3514 | 3.51 | 0 | 3.51 | 0 | 3029.781 | 237025.4392 | Kgs | 256.23 | 0 | 0 | 0 | 217.269
Binding Wire - Kgs | New Labour Camp | STEEL | 6.84 | 61.9 | 423.396 | 6.84 | 61.9 | 423.396 | 6.84 | 0 | 0 | 6.84 | 0 | 6.84 | 0 | 80.24 | 548.8416 | 6.84 | 0 | 5.34 | 1.5 | 3029.781 | 237025.4392 | Kgs | 465.12 | 465.12 | 0 | 0 | -41.724
Binding Wire - Kgs | Wing-1 Substructure Tie Beam Steel | STEEL | 85.25 | 62.85 | 5357.9625 | 85.25 | 62.85 | 5357.9625 | 51.28 | 0 | 33.97 | 51.28 | 33.97 | 51.28 | 0 | 94.3774 | 4839.6756 | 51.28 | 0 | 25.62 | 59.63 | 3029.781 | 237025.4392 | Kgs | 4101.42 | 2224.59 | 33.97 | 0 | 3133.3725
Binding Wire - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 16.58 | 61.9 | 1026.302 | 0 | 0 | 0 | 0 | 16.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.11 | 2.47 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 16.58 | 1026.302
Binding Wire - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 586.41 | 62.85 | 36855.8685 | 586.41 | 62.85 | 36855.8685 | 586.41 | 0 | 0 | 586.41 | 0 | 586.41 | 0 | 98.4057 | 57706.0828 | 586.41 | 0 | 0 | 586.41 | 3029.781 | 237025.4392 | Kgs | 48903.46 | 55949.06 | 0 | 0 | -19093.1915
Binding Wire - Kgs | Wing-1 Substructure RCC Plinth Beam - Steel | STEEL | 85.79 | 62.85 | 5391.9015 | 85.79 | 62.85 | 5391.9015 | 85.79 | 0 | 0 | 85.79 | 0 | 85.79 | 0 | 94.4 | 8098.576 | 85.79 | 0 | 21.79 | 64 | 3029.781 | 237025.4392 | Kgs | 6863.2 | 13726.4 | 0 | 0 | -8334.4985
Binding Wire - Kgs | Wing-1 Substructure Lift Pit RCC - Steel | STEEL | 6 | 62.85 | 377.1 | 6 | 62.85 | 377.1 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 94.4 | 566.4 | 6 | 0 | 6 | 0 | 3029.781 | 237025.4392 | Kgs | 480 | 960 | 0 | 0 | -582.9
Binding Wire - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 838.745 | 61.9 | 51918.3155 | 838.745 | 61.9 | 51918.3155 | 838.745 | 0 | 0 | 838.745 | 0 | 838.745 | 0 | 88.6715 | 74372.8099 | 827.669 | 11.076 | 0 | 838.745 | 3029.781 | 237025.4392 | Kgs | 62285.713 | 84084.8 | 0 | 0 | -32166.4845
Binding Wire - Kgs | UGWT RCC Bottom Slab | STEEL | 82.66 | 61.9 | 5116.654 | 82.66 | 61.9 | 5116.654 | 82.66 | 0 | 0 | 82.66 | 0 | 82.66 | 0 | 94.4 | 7803.104 | 82.66 | 0 | 0.255 | 82.405 | 3029.781 | 237025.4392 | Kgs | 6612.8 | 13225.6 | 0 | 0 | -8108.946
Binding Wire - Kgs | Wing-2 Substructure Footing Reinforcement Steel | STEEL | 840 | 61.9 | 51996 | 840 | 61.9 | 51996 | 840 | 0 | 0 | 840 | 0 | 840 | 0 | 90.8109 | 76281.1708 | 840 | 0 | 0.06 | 839.94 | 3029.781 | 237025.4392 | Kgs | 64645.06 | 112937.34 | 0 | 0 | -60941.34
Binding Wire - Kgs | Wing 1 - P2 to P3 Level Column steel | STEEL | 565 | 62.85 | 35510.25 | 565 | 62.85 | 35510.25 | 565 | 0 | 0 | 565 | 0 | 565 | 0 | 88.5 | 50002.5 | 565 | 0 | 102.04 | 462.96 | 3029.781 | 237025.4392 | Kgs | 42375 | 42375 | 0 | 0 | -6864.75
Binding Wire - Kgs | Wing -2 Parking Footing Steel | STEEL | 24.884 | 61.9 | 1540.3196 | 0 | 0 | 0 | 0 | 24.884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.884 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 24.884 | 1540.3196
Binding Wire - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 1370 | 61.9 | 84803 | 1370 | 61.9 | 84803 | 1370 | 0 | 0 | 1370 | 0 | 1370 | 0 | 82.1442 | 112537.544 | 1370 | 0 | 0.405 | 1369.595 | 3029.781 | 237025.4392 | Kgs | 95370.8 | 90172.72 | 0 | 0 | -5369.72
Binding Wire - Kgs | Wing -2 Parking Column upto GF Slab - Steel | STEEL | 532.49 | 61.9 | 32961.131 | 532.49 | 61.9 | 32961.131 | 532.49 | 0 | 0 | 532.49 | 0 | 532.49 | 0 | 76.7 | 40841.983 | 532.49 | 0 | 124.724 | 407.766 | 3029.781 | 237025.4392 | Kgs | 34611.85 | 0 | 0 | 0 | 32961.131
Binding Wire - Kgs | Wing-1 Substructure RCC Piling work - Steel | STEEL | 96 | 62.85 | 6033.6 | 96 | 62.85 | 6033.6 | 58.82 | 0 | 37.18 | 58.82 | 37.18 | 58.82 | 0 | 73.16 | 4303.2712 | 58.82 | 0 | 96 | 0 | 3029.781 | 237025.4392 | Kgs | 3646.84 | 0 | 37.18 | 0 | 6033.6
Binding Wire - Kgs | Wing-2 Substructure RCC Tie Beam Reinforcement Steel | STEEL | 63.445 | 61.9 | 3927.2455 | 63.445 | 61.9 | 3927.2455 | 63.445 | 0 | 0 | 63.445 | 0 | 63.445 | 0 | 79.06 | 5015.9617 | 63.445 | 0 | 0.325 | 63.12 | 3029.781 | 237025.4392 | Kgs | 4250.815 | 4250.815 | 0 | 0 | -323.5695
Binding Wire - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 571.38 | 62.85 | 35911.233 | 571.38 | 62.85 | 35911.233 | 571.38 | 0 | 0 | 571.38 | 0 | 571.38 | 0 | 80.24 | 45847.5312 | 571.38 | 0 | 48.66 | 522.72 | 3029.781 | 237025.4392 | Kgs | 38853.84 | 38853.84 | 0 | 0 | -2942.607
Binding Wire - Kgs | Wing-2 Substructure RCC Plinth Beam Reinforcement Steel | STEEL | 63.445 | 61.9 | 3927.2455 | 63.445 | 61.9 | 3927.2455 | 63.445 | 0 | 0 | 63.445 | 0 | 63.445 | 0 | 87.4978 | 5551.2982 | 63.445 | 0 | 0 | 63.445 | 3029.781 | 237025.4392 | Kgs | 4704.49 | 4447.5 | 0 | 0 | -520.2545
Binding Wire - Kgs | Wing-1 Substructure Grade Slab Reinforcement Steel | STEEL | 119 | 62.85 | 7479.15 | 119 | 62.85 | 7479.15 | 119 | 0 | 0 | 119 | 0 | 119 | 0 | 80.24 | 9548.56 | 119 | 0 | 119 | 0 | 3029.781 | 237025.4392 | Kgs | 8092 | 8092 | 0 | 0 | -612.85
Binding Wire - Kgs | Wing -1 Emergency Exit Ramp Steel | STEEL | 25.175 | 62.85 | 1582.2488 | 25.175 | 62.85 | 1582.2488 | 25.175 | 0 | 0 | 25.175 | 0 | 25.175 | 0 | 80.24 | 2020.042 | 25.175 | 0 | 25.175 | 0 | 3029.781 | 237025.4392 | Kgs | 1711.9 | 1711.9 | 0 | 0 | -129.6512
Binding Wire - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 483.71 | 62.85 | 30401.1735 | 483.71 | 62.85 | 30401.1735 | 483.71 | 0 | 0 | 483.71 | 0 | 483.71 | 0 | 80.24 | 38812.8904 | 483.71 | 0 | 89.06 | 394.65 | 3029.781 | 237025.4392 | Kgs | 32892.28 | 32892.28 | 0 | 0 | -2491.1065
Binding Wire - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 483.7 | 62.85 | 30400.545 | 483.7 | 62.85 | 30400.545 | 483.7 | 0 | 0 | 483.7 | 0 | 483.7 | 0 | 79.3888 | 38400.3506 | 483.7 | 0 | 49.89 | 433.81 | 3029.781 | 237025.4392 | Kgs | 32542.67 | 28937.06 | 0 | 0 | 1463.485
Binding Wire - Kgs | Wing 1 - P3 to P4 Level Column Steel | STEEL | 588.142 | 62.85 | 36964.7247 | 588.142 | 62.85 | 36964.7247 | 588.142 | 0 | 0 | 588.142 | 0 | 588.142 | 0 | 80.24 | 47192.5141 | 588.142 | 0 | 202.482 | 385.66 | 3029.781 | 237025.4392 | Kgs | 39993.656 | 39993.656 | 0 | 0 | -3028.9313
Binding Wire - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 483.7 | 62.85 | 30400.545 | 483.7 | 62.85 | 30400.545 | 483.7 | 0 | 0 | 483.7 | 0 | 483.7 | 0 | 79.2123 | 38314.9965 | 483.7 | 0 | 0 | 483.7 | 3029.781 | 237025.4392 | Kgs | 32470.336 | 32470.336 | 0 | 0 | -2069.791
Binding Wire - Kgs | Wing 1 - P4 to P5 Level Column Steel | STEEL | 588.142 | 62.85 | 36964.7247 | 588.142 | 62.85 | 36964.7247 | 588.142 | 0 | 0 | 588.142 | 0 | 588.142 | 0 | 79.06 | 46498.5065 | 588.142 | 0 | 34.352 | 553.79 | 3029.781 | 237025.4392 | Kgs | 39405.514 | 39405.514 | 0 | 0 | -2440.7893
Binding Wire - Kgs | Wing -1 Ramp from P1 to P2 - Steel | STEEL | 47.14 | 62.85 | 2962.749 | 47.14 | 62.85 | 2962.749 | 47.14 | 0 | 0 | 47.14 | 0 | 47.14 | 0 | 79.2838 | 3737.4376 | 47.14 | 0 | 0 | 47.14 | 3029.781 | 237025.4392 | Kgs | 3167.32 | 3167.32 | 0 | 0 | -204.571
Binding Wire - Kgs | Wing 1 Ramp from P2 to P3 - Steel | STEEL | 47.14 | 62.85 | 2962.749 | 47.14 | 62.85 | 2962.749 | 47.14 | 0 | 0 | 47.14 | 0 | 47.14 | 0 | 79.06 | 3726.8884 | 47.14 | 0 | 30.28 | 16.86 | 3029.781 | 237025.4392 | Kgs | 3158.38 | 3158.38 | 0 | 0 | -195.631
Binding Wire - Kgs | Wing 1 Ramp from P3 to P4 - Steel | STEEL | 47.14 | 62.85 | 2962.749 | 47.14 | 62.85 | 2962.749 | 47.14 | 0 | 0 | 47.14 | 0 | 47.14 | 0 | 77.88 | 3671.2632 | 47.14 | 0 | 34.88 | 12.26 | 3029.781 | 237025.4392 | Kgs | 3111.24 | 3111.24 | 0 | 0 | -148.491
Binding Wire - Kgs | Wing 1 Ramp from P4 to P5 - Steel | STEEL | 47.14 | 62.85 | 2962.749 | 47.14 | 62.85 | 2962.749 | 47.14 | 0 | 0 | 47.14 | 0 | 47.14 | 0 | 77.88 | 3671.2632 | 47.14 | 0 | 0 | 47.14 | 3029.781 | 237025.4392 | Kgs | 3111.24 | 3111.24 | 0 | 0 | -148.491
Binding Wire - Kgs | Safety Net fixing (Wing 1) | STEEL | 65 | 62.85 | 4085.25 | 65 | 62.85 | 4085.25 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 79.06 | 5138.9 | 65 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 4355 | 0 | 0 | 0 | 4085.25
Binding Wire - Kgs | Goel House Gym Work | STEEL | 18.7 | 61.9 | 1157.53 | 18.7 | 61.9 | 1157.53 | 18.7 | 0 | 0 | 18.7 | 0 | 18.7 | 0 | 77.88 | 1456.356 | 18.7 | 0 | 0.7 | 18 | 3029.781 | 237025.4392 | Kgs | 1234.2 | 1234.2 | 0 | 0 | -76.67
Binding Wire - Kgs | Wing 1 - P5 to P6 level Column Steel | STEEL | 588.142 | 62.85 | 36964.7247 | 588.142 | 62.85 | 36964.7247 | 588.142 | 0 | 0 | 588.142 | 0 | 588.142 | 0 | 77.88 | 45804.499 | 588.142 | 0 | 202.922 | 385.22 | 3029.781 | 237025.4392 | Kgs | 38817.372 | 38817.372 | 0 | 0 | -1852.6473
Binding Wire - Kgs | Sales office renovation - Electrical work | STEEL | 6 | 61.9 | 371.4 | 6 | 61.9 | 371.4 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 79.06 | 474.36 | 6 | 0 | 4 | 2 | 3029.781 | 237025.4392 | Kgs | 402 | 402 | 0 | 0 | -30.6
Binding Wire - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 483.7 | 62.85 | 30400.545 | 483.7 | 62.85 | 30400.545 | 483.7 | 0 | 0 | 483.7 | 0 | 483.7 | 0 | 77.8483 | 37655.2113 | 483.7 | 0 | 148.58 | 335.12 | 3029.781 | 237025.4392 | Kgs | 31911.196 | 31709.634 | 0 | 0 | -1309.089
Binding Wire - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 63.33 | 61.9 | 3920.127 | 5.919 | 61.9 | 366.3861 | 5.919 | 57.411 | 0 | 5.919 | 0 | 5.919 | 0 | 73.1607 | 433.0382 | 5.919 | 0 | 2.21 | 61.12 | 3029.781 | 237025.4392 | Kgs | 366.978 | 0 | 0 | 57.411 | 3920.127
Binding Wire - Kgs | Wing 02 Piling work for Non Tower area | STEEL | 24.63 | 61.9 | 1524.597 | 0 | 0 | 0 | 0 | 24.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.63 | 20 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 24.63 | 1524.597
Binding Wire - Kgs | Wing 1 - 6th Slab (Pod. NTA) Wing 1 P6 to Pod. level Column | STEEL | 49 | 62.85 | 3079.65 | 49 | 62.85 | 3079.65 | 49 | 0 | 0 | 49 | 0 | 49 | 0 | 78.0995 | 3826.8733 | 49 | 0 | 49 | 0 | 3029.781 | 237025.4392 | Kgs | 3243.113 | 3243.113 | 0 | 0 | -163.463
Binding Wire - Kgs | Wing 1 - 6th Slab (Pod. Bld.) Wing 1 P6 to Pod. level Column | STEEL | 593 | 62.85 | 37270.05 | 593 | 62.85 | 37270.05 | 593 | 0 | 0 | 593 | 0 | 593 | 0 | 76.7 | 45483.1 | 593 | 0 | 0 | 593 | 3029.781 | 237025.4392 | Kgs | 38545 | 0 | 0 | 0 | 37270.05
Binding Wire - Kgs | Wing 1 Ramp from P5 to P6 - Steel | STEEL | 47.14 | 62.85 | 2962.749 | 47.14 | 62.85 | 2962.749 | 47.14 | 0 | 0 | 47.14 | 0 | 47.14 | 0 | 76.7 | 3615.638 | 47.14 | 0 | 47.14 | 0 | 3029.781 | 237025.4392 | Kgs | 3064.1 | 0 | 0 | 0 | 2962.749
Binding Wire - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 446 | 62.85 | 28031.1 | 446 | 62.85 | 28031.1 | 446 | 0 | 0 | 446 | 0 | 446 | 0 | 76.7 | 34208.2 | 446 | 0 | 0 | 446 | 3029.781 | 237025.4392 | Kgs | 28990 | 0 | 0 | 0 | 28031.1
Binding Wire - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 468 | 62.85 | 29413.8 | 468 | 62.85 | 29413.8 | 468 | 0 | 0 | 468 | 0 | 468 | 0 | 73.16 | 34238.88 | 468 | 0 | 0.07 | 467.93 | 3029.781 | 237025.4392 | Kgs | 29016 | 0 | 0 | 0 | 29413.8
Binding Wire - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 458.364 | 62.85 | 28808.1774 | 458.364 | 62.85 | 28808.1774 | 458.364 | 0 | 0 | 458.364 | 0 | 458.364 | 0 | 74.1687 | 33996.2578 | 458.364 | 0 | 14.908 | 443.456 | 3029.781 | 237025.4392 | Kgs | 28810.388 | 0 | 0 | 0 | 28808.1774
Binding Wire - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 469.944 | 62.85 | 29535.9804 | 469.944 | 62.85 | 29535.9804 | 469.944 | 0 | 0 | 469.944 | 0 | 469.944 | 0 | 74.2767 | 34905.8726 | 469.944 | 0 | 0 | 469.944 | 3029.781 | 237025.4392 | Kgs | 29581.248 | 0 | 0 | 0 | 29535.9804
Binding Wire - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 470.196 | 62.85 | 29551.8186 | 470.196 | 62.85 | 29551.8186 | 470.196 | 0 | 0 | 470.196 | 0 | 470.196 | 0 | 74.3796 | 34972.9958 | 470.196 | 0 | 0 | 470.196 | 3029.781 | 237025.4392 | Kgs | 29638.132 | 0 | 0 | 0 | 29551.8186
Binding Wire - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 464.688 | 62.85 | 29205.6408 | 464.688 | 62.85 | 29205.6408 | 464.688 | 0 | 0 | 464.688 | 0 | 464.688 | 0 | 74.4638 | 34602.4333 | 464.688 | 0 | 0.682 | 464.006 | 3029.781 | 237025.4392 | Kgs | 29324.096 | 0 | 0 | 0 | 29205.6408
Binding Wire - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 355 | 62.85 | 22311.75 | 355 | 62.85 | 22311.75 | 355 | 0 | 0 | 355 | 0 | 355 | 0 | 73.16 | 25971.8 | 355 | 0 | 0 | 355 | 3029.781 | 237025.4392 | Kgs | 22010 | 0 | 0 | 0 | 22311.75
Binding Wire - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 336 | 62.85 | 21117.6 | 336 | 62.85 | 21117.6 | 336 | 0 | 0 | 336 | 0 | 336 | 0 | 73.16 | 24581.76 | 336 | 0 | 0 | 336 | 3029.781 | 237025.4392 | Kgs | 20832 | 0 | 0 | 0 | 21117.6
Binding Wire - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 325 | 62.85 | 20426.25 | 325 | 62.85 | 20426.25 | 325 | 0 | 0 | 325 | 0 | 325 | 0 | 79.06 | 25694.5 | 325 | 0 | 325 | 0 | 3029.781 | 237025.4392 | Kgs | 21775 | 0 | 0 | 0 | 20426.25
Binding Wire - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 310 | 62.85 | 19483.5 | 310 | 62.85 | 19483.5 | 310 | 0 | 0 | 310 | 0 | 310 | 0 | 76.6848 | 23772.28 | 309.623 | 0.377 | 310 | 0 | 3029.781 | 237025.4392 | Kgs | 20120.741 | 0 | 0 | 0 | 19483.5
Binding Wire - Kgs | Wing 1 . 7th Slab (1st Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 63 | 62.85 | 3959.55 | 63 | 0 | 0 | 63 | 0 | 63 | 0 | 76.7 | 4832.1 | 63 | 0 | 0.5 | 62.5 | 3029.781 | 237025.4392 | Kgs | 4095 | 0 | 0 | 0 | 3959.55
Binding Wire - Kgs | Wing 1-8th Slab (2nd Floor) Shear Wall Steel | STEEL | 98.89 | 62.85 | 6215.2365 | 98.89 | 62.85 | 6215.2365 | 98.89 | 0 | 0 | 98.89 | 0 | 98.89 | 0 | 75.182 | 7434.7434 | 98.89 | 0 | 34.89 | 64 | 3029.781 | 237025.4392 | Kgs | 6300.63 | 0 | 0 | 0 | 6215.2365
Binding Wire - Kgs | Wing 1-9th Slab (3rd Floor) Shear Wall Steel | STEEL | 98.89 | 62.85 | 6215.2365 | 98.89 | 62.85 | 6215.2365 | 98.89 | 0 | 0 | 98.89 | 0 | 98.89 | 0 | 75.182 | 7434.7434 | 98.89 | 0 | 33.89 | 65 | 3029.781 | 237025.4392 | Kgs | 6300.63 | 0 | 0 | 0 | 6215.2365
Binding Wire - Kgs | Wing 1-10th Slab (4th Floor) Shear Wall Steel | STEEL | 98.892 | 62.85 | 6215.3622 | 98.892 | 62.85 | 6215.3622 | 98.892 | 0 | 0 | 98.892 | 0 | 98.892 | 0 | 75.182 | 7434.9015 | 98.892 | 0 | 36.602 | 62.29 | 3029.781 | 237025.4392 | Kgs | 6300.764 | 0 | 0 | 0 | 6215.3622
Binding Wire - Kgs | Wing 1-11th Slab (5th Floor) Shear Wall Steel | STEEL | 98.89 | 62.85 | 6215.2365 | 98.89 | 62.85 | 6215.2365 | 98.89 | 0 | 0 | 98.89 | 0 | 98.89 | 0 | 75.182 | 7434.7434 | 98.89 | 0 | 98.89 | 0 | 3029.781 | 237025.4392 | Kgs | 6300.63 | 0 | 0 | 0 | 6215.2365
Binding Wire - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 63 | 62.85 | 3959.55 | 63 | 0 | 0 | 63 | 0 | 63 | 0 | 73.16 | 4609.08 | 63 | 0 | 0 | 63 | 3029.781 | 237025.4392 | Kgs | 3906 | 0 | 0 | 0 | 3959.55
Binding Wire - Kgs | Wing 1-13th Slab (7th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 65 | 62.85 | 4085.25 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 75.52 | 4908.8 | 65 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 4160 | 0 | 0 | 0 | 4085.25
Binding Wire - Kgs | Wing 1-14th Slab (8th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 65 | 62.85 | 4085.25 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 75.52 | 4908.8 | 65 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 4160 | 0 | 0 | 0 | 4085.25
Binding Wire - Kgs | Wing 1-15th Slab (9th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 65 | 62.85 | 4085.25 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 75.52 | 4908.8 | 65 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 4160 | 0 | 0 | 0 | 4085.25
Binding Wire - Kgs | Wing 1-16th Slab (10th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 65 | 62.85 | 4085.25 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 75.52 | 4908.8 | 65 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 4160 | 0 | 0 | 0 | 4085.25
Binding Wire - Kgs | Wing 1-17th Slab (11th Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 63 | 62.85 | 3959.55 | 63 | 0 | 0 | 63 | 0 | 63 | 0 | 75.52 | 4757.76 | 63 | 0 | 63 | 0 | 3029.781 | 237025.4392 | Kgs | 4032 | 0 | 0 | 0 | 3959.55
Binding Wire - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 251.93 | 62.85 | 15833.8005 | 251.93 | 0 | 0 | 251.93 | 0 | 251.93 | 0 | 75.936 | 19130.5612 | 251.93 | 0 | 0.55 | 251.38 | 3029.781 | 237025.4392 | Kgs | 16212.34 | 0 | 0 | 0 | 15833.8005
Binding Wire - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 317.95 | 62.85 | 19983.1575 | 317.95 | 62.85 | 19983.1575 | 317.95 | 0 | 0 | 317.95 | 0 | 317.95 | 0 | 73.651 | 23417.336 | 317.95 | 0 | 19.32 | 298.63 | 3029.781 | 237025.4392 | Kgs | 19845.2 | 0 | 0 | 0 | 19983.1575
Binding Wire - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 317.95 | 62.85 | 19983.1575 | 317.95 | 62.85 | 19983.1575 | 317.95 | 0 | 0 | 317.95 | 0 | 317.95 | 0 | 73.651 | 23417.336 | 317.95 | 0 | 8.19 | 309.76 | 3029.781 | 237025.4392 | Kgs | 19845.2 | 0 | 0 | 0 | 19983.1575
Binding Wire - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 317.95 | 62.85 | 19983.1575 | 317.95 | 62.85 | 19983.1575 | 317.95 | 0 | 0 | 317.95 | 0 | 317.95 | 0 | 73.6555 | 23418.752 | 317.95 | 0 | 12.41 | 305.54 | 3029.781 | 237025.4392 | Kgs | 19846.4 | 0 | 0 | 0 | 19983.1575
Binding Wire - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 317.95 | 62.85 | 19983.1575 | 317.95 | 62.85 | 19983.1575 | 317.95 | 0 | 0 | 317.95 | 0 | 317.95 | 0 | 75.52 | 24011.584 | 317.95 | 0 | 6.39 | 311.56 | 3029.781 | 237025.4392 | Kgs | 20348.8 | 0 | 0 | 0 | 19983.1575
Binding Wire - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 269.945 | 61.9 | 16709.5955 | 269.945 | 61.9 | 16709.5955 | 269.945 | 0 | 0 | 269.945 | 0 | 269.945 | 0 | 73.5679 | 19859.2997 | 269.945 | 0 | 0 | 269.945 | 3029.781 | 237025.4392 | Kgs | 16829.915 | 0 | 0 | 0 | 16709.5955
Binding Wire - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 417.168 | 61.9 | 25822.6992 | 417.168 | 61.9 | 25822.6992 | 417.168 | 0 | 0 | 417.168 | 0 | 417.168 | 0 | 73.68 | 30736.9421 | 417.168 | 0 | 0 | 417.168 | 3029.781 | 237025.4392 | Kgs | 26048.256 | 0 | 0 | 0 | 25822.6992
Binding Wire - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 419.574 | 61.9 | 25971.6306 | 419.574 | 61.9 | 25971.6306 | 419.574 | 0 | 0 | 419.574 | 0 | 419.574 | 0 | 74.1234 | 31100.2664 | 419.574 | 0 | 9.748 | 409.826 | 3029.781 | 237025.4392 | Kgs | 26356.158 | 0 | 0 | 0 | 25971.6306
Binding Wire - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 419.574 | 61.9 | 25971.6306 | 419.574 | 61.9 | 25971.6306 | 419.574 | 0 | 0 | 419.574 | 0 | 419.574 | 0 | 74.1513 | 31111.9484 | 419.574 | 0 | 6.354 | 413.22 | 3029.781 | 237025.4392 | Kgs | 26366.058 | 0 | 0 | 0 | 25971.6306
Binding Wire - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 417.825 | 61.9 | 25863.3675 | 417.825 | 61.9 | 25863.3675 | 417.825 | 0 | 0 | 417.825 | 0 | 417.825 | 0 | 74.2477 | 31022.5245 | 417.825 | 0 | 14.095 | 403.73 | 3029.781 | 237025.4392 | Kgs | 26290.275 | 0 | 0 | 0 | 25863.3675
Binding Wire - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 324.814 | 61.9 | 20105.9866 | 324.814 | 61.9 | 20105.9866 | 324.814 | 0 | 0 | 324.814 | 0 | 324.814 | 0 | 73.9464 | 24018.8268 | 324.814 | 0 | 40.506 | 284.308 | 3029.781 | 237025.4392 | Kgs | 20354.938 | 0 | 0 | 0 | 20105.9866
Binding Wire - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 287.674 | 61.9 | 17807.0206 | 287.674 | 61.9 | 17807.0206 | 287.674 | 0 | 0 | 287.674 | 0 | 287.674 | 0 | 79.06 | 22743.5064 | 287.674 | 0 | 11.674 | 276 | 3029.781 | 237025.4392 | Kgs | 19274.158 | 0 | 0 | 0 | 17807.0206
Binding Wire - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 285.65 | 61.9 | 17681.735 | 285.65 | 61.9 | 17681.735 | 285.65 | 0 | 0 | 285.65 | 0 | 285.65 | 0 | 79.06 | 22583.489 | 285.65 | 0 | 9.65 | 276 | 3029.781 | 237025.4392 | Kgs | 19138.55 | 0 | 0 | 0 | 17681.735
Binding Wire - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 305 | 62.85 | 19169.25 | 305 | 62.85 | 19169.25 | 305 | 0 | 0 | 305 | 0 | 305 | 0 | 75.52 | 23033.6 | 305 | 0 | 305 | 0 | 3029.781 | 237025.4392 | Kgs | 19520 | 0 | 0 | 0 | 19169.25
Binding Wire - Kgs | Non Tower Area Footing Steel | STEEL | 28 | 61.9 | 1733.2 | 28 | 61.9 | 1733.2 | 28 | 0 | 0 | 28 | 0 | 28 | 0 | 75.52 | 2114.56 | 28 | 0 | 9 | 19 | 3029.781 | 237025.4392 | Kgs | 1792 | 0 | 0 | 0 | 1733.2
Binding Wire - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 316 | 62.85 | 19860.6 | 316 | 62.85 | 19860.6 | 316 | 0 | 0 | 316 | 0 | 316 | 0 | 79.06 | 24982.96 | 316 | 0 | 316 | 0 | 3029.781 | 237025.4392 | Kgs | 21172 | 0 | 0 | 0 | 19860.6
Binding Wire - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 319 | 62.85 | 20049.15 | 319 | 62.85 | 20049.15 | 319 | 0 | 0 | 319 | 0 | 319 | 0 | 79.06 | 25220.14 | 319 | 0 | 319 | 0 | 3029.781 | 237025.4392 | Kgs | 21373 | 0 | 0 | 0 | 20049.15
Binding Wire - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 305 | 62.85 | 19169.25 | 305 | 62.85 | 19169.25 | 305 | 0 | 0 | 305 | 0 | 305 | 0 | 79.06 | 24113.3 | 305 | 0 | 305 | 0 | 3029.781 | 237025.4392 | Kgs | 20435 | 0 | 0 | 0 | 19169.25
Binding Wire - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 304 | 62.85 | 19106.4 | 304 | 62.85 | 19106.4 | 304 | 0 | 0 | 304 | 0 | 304 | 0 | 79.06 | 24034.24 | 304 | 0 | 304 | 0 | 3029.781 | 237025.4392 | Kgs | 20368 | 0 | 0 | 0 | 19106.4
Binding Wire - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 296 | 62.85 | 18603.6 | 296 | 62.85 | 18603.6 | 296 | 0 | 0 | 296 | 0 | 296 | 0 | 75.52 | 22353.92 | 286.5 | 9.5 | 296 | 0 | 3029.781 | 237025.4392 | Kgs | 18336 | 0 | 0 | 0 | 18603.6
Binding Wire - Kgs | Wing 1-15th Floor To 16th Floor Column, LW Steel | STEEL | 285 | 62.85 | 17912.25 | 0 | 0 | 0 | 0 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 285 | 17912.25
Binding Wire - Kgs | Wing 1-16th Floor To 17th Floor Column, LW Steel | STEEL | 273 | 62.85 | 17158.05 | 0 | 0 | 0 | 0 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 273 | 17158.05
Binding Wire - Kgs | Wing 1-17th Floor To 18th Floor Column, LW Steel | STEEL | 255 | 62.85 | 16026.75 | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 255 | 16026.75
Binding Wire - Kgs | Wing 1-20th Floor To 21st Floor Column, LW Steel | STEEL | 231 | 62.85 | 14518.35 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 231 | 14518.35
Binding Wire - Kgs | Wing 1-23rd Floor To 24th Floor Column, LW Steel | STEEL | 221 | 62.85 | 13889.85 | 0 | 0 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 221 | 13889.85
Binding Wire - Kgs | Wing 1-26th Floor To 27th Floor Column, LW Steel | STEEL | 215 | 62.85 | 13512.75 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 215 | 13512.75
Binding Wire - Kgs | Wing 1-27th Floor To 28th Floor Column, LW Steel | STEEL | 215 | 62.85 | 13512.75 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 215 | 13512.75
Binding Wire - Kgs | Wing 1-28th Floor To Terrace Floor Column, LW Steel | STEEL | 215 | 62.85 | 13512.75 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 215 | 13512.75
Binding Wire - Kgs | Wing 1-24th Floor To 25th Floor Column, LW Steel | STEEL | 221 | 62.85 | 13889.85 | 0 | 0 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 221 | 13889.85
Binding Wire - Kgs | Wing 1-25th Floor To 26th Floor Column, LW Steel | STEEL | 221 | 62.85 | 13889.85 | 0 | 0 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 221 | 13889.85
Binding Wire - Kgs | Wing 1-21st Floor To 22nd Floor Column, LW Steel | STEEL | 231 | 62.85 | 14518.35 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 231 | 14518.35
Binding Wire - Kgs | Wing 1-22nd Floor To 23rd Floor Column, LW Steel | STEEL | 231 | 62.85 | 14518.35 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 231 | 14518.35
Binding Wire - Kgs | Wing 1-18th Floor To 19th Floor Column, LW Steel | STEEL | 255 | 62.85 | 16026.75 | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 255 | 16026.75
Binding Wire - Kgs | Wing 1-19th Floor To 20th Floor Column, LW Steel | STEEL | 255 | 62.85 | 16026.75 | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 255 | 16026.75
Binding Wire - Kgs | Wing-3 Substructure (M) Steel For Tie Beam | STEEL | 60.6 | 62.85 | 3808.71 | 0 | 0 | 0 | 0 | 60.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.6 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 60.6 | 3808.71
Binding Wire - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 0 | 0 | 0 | 0 | 251.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.93 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.93 | 15833.8005
Binding Wire - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 0 | 0 | 0 | 0 | 251.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.93 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.93 | 15833.8005
Binding Wire - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 0 | 0 | 0 | 0 | 251.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.93 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.93 | 15833.8005
Binding Wire - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 0 | 0 | 0 | 0 | 251.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.93 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.93 | 15833.8005
Binding Wire - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 251.93 | 62.85 | 15833.8005 | 0 | 0 | 0 | 0 | 251.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.93 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.93 | 15833.8005
Binding Wire - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 251.79 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 251.8 | 62.85 | 15825.63 | 0 | 0 | 0 | 0 | 251.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.8 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 251.8 | 15825.63
Binding Wire - Kgs | Wing 1-22n Slab (16th Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 63 | 3959.55
Binding Wire - Kgs | Wing 1-27th Slab (21st Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 63 | 3959.55
Binding Wire - Kgs | Wing 1-32th Slab (26th Floor) Shear Wall Steel | STEEL | 63 | 62.85 | 3959.55 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 63 | 3959.55
Binding Wire - Kgs | Wing 1-18th Slab (12th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-19th Slab (13th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-20th Slab (14th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-21th Slab (15th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-23th Slab (17th Floor) Shear Wall Steel | STEEL | 25.032 | 62.85 | 1573.2612 | 0 | 0 | 0 | 0 | 25.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.032 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 25.032 | 1573.2612
Binding Wire - Kgs | Wing 1-24th Slab (18th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-25th Slab (19th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-26th Slab (20th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-28th Slab (22nd Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-29th Slab (23rd Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-30th Slab (24th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-31th Slab (25th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-33th Slab (27th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-34th Slab (28th Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Wing 1-35th Slab (Terrace Floor) Shear Wall Steel | STEEL | 65 | 62.85 | 4085.25 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 65 | 4085.25
Binding Wire - Kgs | Non Tower Area Column Upto Plinth | STEEL | 278.654 | 62.85 | 17513.4039 | 0 | 0 | 0 | 0 | 278.654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.352 | 277.302 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 278.654 | 17513.4039
Binding Wire - Kgs | Non Tower Area Intermediate Tie Beam Steel | STEEL | 35.14 | 62.85 | 2208.549 | 0 | 0 | 0 | 0 | 35.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14 | 35 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 35.14 | 2208.549
Binding Wire - Kgs | Wing-3 Parking NTA Piling | STEEL | 104.7 | 62.85 | 6580.395 | 0 | 0 | 0 | 0 | 104.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.7 | 60 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 104.7 | 6580.395
Binding Wire - Kgs | Non Tower Area NTA Piling | STEEL | 34.9 | 62.85 | 2193.465 | 0 | 0 | 0 | 0 | 34.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.9 | 5 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 34.9 | 2193.465
Binding Wire - Kgs | Wing.1 Substructure RCC Pile Cap work - Steel | STEEL | 96 | 62.85 | 6033.6 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 96 | 6033.6
Binding Wire - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 120.55 | 62.85 | 7576.5675 | 0 | 0 | 0 | 0 | 120.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.93 | 101.62 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 120.55 | 7576.5675
Binding Wire - Kgs | Wing 2 . P5 To P6 Column &amp;amp; Lift Steel | STEEL | 340.8 | 61.9 | 21095.52 | 340.8 | 61.9 | 21095.52 | 340.8 | 0 | 0 | 340.8 | 0 | 340.8 | 0 | 79.06 | 26943.648 | 340.8 | 0 | 26.37 | 314.43 | 3029.781 | 237025.4392 | Kgs | 22833.6 | 0 | 0 | 0 | 21095.52
Binding Wire - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 276 | 61.9 | 17084.4 | 0 | 0 | 0 | 0 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.47 | 239.53 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 276 | 17084.4
Binding Wire - Kgs | UGWT RCC Grid Slab Reinforcement Work | STEEL | 41.1 | 62.85 | 2583.135 | 41.1 | 62.85 | 2583.135 | 41.1 | 0 | 0 | 41.1 | 0 | 41.1 | 0 | 79.06 | 3249.366 | 41.1 | 0 | 41.1 | 0 | 3029.781 | 237025.4392 | Kgs | 2753.7 | 0 | 0 | 0 | 2583.135
Binding Wire - Kgs | RCC Raft Reinforcement Work | STEEL | 7.269 | 62.85 | 456.8567 | 0 | 0 | 0 | 0 | 7.269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.269 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 7.269 | 456.8567
Binding Wire - Kgs | Compound Wall Pile Foundation | STEEL | 100.85 | 62.85 | 6338.4225 | 0 | 0 | 0 | 0 | 100.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.85 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 100.85 | 6338.4225
Binding Wire - Kgs | Pile Cap | STEEL | 23.46 | 62.85 | 1474.461 | 0 | 0 | 0 | 0 | 23.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.46 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 23.46 | 1474.461
Binding Wire - Kgs | Non Tower Area Plinth Beam Steel | STEEL | 50.593 | 62.85 | 3179.7701 | 0 | 0 | 0 | 0 | 50.593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.593 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 50.593 | 3179.7701
Binding Wire - Kgs | Non Tower Area Column Ground To P1 Slab Steel | STEEL | 147.635 | 62.85 | 9278.8598 | 0 | 0 | 0 | 0 | 147.635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.62 | 85.015 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 147.635 | 9278.8598
Binding Wire - Kgs | Non Tower Area Column 1st Slab P1 To 2nd Slab P2 Steel | STEEL | 113.235 | 62.85 | 7116.8198 | 0 | 0 | 0 | 0 | 113.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.235 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 113.235 | 7116.8198
Binding Wire - Kgs | Non Tower Area Pile Cap Steel | STEEL | 44.86 | 62.85 | 2819.451 | 0 | 0 | 0 | 0 | 44.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86 | 44 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 44.86 | 2819.451
Binding Wire - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 142.07 | 62.85 | 8929.0995 | 0 | 0 | 0 | 0 | 142.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89 | 141.18 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 142.07 | 8929.0995
Binding Wire - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 7.03 | 62.85 | 441.8355 | 0 | 0 | 0 | 0 | 7.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.03 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 7.03 | 441.8355
Binding Wire - Kgs | Wing 2 . P6 To Podium Column & Lift Steel | STEEL | 322.592 | 61.9 | 19968.4448 | 0 | 0 | 0 | 0 | 322.592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322.592 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 322.592 | 19968.4448
Binding Wire - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 232.37 | 61.9 | 14383.703 | 0 | 0 | 0 | 0 | 232.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232.37 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 232.37 | 14383.703
Binding Wire - Kgs | Phase 2 Weigh Bridge Steel | STEEL | 14.29 | 62.85 | 898.1265 | 0 | 0 | 0 | 0 | 14.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.29 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 14.29 | 898.1265
Binding Wire - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 174.59 | 62.85 | 10972.9815 | 0 | 0 | 0 | 0 | 174.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.59 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 174.59 | 10972.9815
Binding Wire - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 142.07 | 62.85 | 8929.0995 | 0 | 0 | 0 | 0 | 142.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.07 | 0 | 3029.781 | 237025.4392 | Kgs | 0 | 0 | 0 | 142.07 | 8929.0995
GFRP Bars 8mm - Kgs | Wing 1-11th Slab (5th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.01 | 0.32 | 0.33 | 2086 | 4173 | 763241.7 | Kgs | 323331.55 | 646663.1 | 0 | 0 | -438030.1
GFRP Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.33 | 0 | 0.33 | 2086 | 4173 | 763241.7 | Kgs | 323381.15 | 646762.3 | 0 | 0 | -438129.3
GFRP Bars 8mm - Kgs | Wing 1-13th Slab (7th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.33 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 323381.15 | 7024.6 | 0 | 0 | 201608.4
GFRP Bars 8mm - Kgs | Wing 1-14th Slab (8th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 2086.33 | 100 | 208633 | 2086.33 | 0 | 0 | 2086.33 | 0 | 2086.33 | 0 | 182.9 | 381589.757 | 2086.33 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 323381.15 | 0 | 0 | 0 | 208633
GFRP Bars 8mm - Kgs | Wing 1-15th Slab (9th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-16th Slab (10th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-17th Slab (11th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-22n Slab (16th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-27th Slab (21st Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-32th Slab (26th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-18th Slab (12th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-19th Slab (13th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-20th Slab (14th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-21th Slab (15th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-23th Slab (17th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-24th Slab (18th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-25th Slab (19th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-26th Slab (20th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-28th Slab (22nd Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-29th Slab (23rd Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-30th Slab (24th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-31th Slab (25th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-33th Slab (27th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-34th Slab (28th Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
GFRP Bars 8mm - Kgs | Wing 1-35th Slab (Terrace Floor) Shear Wall Steel | STEEL | 2086.33 | 100 | 208633 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.33 | 0 | 4173 | 763241.7 | Kgs | 0 | 0 | 0 | 2086.33 | 208633
Metacolour Sheet10fts x3fts6" - No. | MS Barrication for plot boundry | STEEL | 126 | 832 | 104832 | 0 | 0 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 102 | 0 | 0 | No. | 0 | 0 | 0 | 126 | 104832
Metacolour Sheet10fts x3fts6" - No. | Labour Camp Work | STEEL | 361 | 832 | 300352 | 361 | 832 | 300352 | 361 | 0 | 0 | 361 | 0 | 361 | 0 | 1464.7036 | 528758 | 361 | 0 | 67 | 294 | 0 | 0 | No. | 448100 | 770050 | 0 | 0 | -469698
Metacolour Sheet10fts x3fts6" - No. | New Labour Camp | STEEL | 205 | 832 | 170560 | 205 | 832 | 170560 | 205 | 0 | 0 | 205 | 0 | 205 | 0 | 1661.2673 | 340559.8 | 205 | 0 | 0 | 205 | 0 | 0 | No. | 288610 | 101500 | 0 | 0 | 69060
Metacolour Sheet11fts x3fts6" - No. | New Labour Camp | STEEL | 1 | 832 | 832 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No. | 0 | 0 | 0 | 1 | 832
MS Plate 425 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 1st Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 1401.84 | 5607.36 | 4 | 0 | 0 | 4 | 16 | 22360.52 | No. | 4752 | 0 | 0 | 0 | 400
MS Plate 425 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 2nd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 1394.76 | 11158.08 | 8 | 0 | 0 | 8 | 16 | 22360.52 | No. | 9456 | 0 | 0 | 0 | 800
MS Plate 425 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 3rd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 1394.76 | 11158.08 | 8 | 0 | 4 | 4 | 16 | 22360.52 | No. | 9456 | 4752 | 0 | 0 | -3952
MS Plate 425 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 4th Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 1387.68 | 11101.44 | 8 | 0 | 8 | 0 | 16 | 22360.52 | No. | 9408 | 0 | 0 | 0 | 800
MS Plate 425 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 5th Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 1387.68 | 5550.72 | 4 | 0 | 4 | 0 | 16 | 22360.52 | No. | 4704 | 0 | 0 | 0 | 400
MS Plate 425 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 1st Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 2102.76 | 8411.04 | 4 | 0 | 0 | 4 | 16 | 33445.7124 | No. | 7128 | 0 | 0 | 0 | 400
MS Plate 425 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 2nd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 2089.19 | 16713.52 | 8 | 0 | 0 | 8 | 16 | 33445.7124 | No. | 14164 | 0 | 0 | 0 | 800
MS Plate 425 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 3rd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 2089.19 | 16713.52 | 8 | 0 | 4 | 4 | 16 | 33445.7124 | No. | 14164 | 7128 | 0 | 0 | -6328
MS Plate 425 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 4th Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 2075.62 | 16604.96 | 8 | 0 | 8 | 0 | 16 | 33445.7124 | No. | 14072 | 0 | 0 | 0 | 800
MS Plate 425 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 5th Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 2075.62 | 8302.48 | 4 | 0 | 4 | 0 | 16 | 33445.7124 | No. | 7036 | 0 | 0 | 0 | 400
MS Plate 430 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 1st Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 1418.36 | 5673.44 | 4 | 0 | 0 | 4 | 16 | 22835.8724 | No. | 4808 | 0 | 0 | 0 | 400
MS Plate 430 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 2nd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 1417.77 | 11342.16 | 8 | 0 | 0 | 8 | 16 | 22835.8724 | No. | 9612 | 0 | 0 | 0 | 800
MS Plate 430 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 3rd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 1417.77 | 11342.16 | 8 | 0 | 4 | 4 | 16 | 22835.8724 | No. | 9612 | 4808 | 0 | 0 | -4008
MS Plate 430 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 4th Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 1417.18 | 11337.44 | 8 | 0 | 8 | 0 | 16 | 22835.8724 | No. | 9608 | 0 | 0 | 0 | 800
MS Plate 430 x 200 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 5th Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 1417.18 | 5668.72 | 4 | 0 | 4 | 0 | 16 | 22835.8724 | No. | 4804 | 0 | 0 | 0 | 400
MS Plate 430 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 1st Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 2127.54 | 8510.16 | 4 | 0 | 0 | 4 | 16 | 33502.7524 | No. | 7212 | 0 | 0 | 0 | 400
MS Plate 430 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 2nd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 2103.35 | 16826.8 | 8 | 0 | 0 | 8 | 16 | 33502.7524 | No. | 14260 | 0 | 0 | 0 | 800
MS Plate 430 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 3rd Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 2103.35 | 16826.8 | 8 | 0 | 4 | 4 | 16 | 33502.7524 | No. | 14260 | 7212 | 0 | 0 | -6412
MS Plate 430 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 4th Stage | STEEL | 8 | 100 | 800 | 8 | 100 | 800 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 2079.16 | 16633.28 | 8 | 0 | 8 | 0 | 16 | 33502.7524 | No. | 14096 | 0 | 0 | 0 | 800
MS Plate 430 x 300 x 20mm - No. | MS Plate for Lift Cut Out for Tower Crane - 5th Stage | STEEL | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 2079.16 | 8316.64 | 4 | 0 | 4 | 0 | 16 | 33502.7524 | No. | 7048 | 0 | 0 | 0 | 400
Steel Bar 25mm - Kgs | Labour Camp Work | STEEL | 350 | 40 | 14000 | 350 | 40 | 14000 | 350 | 0 | 0 | 350 | 0 | 350 | 0 | 50.709 | 17748.15 | 350 | 0 | 0 | 350 | 7289 | 445712.0023 | Kgs | 17748.15 | 0 | 0 | 0 | 14000
Steel Bar 25mm - Kgs | Wing-1 Substructure Footing Steel-(Kgs) | STEEL | 16140.92 | 50.85 | 820765.782 | 20857.09 | 50.85 | 1060583.0265 | 16140.92 | -4716.17 | 4716.17 | 16140.92 | 4716.17 | 16140.92 | 0 | 70.5697 | 1139059.737 | 16140.92 | 0 | 0 | 16140.92 | 7289 | 445712.0023 | Kgs | 965304.9731 | 3347549.828 | 4716.17 | -4716.17 | -2526784.046
Steel Bar 25mm - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 53194 | 50.85 | 2704914.9 | 53194 | 50.85 | 2704914.9 | 53194 | 0 | 0 | 53194 | 0 | 53194 | 0 | 65.6694 | 3493217.5455 | 53194 | 0 | 0 | 53194 | 7289 | 445712.0023 | Kgs | 2960353.9419 | 7021658.4712 | 0 | 0 | -4316743.5712
Steel Bar 25mm - Kgs | Wing-1 Substructure Tie Beam Steel | STEEL | 287.15 | 50.85 | 14601.5775 | 287.15 | 50.85 | 14601.5775 | 287.15 | 0 | 0 | 287.15 | 0 | 287.15 | 0 | 79.2346 | 22752.2275 | 287.15 | 0 | 0 | 287.15 | 7289 | 445712.0023 | Kgs | 19281.5442 | 25776.5976 | 0 | 0 | -11175.0201
Steel Bar 25mm - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 13857.69 | 50.85 | 704663.5365 | 13857.69 | 50.85 | 704663.5365 | 13857.69 | 0 | 0 | 13857.69 | 0 | 13857.69 | 0 | 73.4724 | 1018157.9029 | 13857.69 | 0 | 0.61 | 13857.08 | 7289 | 445712.0023 | Kgs | 862845.7535 | 2143732.6872 | 0 | 0 | -1439069.1507
Steel Bar 25mm - Kgs | Wing-1 Substructure RCC Plinth Beam - Steel | STEEL | 650 | 50.85 | 33052.5 | 650 | 50.85 | 33052.5 | 650 | 0 | 0 | 650 | 0 | 650 | 0 | 72.8487 | 47351.6345 | 650 | 0 | 316.1 | 333.9 | 7289 | 445712.0023 | Kgs | 40128.4943 | 12867.0342 | 0 | 0 | 20185.4658
Steel Bar 25mm - Kgs | Wing-2 Substructure Footing Reinforcement Steel | STEEL | 12506.51 | 50.85 | 635956.0335 | 8390 | 50.85 | 426631.5 | 8390 | 4116.51 | 0 | 8390 | 0 | 8390 | 0 | 70.3631 | 590346.7931 | 8390 | 0 | 88.51 | 12418 | 7289 | 445712.0023 | Kgs | 500293.7915 | 404905.16 | 0 | 4116.51 | 231050.8735
Steel Bar 25mm - Kgs | Wing 1 - P2 to P3 Level Column steel | STEEL | 13813.8 | 50.85 | 702431.73 | 12972.96 | 50.85 | 659675.016 | 12972.96 | 840.84 | 0 | 12972.96 | 0 | 12972.96 | 0 | 65.7267 | 852669.2867 | 12972.96 | 0 | 16.8 | 13797 | 7289 | 445712.0023 | Kgs | 722601.0904 | 1444182.5818 | 0 | 840.84 | -741750.8518
Steel Bar 25mm - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 2836.6 | 50.85 | 144241.11 | 2836.6 | 50.85 | 144241.11 | 2836.6 | 0 | 0 | 2836.6 | 0 | 2836.6 | 0 | 67.2074 | 190640.5819 | 2836.6 | 0 | 33.6 | 2803 | 7289 | 445712.0023 | Kgs | 161559.8973 | 276497.1247 | 0 | 0 | -132256.0147
Steel Bar 25mm - Kgs | Wing -2 Parking Column upto GF Slab - Steel | STEEL | 30216.34 | 50.85 | 1536500.889 | 24216.34 | 50.85 | 1231400.889 | 24216.34 | 6000 | 0 | 24216.34 | 0 | 24216.34 | 0 | 67.3472 | 1630902.1012 | 24216.34 | 0 | 16234.34 | 13982 | 7289 | 445712.0023 | Kgs | 1382121.0979 | 2851271.3009 | 0 | 6000 | -1314770.4119
Steel Bar 25mm - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 6000 | 50.85 | 305100 | 6000 | 50.85 | 305100 | 6000 | 0 | 0 | 6000 | 0 | 6000 | 0 | 67.4325 | 404594.9221 | 6000 | 0 | 26 | 5974 | 7289 | 445712.0023 | Kgs | 342877.2475 | 983740.5445 | 0 | 0 | -678640.5445
Steel Bar 25mm - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 2940.7 | 50.85 | 149534.595 | 2940.7 | 50.85 | 149534.595 | 2940.7 | 0 | 0 | 2940.7 | 0 | 2940.7 | 0 | 69.7969 | 205251.7945 | 2940.7 | 0 | 22.7 | 2918 | 7289 | 445712.0023 | Kgs | 173942.1987 | 27500.64 | 0 | 0 | 122033.955
Steel Bar 25mm - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 2940.7 | 50.85 | 149534.595 | 2940.7 | 50.85 | 149534.595 | 2940.7 | 0 | 0 | 2940.7 | 0 | 2940.7 | 0 | 62.54 | 183911.378 | 2940.7 | 0 | 23.7 | 2917 | 7289 | 445712.0023 | Kgs | 155857.1 | 311714.2 | 0 | 0 | -162179.605
Steel Bar 25mm - Kgs | Wing 1 - P3 to P4 Level Column Steel | STEEL | 13857 | 50.85 | 704628.45 | 13857 | 50.85 | 704628.45 | 13857 | 0 | 0 | 13857 | 0 | 13777 | 80 | 68.032 | 937276.482 | 13777 | 0 | 14 | 13843 | 7289 | 445712.0023 | Kgs | 794302.34 | 798553.88 | 80 | 0 | -93925.43
Steel Bar 25mm - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 2940.7 | 50.85 | 149534.595 | 2940.7 | 50.85 | 149534.595 | 2940.7 | 0 | 0 | 2940.7 | 0 | 2940.7 | 0 | 67.8006 | 199381.119 | 2940.7 | 0 | 23.7 | 2917 | 7289 | 445712.0023 | Kgs | 168967.05 | 0 | 0 | 0 | 149534.595
Steel Bar 25mm - Kgs | Wing 1 - P4 to P5 Level Column Steel | STEEL | 13857 | 50.85 | 704628.45 | 13857 | 50.85 | 704628.45 | 13857 | 0 | 0 | 13857 | 0 | 13827 | 30 | 67.9233 | 939176.1061 | 13827 | 0 | 153 | 13704 | 7289 | 445712.0023 | Kgs | 795911.9543 | 461314 | 30 | 0 | 243314.45
Steel Bar 25mm - Kgs | Wing 1 - P5 to P6 level Column Steel | STEEL | 13857 | 50.85 | 704628.45 | 13857 | 50.85 | 704628.45 | 13857 | 0 | 0 | 13857 | 0 | 7621.59 | 6235.41 | 67.0756 | 511222.5333 | 7621.59 | 0 | 4500 | 9357 | 7289 | 445712.0023 | Kgs | 433239.435 | 0 | 6235.41 | 0 | 704628.45
Steel Bar 25mm - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 2940.7 | 50.85 | 149534.595 | 2940.7 | 50.85 | 149534.595 | 2940.7 | 0 | 0 | 2940.7 | 0 | 2940.7 | 0 | 65.8474 | 193637.469 | 2940.7 | 0 | 625.7 | 2315 | 7289 | 445712.0023 | Kgs | 164099.55 | 0 | 0 | 0 | 149534.595
Steel Bar 25mm - Kgs | Wing 1 - 6th Slab (Pod. Bld.) Wing 1 P6 to Pod. level Column | STEEL | 7931 | 50.85 | 403291.35 | 7931 | 50.85 | 403291.35 | 7931 | 0 | 0 | 7931 | 0 | 0 | 7931 | 0 | 0 | 0 | 0 | 3301 | 4630 | 7289 | 445712.0023 | Kgs | 0 | 0 | 7931 | 0 | 403291.35
Steel Bar 25mm - Kgs | Wing-3 Substructure Steel For Column Up to Plinth | STEEL | 3028.781 | 50.85 | 154013.5139 | 0 | 0 | 0 | 0 | 3028.781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3028.781 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3028.781 | 154013.5139
Steel Bar 25mm - Kgs | Wing-3 Substructure Steel For Footing | STEEL | 16507.33 | 50.85 | 839397.7305 | 0 | 0 | 0 | 0 | 16507.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16507.33 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 16507.33 | 839397.7305
Steel Bar 25mm - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 5846.16 | 50.85 | 297277.236 | 5846.16 | 50.85 | 297277.236 | 5846.16 | 0 | 0 | 5846.16 | 0 | 0 | 5846.16 | 0 | 0 | 0 | 0 | 1262.16 | 4584 | 7289 | 445712.0023 | Kgs | 0 | 0 | 5846.16 | 0 | 297277.236
Steel Bar 25mm - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 3762 | 50.85 | 191297.7 | 3762 | 50.85 | 191297.7 | 3762 | 0 | 0 | 3762 | 0 | 0 | 3762 | 0 | 0 | 0 | 0 | 58 | 3704 | 7289 | 445712.0023 | Kgs | 0 | 0 | 3762 | 0 | 191297.7
Steel Bar 25mm - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 4028 | 50.85 | 204823.8 | 4028 | 50.85 | 204823.8 | 4028 | 0 | 0 | 4028 | 0 | 0 | 4028 | 0 | 0 | 0 | 0 | 0 | 4028 | 7289 | 445712.0023 | Kgs | 0 | 0 | 4028 | 0 | 204823.8
Steel Bar 25mm - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 4329 | 50.85 | 220129.65 | 0 | 0 | 0 | 0 | 4329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 4306 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 4329 | 220129.65
Steel Bar 25mm - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 4444 | 50.85 | 225977.4 | 4444 | 50.85 | 225977.4 | 4444 | 0 | 0 | 4444 | 0 | 0 | 4444 | 0 | 0 | 0 | 0 | 0 | 4444 | 7289 | 445712.0023 | Kgs | 0 | 0 | 4444 | 0 | 225977.4
Steel Bar 25mm - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 4028 | 50.85 | 204823.8 | 3611 | 50.85 | 183619.35 | 3611 | 417 | 0 | 3611 | 0 | 0 | 3611 | 0 | 0 | 0 | 0 | 0 | 4028 | 7289 | 445712.0023 | Kgs | 0 | 0 | 3611 | 417 | 204823.8
Steel Bar 25mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 4051 | 50.85 | 205993.35 | 0 | 0 | 0 | 0 | 4051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 4028 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 4051 | 205993.35
Steel Bar 25mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 3380 | 50.85 | 171873 | 0 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3380 | 171873
Steel Bar 25mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3981 | 50.85 | 202433.85 | 0 | 0 | 0 | 0 | 3981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1203 | 5184 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3981 | 202433.85
Steel Bar 25mm - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 3426 | 50.85 | 174212.1 | 0 | 0 | 0 | 0 | 3426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3426 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3426 | 174212.1
Steel Bar 25mm - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 3303.13 | 50.85 | 167964.1605 | 3303.13 | 0 | 0 | 3303.13 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 16.13 | 3287 | 7289 | 445712.0023 | Kgs | 0 | 0 | 3303.13 | 0 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 3536.73 | 50.85 | 179842.7205 | 3303.13 | 50.85 | 167964.1605 | 3303.13 | 233.6 | 0 | 3303.13 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 249.73 | 3287 | 7289 | 445712.0023 | Kgs | 0 | 0 | 3303.13 | 233.6 | 179842.7205
Steel Bar 25mm - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 3536.76 | 50.85 | 179844.246 | 3303.13 | 50.85 | 167964.1605 | 3303.13 | 233.63 | 0 | 3303.13 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 18.76 | 3518 | 7289 | 445712.0023 | Kgs | 0 | 0 | 3303.13 | 233.63 | 179844.246
Steel Bar 25mm - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 3536.73 | 50.85 | 179842.7205 | 3303.13 | 50.85 | 167964.1605 | 3303.13 | 233.6 | 0 | 3303.13 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 18.73 | 3518 | 7289 | 445712.0023 | Kgs | 0 | 0 | 3303.13 | 233.6 | 179842.7205
Steel Bar 25mm - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 3536.73 | 50.85 | 179842.7205 | 0 | 0 | 0 | 0 | 3536.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.73 | 3519 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3536.73 | 179842.7205
Steel Bar 25mm - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 1663.2 | 50.85 | 84573.72 | 0 | 0 | 0 | 0 | 1663.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.2 | 1111 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1663.2 | 84573.72
Steel Bar 25mm - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 1846.85 | 50.85 | 93912.3225 | 0 | 0 | 0 | 0 | 1846.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244.85 | 602 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1846.85 | 93912.3225
Steel Bar 25mm - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 1846.85 | 50.85 | 93912.3225 | 0 | 0 | 0 | 0 | 1846.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198.85 | 648 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1846.85 | 93912.3225
Steel Bar 25mm - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 1846.85 | 50.85 | 93912.3225 | 0 | 0 | 0 | 0 | 1846.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 874.85 | 972 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1846.85 | 93912.3225
Steel Bar 25mm - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 1846.85 | 50.85 | 93912.3225 | 0 | 0 | 0 | 0 | 1846.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1106.85 | 740 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1846.85 | 93912.3225
Steel Bar 25mm - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 1938.27 | 50.85 | 98561.0295 | 0 | 0 | 0 | 0 | 1938.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.27 | 1898 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1938.27 | 98561.0295
Steel Bar 25mm - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 1663.2 | 50.85 | 84573.72 | 0 | 0 | 0 | 0 | 1663.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274.2 | 1389 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1663.2 | 84573.72
Steel Bar 25mm - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 1663.2 | 50.85 | 84573.72 | 0 | 0 | 0 | 0 | 1663.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243.2 | 1420 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1663.2 | 84573.72
Steel Bar 25mm - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 3218 | 50.85 | 163635.3 | 0 | 0 | 0 | 0 | 3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3218 | 163635.3
Steel Bar 25mm - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 4084 | 50.85 | 207671.4 | 0 | 0 | 0 | 0 | 4084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4084 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 4084 | 207671.4
Steel Bar 25mm - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 3436 | 50.85 | 174720.6 | 0 | 0 | 0 | 0 | 3436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3436 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3436 | 174720.6
Steel Bar 25mm - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 4109 | 50.85 | 208942.65 | 0 | 0 | 0 | 0 | 4109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4109 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 4109 | 208942.65
Steel Bar 25mm - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 4109 | 50.85 | 208942.65 | 0 | 0 | 0 | 0 | 4109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4109 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 4109 | 208942.65
Steel Bar 25mm - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 2581 | 50.85 | 131243.85 | 0 | 0 | 0 | 0 | 2581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 2581 | 131243.85
Steel Bar 25mm - Kgs | Wing 1-15th Floor To 16th Floor Column, LW Steel | STEEL | 1506 | 50.85 | 76580.1 | 0 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1506 | 76580.1
Steel Bar 25mm - Kgs | Wing 1-16th Floor To 17th Floor Column, LW Steel | STEEL | 765 | 50.85 | 38900.25 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 765 | 38900.25
Steel Bar 25mm - Kgs | Wing 1-17th Floor To 18th Floor Column, LW Steel | STEEL | 139 | 50.85 | 7068.15 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 139 | 7068.15
Steel Bar 25mm - Kgs | Wing 1-20th Floor To 21st Floor Column, LW Steel | STEEL | 93 | 50.85 | 4729.05 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 93 | 4729.05
Steel Bar 25mm - Kgs | Wing 1-23rd Floor To 24th Floor Column, LW Steel | STEEL | 92.59 | 50.85 | 4708.2015 | 0 | 0 | 0 | 0 | 92.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.59 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 92.59 | 4708.2015
Steel Bar 25mm - Kgs | Wing 1-26th Floor To 27th Floor Column, LW Steel | STEEL | 139 | 50.85 | 7068.15 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 139 | 7068.15
Steel Bar 25mm - Kgs | Wing 1-27th Floor To 28th Floor Column, LW Steel | STEEL | 139 | 50.85 | 7068.15 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 139 | 7068.15
Steel Bar 25mm - Kgs | Wing 1-28th Floor To Terrace Floor Column, LW Steel | STEEL | 138.89 | 50.85 | 7062.5565 | 0 | 0 | 0 | 0 | 138.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.89 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 138.89 | 7062.5565
Steel Bar 25mm - Kgs | Wing 1-24th Floor To 25th Floor Column, LW Steel | STEEL | 92.59 | 50.85 | 4708.2015 | 0 | 0 | 0 | 0 | 92.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.59 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 92.59 | 4708.2015
Steel Bar 25mm - Kgs | Wing 1-25th Floor To 26th Floor Column, LW Steel | STEEL | 92.59 | 50.85 | 4708.2015 | 0 | 0 | 0 | 0 | 92.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.59 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 92.59 | 4708.2015
Steel Bar 25mm - Kgs | Wing 1-21st Floor To 22nd Floor Column, LW Steel | STEEL | 93 | 50.85 | 4729.05 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 93 | 4729.05
Steel Bar 25mm - Kgs | Wing 1-22nd Floor To 23rd Floor Column, LW Steel | STEEL | 93 | 50.85 | 4729.05 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 93 | 4729.05
Steel Bar 25mm - Kgs | Wing 1-18th Floor To 19th Floor Column, LW Steel | STEEL | 139 | 50.85 | 7068.15 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 139 | 7068.15
Steel Bar 25mm - Kgs | Wing 1-19th Floor To 20th Floor Column, LW Steel | STEEL | 139 | 50.85 | 7068.15 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 139 | 7068.15
Steel Bar 25mm - Kgs | Wing-3 Substructure (M) Steel For Tie Beam | STEEL | 389.47 | 50.85 | 19804.5495 | 0 | 0 | 0 | 0 | 389.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389.47 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 389.47 | 19804.5495
Steel Bar 25mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.13 | 3287 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.13 | 3288 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2099.13 | 1204 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 3303.13 | 50.85 | 167964.1605 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303.13 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 3303.13 | 167964.1605
Steel Bar 25mm - Kgs | Non Tower Area Column Upto Plinth | STEEL | 15779.68 | 50.85 | 802396.728 | 0 | 0 | 0 | 0 | 15779.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593.68 | 15186 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 15779.68 | 802396.728
Steel Bar 25mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 668.84 | 50.85 | 34010.514 | 0 | 0 | 0 | 0 | 668.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.84 | 556 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 668.84 | 34010.514
Steel Bar 25mm - Kgs | Wing 2 . P5 To P6 Column &amp;amp; Lift Steel | STEEL | 416.67 | 50.85 | 21187.6695 | 0 | 0 | 0 | 0 | 416.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67 | 416 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 416.67 | 21187.6695
Steel Bar 25mm - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 1420.3 | 50.85 | 72222.255 | 0 | 0 | 0 | 0 | 1420.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.3 | 1389 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1420.3 | 72222.255
Steel Bar 25mm - Kgs | Non Tower Area Column Ground To P1 Slab Steel | STEEL | 8425.93 | 50.85 | 428458.5405 | 0 | 0 | 0 | 0 | 8425.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5740.93 | 2685 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 8425.93 | 428458.5405
Steel Bar 25mm - Kgs | Non Tower Area Column 1st Slab P1 To 2nd Slab P2 Steel | STEEL | 6623.76 | 50.85 | 336818.196 | 0 | 0 | 0 | 0 | 6623.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2641.76 | 3982 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 6623.76 | 336818.196
Steel Bar 25mm - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 143.75 | 50.85 | 7309.6875 | 0 | 0 | 0 | 0 | 143.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.75 | 139 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 143.75 | 7309.6875
Steel Bar 25mm - Kgs | Wing 2 . P6 To Podium Column & Lift Steel | STEEL | 486.11 | 50.85 | 24718.6935 | 0 | 0 | 0 | 0 | 486.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486.11 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 486.11 | 24718.6935
Steel Bar 25mm - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 2166.77 | 50.85 | 110180.2545 | 0 | 0 | 0 | 0 | 2166.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166.77 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 2166.77 | 110180.2545
Steel Bar 25mm - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 1570.7 | 50.85 | 79870.095 | 0 | 0 | 0 | 0 | 1570.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570.7 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 1570.7 | 79870.095
Steel Bar 25mm - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 143.75 | 50.85 | 7309.6875 | 0 | 0 | 0 | 0 | 143.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.75 | 0 | 7289 | 445712.0023 | Kgs | 0 | 0 | 0 | 143.75 | 7309.6875
Steel Bars 10mm - Kgs | Labour Camp Work | STEEL | 100 | 43 | 4300 | 100 | 43 | 4300 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 50.709 | 5070.9 | 100 | 0 | 0 | 100 | 3082 | 203156.4309 | Kgs | 5070.9 | 0 | 0 | 0 | 4300
Steel Bars 10mm - Kgs | Wing-1 Substructure Footing Steel-(Kgs) | STEEL | 3854.815 | 50.85 | 196017.3428 | 4429.21 | 50.85 | 225225.3285 | 3260.55 | -574.395 | 1168.66 | 3260.55 | 1168.66 | 3260.55 | 0 | 66.6344 | 217264.7738 | 3260.55 | 0 | 0.005 | 3854.81 | 3082 | 203156.4309 | Kgs | 184122.6878 | 378355.4873 | 1168.66 | -574.395 | -182338.1445
Steel Bars 10mm - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 18684 | 50.85 | 950081.4 | 16860.2 | 50.85 | 857341.17 | 16822.53 | 1823.8 | 37.67 | 16822.53 | 37.67 | 16822.53 | 0 | 67.2752 | 1131739.783 | 16822.53 | 0 | 173.808 | 18510.192 | 3082 | 203156.4309 | Kgs | 959101.5672 | 2568244.6662 | 37.67 | 1823.8 | -1618163.2662
Steel Bars 10mm - Kgs | Wing-1 Substructure Tie Beam Steel | STEEL | 630.16 | 50.85 | 32043.636 | 630.16 | 50.85 | 32043.636 | 630.16 | 0 | 0 | 630.16 | 0 | 630.16 | 0 | 81.7315 | 51503.922 | 630.16 | 0 | 1.16 | 629 | 3082 | 203156.4309 | Kgs | 43647.4022 | 218237.0112 | 0 | 0 | -186193.3752
Steel Bars 10mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 24.14 | 50.85 | 1227.519 | 24.14 | 50.85 | 1227.519 | 24.14 | 0 | 0 | 24.14 | 0 | 24.14 | 0 | 81.7315 | 1972.9984 | 24.14 | 0 | 0.7 | 23.44 | 3082 | 203156.4309 | Kgs | 1672.033 | 8360.1648 | 0 | 0 | -7132.6458
Steel Bars 10mm - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 5007 | 50.85 | 254605.95 | 5007 | 50.85 | 254605.95 | 5007 | 0 | 0 | 5007 | 0 | 5007 | 0 | 72.6155 | 363585.585 | 5007 | 0 | 0.002 | 5006.998 | 3082 | 203156.4309 | Kgs | 308123.4067 | 861297.3604 | 0 | 0 | -606691.4104
Steel Bars 10mm - Kgs | Wing-1 Substructure RCC Plinth Beam - Steel | STEEL | 323 | 50.85 | 16424.55 | 296.08 | 50.85 | 15055.668 | 296.08 | 26.92 | 0 | 296.08 | 0 | 296.08 | 0 | 78.0205 | 23100.2976 | 296.08 | 0 | 79 | 244 | 3082 | 203156.4309 | Kgs | 19576.5156 | 888.972 | 0 | 26.92 | 15535.578
Steel Bars 10mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 17337.88 | 43 | 745528.84 | 9297.41 | 43 | 399788.63 | 9297.41 | 8040.47 | 0 | 9297.41 | 0 | 9297.41 | 0 | 78.361 | 728554.345 | 9297.41 | 0 | 0.88 | 17337 | 3082 | 203156.4309 | Kgs | 617418.6843 | 0 | 0 | 8040.47 | 745528.84
Steel Bars 10mm - Kgs | UGWT RCC Bottom Slab | STEEL | 6041.73 | 50.85 | 307221.9705 | 0 | 0 | 0 | 0 | 6041.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.73 | 6024 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 6041.73 | 307221.9705
Steel Bars 10mm - Kgs | Wing-2 Substructure Footing Reinforcement Steel | STEEL | 198.79 | 50.85 | 10108.4715 | 197 | 50.85 | 10017.45 | 164.49 | 1.79 | 32.51 | 164.49 | 32.51 | 164.49 | 0 | 78.361 | 12889.6009 | 164.49 | 0 | 1.79 | 197 | 3082 | 203156.4309 | Kgs | 10923.3861 | 0 | 32.51 | 1.79 | 10108.4715
Steel Bars 10mm - Kgs | Wing 1 - P2 to P3 Level Column steel | STEEL | 3903.71 | 50.85 | 198503.6535 | 3903.71 | 50.85 | 198503.6535 | 3885.68 | 0 | 18.03 | 3885.68 | 18.03 | 3885.68 | 0 | 68.1828 | 264936.4037 | 3885.68 | 0 | 74.71 | 3829 | 3082 | 203156.4309 | Kgs | 224522.376 | 210064.752 | 18.03 | 0 | -11561.0985
Steel Bars 10mm - Kgs | Wing 1 - P2 to P3 Lvl Column steel (MTBT Basis from GDT) | STEEL | 2000 | 50.85 | 101700 | 2000 | 50.85 | 101700 | 2000 | 0 | 0 | 2000 | 0 | 2000 | 0 | 67.614 | 135228 | 2000 | 0 | 2000 | 0 | 3082 | 203156.4309 | Kgs | 114600 | 0 | 0 | 0 | 101700
Steel Bars 10mm - Kgs | Wing 1 - RCC Retaining wall Steel | STEEL | 1131.71 | 50.85 | 57547.4535 | 1131.71 | 50.85 | 57547.4535 | 1131.71 | 0 | 0 | 1131.71 | 0 | 1131.71 | 0 | 65.726 | 74382.7715 | 1131.71 | 0 | 5.71 | 1126 | 3082 | 203156.4309 | Kgs | 63036.247 | 126072.494 | 0 | 0 | -68525.0405
Steel Bars 10mm - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 3970.26 | 50.85 | 201887.721 | 3970.26 | 50.85 | 201887.721 | 3970.26 | 0 | 0 | 3970.26 | 0 | 3970.26 | 0 | 67.2989 | 267194.1307 | 3970.26 | 0 | 12.26 | 3958 | 3082 | 203156.4309 | Kgs | 226435.8386 | 679307.5157 | 0 | 0 | -477419.7947
Steel Bars 10mm - Kgs | Wing -2 Parking Column upto GF Slab - Steel | STEEL | 650.05 | 50.85 | 33055.0425 | 0 | 0 | 0 | 0 | 650.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650.05 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 650.05 | 33055.0425
Steel Bars 10mm - Kgs | Wing-1 Substructure RCC Piling work - Steel | STEEL | 290.38 | 50.85 | 14765.823 | 90 | 50.85 | 4576.5 | 90 | 200.38 | 0 | 90 | 0 | 90 | 0 | 66.9617 | 6026.555 | 90 | 0 | 290.38 | 0 | 3082 | 203156.4309 | Kgs | 5107.25 | 4240 | 0 | 200.38 | 10525.823
Steel Bars 10mm - Kgs | Wing-2 Substructure RCC Tie Beam Reinforcement Steel | STEEL | 139.81 | 50.85 | 7109.3385 | 139.81 | 50.85 | 7109.3385 | 139.81 | 0 | 0 | 139.81 | 0 | 139.81 | 0 | 70.4991 | 9856.4792 | 139.81 | 0 | 65.81 | 74 | 3082 | 203156.4309 | Kgs | 8352.9485 | 0 | 0 | 0 | 7109.3385
Steel Bars 10mm - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 10000 | 50.85 | 508500 | 10000 | 50.85 | 508500 | 10000 | 0 | 0 | 10000 | 0 | 10000 | 0 | 67.2989 | 672989 | 10000 | 0 | 158 | 9842 | 3082 | 203156.4309 | Kgs | 570330 | 1710990 | 0 | 0 | -1202490
Steel Bars 10mm - Kgs | Wing-2 Substructure RCC Plinth Beam Reinforcement Steel | STEEL | 244.31 | 50.85 | 12423.1635 | 244.31 | 50.85 | 12423.1635 | 244.31 | 0 | 0 | 244.31 | 0 | 244.31 | 0 | 70.4991 | 17223.6351 | 244.31 | 0 | 0.31 | 244 | 3082 | 203156.4309 | Kgs | 14596.301 | 0 | 0 | 0 | 12423.1635
Steel Bars 10mm - Kgs | Wing-1 Substructure Grade Slab Reinforcement Steel | STEEL | 9961.49 | 50.85 | 506541.7665 | 9961.49 | 50.85 | 506541.7665 | 6596.8 | 0 | 3364.69 | 6596.8 | 3364.69 | 6596.8 | 0 | 65.7823 | 433952.9249 | 6596.8 | 0 | 1603.48 | 8358.01 | 3082 | 203156.4309 | Kgs | 367756.716 | 0 | 3364.69 | 0 | 506541.7665
Steel Bars 10mm - Kgs | Wing -1 Emergency Exit Ramp Steel | STEEL | 717.44 | 50.85 | 36481.824 | 717.44 | 50.85 | 36481.824 | 717.44 | 0 | 0 | 717.44 | 0 | 717.44 | 0 | 70.4991 | 50578.8743 | 717.44 | 0 | 6.44 | 711 | 3082 | 203156.4309 | Kgs | 42863.4528 | 0 | 0 | 0 | 36481.824
Steel Bars 10mm - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 11403.38 | 50.85 | 579861.873 | 11403.38 | 50.85 | 579861.873 | 11403.38 | 0 | 0 | 11403.38 | 0 | 11403.38 | 0 | 63.5195 | 724337.027 | 11403.38 | 0 | 3495.38 | 7908 | 3082 | 203156.4309 | Kgs | 613844.9381 | 1060000 | 0 | 0 | -480138.127
Steel Bars 10mm - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 10532 | 50.85 | 535552.2 | 10000 | 50.85 | 508500 | 10000 | 532 | 0 | 10000 | 0 | 10000 | 0 | 68.0994 | 680994.2 | 10000 | 0 | 158 | 10374 | 3082 | 203156.4309 | Kgs | 577114 | 915248 | 0 | 532 | -379695.8
Steel Bars 10mm - Kgs | Wing 1 - P3 to P4 Level Column Steel | STEEL | 4684.44 | 50.85 | 238203.774 | 4684.44 | 50.85 | 238203.774 | 4684.44 | 0 | 0 | 4684.44 | 0 | 4684.44 | 0 | 70.4991 | 330248.804 | 4684.44 | 0 | 686.44 | 3998 | 3082 | 203156.4309 | Kgs | 279871.8678 | 0 | 0 | 0 | 238203.774
Steel Bars 10mm - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 10532 | 50.85 | 535552.2 | 10000 | 50.85 | 508500 | 10000 | 532 | 0 | 10000 | 0 | 10000 | 0 | 68.797 | 687969.9988 | 10000 | 0 | 643 | 9889 | 3082 | 203156.4309 | Kgs | 583025.4227 | 1018927.588 | 0 | 532 | -483375.388
Steel Bars 10mm - Kgs | Wing 1 - P4 to P5 Level Column Steel | STEEL | 4684.44 | 50.85 | 238203.774 | 0 | 0 | 0 | 0 | 4684.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160.44 | 4524 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 4684.44 | 238203.774
Steel Bars 10mm - Kgs | Wing -1 Ramp from P1 to P2 - Steel | STEEL | 932.56 | 50.85 | 47420.676 | 932.56 | 50.85 | 47420.676 | 932.56 | 0 | 0 | 932.56 | 0 | 932.56 | 0 | 70.4991 | 65744.6407 | 932.56 | 0 | 0 | 932.56 | 3082 | 203156.4309 | Kgs | 55715.7972 | 0 | 0 | 0 | 47420.676
Steel Bars 10mm - Kgs | Wing 1 Ramp from P2 to P3 - Steel | STEEL | 932.56 | 50.85 | 47420.676 | 932.56 | 50.85 | 47420.676 | 932.56 | 0 | 0 | 932.56 | 0 | 932.56 | 0 | 68.558 | 63934.4485 | 932.56 | 0 | 117.56 | 815 | 3082 | 203156.4309 | Kgs | 54181.736 | 108363.472 | 0 | 0 | -60942.796
Steel Bars 10mm - Kgs | Wing 1 Ramp from P3 to P4 - Steel | STEEL | 932.56 | 50.85 | 47420.676 | 0 | 0 | 0 | 0 | 932.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932.56 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 932.56 | 47420.676
Steel Bars 10mm - Kgs | Wing 1 Ramp from P4 to P5 - Steel | STEEL | 932.56 | 50.85 | 47420.676 | 0 | 0 | 0 | 0 | 932.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932.56 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 932.56 | 47420.676
Steel Bars 10mm - Kgs | Goel House Gym Work | STEEL | 278.7 | 43 | 11984.1 | 268.7 | 43 | 11554.1 | 268.7 | 10 | 0 | 268.7 | 0 | 268.7 | 0 | 68.558 | 18421.5346 | 268.7 | 0 | 115.7 | 163 | 3082 | 203156.4309 | Kgs | 15611.47 | 31222.94 | 0 | 10 | -19238.84
Steel Bars 10mm - Kgs | Wing 1 - P5 to P6 level Column Steel | STEEL | 4684.44 | 50.85 | 238203.774 | 0 | 0 | 0 | 0 | 4684.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285.44 | 4399 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 4684.44 | 238203.774
Steel Bars 10mm - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 10532 | 50.85 | 535552.2 | 7990 | 50.85 | 406291.5 | 7990 | 2542 | 0 | 7990 | 0 | 7990 | 0 | 67.614 | 540235.86 | 7990 | 0 | 6623 | 3909 | 3082 | 203156.4309 | Kgs | 457827 | 0 | 0 | 2542 | 535552.2
Steel Bars 10mm - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 170.34 | 50.85 | 8661.789 | 0 | 0 | 0 | 0 | 170.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.34 | 163 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 170.34 | 8661.789
Steel Bars 10mm - Kgs | Wing 02 Piling work for Non Tower area | STEEL | 66.24 | 50.85 | 3368.304 | 66.24 | 50.85 | 3368.304 | 66.24 | 0 | 0 | 66.24 | 0 | 0 | 66.24 | 0 | 0 | 0 | 0 | 7.24 | 59 | 3082 | 203156.4309 | Kgs | 0 | 0 | 66.24 | 0 | 3368.304
Steel Bars 10mm - Kgs | Wing 1 - 6th Slab (Pod. Bld.) Wing 1 P6 to Pod. level Column | STEEL | 6593.73 | 50.85 | 335291.1705 | 0 | 0 | 0 | 0 | 6593.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 6590 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 6593.73 | 335291.1705
Steel Bars 10mm - Kgs | Wing-3 Substructure Steel For Footing | STEEL | 3195.38 | 50.85 | 162485.073 | 0 | 0 | 0 | 0 | 3195.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3032.38 | 163 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3195.38 | 162485.073
Steel Bars 10mm - Kgs | Wing 1 Ramp from P5 to P6 - Steel | STEEL | 932.56 | 50.85 | 47420.676 | 0 | 0 | 0 | 0 | 932.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932.56 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 932.56 | 47420.676
Steel Bars 10mm - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 4124.48 | 50.85 | 209729.808 | 4124.48 | 50.85 | 209729.808 | 4124.48 | 0 | 0 | 4124.48 | 0 | 0 | 4124.48 | 0 | 0 | 0 | 0 | 52.48 | 4072 | 3082 | 203156.4309 | Kgs | 0 | 0 | 4124.48 | 0 | 209729.808
Steel Bars 10mm - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 3192 | 50.85 | 162313.2 | 3192 | 50.85 | 162313.2 | 3192 | 0 | 0 | 3192 | 0 | 3192 | 0 | 63.2421 | 201868.7832 | 3192 | 0 | 1 | 3191 | 3082 | 203156.4309 | Kgs | 171075.24 | 171075.24 | 0 | 0 | -8762.04
Steel Bars 10mm - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 3279 | 50.85 | 166737.15 | 3192 | 50.85 | 162313.2 | 3192 | 87 | 0 | 3192 | 0 | 0 | 3192 | 0 | 0 | 0 | 0 | 88 | 3191 | 3082 | 203156.4309 | Kgs | 0 | 0 | 3192 | 87 | 166737.15
Steel Bars 10mm - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 3279 | 50.85 | 166737.15 | 3270 | 50.85 | 166279.5 | 3270 | 9 | 0 | 3270 | 0 | 50 | 3220 | 62.54 | 3127 | 50 | 0 | 22 | 3257 | 3082 | 203156.4309 | Kgs | 2650 | 2650 | 3220 | 9 | 164087.15
Steel Bars 10mm - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 3279 | 50.85 | 166737.15 | 3220 | 50.85 | 163737 | 3220 | 59 | 0 | 3220 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 103 | 3176 | 3082 | 203156.4309 | Kgs | 0 | 0 | 3220 | 59 | 166737.15
Steel Bars 10mm - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 3279 | 50.85 | 166737.15 | 3279 | 50.85 | 166737.15 | 3279 | 0 | 0 | 3279 | 0 | 3279 | 0 | 62.54 | 205068.66 | 3279 | 0 | 21 | 3258 | 3082 | 203156.4309 | Kgs | 173787 | 173787 | 0 | 0 | -7049.85
Steel Bars 10mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 3220 | 50.85 | 163737 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 3175 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3220 | 163737
Steel Bars 10mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 3220 | 50.85 | 163737 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 3095 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3220 | 163737
Steel Bars 10mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3282 | 50.85 | 166889.7 | 0 | 0 | 0 | 0 | 3282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002 | 2280 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3282 | 166889.7
Steel Bars 10mm - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 3282 | 50.85 | 166889.7 | 0 | 0 | 0 | 0 | 3282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3282 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3282 | 166889.7
Steel Bars 10mm - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 3382.53 | 50.85 | 172001.6505 | 3382.53 | 0 | 0 | 3382.53 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 5.53 | 3377 | 3082 | 203156.4309 | Kgs | 0 | 0 | 3382.53 | 0 | 172001.6505
Steel Bars 10mm - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 3561.57 | 50.85 | 181105.8345 | 3363.91 | 50.85 | 171054.8235 | 3363.91 | 197.66 | 0 | 3363.91 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 199.57 | 3362 | 3082 | 203156.4309 | Kgs | 0 | 0 | 3363.91 | 197.66 | 181105.8345
Steel Bars 10mm - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 3561.57 | 50.85 | 181105.8345 | 3561.57 | 50.85 | 181105.8345 | 3561.57 | 0 | 0 | 3561.57 | 0 | 191 | 3370.57 | 62.54 | 11945.14 | 191 | 0 | 58.57 | 3503 | 3082 | 203156.4309 | Kgs | 10123 | 10123 | 3370.57 | 0 | 170982.8345
Steel Bars 10mm - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 3561.57 | 50.85 | 181105.8345 | 3363.91 | 50.85 | 171054.8235 | 3363.91 | 197.66 | 0 | 3363.91 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 59.57 | 3502 | 3082 | 203156.4309 | Kgs | 0 | 0 | 3363.91 | 197.66 | 181105.8345
Steel Bars 10mm - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 3561.57 | 50.85 | 181105.8345 | 1530 | 50.85 | 77800.5 | 1530 | 2031.57 | 0 | 1530 | 0 | 1530 | 0 | 62.54 | 95686.2 | 1530 | 0 | 58.57 | 3503 | 3082 | 203156.4309 | Kgs | 81090 | 81090 | 0 | 2031.57 | 100015.8345
Steel Bars 10mm - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 3297.71 | 50.85 | 167688.5535 | 3297.71 | 50.85 | 167688.5535 | 3297.71 | 0 | 0 | 3297.71 | 0 | 3297.71 | 0 | 63.2421 | 208554.1056 | 3297.71 | 0 | 3.71 | 3294 | 3082 | 203156.4309 | Kgs | 176740.7675 | 176740.7675 | 0 | 0 | -9052.214
Steel Bars 10mm - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 817.86 | 50.85 | 41588.181 | 817.86 | 50.85 | 41588.181 | 817.86 | 0 | 0 | 817.86 | 0 | 817.86 | 0 | 63.2421 | 51723.1839 | 817.86 | 0 | 3.86 | 814 | 3082 | 203156.4309 | Kgs | 43833.2067 | 43833.2067 | 0 | 0 | -2245.0257
Steel Bars 10mm - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 817.86 | 50.85 | 41588.181 | 728.69 | 50.85 | 37053.8865 | 728.69 | 89.17 | 0 | 728.69 | 0 | 728.69 | 0 | 63.2421 | 46083.8858 | 728.69 | 0 | 91.86 | 726 | 3082 | 203156.4309 | Kgs | 39054.1406 | 39054.1406 | 0 | 89.17 | 2534.0404
Steel Bars 10mm - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 817.86 | 50.85 | 41588.181 | 728.69 | 50.85 | 37053.8865 | 728.69 | 89.17 | 0 | 728.69 | 0 | 728.69 | 0 | 63.2421 | 46083.8858 | 728.69 | 0 | 89.86 | 728 | 3082 | 203156.4309 | Kgs | 39054.1406 | 39054.1406 | 0 | 89.17 | 2534.0404
Steel Bars 10mm - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 817.86 | 50.85 | 41588.181 | 728.69 | 50.85 | 37053.8865 | 728.69 | 89.17 | 0 | 728.69 | 0 | 728.69 | 0 | 63.2421 | 46083.8858 | 728.69 | 0 | 89.86 | 728 | 3082 | 203156.4309 | Kgs | 39054.1406 | 39054.1406 | 0 | 89.17 | 2534.0404
Steel Bars 10mm - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 3333.57 | 50.85 | 169512.0345 | 3333.57 | 50.85 | 169512.0345 | 3333.57 | 0 | 0 | 3333.57 | 0 | 141.57 | 3192 | 63.2421 | 8953.1841 | 141.57 | 0 | 1.57 | 3332 | 3082 | 203156.4309 | Kgs | 7587.4442 | 7587.4442 | 3192 | 0 | 161924.5903
Steel Bars 10mm - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 3692.92 | 50.85 | 187784.982 | 3692.92 | 50.85 | 187784.982 | 2364.79 | 0 | 1328.13 | 2364.79 | 1328.13 | 2364.79 | 0 | 59.355 | 140362.0857 | 2364.79 | 0 | 1394.92 | 2298 | 3082 | 203156.4309 | Kgs | 118950.9201 | 19550.9201 | 1328.13 | 0 | 168234.0619
Steel Bars 10mm - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 3692.92 | 50.85 | 187784.982 | 3692.92 | 50.85 | 187784.982 | 2800 | 0 | 892.92 | 2800 | 892.92 | 2800 | 0 | 58.646 | 164208.8 | 2800 | 0 | 27.92 | 3665 | 3082 | 203156.4309 | Kgs | 139160 | 0 | 892.92 | 0 | 187784.982
Steel Bars 10mm - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 3302 | 50.85 | 167906.7 | 0 | 0 | 0 | 0 | 3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3302 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3302 | 167906.7
Steel Bars 10mm - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 3324 | 50.85 | 169025.4 | 0 | 0 | 0 | 0 | 3324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3324 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3324 | 169025.4
Steel Bars 10mm - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 3324 | 50.85 | 169025.4 | 0 | 0 | 0 | 0 | 3324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3324 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3324 | 169025.4
Steel Bars 10mm - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 3380 | 50.85 | 171873 | 0 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3380 | 171873
Steel Bars 10mm - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 3380 | 50.85 | 171873 | 0 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3380 | 171873
Steel Bars 10mm - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 3380 | 50.85 | 171873 | 0 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3380 | 171873
Steel Bars 10mm - Kgs | Wing 1-15th Floor To 16th Floor Column, LW Steel | STEEL | 3380 | 50.85 | 171873 | 0 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3380 | 171873
Steel Bars 10mm - Kgs | Wing 1-16th Floor To 17th Floor Column, LW Steel | STEEL | 3380 | 50.85 | 171873 | 0 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3380 | 171873
Steel Bars 10mm - Kgs | Wing 1-17th Floor To 18th Floor Column, LW Steel | STEEL | 3448 | 50.85 | 175330.8 | 0 | 0 | 0 | 0 | 3448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3448 | 175330.8
Steel Bars 10mm - Kgs | Wing 1-20th Floor To 21st Floor Column, LW Steel | STEEL | 3309 | 50.85 | 168262.65 | 0 | 0 | 0 | 0 | 3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3309 | 168262.65
Steel Bars 10mm - Kgs | Wing 1-23rd Floor To 24th Floor Column, LW Steel | STEEL | 3309 | 50.85 | 168262.65 | 0 | 0 | 0 | 0 | 3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3309 | 168262.65
Steel Bars 10mm - Kgs | Wing 1-26th Floor To 27th Floor Column, LW Steel | STEEL | 3522 | 50.85 | 179093.7 | 0 | 0 | 0 | 0 | 3522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3522 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3522 | 179093.7
Steel Bars 10mm - Kgs | Wing 1-27th Floor To 28th Floor Column, LW Steel | STEEL | 3522 | 50.85 | 179093.7 | 0 | 0 | 0 | 0 | 3522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3522 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3522 | 179093.7
Steel Bars 10mm - Kgs | Wing 1-28th Floor To Terrace Floor Column, LW Steel | STEEL | 3522 | 50.85 | 179093.7 | 0 | 0 | 0 | 0 | 3522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3522 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3522 | 179093.7
Steel Bars 10mm - Kgs | Wing 1-24th Floor To 25th Floor Column, LW Steel | STEEL | 3309 | 50.85 | 168262.65 | 0 | 0 | 0 | 0 | 3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3309 | 168262.65
Steel Bars 10mm - Kgs | Wing 1-25th Floor To 26th Floor Column, LW Steel | STEEL | 3309 | 50.85 | 168262.65 | 0 | 0 | 0 | 0 | 3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3309 | 168262.65
Steel Bars 10mm - Kgs | Wing 1-21st Floor To 22nd Floor Column, LW Steel | STEEL | 3309 | 50.85 | 168262.65 | 0 | 0 | 0 | 0 | 3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3309 | 168262.65
Steel Bars 10mm - Kgs | Wing 1-22nd Floor To 23rd Floor Column, LW Steel | STEEL | 3309 | 50.85 | 168262.65 | 0 | 0 | 0 | 0 | 3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3309 | 168262.65
Steel Bars 10mm - Kgs | Wing 1-18th Floor To 19th Floor Column, LW Steel | STEEL | 3448 | 50.85 | 175330.8 | 0 | 0 | 0 | 0 | 3448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3448 | 175330.8
Steel Bars 10mm - Kgs | Wing 1-19th Floor To 20th Floor Column, LW Steel | STEEL | 3448 | 50.85 | 175330.8 | 0 | 0 | 0 | 0 | 3448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3448 | 175330.8
Steel Bars 10mm - Kgs | Wing-3 Substructure (M) Steel For Tie Beam | STEEL | 274.96 | 50.85 | 13981.716 | 0 | 0 | 0 | 0 | 274.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274.96 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 274.96 | 13981.716
Steel Bars 10mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.53 | 3339 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3382.53 | 172001.6505
Steel Bars 10mm - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3382.53 | 172001.6505
Steel Bars 10mm - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3382.53 | 172001.6505
Steel Bars 10mm - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3382.53 | 172001.6505
Steel Bars 10mm - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 3382.53 | 50.85 | 172001.6505 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382.53 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3382.53 | 172001.6505
Steel Bars 10mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.91 | 3338 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 3363.91 | 50.85 | 171054.8235 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.91 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3363.91 | 171054.8235
Steel Bars 10mm - Kgs | Non Tower Area Column Upto Plinth | STEEL | 379.74 | 50.85 | 19309.779 | 379.74 | 50.85 | 19309.779 | 379.74 | 0 | 0 | 379.74 | 0 | 0 | 379.74 | 0 | 0 | 0 | 0 | 42.74 | 337 | 3082 | 203156.4309 | Kgs | 0 | 0 | 379.74 | 0 | 19309.779
Steel Bars 10mm - Kgs | Wing-3 Parking NTA Piling | STEEL | 319.8 | 50.85 | 16261.83 | 191.88 | 50.85 | 9757.098 | 191.88 | 127.92 | 0 | 191.88 | 0 | 0 | 191.88 | 0 | 0 | 0 | 0 | 0.8 | 319 | 3082 | 203156.4309 | Kgs | 0 | 0 | 191.88 | 127.92 | 16261.83
Steel Bars 10mm - Kgs | Non Tower Area NTA Piling | STEEL | 106.6 | 50.85 | 5420.61 | 31.98 | 50.85 | 1626.183 | 31.98 | 74.62 | 0 | 31.98 | 0 | 0 | 31.98 | 0 | 0 | 0 | 0 | 25.6 | 81 | 3082 | 203156.4309 | Kgs | 0 | 0 | 31.98 | 74.62 | 5420.61
Steel Bars 10mm - Kgs | Wing.1 Substructure RCC Pile Cap work - Steel | STEEL | 290.38 | 50.85 | 14765.823 | 0 | 0 | 0 | 0 | 290.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.38 | 81 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 290.38 | 14765.823
Steel Bars 10mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 2450.13 | 50.85 | 124589.1105 | 0 | 0 | 0 | 0 | 2450.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.13 | 2442 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 2450.13 | 124589.1105
Steel Bars 10mm - Kgs | Wing 2 . P5 To P6 Column &amp;amp; Lift Steel | STEEL | 728.69 | 50.85 | 37053.8865 | 0 | 0 | 0 | 0 | 728.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.69 | 652 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 728.69 | 37053.8865
Steel Bars 10mm - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 3692.92 | 50.85 | 187784.982 | 0 | 0 | 0 | 0 | 3692.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.92 | 3665 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3692.92 | 187784.982
Steel Bars 10mm - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 3514.98 | 50.85 | 178736.733 | 0 | 0 | 0 | 0 | 3514.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.98 | 3502 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3514.98 | 178736.733
Steel Bars 10mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 6.43 | 50.85 | 326.9655 | 0 | 0 | 0 | 0 | 6.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.43 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 6.43 | 326.9655
Steel Bars 10mm - Kgs | Wing 2 . P6 To Podium Column & Lift Steel | STEEL | 1058.7 | 50.85 | 53834.895 | 0 | 0 | 0 | 0 | 1058.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058.7 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 1058.7 | 53834.895
Steel Bars 10mm - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 3185.5 | 50.85 | 161982.675 | 0 | 0 | 0 | 0 | 3185.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3185.5 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3185.5 | 161982.675
Steel Bars 10mm - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 5975.2 | 50.85 | 303838.92 | 0 | 0 | 0 | 0 | 5975.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5975.2 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 5975.2 | 303838.92
Steel Bars 10mm - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 3514.98 | 50.85 | 178736.733 | 0 | 0 | 0 | 0 | 3514.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514.98 | 0 | 3082 | 203156.4309 | Kgs | 0 | 0 | 0 | 3514.98 | 178736.733
Steel Bars 12mm - Kgs | Labour Camp Work | STEEL | 882 | 43 | 37926 | 882 | 43 | 37926 | 882 | 0 | 0 | 882 | 0 | 882 | 0 | 48.815 | 43054.83 | 882 | 0 | 0 | 882 | 5202 | 324912.7522 | Kgs | 43054.83 | 0 | 0 | 0 | 37926
Steel Bars 12mm - Kgs | Wing-1 Substructure Footing Steel-(Kgs) | STEEL | 4886.13 | 50.85 | 248459.7105 | 3758.13 | 50.85 | 191100.9105 | 3758.13 | 1128 | 0 | 3758.13 | 0 | 3758.13 | 0 | 62.3393 | 234279.2256 | 3758.13 | 0 | 0 | 4886.13 | 5202 | 324912.7522 | Kgs | 198541.7166 | 393763.5582 | 0 | 1128 | -145303.8477
Steel Bars 12mm - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 16384.4 | 50.85 | 833146.74 | 15803.386 | 50.85 | 803602.1781 | 15803.386 | 581.014 | 0 | 15803.386 | 0 | 15803.386 | 0 | 67.2345 | 1062533.3115 | 15803.386 | 0 | 11.16 | 16373.24 | 5202 | 324912.7522 | Kgs | 900451.9589 | 1248949.9688 | 0 | 581.014 | -415803.2288
Steel Bars 12mm - Kgs | Wing-1 Parking Footing Steel | STEEL | 31.64 | 50.85 | 1608.894 | 31.64 | 50.85 | 1608.894 | 31.64 | 0 | 0 | 31.64 | 0 | 31.64 | 0 | 81.7315 | 2585.9847 | 31.64 | 0 | 0 | 31.64 | 5202 | 324912.7522 | Kgs | 2191.513 | 10957.5648 | 0 | 0 | -9348.6708
Steel Bars 12mm - Kgs | Weigh Bridge Beam Steel | STEEL | 48.601 | 43 | 2089.843 | 48.601 | 43 | 2089.843 | 48.601 | 0 | 0 | 48.601 | 0 | 48.601 | 0 | 69.9933 | 3401.7442 | 48.601 | 0 | 48.601 | 0 | 5202 | 324912.7522 | Kgs | 2882.8344 | 9649.5091 | 0 | 0 | -7559.6661
Steel Bars 12mm - Kgs | Weigh Bridge Column Steel | STEEL | 380.894 | 43 | 16378.442 | 380.894 | 43 | 16378.442 | 380.894 | 0 | 0 | 380.894 | 0 | 380.894 | 0 | 79.9693 | 30459.8197 | 380.894 | 0 | 380.894 | 0 | 5202 | 324912.7522 | Kgs | 25813.4042 | 62943.3137 | 0 | 0 | -46564.8717
Steel Bars 12mm - Kgs | Weigh Bridge Footing Steel | STEEL | 292.52 | 43 | 12578.36 | 292.52 | 43 | 12578.36 | 292.52 | 0 | 0 | 292.52 | 0 | 292.52 | 0 | 62.658 | 18328.7182 | 292.52 | 0 | 292.52 | 0 | 5202 | 324912.7522 | Kgs | 15532.812 | 31065.624 | 0 | 0 | -18487.264
Steel Bars 12mm - Kgs | New Labour Camp | STEEL | 570 | 43 | 24510 | 570 | 43 | 24510 | 570 | 0 | 0 | 570 | 0 | 570 | 0 | 68.558 | 39078.06 | 570 | 0 | 5 | 565 | 5202 | 324912.7522 | Kgs | 33117 | 66234 | 0 | 0 | -41724
Steel Bars 12mm - Kgs | Wing-1 Substructure Tie Beam Steel | STEEL | 1760.98 | 50.85 | 89545.833 | 1760.98 | 50.85 | 89545.833 | 1760.98 | 0 | 0 | 1760.98 | 0 | 1760.98 | 0 | 81.7315 | 143927.5369 | 1760.98 | 0 | 0 | 1760.98 | 5202 | 324912.7522 | Kgs | 121972.5187 | 609862.5936 | 0 | 0 | -520316.7606
Steel Bars 12mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 501.01 | 50.85 | 25476.3585 | 501.01 | 50.85 | 25476.3585 | 501.01 | 0 | 0 | 501.01 | 0 | 501.01 | 0 | 69.1086 | 34624.095 | 501.01 | 0 | 0 | 501.01 | 5202 | 324912.7522 | Kgs | 29342.4534 | 30201.327 | 0 | 0 | -4724.9685
Steel Bars 12mm - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 6180.96 | 50.85 | 314301.816 | 6180.96 | 50.85 | 314301.816 | 6180.96 | 0 | 0 | 6180.96 | 0 | 6180.96 | 0 | 81.7315 | 505179.1322 | 6180.96 | 0 | 66.96 | 6114 | 5202 | 324912.7522 | Kgs | 428118.0134 | 2140590.0672 | 0 | 0 | -1826288.2512
Steel Bars 12mm - Kgs | Wing-1 Substructure RCC Plinth Beam - Steel | STEEL | 1809.97 | 50.85 | 92036.9745 | 1809.97 | 50.85 | 92036.9745 | 1809.97 | 0 | 0 | 1809.97 | 0 | 1809.97 | 0 | 77.4557 | 140192.426 | 1809.97 | 0 | 0.97 | 1809 | 5202 | 324912.7522 | Kgs | 118807.0951 | 14447.466 | 0 | 0 | 77589.5085
Steel Bars 12mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 9437.35 | 43 | 405806.05 | 9437.35 | 43 | 405806.05 | 9437.35 | 0 | 0 | 9437.35 | 0 | 9437.35 | 0 | 76.4003 | 721015.9815 | 9437.35 | 0 | 2610.35 | 6827 | 5202 | 324912.7522 | Kgs | 611030.2767 | 160035.4576 | 0 | 0 | 245770.5924
Steel Bars 12mm - Kgs | Wing-2 Substructure Footing Reinforcement Steel | STEEL | 2891.17 | 50.85 | 147015.9945 | 2697 | 50.85 | 137142.45 | 2697 | 194.17 | 0 | 2697 | 0 | 2677 | 20 | 65.3749 | 175008.6963 | 2677 | 0 | 29.17 | 2862 | 5202 | 324912.7522 | Kgs | 148312.463 | 283060.566 | 20 | 194.17 | -136044.5715
Steel Bars 12mm - Kgs | Wing 1 - P2 to P3 Level Column steel | STEEL | 7148.84 | 50.85 | 363518.514 | 6085.84 | 50.85 | 309464.964 | 6085.84 | 1063 | 0 | 6085.84 | 0 | 6085.84 | 0 | 66.3862 | 404015.6543 | 6085.84 | 0 | 1126.84 | 6022 | 5202 | 324912.7522 | Kgs | 342386.3145 | 965296.2834 | 0 | 1063 | -601777.7694
Steel Bars 12mm - Kgs | Wing 1 - RCC Retaining wall Steel | STEEL | 110.39 | 50.85 | 5613.3315 | 110.39 | 50.85 | 5613.3315 | 110.39 | 0 | 0 | 110.39 | 0 | 110.39 | 0 | 65.726 | 7255.4931 | 110.39 | 0 | 110.39 | 0 | 5202 | 324912.7522 | Kgs | 6148.723 | 12297.446 | 0 | 0 | -6684.1145
Steel Bars 12mm - Kgs | Wing -2 Parking Footing Steel | STEEL | 110.36 | 50.85 | 5611.806 | 110.36 | 50.85 | 5611.806 | 110.36 | 0 | 0 | 110.36 | 0 | 110.36 | 0 | 65.726 | 7253.5214 | 110.36 | 0 | 110.36 | 0 | 5202 | 324912.7522 | Kgs | 6147.052 | 12294.104 | 0 | 0 | -6682.298
Steel Bars 12mm - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 26878.04 | 50.85 | 1366748.334 | 26878.04 | 50.85 | 1366748.334 | 26878.04 | 0 | 0 | 26878.04 | 0 | 26878.04 | 0 | 67.2989 | 1808862.5262 | 26878.04 | 0 | 33.04 | 26845 | 5202 | 324912.7522 | Kgs | 1532935.2553 | 3678464.245 | 0 | 0 | -2311715.911
Steel Bars 12mm - Kgs | Wing -2 Parking Column upto GF Slab - Steel | STEEL | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 0 | 0
Steel Bars 12mm - Kgs | Wing-2 Substructure RCC Tie Beam Reinforcement Steel | STEEL | 2140.07 | 50.85 | 108822.5595 | 2140.07 | 50.85 | 108822.5595 | 2140.07 | 0 | 0 | 2140.07 | 0 | 2140.07 | 0 | 68.5578 | 146718.558 | 2140.07 | 0 | 6.07 | 2134 | 5202 | 324912.7522 | Kgs | 124337.761 | 248675.522 | 0 | 0 | -139852.9625
Steel Bars 12mm - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 10000 | 50.85 | 508500 | 10000 | 50.85 | 508500 | 10000 | 0 | 0 | 10000 | 0 | 10000 | 0 | 67.1068 | 671068.0224 | 10000 | 0 | 4 | 9996 | 5202 | 324912.7522 | Kgs | 568702.0392 | 1684712.1377 | 0 | 0 | -1176212.1377
Steel Bars 12mm - Kgs | Wing-2 Substructure RCC Plinth Beam Reinforcement Steel | STEEL | 2429.06 | 50.85 | 123517.701 | 2429.06 | 50.85 | 123517.701 | 2429.06 | 0 | 0 | 2429.06 | 0 | 2429.06 | 0 | 62.54 | 151913.4124 | 2429.06 | 0 | 39.06 | 2390 | 5202 | 324912.7522 | Kgs | 128740.18 | 257480.36 | 0 | 0 | -133962.659
Steel Bars 12mm - Kgs | Wing -1 Emergency Exit Ramp Steel | STEEL | 1380.51 | 50.85 | 70198.9335 | 1380.51 | 50.85 | 70198.9335 | 1380.51 | 0 | 0 | 1380.51 | 0 | 1380.51 | 0 | 70.4991 | 97324.7125 | 1380.51 | 0 | 14.51 | 1366 | 5202 | 324912.7522 | Kgs | 82478.57 | 0 | 0 | 0 | 70198.9335
Steel Bars 12mm - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 8918.33 | 50.85 | 453497.0805 | 8918.33 | 50.85 | 453497.0805 | 8918.33 | 0 | 0 | 8918.33 | 0 | 8918.33 | 0 | 67.703 | 603797.4155 | 8918.33 | 0 | 21.33 | 8897 | 5202 | 324912.7522 | Kgs | 511692.725 | 97668.424 | 0 | 0 | 355828.6565
Steel Bars 12mm - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 5333.35 | 50.85 | 271200.8475 | 3991.87 | 50.85 | 202986.5895 | 3991.87 | 1341.48 | 0 | 3991.87 | 0 | 3991.87 | 0 | 66.67 | 266137.9729 | 3991.87 | 0 | 40.35 | 5293 | 5202 | 324912.7522 | Kgs | 225540.655 | 0 | 0 | 1341.48 | 271200.8475
Steel Bars 12mm - Kgs | Wing 1 - P3 to P4 Level Column Steel | STEEL | 6180.96 | 50.85 | 314301.816 | 6180.959 | 50.85 | 314301.7652 | 6180.959 | 0.001 | 0 | 6180.959 | 0 | 6180.959 | 0 | 68.0155 | 420401.0343 | 6180.959 | 0 | 35.96 | 6145 | 5202 | 324912.7522 | Kgs | 356272.063 | 348600 | 0 | 0.001 | -34298.184
Steel Bars 12mm - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 5333.35 | 50.85 | 271200.8475 | 5333.35 | 50.85 | 271200.8475 | 5333.35 | 0 | 0 | 5333.35 | 0 | 5103.35 | 230 | 66.4472 | 339103.4145 | 5103.35 | 0 | 63.35 | 5270 | 5202 | 324912.7522 | Kgs | 287375.775 | 0 | 230 | 0 | 271200.8475
Steel Bars 12mm - Kgs | Wing 1 - P4 to P5 Level Column Steel | STEEL | 6180.96 | 50.85 | 314301.816 | 6180.96 | 50.85 | 314301.816 | 6180.96 | 0 | 0 | 6180.96 | 0 | 6180.96 | 0 | 67.5864 | 417748.6032 | 6180.96 | 0 | 12.96 | 6168 | 5202 | 324912.7522 | Kgs | 354024.24 | 348600 | 0 | 0 | -34298.184
Steel Bars 12mm - Kgs | Wing -1 Ramp from P1 to P2 - Steel | STEEL | 1341.48 | 50.85 | 68214.258 | 1341.48 | 50.85 | 68214.258 | 1341.48 | 0 | 0 | 1341.48 | 0 | 1341.48 | 0 | 69.4544 | 93171.6779 | 1341.48 | 0 | 60.48 | 1281 | 5202 | 324912.7522 | Kgs | 78959.0491 | 83895.238 | 0 | 0 | -15680.98
Steel Bars 12mm - Kgs | Wing 1 Ramp from P2 to P3 - Steel | STEEL | 1341.48 | 50.85 | 68214.258 | 1341.48 | 50.85 | 68214.258 | 1341.48 | 0 | 0 | 1341.48 | 0 | 1341.48 | 0 | 68.558 | 91969.1858 | 1341.48 | 0 | 60.48 | 1281 | 5202 | 324912.7522 | Kgs | 77939.988 | 155879.976 | 0 | 0 | -87665.718
Steel Bars 12mm - Kgs | Wing 1 Ramp from P3 to P4 - Steel | STEEL | 1341.48 | 50.85 | 68214.258 | 1341.48 | 50.85 | 68214.258 | 1341.48 | 0 | 0 | 1341.48 | 0 | 1341.48 | 0 | 61.8639 | 82989.1846 | 1341.48 | 0 | 0.48 | 1341 | 5202 | 324912.7522 | Kgs | 70329.772 | 0 | 0 | 0 | 68214.258
Steel Bars 12mm - Kgs | Wing 1 Ramp from P4 to P5 - Steel | STEEL | 1341.48 | 50.85 | 68214.258 | 1341.48 | 50.85 | 68214.258 | 1341.48 | 0 | 0 | 1341.48 | 0 | 1341.48 | 0 | 61.8639 | 82989.1846 | 1341.48 | 0 | 0.48 | 1341 | 5202 | 324912.7522 | Kgs | 70329.772 | 0 | 0 | 0 | 68214.258
Steel Bars 12mm - Kgs | Goel House Gym Work | STEEL | 386 | 43 | 16598 | 386 | 43 | 16598 | 386 | 0 | 0 | 386 | 0 | 386 | 0 | 68.558 | 26463.388 | 386 | 0 | 45 | 341 | 5202 | 324912.7522 | Kgs | 22426.6 | 44853.2 | 0 | 0 | -28255.2
Steel Bars 12mm - Kgs | Wing 1 - P5 to P6 level Column Steel | STEEL | 6180.96 | 50.85 | 314301.816 | 6180.96 | 50.85 | 314301.816 | 6180.96 | 0 | 0 | 6180.96 | 0 | 6180.96 | 0 | 65.3002 | 403618.1032 | 6180.96 | 0 | 0.96 | 6180 | 5202 | 324912.7522 | Kgs | 342049.24 | 0 | 0 | 0 | 314301.816
Steel Bars 12mm - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 5333.35 | 50.85 | 271200.8475 | 5333.35 | 50.85 | 271200.8475 | 5333.35 | 0 | 0 | 5333.35 | 0 | 5333.35 | 0 | 65.0407 | 346884.9245 | 5333.35 | 0 | 42.35 | 5291 | 5202 | 324912.7522 | Kgs | 293970.275 | 1162 | 0 | 0 | 270038.8475
Steel Bars 12mm - Kgs | Wing 1 - 6th Slab (Pod. Bld.) Wing 1 P6 to Pod. level Column | STEEL | 10814.14 | 50.85 | 549899.019 | 10814.14 | 50.85 | 549899.019 | 10814.14 | 0 | 0 | 10814.14 | 0 | 5613.44 | 5200.7 | 62.8167 | 352617.7077 | 5613.44 | 0 | 60.14 | 10754 | 5202 | 324912.7522 | Kgs | 298828.4515 | 0 | 5200.7 | 0 | 549899.019
Steel Bars 12mm - Kgs | Wing-3 Substructure Steel For Footing | STEEL | 3871.27 | 50.85 | 196854.0795 | 362.67 | 50.85 | 18441.7695 | 362.67 | 3508.6 | 0 | 362.67 | 0 | 362.67 | 0 | 61.8639 | 22436.1806 | 362.67 | 0 | 3871.27 | 0 | 5202 | 324912.7522 | Kgs | 19013.7001 | 0 | 0 | 3508.6 | 196854.0795
Steel Bars 12mm - Kgs | Wing 1 Ramp from P5 to P6 - Steel | STEEL | 1341.48 | 50.85 | 68214.258 | 1341.48 | 50.85 | 68214.258 | 1341.48 | 0 | 0 | 1341.48 | 0 | 1341.48 | 0 | 61.8639 | 82989.1846 | 1341.48 | 0 | 268.48 | 1073 | 5202 | 324912.7522 | Kgs | 70329.772 | 0 | 0 | 0 | 68214.258
Steel Bars 12mm - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 7583.91 | 50.85 | 385641.8235 | 1637 | 50.85 | 83241.45 | 1637 | 5946.91 | 0 | 1637 | 0 | 1637 | 0 | 61.8639 | 101271.2043 | 1637 | 0 | 72.91 | 7511 | 5202 | 324912.7522 | Kgs | 85822.999 | 0 | 0 | 5946.91 | 385641.8235
Steel Bars 12mm - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 1959 | 50.85 | 99615.15 | 1959 | 50.85 | 99615.15 | 1959 | 0 | 0 | 1959 | 0 | 0 | 1959 | 0 | 0 | 0 | 0 | 7 | 1952 | 5202 | 324912.7522 | Kgs | 0 | 0 | 1959 | 0 | 99615.15
Steel Bars 12mm - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 1959 | 50.85 | 99615.15 | 1959 | 50.85 | 99615.15 | 1959 | 0 | 0 | 1959 | 0 | 0 | 1959 | 0 | 0 | 0 | 0 | 82 | 1877 | 5202 | 324912.7522 | Kgs | 0 | 0 | 1959 | 0 | 99615.15
Steel Bars 12mm - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 1989 | 50.85 | 101140.65 | 1989 | 50.85 | 101140.65 | 1989 | 0 | 0 | 1989 | 0 | 0 | 1989 | 0 | 0 | 0 | 0 | 26 | 1963 | 5202 | 324912.7522 | Kgs | 0 | 0 | 1989 | 0 | 101140.65
Steel Bars 12mm - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 2312 | 50.85 | 117565.2 | 2312 | 50.85 | 117565.2 | 2312 | 0 | 0 | 2312 | 0 | 0 | 2312 | 0 | 0 | 0 | 0 | 8 | 2304 | 5202 | 324912.7522 | Kgs | 0 | 0 | 2312 | 0 | 117565.2
Steel Bars 12mm - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 2459 | 50.85 | 125040.15 | 0 | 0 | 0 | 0 | 2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 2390 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2459 | 125040.15
Steel Bars 12mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 2587 | 50.85 | 131548.95 | 0 | 0 | 0 | 0 | 2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 2560 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2587 | 131548.95
Steel Bars 12mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 2819 | 50.85 | 143346.15 | 0 | 0 | 0 | 0 | 2819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 2560 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2819 | 143346.15
Steel Bars 12mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 2868 | 50.85 | 145837.8 | 0 | 0 | 0 | 0 | 2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 2646 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2868 | 145837.8
Steel Bars 12mm - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 2953 | 50.85 | 150160.05 | 0 | 0 | 0 | 0 | 2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2953 | 150160.05
Steel Bars 12mm - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 2874.67 | 50.85 | 146176.9695 | 2874.67 | 0 | 0 | 2874.67 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 4.67 | 2870 | 5202 | 324912.7522 | Kgs | 0 | 0 | 2874.67 | 0 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 3023.16 | 50.85 | 153727.686 | 3005.56 | 50.85 | 152832.726 | 3005.56 | 17.6 | 0 | 3005.56 | 0 | 0 | 3005.56 | 0 | 0 | 0 | 0 | 36.16 | 2987 | 5202 | 324912.7522 | Kgs | 0 | 0 | 3005.56 | 17.6 | 153727.686
Steel Bars 12mm - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 3023.16 | 50.85 | 153727.686 | 2874.67 | 50.85 | 146176.9695 | 2874.67 | 148.49 | 0 | 2874.67 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 36.16 | 2987 | 5202 | 324912.7522 | Kgs | 0 | 0 | 2874.67 | 148.49 | 153727.686
Steel Bars 12mm - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 3023.16 | 50.85 | 153727.686 | 2874.67 | 50.85 | 146176.9695 | 2874.67 | 148.49 | 0 | 2874.67 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 36.16 | 2987 | 5202 | 324912.7522 | Kgs | 0 | 0 | 2874.67 | 148.49 | 153727.686
Steel Bars 12mm - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 3023.16 | 50.85 | 153727.686 | 0 | 0 | 0 | 0 | 3023.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.16 | 2987 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3023.16 | 153727.686
Steel Bars 12mm - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 3973.06 | 50.85 | 202030.101 | 3973.06 | 50.85 | 202030.101 | 3973.06 | 0 | 0 | 3973.06 | 0 | 0 | 3973.06 | 0 | 0 | 0 | 0 | 2266.06 | 1707 | 5202 | 324912.7522 | Kgs | 0 | 0 | 3973.06 | 0 | 202030.101
Steel Bars 12mm - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 8810.2 | 50.85 | 447998.67 | 8512.37 | 50.85 | 432854.0145 | 8512.37 | 297.83 | 0 | 8512.37 | 0 | 0 | 8512.37 | 0 | 0 | 0 | 0 | 1897.2 | 6913 | 5202 | 324912.7522 | Kgs | 0 | 0 | 8512.37 | 297.83 | 447998.67
Steel Bars 12mm - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 8810.2 | 50.85 | 447998.67 | 0 | 0 | 0 | 0 | 8810.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277.2 | 8533 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 8810.2 | 447998.67
Steel Bars 12mm - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 8810.2 | 50.85 | 447998.67 | 0 | 0 | 0 | 0 | 8810.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.2 | 8534 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 8810.2 | 447998.67
Steel Bars 12mm - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 8664.41 | 50.85 | 440585.2485 | 0 | 0 | 0 | 0 | 8664.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.41 | 8620 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 8664.41 | 440585.2485
Steel Bars 12mm - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 3973.06 | 50.85 | 202030.101 | 0 | 0 | 0 | 0 | 3973.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218.06 | 3755 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3973.06 | 202030.101
Steel Bars 12mm - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 3973.06 | 50.85 | 202030.101 | 0 | 0 | 0 | 0 | 3973.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559.06 | 3414 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3973.06 | 202030.101
Steel Bars 12mm - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 3973.06 | 50.85 | 202030.101 | 0 | 0 | 0 | 0 | 3973.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559.06 | 3414 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3973.06 | 202030.101
Steel Bars 12mm - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 2953 | 50.85 | 150160.05 | 0 | 0 | 0 | 0 | 2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2953 | 150160.05
Steel Bars 12mm - Kgs | Non Tower Area Footing Steel | STEEL | 149 | 50.85 | 7576.65 | 149 | 50.85 | 7576.65 | 149 | 0 | 0 | 149 | 0 | 0 | 149 | 0 | 0 | 0 | 0 | 149 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 149 | 0 | 7576.65
Steel Bars 12mm - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 3517 | 50.85 | 178839.45 | 0 | 0 | 0 | 0 | 3517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3517 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3517 | 178839.45
Steel Bars 12mm - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 3599 | 50.85 | 183009.15 | 0 | 0 | 0 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3599 | 183009.15
Steel Bars 12mm - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 3599 | 50.85 | 183009.15 | 0 | 0 | 0 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3599 | 183009.15
Steel Bars 12mm - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 3795 | 50.85 | 192975.75 | 0 | 0 | 0 | 0 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3795 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3795 | 192975.75
Steel Bars 12mm - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 3707 | 50.85 | 188500.95 | 0 | 0 | 0 | 0 | 3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3707 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3707 | 188500.95
Steel Bars 12mm - Kgs | Wing 1-15th Floor To 16th Floor Column, LW Steel | STEEL | 3836 | 50.85 | 195060.6 | 0 | 0 | 0 | 0 | 3836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3836 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3836 | 195060.6
Steel Bars 12mm - Kgs | Wing 1-16th Floor To 17th Floor Column, LW Steel | STEEL | 4139 | 50.85 | 210468.15 | 0 | 0 | 0 | 0 | 4139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4139 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 4139 | 210468.15
Steel Bars 12mm - Kgs | Wing 1-17th Floor To 18th Floor Column, LW Steel | STEEL | 4714 | 50.85 | 239706.9 | 0 | 0 | 0 | 0 | 4714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4714 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 4714 | 239706.9
Steel Bars 12mm - Kgs | Wing 1-20th Floor To 21st Floor Column, LW Steel | STEEL | 5297 | 50.85 | 269352.45 | 0 | 0 | 0 | 0 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5297 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 5297 | 269352.45
Steel Bars 12mm - Kgs | Wing 1-23rd Floor To 24th Floor Column, LW Steel | STEEL | 6446 | 50.85 | 327779.1 | 0 | 0 | 0 | 0 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6446 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 6446 | 327779.1
Steel Bars 12mm - Kgs | Wing 1-26th Floor To 27th Floor Column, LW Steel | STEEL | 6507 | 50.85 | 330880.95 | 0 | 0 | 0 | 0 | 6507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6507 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 6507 | 330880.95
Steel Bars 12mm - Kgs | Wing 1-27th Floor To 28th Floor Column, LW Steel | STEEL | 6507 | 50.85 | 330880.95 | 0 | 0 | 0 | 0 | 6507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6507 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 6507 | 330880.95
Steel Bars 12mm - Kgs | Wing 1-28th Floor To Terrace Floor Column, LW Steel | STEEL | 6539 | 50.85 | 332508.15 | 0 | 0 | 0 | 0 | 6539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6539 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 6539 | 332508.15
Steel Bars 12mm - Kgs | Wing 1-24th Floor To 25th Floor Column, LW Steel | STEEL | 6446 | 50.85 | 327779.1 | 0 | 0 | 0 | 0 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6446 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 6446 | 327779.1
Steel Bars 12mm - Kgs | Wing 1-25th Floor To 26th Floor Column, LW Steel | STEEL | 6446 | 50.85 | 327779.1 | 0 | 0 | 0 | 0 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6446 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 6446 | 327779.1
Steel Bars 12mm - Kgs | Wing 1-21st Floor To 22nd Floor Column, LW Steel | STEEL | 5297 | 50.85 | 269352.45 | 0 | 0 | 0 | 0 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5297 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 5297 | 269352.45
Steel Bars 12mm - Kgs | Wing 1-22nd Floor To 23rd Floor Column, LW Steel | STEEL | 5297 | 50.85 | 269352.45 | 0 | 0 | 0 | 0 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5297 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 5297 | 269352.45
Steel Bars 12mm - Kgs | Wing 1-18th Floor To 19th Floor Column, LW Steel | STEEL | 4714 | 50.85 | 239706.9 | 0 | 0 | 0 | 0 | 4714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4714 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 4714 | 239706.9
Steel Bars 12mm - Kgs | Wing 1-19th Floor To 20th Floor Column, LW Steel | STEEL | 4714 | 50.85 | 239706.9 | 0 | 0 | 0 | 0 | 4714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4714 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 4714 | 239706.9
Steel Bars 12mm - Kgs | Wing-3 Substructure (M) Steel For Tie Beam | STEEL | 1514.15 | 50.85 | 76994.5275 | 0 | 0 | 0 | 0 | 1514.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1514.15 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 1514.15 | 76994.5275
Steel Bars 12mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.67 | 2731 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.67 | 2816 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228.67 | 2646 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 2874.67 | 50.85 | 146176.9695 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874.67 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 2874.67 | 146176.9695
Steel Bars 12mm - Kgs | Non Tower Area Intermediate Tie Beam Steel | STEEL | 124.54 | 50.85 | 6332.859 | 0 | 0 | 0 | 0 | 124.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.54 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 124.54 | 6332.859
Steel Bars 12mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 1428.14 | 50.85 | 72620.919 | 0 | 0 | 0 | 0 | 1428.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1001.14 | 427 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 1428.14 | 72620.919
Steel Bars 12mm - Kgs | Wing 2 . P5 To P6 Column &amp;amp; Lift Steel | STEEL | 8664.41 | 50.85 | 440585.2485 | 0 | 0 | 0 | 0 | 8664.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.41 | 8620 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 8664.41 | 440585.2485
Steel Bars 12mm - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 3417.32 | 50.85 | 173770.722 | 0 | 0 | 0 | 0 | 3417.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.32 | 3414 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3417.32 | 173770.722
Steel Bars 12mm - Kgs | Compound Wall Pile Foundation | STEEL | 427.76 | 50.85 | 21751.596 | 0 | 0 | 0 | 0 | 427.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427.76 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 427.76 | 21751.596
Steel Bars 12mm - Kgs | Non Tower Area Plinth Beam Steel | STEEL | 497.76 | 50.85 | 25311.096 | 0 | 0 | 0 | 0 | 497.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326.76 | 171 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 497.76 | 25311.096
Steel Bars 12mm - Kgs | Non Tower Area Column Ground To P1 Slab Steel | STEEL | 1063 | 50.85 | 54053.55 | 0 | 0 | 0 | 0 | 1063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 1063 | 54053.55
Steel Bars 12mm - Kgs | Non Tower Area Pile Cap Steel | STEEL | 211.555 | 50.85 | 10757.5718 | 0 | 0 | 0 | 0 | 211.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.555 | 171 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 211.555 | 10757.5718
Steel Bars 12mm - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 1664.09 | 50.85 | 84618.9765 | 0 | 0 | 0 | 0 | 1664.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.09 | 1622 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 1664.09 | 84618.9765
Steel Bars 12mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 21.09 | 50.85 | 1072.4265 | 0 | 0 | 0 | 0 | 21.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.09 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 21.09 | 1072.4265
Steel Bars 12mm - Kgs | Wing 2 . P6 To Podium Column & Lift Steel | STEEL | 12080.56 | 50.85 | 614296.476 | 0 | 0 | 0 | 0 | 12080.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12080.56 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 12080.56 | 614296.476
Steel Bars 12mm - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 3198.19 | 50.85 | 162627.9615 | 0 | 0 | 0 | 0 | 3198.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3198.19 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 3198.19 | 162627.9615
Steel Bars 12mm - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 564.24 | 50.85 | 28691.604 | 0 | 0 | 0 | 0 | 564.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564.24 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 564.24 | 28691.604
Steel Bars 12mm - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 1664.09 | 50.85 | 84618.9765 | 0 | 0 | 0 | 0 | 1664.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1664.09 | 0 | 5202 | 324912.7522 | Kgs | 0 | 0 | 0 | 1664.09 | 84618.9765
Steel Bars 16mm - Kgs | Wing-1 Substructure Footing Steel-(Kgs) | STEEL | 10024.74 | 50.85 | 509758.029 | 10024.74 | 50.85 | 509758.029 | 10024.74 | 0 | 0 | 10024.74 | 0 | 10024.74 | 0 | 66.5806 | 667452.7064 | 10024.74 | 0 | 0.74 | 10024 | 1263 | 88665.1986 | Kgs | 565637.8942 | 1050490.5364 | 0 | 0 | -540732.5074
Steel Bars 16mm - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 27541 | 50.85 | 1400459.85 | 27541 | 50.85 | 1400459.85 | 27541 | 0 | 0 | 27541 | 0 | 27541 | 0 | 64.625 | 1779838.0074 | 27541 | 0 | 14 | 27527 | 1263 | 88665.1986 | Kgs | 1508337.2944 | 2780635.8638 | 0 | 0 | -1380176.0138
Steel Bars 16mm - Kgs | Wing-1 Parking Footing Steel | STEEL | 727.07 | 50.85 | 36971.5095 | 727.07 | 50.85 | 36971.5095 | 727.07 | 0 | 0 | 727.07 | 0 | 727.07 | 0 | 69.03 | 50189.6421 | 727.07 | 0 | 611.07 | 116 | 1263 | 88665.1986 | Kgs | 42533.595 | 42533.595 | 0 | 0 | -5562.0855
Steel Bars 16mm - Kgs | Weigh Bridge Column Steel | STEEL | 171.91 | 51 | 8767.41 | 171.91 | 51 | 8767.41 | 171.91 | 0 | 0 | 171.91 | 0 | 171.91 | 0 | 81.7315 | 14050.4622 | 171.91 | 0 | 171.91 | 0 | 1263 | 88665.1986 | Kgs | 11907.1742 | 59535.8712 | 0 | 0 | -50768.4612
Steel Bars 16mm - Kgs | Wing-1 Substructure Tie Beam Steel | STEEL | 1364.54 | 50.85 | 69386.859 | 1364.54 | 50.85 | 69386.859 | 1364.54 | 0 | 0 | 1364.54 | 0 | 1364.54 | 0 | 72.1007 | 98384.2675 | 1364.54 | 0 | 0 | 1364.54 | 1263 | 88665.1986 | Kgs | 83376.4939 | 113542.65 | 0 | 0 | -44155.791
Steel Bars 16mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 273.02 | 50.85 | 13883.067 | 273.02 | 50.85 | 13883.067 | 273.02 | 0 | 0 | 273.02 | 0 | 273.02 | 0 | 69.03 | 18846.5706 | 273.02 | 0 | 0.02 | 273 | 1263 | 88665.1986 | Kgs | 15971.67 | 15971.67 | 0 | 0 | -2088.603
Steel Bars 16mm - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 9525.88 | 50.85 | 484390.998 | 9525.88 | 50.85 | 484390.998 | 9525.88 | 0 | 0 | 9525.88 | 0 | 9525.88 | 0 | 77.8883 | 741954.9278 | 9525.88 | 0 | 6.88 | 9519 | 1263 | 88665.1986 | Kgs | 628775.4751 | 2469419.1756 | 0 | 0 | -1985028.1776
Steel Bars 16mm - Kgs | Wing-1 Substructure RCC Plinth Beam - Steel | STEEL | 2550.557 | 50.85 | 129695.8235 | 2550.557 | 50.85 | 129695.8235 | 2550.557 | 0 | 0 | 2550.557 | 0 | 2550.557 | 0 | 76.3595 | 194759.1896 | 2550.557 | 0 | 26.097 | 2524.46 | 1263 | 88665.1986 | Kgs | 165050.1025 | 45009.7218 | 0 | 0 | 84686.1017
Steel Bars 16mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 41360 | 51 | 2109360 | 20799.89 | 51 | 1060794.39 | 20799.89 | 20560.11 | 0 | 20799.89 | 0 | 20799.89 | 0 | 73.4375 | 1527491.6016 | 20799.89 | 0 | 303 | 41057 | 1263 | 88665.1986 | Kgs | 1294484.063 | 868907.746 | 0 | 20560.11 | 1240452.254
Steel Bars 16mm - Kgs | Wing-2 Substructure Footing Reinforcement Steel | STEEL | 9310.88 | 50.85 | 473458.248 | 6383 | 50.85 | 324575.55 | 6383 | 2927.88 | 0 | 6383 | 0 | 6383 | 0 | 66.3069 | 423236.7666 | 6383 | 0 | 31.88 | 9279 | 1263 | 88665.1986 | Kgs | 358675.3078 | 710875.7482 | 0 | 2927.88 | -237417.5002
Steel Bars 16mm - Kgs | Wing 1 - P2 to P3 Level Column steel | STEEL | 8751.97 | 50.85 | 445037.6745 | 8751.97 | 50.85 | 445037.6745 | 1048.673 | 0 | 7703.297 | 1048.673 | 7703.297 | 1048.673 | 0 | 65.8451 | 69050.0177 | 1048.673 | 0 | 28.97 | 8723 | 1263 | 88665.1986 | Kgs | 58516.9642 | 42819.7 | 7703.297 | 0 | 402217.9745
Steel Bars 16mm - Kgs | Wing 1 - P2 to P3 Lvl Column steel (MTBT Basis from GDT) | STEEL | 2000 | 50.85 | 101700 | 2000 | 50.85 | 101700 | 2000 | 0 | 0 | 2000 | 0 | 2000 | 0 | 64.251 | 128502 | 2000 | 0 | 2000 | 0 | 1263 | 88665.1986 | Kgs | 108900 | 0 | 0 | 0 | 101700
Steel Bars 16mm - Kgs | Wing 1 - RCC Retaining wall Steel | STEEL | 790.89 | 50.85 | 40216.7565 | 790.89 | 50.85 | 40216.7565 | 790.89 | 0 | 0 | 790.89 | 0 | 790.89 | 0 | 65.726 | 51982.0361 | 790.89 | 0 | 31.89 | 759 | 1263 | 88665.1986 | Kgs | 44052.573 | 88105.146 | 0 | 0 | -47888.3895
Steel Bars 16mm - Kgs | Wing -2 Parking Footing Steel | STEEL | 1963.31 | 50.85 | 99834.3135 | 1963.31 | 50.85 | 99834.3135 | 1963.31 | 0 | 0 | 1963.31 | 0 | 1963.31 | 0 | 65.726 | 129040.5131 | 1963.31 | 0 | 825.31 | 1138 | 1263 | 88665.1986 | Kgs | 109356.367 | 218712.734 | 0 | 0 | -118878.4205
Steel Bars 16mm - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 17827.18 | 50.85 | 906512.103 | 17827.18 | 50.85 | 906512.103 | 17827.18 | 0 | 0 | 17827.18 | 0 | 17827.18 | 0 | 66.7225 | 1189473.6972 | 17827.18 | 0 | 12.18 | 17815 | 1263 | 88665.1986 | Kgs | 1008029.06 | 2016058.12 | 0 | 0 | -1109546.017
Steel Bars 16mm - Kgs | Wing -2 Parking Column upto GF Slab - Steel | STEEL | 1250.13 | 50.85 | 63569.1105 | 0 | 0 | 0 | 0 | 1250.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568.13 | 682 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1250.13 | 63569.1105
Steel Bars 16mm - Kgs | Wing-2 Substructure RCC Tie Beam Reinforcement Steel | STEEL | 411.73 | 50.85 | 20936.4705 | 411.73 | 50.85 | 20936.4705 | 411.73 | 0 | 0 | 411.73 | 0 | 411.73 | 0 | 62.54 | 25749.5942 | 411.73 | 0 | 8.73 | 403 | 1263 | 88665.1986 | Kgs | 21821.69 | 43643.38 | 0 | 0 | -22706.9095
Steel Bars 16mm - Kgs | Wing -2 Parking RCC Tie Beam (Non Tower area) Reinforcement | STEEL | 1349.18 | 50.85 | 68605.803 | 1349.18 | 50.85 | 68605.803 | 1349.18 | 0 | 0 | 1349.18 | 0 | 1349.18 | 0 | 62.54 | 84377.7172 | 1349.18 | 0 | 1349.18 | 0 | 1263 | 88665.1986 | Kgs | 71506.54 | 143013.08 | 0 | 0 | -74407.277
Steel Bars 16mm - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 5000 | 50.85 | 254250 | 5000 | 50.85 | 254250 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 67.2989 | 336494.5 | 5000 | 0 | 0 | 5000 | 1263 | 88665.1986 | Kgs | 285165 | 570330 | 0 | 0 | -316080
Steel Bars 16mm - Kgs | Wing-2 Substructure RCC Plinth Beam Reinforcement Steel | STEEL | 416.95 | 50.85 | 21201.9075 | 416.95 | 50.85 | 21201.9075 | 416.95 | 0 | 0 | 416.95 | 0 | 416.95 | 0 | 62.54 | 26076.053 | 416.95 | 0 | 37.95 | 379 | 1263 | 88665.1986 | Kgs | 22098.35 | 44196.7 | 0 | 0 | -22994.7925
Steel Bars 16mm - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 4966.46 | 50.85 | 252544.491 | 4966.46 | 50.85 | 252544.491 | 4966.46 | 0 | 0 | 4966.46 | 0 | 4966.46 | 0 | 70.4991 | 350130.9602 | 4966.46 | 0 | 149.46 | 4817 | 1263 | 88665.1986 | Kgs | 296721.1527 | 0 | 0 | 0 | 252544.491
Steel Bars 16mm - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 4966.46 | 50.85 | 252544.491 | 4966.46 | 50.85 | 252544.491 | 4966.46 | 0 | 0 | 4966.46 | 0 | 4966.46 | 0 | 64.9289 | 322466.8954 | 4966.46 | 0 | 0.46 | 4966 | 1263 | 88665.1986 | Kgs | 273277.03 | 546554.06 | 0 | 0 | -294009.569
Steel Bars 16mm - Kgs | Wing 1 - P3 to P4 Level Column Steel | STEEL | 9525.88 | 50.85 | 484390.998 | 9525.88 | 50.85 | 484390.998 | 9525.88 | 0 | 0 | 9525.88 | 0 | 9525.88 | 0 | 64.6629 | 615970.8159 | 9525.88 | 0 | 0.88 | 9525 | 1263 | 88665.1986 | Kgs | 522009.166 | 714500 | 0 | 0 | -230109.002
Steel Bars 16mm - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 4966.46 | 50.85 | 252544.491 | 4966.46 | 50.85 | 252544.491 | 4966.46 | 0 | 0 | 4966.46 | 0 | 4966.46 | 0 | 64.549 | 320579.8996 | 4966.46 | 0 | 0.46 | 4966 | 1263 | 88665.1986 | Kgs | 271677.881 | 4913.65 | 0 | 0 | 247630.841
Steel Bars 16mm - Kgs | Wing 1 - P4 to P5 Level Column Steel | STEEL | 9525.88 | 50.85 | 484390.998 | 9525.88 | 50.85 | 484390.998 | 9525.88 | 0 | 0 | 9525.88 | 0 | 9525.88 | 0 | 66.0253 | 628949.3503 | 9525.88 | 0 | 24.88 | 9501 | 1263 | 88665.1986 | Kgs | 533007.924 | 0 | 0 | 0 | 484390.998
Steel Bars 16mm - Kgs | Wing 1 - P5 to P6 level Column Steel | STEEL | 9525.88 | 50.85 | 484390.998 | 9525.88 | 50.85 | 484390.998 | 9525.88 | 0 | 0 | 9525.88 | 0 | 9525.88 | 0 | 67.614 | 644082.8503 | 9525.88 | 0 | 7.88 | 9518 | 1263 | 88665.1986 | Kgs | 545832.924 | 0 | 0 | 0 | 484390.998
Steel Bars 16mm - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 4966.46 | 50.85 | 252544.491 | 4966.46 | 50.85 | 252544.491 | 4966.46 | 0 | 0 | 4966.46 | 0 | 4966.46 | 0 | 64.251 | 319100.0215 | 4966.46 | 0 | 37.46 | 4929 | 1263 | 88665.1986 | Kgs | 270423.747 | 0 | 0 | 0 | 252544.491
Steel Bars 16mm - Kgs | Wing 1 - 6th Slab (Pod. NTA) Wing 1 P6 to Pod. level Column | STEEL | 1281.01 | 50.85 | 65139.3585 | 0 | 0 | 0 | 0 | 1281.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281.01 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1281.01 | 65139.3585
Steel Bars 16mm - Kgs | Wing 1 - 6th Slab (Pod. Bld.) Wing 1 P6 to Pod. level Column | STEEL | 4872.43 | 50.85 | 247763.0655 | 4872.43 | 50.85 | 247763.0655 | 4872.43 | 0 | 0 | 4872.43 | 0 | 4681.01 | 191.42 | 62.3111 | 291678.8822 | 4681.01 | 0 | 18.43 | 4854 | 1263 | 88665.1986 | Kgs | 247185.4141 | 247185.4141 | 191.42 | 0 | 577.6514
Steel Bars 16mm - Kgs | Wing-3 Substructure Steel For Column Up to Plinth | STEEL | 826.558 | 50.85 | 42030.4743 | 0 | 0 | 0 | 0 | 826.558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826.558 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 826.558 | 42030.4743
Steel Bars 16mm - Kgs | Wing-3 Substructure Steel For Footing | STEEL | 4020.22 | 50.85 | 204428.187 | 4020.22 | 50.85 | 204428.187 | 4020.22 | 0 | 0 | 4020.22 | 0 | 3136.42 | 883.8 | 58.646 | 183938.4873 | 3136.42 | 0 | 4020.22 | 0 | 1263 | 88665.1986 | Kgs | 155880.074 | 0 | 883.8 | 0 | 204428.187
Steel Bars 16mm - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 3988.3 | 50.85 | 202805.055 | 3988.3 | 50.85 | 202805.055 | 3988.3 | 0 | 0 | 3988.3 | 0 | 3988.3 | 0 | 58.646 | 233897.8418 | 2488.3 | 1500 | 196.3 | 3792 | 1263 | 88665.1986 | Kgs | 123668.51 | 0 | 0 | 0 | 202805.055
Steel Bars 16mm - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 3878 | 50.85 | 197196.3 | 3878 | 50.85 | 197196.3 | 3878 | 0 | 0 | 3878 | 0 | 3878 | 0 | 63.2421 | 245252.8638 | 3878 | 0 | 10 | 3868 | 1263 | 88665.1986 | Kgs | 207841.41 | 207841.41 | 0 | 0 | -10645.11
Steel Bars 16mm - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 3475 | 50.85 | 176703.75 | 3475 | 50.85 | 176703.75 | 3475 | 0 | 0 | 3475 | 0 | 3475 | 0 | 63.2421 | 219766.2975 | 3475 | 0 | 62 | 3413 | 1263 | 88665.1986 | Kgs | 186242.625 | 186242.625 | 0 | 0 | -9538.875
Steel Bars 16mm - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 3475 | 50.85 | 176703.75 | 0 | 0 | 0 | 0 | 3475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 3413 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3475 | 176703.75
Steel Bars 16mm - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 3475 | 50.85 | 176703.75 | 0 | 0 | 0 | 0 | 3475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 3413 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3475 | 176703.75
Steel Bars 16mm - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 3475 | 50.85 | 176703.75 | 0 | 0 | 0 | 0 | 3475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 3413 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3475 | 176703.75
Steel Bars 16mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 3238 | 50.85 | 164652.3 | 0 | 0 | 0 | 0 | 3238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 3185 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3238 | 164652.3
Steel Bars 16mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 3701 | 50.85 | 188195.85 | 0 | 0 | 0 | 0 | 3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 3641 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3701 | 188195.85
Steel Bars 16mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3622 | 50.85 | 184178.7 | 0 | 0 | 0 | 0 | 3622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 3413 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3622 | 184178.7
Steel Bars 16mm - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 3780 | 50.85 | 192213 | 0 | 0 | 0 | 0 | 3780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3780 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3780 | 192213
Steel Bars 16mm - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 2914.07 | 50.85 | 148180.4595 | 2914.07 | 50.85 | 148180.4595 | 2914.07 | 0 | 0 | 2914.07 | 0 | 2914.07 | 0 | 63.2421 | 184291.9063 | 2914.07 | 0 | 32.07 | 2882 | 1263 | 88665.1986 | Kgs | 156179.5817 | 156179.5817 | 0 | 0 | -7999.1222
Steel Bars 16mm - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 3014.31 | 50.85 | 153277.6635 | 2808.58 | 50.85 | 142816.293 | 2808.58 | 205.73 | 0 | 2808.58 | 0 | 0 | 2808.58 | 0 | 0 | 0 | 0 | 139.31 | 2875 | 1263 | 88665.1986 | Kgs | 0 | 0 | 2808.58 | 205.73 | 153277.6635
Steel Bars 16mm - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 3014.31 | 50.85 | 153277.6635 | 0 | 0 | 0 | 0 | 3014.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.31 | 2958 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3014.31 | 153277.6635
Steel Bars 16mm - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 3014.31 | 50.85 | 153277.6635 | 0 | 0 | 0 | 0 | 3014.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.31 | 2958 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3014.31 | 153277.6635
Steel Bars 16mm - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 3014.31 | 50.85 | 153277.6635 | 2875.28 | 50.85 | 146207.988 | 2875.28 | 139.03 | 0 | 2875.28 | 0 | 2875.28 | 0 | 58.646 | 168623.6709 | 2875.28 | 0 | 56.31 | 2958 | 1263 | 88665.1986 | Kgs | 142901.416 | 0 | 0 | 139.03 | 153277.6635
Steel Bars 16mm - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 3216.116 | 50.85 | 163539.4986 | 2914.96 | 50.85 | 148225.716 | 2914.96 | 301.156 | 0 | 2914.96 | 0 | 2914.96 | 0 | 62.3111 | 181634.3641 | 2914.96 | 0 | 334.116 | 2882 | 1263 | 88665.1986 | Kgs | 153927.3778 | 153927.3778 | 0 | 301.156 | 9612.1208
Steel Bars 16mm - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 4825.17 | 50.85 | 245359.8945 | 4665 | 50.85 | 237215.25 | 4665 | 160.17 | 0 | 4665 | 0 | 4665 | 0 | 62.3111 | 290681.2815 | 4665 | 0 | 198.17 | 4627 | 1263 | 88665.1986 | Kgs | 246339.99 | 246339.99 | 0 | 160.17 | -980.0955
Steel Bars 16mm - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 4825.17 | 50.85 | 245359.8945 | 3903.91 | 50.85 | 198513.8235 | 3903.91 | 921.26 | 0 | 3903.91 | 0 | 3903.91 | 0 | 62.3111 | 243256.9264 | 3903.91 | 0 | 957.17 | 3868 | 1263 | 88665.1986 | Kgs | 206149.8715 | 206149.8715 | 0 | 921.26 | 39210.023
Steel Bars 16mm - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 4825.17 | 50.85 | 245359.8945 | 4172.91 | 50.85 | 212192.4735 | 4172.91 | 652.26 | 0 | 4172.91 | 0 | 4172.91 | 0 | 62.3111 | 260018.6123 | 4172.91 | 0 | 654.17 | 4171 | 1263 | 88665.1986 | Kgs | 220354.6855 | 220354.6855 | 0 | 652.26 | 25005.209
Steel Bars 16mm - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 4825.17 | 50.85 | 245359.8945 | 4440.48 | 50.85 | 225798.408 | 4440.48 | 384.69 | 0 | 4440.48 | 0 | 4440.48 | 0 | 62.3111 | 276691.1933 | 4440.48 | 0 | 426.17 | 4399 | 1263 | 88665.1986 | Kgs | 234483.9869 | 234483.9869 | 0 | 384.69 | 10875.9076
Steel Bars 16mm - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 3216.116 | 50.85 | 163539.4986 | 3152.03 | 50.85 | 160280.7255 | 3046.38 | 64.086 | 105.65 | 3046.38 | 105.65 | 3046.38 | 0 | 62.65 | 190855.7359 | 3046.38 | 0 | 941.116 | 2275 | 1263 | 88665.1986 | Kgs | 161742.1196 | 161742.1196 | 105.65 | 64.086 | 1797.379
Steel Bars 16mm - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 3296.98 | 50.85 | 167651.433 | 3296.98 | 50.85 | 167651.433 | 3296.98 | 0 | 0 | 3296.98 | 0 | 3296.98 | 0 | 63.2421 | 208507.9389 | 3296.98 | 0 | 262.98 | 3034 | 1263 | 88665.1986 | Kgs | 176701.6431 | 176701.6431 | 0 | 0 | -9050.2101
Steel Bars 16mm - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 3296.98 | 50.85 | 167651.433 | 3296.98 | 50.85 | 167651.433 | 3296.98 | 0 | 0 | 3296.98 | 0 | 3296.98 | 0 | 63.2421 | 208507.9389 | 3296.98 | 0 | 35.98 | 3261 | 1263 | 88665.1986 | Kgs | 176701.6431 | 176701.6431 | 0 | 0 | -9050.2101
Steel Bars 16mm - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 3894 | 50.85 | 198009.9 | 0 | 0 | 0 | 0 | 3894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3894 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3894 | 198009.9
Steel Bars 16mm - Kgs | Non Tower Area Footing Steel | STEEL | 2192 | 50.85 | 111463.2 | 284.32 | 50.85 | 14457.672 | 284.32 | 1907.68 | 0 | 284.32 | 0 | 284.32 | 0 | 62.3111 | 17716.292 | 284.32 | 0 | 68 | 2124 | 1263 | 88665.1986 | Kgs | 15013.8019 | 15013.8019 | 0 | 1907.68 | 96449.3981
Steel Bars 16mm - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 3265 | 50.85 | 166025.25 | 0 | 0 | 0 | 0 | 3265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3265 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3265 | 166025.25
Steel Bars 16mm - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 2627 | 50.85 | 133582.95 | 0 | 0 | 0 | 0 | 2627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2627 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2627 | 133582.95
Steel Bars 16mm - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 2462 | 50.85 | 125192.7 | 0 | 0 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2462 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2462 | 125192.7
Steel Bars 16mm - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 2297 | 50.85 | 116802.45 | 0 | 0 | 0 | 0 | 2297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2297 | 116802.45
Steel Bars 16mm - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 2462 | 50.85 | 125192.7 | 0 | 0 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2462 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2462 | 125192.7
Steel Bars 16mm - Kgs | Wing 1-15th Floor To 16th Floor Column, LW Steel | STEEL | 2739 | 50.85 | 139278.15 | 0 | 0 | 0 | 0 | 2739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2739 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2739 | 139278.15
Steel Bars 16mm - Kgs | Wing 1-16th Floor To 17th Floor Column, LW Steel | STEEL | 3259 | 50.85 | 165720.15 | 0 | 0 | 0 | 0 | 3259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3259 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3259 | 165720.15
Steel Bars 16mm - Kgs | Wing 1-17th Floor To 18th Floor Column, LW Steel | STEEL | 3329 | 50.85 | 169279.65 | 0 | 0 | 0 | 0 | 3329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3329 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3329 | 169279.65
Steel Bars 16mm - Kgs | Wing 1-20th Floor To 21st Floor Column, LW Steel | STEEL | 4684 | 50.85 | 238181.4 | 0 | 0 | 0 | 0 | 4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4684 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 4684 | 238181.4
Steel Bars 16mm - Kgs | Wing 1-23rd Floor To 24th Floor Column, LW Steel | STEEL | 2523 | 50.85 | 128294.55 | 0 | 0 | 0 | 0 | 2523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2523 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2523 | 128294.55
Steel Bars 16mm - Kgs | Wing 1-26th Floor To 27th Floor Column, LW Steel | STEEL | 1567 | 50.85 | 79681.95 | 0 | 0 | 0 | 0 | 1567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1567 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1567 | 79681.95
Steel Bars 16mm - Kgs | Wing 1-27th Floor To 28th Floor Column, LW Steel | STEEL | 1567 | 50.85 | 79681.95 | 0 | 0 | 0 | 0 | 1567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1567 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1567 | 79681.95
Steel Bars 16mm - Kgs | Wing 1-28th Floor To Terrace Floor Column, LW Steel | STEEL | 1510 | 50.85 | 76783.5 | 0 | 0 | 0 | 0 | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1510 | 76783.5
Steel Bars 16mm - Kgs | Wing 1-24th Floor To 25th Floor Column, LW Steel | STEEL | 2523 | 50.85 | 128294.55 | 0 | 0 | 0 | 0 | 2523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2523 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2523 | 128294.55
Steel Bars 16mm - Kgs | Wing 1-25th Floor To 26th Floor Column, LW Steel | STEEL | 2523 | 50.85 | 128294.55 | 0 | 0 | 0 | 0 | 2523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2523 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2523 | 128294.55
Steel Bars 16mm - Kgs | Wing 1-21st Floor To 22nd Floor Column, LW Steel | STEEL | 4684 | 50.85 | 238181.4 | 0 | 0 | 0 | 0 | 4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4684 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 4684 | 238181.4
Steel Bars 16mm - Kgs | Wing 1-22nd Floor To 23rd Floor Column, LW Steel | STEEL | 4684 | 50.85 | 238181.4 | 0 | 0 | 0 | 0 | 4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4684 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 4684 | 238181.4
Steel Bars 16mm - Kgs | Wing 1-18th Floor To 19th Floor Column, LW Steel | STEEL | 3329 | 50.85 | 169279.65 | 0 | 0 | 0 | 0 | 3329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3329 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3329 | 169279.65
Steel Bars 16mm - Kgs | Wing 1-19th Floor To 20th Floor Column, LW Steel | STEEL | 3329 | 50.85 | 169279.65 | 0 | 0 | 0 | 0 | 3329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3329 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3329 | 169279.65
Steel Bars 16mm - Kgs | Wing-3 Substructure (M) Steel For Tie Beam | STEEL | 1597.34 | 50.85 | 81224.739 | 0 | 0 | 0 | 0 | 1597.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1597.34 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1597.34 | 81224.739
Steel Bars 16mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.28 | 2806 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.28 | 2806 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509.28 | 1366 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 2875.28 | 50.85 | 146207.988 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.28 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2875.28 | 146207.988
Steel Bars 16mm - Kgs | Non Tower Area Column Upto Plinth | STEEL | 692.04 | 50.85 | 35190.234 | 692.04 | 50.85 | 35190.234 | 692.04 | 0 | 0 | 692.04 | 0 | 0 | 692.04 | 0 | 0 | 0 | 0 | 9.04 | 683 | 1263 | 88665.1986 | Kgs | 0 | 0 | 692.04 | 0 | 35190.234
Steel Bars 16mm - Kgs | Non Tower Area Intermediate Tie Beam Steel | STEEL | 2434.88 | 50.85 | 123813.648 | 0 | 0 | 0 | 0 | 2434.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917.88 | 1517 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2434.88 | 123813.648
Steel Bars 16mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 1182.28 | 50.85 | 60118.938 | 0 | 0 | 0 | 0 | 1182.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.28 | 1149 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1182.28 | 60118.938
Steel Bars 16mm - Kgs | Wing 2 . P5 To P6 Column &amp;amp; Lift Steel | STEEL | 4440.48 | 50.85 | 225798.408 | 0 | 0 | 0 | 0 | 4440.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.48 | 4399 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 4440.48 | 225798.408
Steel Bars 16mm - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 3296.98 | 50.85 | 167651.433 | 0 | 0 | 0 | 0 | 3296.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.98 | 3261 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3296.98 | 167651.433
Steel Bars 16mm - Kgs | Pile Cap | STEEL | 1498.54 | 50.85 | 76200.759 | 0 | 0 | 0 | 0 | 1498.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1498.54 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1498.54 | 76200.759
Steel Bars 16mm - Kgs | Non Tower Area Plinth Beam Steel | STEEL | 3261.08 | 50.85 | 165825.918 | 0 | 0 | 0 | 0 | 3261.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3033.08 | 228 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 3261.08 | 165825.918
Steel Bars 16mm - Kgs | Non Tower Area Column Ground To P1 Slab Steel | STEEL | 339.06 | 50.85 | 17241.201 | 0 | 0 | 0 | 0 | 339.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.06 | 152 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 339.06 | 17241.201
Steel Bars 16mm - Kgs | Non Tower Area Column 1st Slab P1 To 2nd Slab P2 Steel | STEEL | 339 | 50.85 | 17238.15 | 0 | 0 | 0 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 303 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 339 | 17238.15
Steel Bars 16mm - Kgs | Non Tower Area Pile Cap Steel | STEEL | 1376.6 | 50.85 | 70000.11 | 0 | 0 | 0 | 0 | 1376.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6 | 1365 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1376.6 | 70000.11
Steel Bars 16mm - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 300 | 50.85 | 15255 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 228 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 300 | 15255
Steel Bars 16mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 478.16 | 50.85 | 24314.436 | 0 | 0 | 0 | 0 | 478.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.16 | 455 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 478.16 | 24314.436
Steel Bars 16mm - Kgs | Wing 2 . P6 To Podium Column & Lift Steel | STEEL | 4373.99 | 50.85 | 222417.3915 | 0 | 0 | 0 | 0 | 4373.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4373.99 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 4373.99 | 222417.3915
Steel Bars 16mm - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 2918.25 | 50.85 | 148393.0125 | 0 | 0 | 0 | 0 | 2918.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2918.25 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 2918.25 | 148393.0125
Steel Bars 16mm - Kgs | Phase 2 Weigh Bridge Steel | STEEL | 308.46 | 50.85 | 15685.191 | 0 | 0 | 0 | 0 | 308.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.46 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 308.46 | 15685.191
Steel Bars 16mm - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 1636.85 | 50.85 | 83233.8225 | 0 | 0 | 0 | 0 | 1636.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636.85 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 1636.85 | 83233.8225
Steel Bars 16mm - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 300 | 50.85 | 15255 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 1263 | 88665.1986 | Kgs | 0 | 0 | 0 | 300 | 15255
Steel Bars 20mm - Kgs | Wing-1 Substructure Footing Steel-(Kgs) | STEEL | 32535.76 | 50.85 | 1654443.396 | 32535.76 | 50.85 | 1654443.396 | 32535.76 | 0 | 0 | 32535.76 | 0 | 32535.76 | 0 | 64.5625 | 2100589.0634 | 32535.76 | 0 | 0 | 32535.76 | 6448.66 | 419333.0124 | Kgs | 1780160.2268 | 3204027.8416 | 0 | 0 | -1549584.4456
Steel Bars 20mm - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 31084.06 | 50.85 | 1580624.451 | 31116.27 | 50.85 | 1582262.3295 | 31084.06 | -32.21 | 32.21 | 31084.06 | 32.21 | 31084.06 | 0 | 67.7872 | 2107102.0185 | 31084.06 | 0 | 0.822 | 31083.238 | 6448.66 | 419333.0124 | Kgs | 1785679.777 | 4812773.6434 | 32.21 | -32.21 | -3232149.1924
Steel Bars 20mm - Kgs | Wing-1 Parking Column Upto Grid Slab Steel | STEEL | 6855.02 | 50.85 | 348577.767 | 6855.02 | 50.85 | 348577.767 | 6855.02 | 0 | 0 | 6855.02 | 0 | 6855.02 | 0 | 81.7315 | 560271.0671 | 6855.02 | 0 | 0.02 | 6855 | 6448.66 | 419333.0124 | Kgs | 474806.1053 | 2374030.5264 | 0 | 0 | -2025452.7594
Steel Bars 20mm - Kgs | Wing-1 Parking Footing Steel | STEEL | 1342.96 | 50.85 | 68289.516 | 1342.96 | 50.85 | 68289.516 | 1342.96 | 0 | 0 | 1342.96 | 0 | 1342.96 | 0 | 62.658 | 84147.1877 | 1342.96 | 0 | 0.96 | 1342 | 6448.66 | 419333.0124 | Kgs | 71311.176 | 142622.352 | 0 | 0 | -74332.836
Steel Bars 20mm - Kgs | Wing-1 Substructure Tie Beam Steel | STEEL | 505.41 | 50.85 | 25700.0985 | 505.41 | 50.85 | 25700.0985 | 505.41 | 0 | 0 | 505.41 | 0 | 505.41 | 0 | 81.619 | 41251.0571 | 505.41 | 0 | 0 | 505.41 | 6448.66 | 419333.0124 | Kgs | 34958.5308 | 169191.1728 | 0 | 0 | -143491.0743
Steel Bars 20mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 283.85 | 50.85 | 14433.7725 | 283.85 | 50.85 | 14433.7725 | 283.85 | 0 | 0 | 283.85 | 0 | 283.85 | 0 | 81.7315 | 23199.4863 | 283.85 | 0 | 0 | 283.85 | 6448.66 | 419333.0124 | Kgs | 19660.5864 | 98302.932 | 0 | 0 | -83869.1595
Steel Bars 20mm - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 6736.579 | 50.85 | 342555.0422 | 6736.579 | 50.85 | 342555.0422 | 6736.579 | 0 | 0 | 6736.579 | 0 | 6736.579 | 0 | 73.4766 | 494980.7341 | 6736.579 | 0 | 0.579 | 6736 | 6448.66 | 419333.0124 | Kgs | 419475.2525 | 1508397.7532 | 0 | 0 | -1165842.711
Steel Bars 20mm - Kgs | Wing-1 Substructure RCC Plinth Beam - Steel | STEEL | 1330.466 | 50.85 | 67654.1961 | 1330.466 | 50.85 | 67654.1961 | 1330.466 | 0 | 0 | 1330.466 | 0 | 1330.466 | 0 | 75.9027 | 100986.0007 | 1330.466 | 0 | 0.876 | 1329.59 | 6448.66 | 419333.0124 | Kgs | 85581.3274 | 28836.5584 | 0 | 0 | 38817.6377
Steel Bars 20mm - Kgs | Wing-2 Substructure Footing Reinforcement Steel | STEEL | 40190 | 50.85 | 2043661.5 | 40055 | 50.85 | 2036796.75 | 40055 | 135 | 0 | 40055 | 0 | 40055 | 0 | 71.3839 | 2859280.7178 | 40055 | 0 | 0 | 40190 | 6448.66 | 419333.0124 | Kgs | 2423119.3567 | 2796466.059 | 0 | 135 | -752804.559
Steel Bars 20mm - Kgs | Wing 1 - P2 to P3 Level Column steel | STEEL | 4098.03 | 50.85 | 208384.8255 | 4098.03 | 50.85 | 208384.8255 | 4098.03 | 0 | 0 | 4098.03 | 0 | 4098.03 | 0 | 62.6084 | 256571.2952 | 4098.03 | 0 | 74.03 | 4024 | 6448.66 | 419333.0124 | Kgs | 217433.301 | 434866.602 | 0 | 0 | -226481.7765
Steel Bars 20mm - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 7598.95 | 50.85 | 386406.6075 | 7598.95 | 50.85 | 386406.6075 | 7598.95 | 0 | 0 | 7598.95 | 0 | 7598.95 | 0 | 66.5931 | 506037.8386 | 7598.95 | 0 | 0.95 | 7598 | 6448.66 | 419333.0124 | Kgs | 428845.8453 | 1226808.126 | 0 | 0 | -840401.5185
Steel Bars 20mm - Kgs | Wing -2 Parking Column upto GF Slab - Steel | STEEL | 1071.39 | 50.85 | 54480.1815 | 1071.39 | 50.85 | 54480.1815 | 1071.39 | 0 | 0 | 1071.39 | 0 | 1071.39 | 0 | 62.54 | 67004.7306 | 1071.39 | 0 | 1071.39 | 0 | 6448.66 | 419333.0124 | Kgs | 56783.67 | 113567.34 | 0 | 0 | -59087.1585
Steel Bars 20mm - Kgs | Wing-1 Substructure RCC Piling work - Steel | STEEL | 6530.68 | 50.85 | 332085.078 | 6430.68 | 50.85 | 327000.078 | 6430.68 | 100 | 0 | 6430.68 | 0 | 6430.68 | 0 | 66.67 | 428733.4356 | 6430.68 | 0 | 6530.68 | 0 | 6448.66 | 419333.0124 | Kgs | 363333.42 | 0 | 0 | 100 | 332085.078
Steel Bars 20mm - Kgs | Wing-2 Substructure RCC Tie Beam Reinforcement Steel | STEEL | 81.81 | 50.85 | 4160.0385 | 81.81 | 50.85 | 4160.0385 | 81.81 | 0 | 0 | 81.81 | 0 | 81.81 | 0 | 67.3623 | 5510.9127 | 81.81 | 0 | 81.81 | 0 | 6448.66 | 419333.0124 | Kgs | 4670.265 | 3486 | 0 | 0 | 674.0385
Steel Bars 20mm - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 5000 | 50.85 | 254250 | 5000 | 50.85 | 254250 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 66.5394 | 332696.993 | 5000 | 0 | 52 | 4948 | 6448.66 | 419333.0124 | Kgs | 281946.7467 | 803547.3 | 0 | 0 | -549297.3
Steel Bars 20mm - Kgs | Wing-2 Substructure RCC Plinth Beam Reinforcement Steel | STEEL | 105.67 | 50.85 | 5373.3195 | 105.67 | 50.85 | 5373.3195 | 105.67 | 0 | 0 | 105.67 | 0 | 105.67 | 0 | 62.54 | 6608.6018 | 105.67 | 0 | 16.67 | 89 | 6448.66 | 419333.0124 | Kgs | 5600.51 | 11201.02 | 0 | 0 | -5827.7005
Steel Bars 20mm - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 3311.98 | 50.85 | 168414.183 | 3311.98 | 50.85 | 168414.183 | 3311.98 | 0 | 0 | 3311.98 | 0 | 2866.57 | 445.41 | 62.54 | 179275.2878 | 2866.57 | 0 | 21.98 | 3290 | 6448.66 | 419333.0124 | Kgs | 151928.21 | 303856.42 | 445.41 | 0 | -135442.237
Steel Bars 20mm - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 2866.57 | 50.85 | 145765.0845 | 2866.57 | 50.85 | 145765.0845 | 2866.57 | 0 | 0 | 2866.57 | 0 | 2266.57 | 600 | 67.9195 | 153944.2219 | 2266.57 | 0 | 51.57 | 2815 | 6448.66 | 419333.0124 | Kgs | 130461.205 | 174300 | 600 | 0 | -28534.9155
Steel Bars 20mm - Kgs | Wing 1 - P3 to P4 Level Column Steel | STEEL | 4917.62 | 50.85 | 250060.977 | 4917.62 | 50.85 | 250060.977 | 4917.62 | 0 | 0 | 4917.62 | 0 | 4917.62 | 0 | 68.558 | 337142.192 | 4917.62 | 0 | 28.62 | 4889 | 6448.66 | 419333.0124 | Kgs | 285713.722 | 571427.444 | 0 | 0 | -321366.467
Steel Bars 20mm - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 2866.57 | 50.85 | 145765.0845 | 2866.57 | 50.85 | 145765.0845 | 2866.57 | 0 | 0 | 2866.57 | 0 | 2266.57 | 600 | 67.9195 | 153944.2219 | 2266.57 | 0 | 20.57 | 2846 | 6448.66 | 419333.0124 | Kgs | 130461.205 | 174300 | 600 | 0 | -28534.9155
Steel Bars 20mm - Kgs | Wing 1 - P4 to P5 Level Column Steel | STEEL | 4917.62 | 50.85 | 250060.977 | 4917.62 | 50.85 | 250060.977 | 4917.62 | 0 | 0 | 4917.62 | 0 | 4198.843 | 718.777 | 67.5854 | 283780.3966 | 4198.843 | 0 | 58.62 | 4859 | 6448.66 | 419333.0124 | Kgs | 240491.8615 | 236556.474 | 718.777 | 0 | 13504.503
Steel Bars 20mm - Kgs | Wing 1 - P5 to P6 level Column Steel | STEEL | 4917.62 | 50.85 | 250060.977 | 4917.62 | 50.85 | 250060.977 | 4917.62 | 0 | 0 | 4917.62 | 0 | 4917.62 | 0 | 66.67 | 327857.7254 | 4917.62 | 0 | 27.62 | 4890 | 6448.66 | 419333.0124 | Kgs | 277845.53 | 0 | 0 | 0 | 250060.977
Steel Bars 20mm - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 2866.57 | 50.85 | 145765.0845 | 2866.57 | 50.85 | 145765.0845 | 2866.57 | 0 | 0 | 2866.57 | 0 | 766.57 | 2100 | 66.67 | 51107.2219 | 766.57 | 0 | 22.57 | 2844 | 6448.66 | 419333.0124 | Kgs | 43311.205 | 0 | 2100 | 0 | 145765.0845
Steel Bars 20mm - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 4362 | 50.85 | 221807.7 | 0 | 0 | 0 | 0 | 4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 4296 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 4362 | 221807.7
Steel Bars 20mm - Kgs | Wing 02 Piling work for Non Tower area | STEEL | 1696.5 | 50.85 | 86267.025 | 1696.5 | 50.85 | 86267.025 | 1696.5 | 0 | 0 | 1696.5 | 0 | 0 | 1696.5 | 0 | 0 | 0 | 0 | 8.5 | 1688 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 1696.5 | 0 | 86267.025
Steel Bars 20mm - Kgs | Wing 1 - 6th Slab (Pod. NTA) Wing 1 P6 to Pod. level Column | STEEL | 1031.18 | 50.85 | 52435.503 | 0 | 0 | 0 | 0 | 1031.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031.18 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1031.18 | 52435.503
Steel Bars 20mm - Kgs | Wing 1 - 6th Slab (Pod. Bld.) Wing 1 P6 to Pod. level Column | STEEL | 5818.78 | 50.85 | 295884.963 | 5818.78 | 50.85 | 295884.963 | 5818.78 | 0 | 0 | 5818.78 | 0 | 0 | 5818.78 | 0 | 0 | 0 | 0 | 13.78 | 5805 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 5818.78 | 0 | 295884.963
Steel Bars 20mm - Kgs | Wing-3 Substructure Steel For Footing | STEEL | 29729.63 | 50.85 | 1511751.6855 | 0 | 0 | 0 | 0 | 29729.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28840.63 | 889 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 29729.63 | 1511751.6855
Steel Bars 20mm - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 3787.78 | 50.85 | 192608.613 | 3787.78 | 50.85 | 192608.613 | 3787.78 | 0 | 0 | 3787.78 | 0 | 0 | 3787.78 | 0 | 0 | 0 | 0 | 24.78 | 3763 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 3787.78 | 0 | 192608.613
Steel Bars 20mm - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 14651 | 50.85 | 745003.35 | 14651 | 50.85 | 745003.35 | 14651 | 0 | 0 | 14651 | 0 | 0 | 14651 | 0 | 0 | 0 | 0 | 75 | 14576 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 14651 | 0 | 745003.35
Steel Bars 20mm - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 10361 | 50.85 | 526856.85 | 0 | 0 | 0 | 0 | 10361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | 7111 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 10361 | 526856.85
Steel Bars 20mm - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 10361 | 50.85 | 526856.85 | 9406 | 50.85 | 478295.1 | 9406 | 955 | 0 | 9406 | 0 | 0 | 9406 | 0 | 0 | 0 | 0 | 50 | 10311 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 9406 | 955 | 526856.85
Steel Bars 20mm - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 10361 | 50.85 | 526856.85 | 8708 | 50.85 | 442801.8 | 8708 | 1653 | 0 | 8708 | 0 | 2000 | 6708 | 58.646 | 117292 | 2000 | 0 | 73 | 10288 | 6448.66 | 419333.0124 | Kgs | 99400 | 0 | 6708 | 1653 | 526856.85
Steel Bars 20mm - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 10361 | 50.85 | 526856.85 | 8910 | 50.85 | 453073.5 | 8910 | 1451 | 0 | 8910 | 0 | 0 | 8910 | 0 | 0 | 0 | 0 | 50 | 10311 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 8910 | 1451 | 526856.85
Steel Bars 20mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 8542 | 50.85 | 434360.7 | 8542 | 50.85 | 434360.7 | 6510 | 0 | 2032 | 6510 | 2032 | 6510 | 0 | 58.646 | 381785.46 | 6510 | 0 | 8 | 8534 | 6448.66 | 419333.0124 | Kgs | 323547 | 0 | 2032 | 0 | 434360.7
Steel Bars 20mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 8175 | 50.85 | 415698.75 | 0 | 0 | 0 | 0 | 8175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8175 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 8175 | 415698.75
Steel Bars 20mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 7550 | 50.85 | 383917.5 | 0 | 0 | 0 | 0 | 7550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417 | 6133 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 7550 | 383917.5
Steel Bars 20mm - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 7936 | 50.85 | 403545.6 | 0 | 0 | 0 | 0 | 7936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7936 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 7936 | 403545.6
Steel Bars 20mm - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 4113.5 | 50.85 | 209171.475 | 4113.5 | 50.85 | 209171.475 | 4113.5 | 0 | 0 | 4113.5 | 0 | 0 | 4113.5 | 0 | 0 | 0 | 0 | 24.5 | 4089 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 4113.5 | 0 | 209171.475
Steel Bars 20mm - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 4184.97 | 50.85 | 212805.7245 | 3946.33 | 50.85 | 200670.8805 | 3946.33 | 238.64 | 0 | 3946.33 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 240.82 | 3944.15 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 3946.33 | 238.64 | 212805.7245
Steel Bars 20mm - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 4184.97 | 50.85 | 212805.7245 | 3946.33 | 50.85 | 200670.8805 | 3946.33 | 238.64 | 0 | 3946.33 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 6.97 | 4178 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 3946.33 | 238.64 | 212805.7245
Steel Bars 20mm - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 4184.97 | 50.85 | 212805.7245 | 4184.97 | 50.85 | 212805.7245 | 4184.97 | 0 | 0 | 4184.97 | 0 | 237.686 | 3947.284 | 62.54 | 14864.8824 | 237.686 | 0 | 6.97 | 4178 | 6448.66 | 419333.0124 | Kgs | 12597.358 | 12597.358 | 3947.284 | 0 | 200208.3665
Steel Bars 20mm - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 4184.97 | 50.85 | 212805.7245 | 4184.97 | 50.85 | 212805.7245 | 4184.97 | 0 | 0 | 4184.97 | 0 | 4184.97 | 0 | 62.54 | 261728.0238 | 4184.97 | 0 | 67.97 | 4117 | 6448.66 | 419333.0124 | Kgs | 221803.41 | 221803.41 | 0 | 0 | -8997.6855
Steel Bars 20mm - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 1598.954 | 50.85 | 81306.8109 | 1598.954 | 50.85 | 81306.8109 | 1598.954 | 0 | 0 | 1598.954 | 0 | 79.314 | 1519.64 | 62.54 | 4960.2976 | 79.314 | 0 | 87.954 | 1511 | 6448.66 | 419333.0124 | Kgs | 4203.642 | 4203.642 | 1519.64 | 0 | 77103.1689
Steel Bars 20mm - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 3354.67 | 50.85 | 170584.9695 | 3354.67 | 50.85 | 170584.9695 | 3354.67 | 0 | 0 | 3354.67 | 0 | 0 | 3354.67 | 0 | 0 | 0 | 0 | 65.67 | 3289 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 3354.67 | 0 | 170584.9695
Steel Bars 20mm - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 3354.67 | 50.85 | 170584.9695 | 0 | 0 | 0 | 0 | 3354.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576.67 | 1778 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3354.67 | 170584.9695
Steel Bars 20mm - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 3354.67 | 50.85 | 170584.9695 | 0 | 0 | 0 | 0 | 3354.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161.67 | 2193 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3354.67 | 170584.9695
Steel Bars 20mm - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 3354.67 | 50.85 | 170584.9695 | 3354.67 | 50.85 | 170584.9695 | 3354.67 | 0 | 0 | 3354.67 | 0 | 3354.67 | 0 | 62.54 | 209801.0618 | 3354.67 | 0 | 539.67 | 2815 | 6448.66 | 419333.0124 | Kgs | 177797.51 | 177797.51 | 0 | 0 | -7212.5405
Steel Bars 20mm - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 2255.99 | 50.85 | 114717.0915 | 0 | 0 | 0 | 0 | 2255.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477.99 | 1778 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 2255.99 | 114717.0915
Steel Bars 20mm - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 2134.36 | 50.85 | 108532.206 | 0 | 0 | 0 | 0 | 2134.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.36 | 2133 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 2134.36 | 108532.206
Steel Bars 20mm - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 2134.36 | 50.85 | 108532.206 | 2134.36 | 50.85 | 108532.206 | 2134.36 | 0 | 0 | 2134.36 | 0 | 2134.36 | 0 | 62.54 | 133482.8744 | 2084.36 | 50 | 1.36 | 2133 | 6448.66 | 419333.0124 | Kgs | 110471.08 | 110471.08 | 0 | 0 | -1938.874
Steel Bars 20mm - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 7642 | 50.85 | 388595.7 | 0 | 0 | 0 | 0 | 7642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7642 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 7642 | 388595.7
Steel Bars 20mm - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 7414 | 50.85 | 377001.9 | 0 | 0 | 0 | 0 | 7414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7414 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 7414 | 377001.9
Steel Bars 20mm - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 8208 | 50.85 | 417376.8 | 0 | 0 | 0 | 0 | 8208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8208 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 8208 | 417376.8
Steel Bars 20mm - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 7956 | 50.85 | 404562.6 | 0 | 0 | 0 | 0 | 7956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7956 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 7956 | 404562.6
Steel Bars 20mm - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 7859 | 50.85 | 399630.15 | 0 | 0 | 0 | 0 | 7859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7859 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 7859 | 399630.15
Steel Bars 20mm - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 9008 | 50.85 | 458056.8 | 0 | 0 | 0 | 0 | 9008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9008 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 9008 | 458056.8
Steel Bars 20mm - Kgs | Wing 1-15th Floor To 16th Floor Column, LW Steel | STEEL | 8995 | 50.85 | 457395.75 | 0 | 0 | 0 | 0 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8995 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 8995 | 457395.75
Steel Bars 20mm - Kgs | Wing 1-16th Floor To 17th Floor Column, LW Steel | STEEL | 7672 | 50.85 | 390121.2 | 0 | 0 | 0 | 0 | 7672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7672 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 7672 | 390121.2
Steel Bars 20mm - Kgs | Wing 1-17th Floor To 18th Floor Column, LW Steel | STEEL | 5841 | 50.85 | 297014.85 | 0 | 0 | 0 | 0 | 5841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5841 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 5841 | 297014.85
Steel Bars 20mm - Kgs | Wing 1-20th Floor To 21st Floor Column, LW Steel | STEEL | 1665 | 50.85 | 84665.25 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1665 | 84665.25
Steel Bars 20mm - Kgs | Wing 1-23rd Floor To 24th Floor Column, LW Steel | STEEL | 1665 | 50.85 | 84665.25 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1665 | 84665.25
Steel Bars 20mm - Kgs | Wing 1-26th Floor To 27th Floor Column, LW Steel | STEEL | 1626 | 50.85 | 82682.1 | 0 | 0 | 0 | 0 | 1626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1626 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1626 | 82682.1
Steel Bars 20mm - Kgs | Wing 1-27th Floor To 28th Floor Column, LW Steel | STEEL | 1626 | 50.85 | 82682.1 | 0 | 0 | 0 | 0 | 1626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1626 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1626 | 82682.1
Steel Bars 20mm - Kgs | Wing 1-28th Floor To Terrace Floor Column, LW Steel | STEEL | 1626 | 50.85 | 82682.1 | 0 | 0 | 0 | 0 | 1626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1626 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1626 | 82682.1
Steel Bars 20mm - Kgs | Wing 1-24th Floor To 25th Floor Column, LW Steel | STEEL | 1665 | 50.85 | 84665.25 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1665 | 84665.25
Steel Bars 20mm - Kgs | Wing 1-25th Floor To 26th Floor Column, LW Steel | STEEL | 1665 | 50.85 | 84665.25 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1665 | 84665.25
Steel Bars 20mm - Kgs | Wing 1-21st Floor To 22nd Floor Column, LW Steel | STEEL | 1665 | 50.85 | 84665.25 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1665 | 84665.25
Steel Bars 20mm - Kgs | Wing 1-22nd Floor To 23rd Floor Column, LW Steel | STEEL | 1665 | 50.85 | 84665.25 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1665 | 84665.25
Steel Bars 20mm - Kgs | Wing 1-18th Floor To 19th Floor Column, LW Steel | STEEL | 5841 | 50.85 | 297014.85 | 0 | 0 | 0 | 0 | 5841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5841 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 5841 | 297014.85
Steel Bars 20mm - Kgs | Wing 1-19th Floor To 20th Floor Column, LW Steel | STEEL | 5841 | 50.85 | 297014.85 | 0 | 0 | 0 | 0 | 5841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5841 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 5841 | 297014.85
Steel Bars 20mm - Kgs | Wing-3 Substructure (M) Steel For Tie Beam | STEEL | 776.07 | 50.85 | 39463.1595 | 0 | 0 | 0 | 0 | 776.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.07 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 776.07 | 39463.1595
Steel Bars 20mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.33 | 3912 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.33 | 3911 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 3946.33 | 50.85 | 200670.8805 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.33 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 3946.33 | 200670.8805
Steel Bars 20mm - Kgs | Non Tower Area Column Upto Plinth | STEEL | 574.66 | 50.85 | 29221.461 | 574.66 | 50.85 | 29221.461 | 574.66 | 0 | 0 | 574.66 | 0 | 0 | 574.66 | 0 | 0 | 0 | 0 | 41.66 | 533 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 574.66 | 0 | 29221.461
Steel Bars 20mm - Kgs | Wing-3 Parking NTA Piling | STEEL | 7190.4 | 50.85 | 365631.84 | 4314.24 | 50.85 | 219379.104 | 4314.24 | 2876.16 | 0 | 4314.24 | 0 | 0 | 4314.24 | 0 | 0 | 0 | 0 | 79.4 | 7111 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 4314.24 | 2876.16 | 365631.84
Steel Bars 20mm - Kgs | Non Tower Area NTA Piling | STEEL | 2396.8 | 50.85 | 121877.28 | 719.04 | 50.85 | 36563.184 | 719.04 | 1677.76 | 0 | 719.04 | 0 | 0 | 719.04 | 0 | 0 | 0 | 0 | 1241.8 | 1155 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 719.04 | 1677.76 | 121877.28
Steel Bars 20mm - Kgs | Wing.1 Substructure RCC Pile Cap work - Steel | STEEL | 6530.68 | 50.85 | 332085.078 | 0 | 0 | 0 | 0 | 6530.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6530.68 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 6530.68 | 332085.078
Steel Bars 20mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 821.82 | 50.85 | 41789.547 | 0 | 0 | 0 | 0 | 821.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 821.82 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 821.82 | 41789.547
Steel Bars 20mm - Kgs | Wing 2 . P5 To P6 Column &amp;amp; Lift Steel | STEEL | 1588.15 | 50.85 | 80757.4275 | 0 | 0 | 0 | 0 | 1588.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.15 | 1511 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1588.15 | 80757.4275
Steel Bars 20mm - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 2134.36 | 50.85 | 108532.206 | 0 | 0 | 0 | 0 | 2134.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.36 | 2133 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 2134.36 | 108532.206
Steel Bars 20mm - Kgs | Compound Wall Pile Foundation | STEEL | 6265.43 | 50.85 | 318597.1155 | 0 | 0 | 0 | 0 | 6265.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6265.43 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 6265.43 | 318597.1155
Steel Bars 20mm - Kgs | Non Tower Area Column Ground To P1 Slab Steel | STEEL | 293.93 | 50.85 | 14946.3405 | 0 | 0 | 0 | 0 | 293.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.93 | 293 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 293.93 | 14946.3405
Steel Bars 20mm - Kgs | Non Tower Area Column 1st Slab P1 To 2nd Slab P2 Steel | STEEL | 292.84 | 50.85 | 14890.914 | 0 | 0 | 0 | 0 | 292.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.84 | 178 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 292.84 | 14890.914
Steel Bars 20mm - Kgs | Non Tower Area Pile Cap Steel | STEEL | 2150.9 | 50.85 | 109373.265 | 0 | 0 | 0 | 0 | 2150.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995.9 | 1155 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 2150.9 | 109373.265
Steel Bars 20mm - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 2633.22 | 50.85 | 133899.237 | 0 | 0 | 0 | 0 | 2633.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321.22 | 2312 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 2633.22 | 133899.237
Steel Bars 20mm - Kgs | Wing 2 . P6 To Podium Column & Lift Steel | STEEL | 1575.85 | 50.85 | 80131.9725 | 0 | 0 | 0 | 0 | 1575.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575.85 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1575.85 | 80131.9725
Steel Bars 20mm - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 1841.54 | 50.85 | 93642.309 | 0 | 0 | 0 | 0 | 1841.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1841.54 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 1841.54 | 93642.309
Steel Bars 20mm - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 858.25 | 50.85 | 43642.0125 | 0 | 0 | 0 | 0 | 858.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 858.25 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 858.25 | 43642.0125
Steel Bars 20mm - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 2633.22 | 50.85 | 133899.237 | 0 | 0 | 0 | 0 | 2633.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2633.22 | 0 | 6448.66 | 419333.0124 | Kgs | 0 | 0 | 0 | 2633.22 | 133899.237
Steel Bars 32mm - Kgs | Wing-1 Substructure Footing Steel-(Kgs) | STEEL | 1505.659 | 50.85 | 76562.7602 | 1503.74 | 50.85 | 76465.179 | 1462.68 | 1.919 | 41.06 | 1462.68 | 41.06 | 1462.68 | 0 | 65.2982 | 95510.3788 | 1462.68 | 0 | 42.979 | 1462.68 | 2711 | 174043.42 | Kgs | 80940.999 | 142686.048 | 41.06 | 1.919 | -66123.2878
Steel Bars 32mm - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 328.62 | 50.85 | 16710.327 | 328.62 | 50.85 | 16710.327 | 328.62 | 0 | 0 | 328.62 | 0 | 328.62 | 0 | 64.7369 | 21273.8495 | 328.62 | 0 | 61.3 | 267.32 | 2711 | 174043.42 | Kgs | 18028.686 | 33298.952 | 0 | 0 | -16588.625
Steel Bars 32mm - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 29.12 | 50.85 | 1480.752 | 29.12 | 50.85 | 1480.752 | 29.12 | 0 | 0 | 29.12 | 0 | 29.12 | 0 | 79.591 | 2317.6899 | 29.12 | 0 | 29.12 | 0 | 2711 | 174043.42 | Kgs | 1964.144 | 0 | 0 | 0 | 1480.752
Steel Bars 32mm - Kgs | Wing-2 Substructure Footing Reinforcement Steel | STEEL | 4989.6 | 50.85 | 253721.16 | 5050 | 50.85 | 256792.5 | 4989.6 | -60.4 | 60.4 | 4989.6 | 60.4 | 4989.6 | 0 | 71.8654 | 358579.4065 | 4989.6 | 0 | 5.6 | 4984 | 2711 | 174043.42 | Kgs | 303880.853 | 346112.364 | 60.4 | -60.4 | -92391.204
Steel Bars 32mm - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 1982.66 | 50.85 | 100818.261 | 1982.66 | 50.85 | 100818.261 | 1982.66 | 0 | 0 | 1982.66 | 0 | 1982.66 | 0 | 69.6584 | 138108.9063 | 1982.66 | 0 | 0.66 | 1982 | 2711 | 174043.42 | Kgs | 117041.446 | 234082.892 | 0 | 0 | -133264.631
Steel Bars 32mm - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 1212 | 50.85 | 61630.2 | 1212 | 50.85 | 61630.2 | 1212 | 0 | 0 | 1212 | 0 | 1212 | 0 | 68.6996 | 83263.9152 | 1212 | 0 | 0 | 1212 | 2711 | 174043.42 | Kgs | 70562.64 | 141125.28 | 0 | 0 | -79495.08
Steel Bars 32mm - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 1212 | 50.85 | 61630.2 | 1212 | 50.85 | 61630.2 | 1212 | 0 | 0 | 1212 | 0 | 1212 | 0 | 68.6996 | 83263.9152 | 1212 | 0 | 0 | 1212 | 2711 | 174043.42 | Kgs | 70562.64 | 141125.28 | 0 | 0 | -79495.08
Steel Bars 32mm - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 1212 | 50.85 | 61630.2 | 1212 | 50.85 | 61630.2 | 1212 | 0 | 0 | 1212 | 0 | 1212 | 0 | 68.6996 | 83263.9152 | 1212 | 0 | 0 | 1212 | 2711 | 174043.42 | Kgs | 70562.64 | 141125.28 | 0 | 0 | -79495.08
Steel Bars 32mm - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 1212 | 50.85 | 61630.2 | 1212 | 50.85 | 61630.2 | 1212 | 0 | 0 | 1212 | 0 | 1212 | 0 | 68.6996 | 83263.9152 | 1212 | 0 | 67 | 1145 | 2711 | 174043.42 | Kgs | 70562.64 | 141125.28 | 0 | 0 | -79495.08
Steel Bars 32mm - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 1212 | 50.85 | 61630.2 | 1212 | 50.85 | 61630.2 | 1212 | 0 | 0 | 1212 | 0 | 1069.32 | 142.68 | 68.864 | 73637.6782 | 1069.32 | 0 | 0 | 1212 | 2711 | 174043.42 | Kgs | 62404.812 | 9375.624 | 142.68 | 0 | 52254.576
Steel Bars 32mm - Kgs | Wing-3 Substructure Steel For Footing | STEEL | 1463.59 | 50.85 | 74423.5515 | 0 | 0 | 0 | 0 | 1463.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1463.59 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 1463.59 | 74423.5515
Steel Bars 32mm - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 2233.2 | 50.85 | 113558.22 | 2233.2 | 50.85 | 113558.22 | 2233.2 | 0 | 0 | 2233.2 | 0 | 0 | 2233.2 | 0 | 0 | 0 | 0 | 0.2 | 2233 | 2711 | 174043.42 | Kgs | 0 | 0 | 2233.2 | 0 | 113558.22
Steel Bars 32mm - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 11341 | 50.85 | 576689.85 | 11341 | 50.85 | 576689.85 | 11341 | 0 | 0 | 11341 | 0 | 0 | 11341 | 0 | 0 | 0 | 0 | 0 | 11341 | 2711 | 174043.42 | Kgs | 0 | 0 | 11341 | 0 | 576689.85
Steel Bars 32mm - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 6940 | 50.85 | 352899 | 6940 | 50.85 | 352899 | 6940 | 0 | 0 | 6940 | 0 | 0 | 6940 | 0 | 0 | 0 | 0 | 0 | 6940 | 2711 | 174043.42 | Kgs | 0 | 0 | 6940 | 0 | 352899
Steel Bars 32mm - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 7547 | 50.85 | 383764.95 | 7547 | 50.85 | 383764.95 | 7547 | 0 | 0 | 7547 | 0 | 0 | 7547 | 0 | 0 | 0 | 0 | 39 | 7508 | 2711 | 174043.42 | Kgs | 0 | 0 | 7547 | 0 | 383764.95
Steel Bars 32mm - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 7130 | 50.85 | 362560.5 | 7130 | 50.85 | 362560.5 | 7130 | 0 | 0 | 7130 | 0 | 0 | 7130 | 0 | 0 | 0 | 0 | 1 | 7129 | 2711 | 174043.42 | Kgs | 0 | 0 | 7130 | 0 | 362560.5
Steel Bars 32mm - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 6940 | 50.85 | 352899 | 6372 | 50.85 | 324016.2 | 6372 | 568 | 0 | 6372 | 0 | 0 | 6372 | 0 | 0 | 0 | 0 | 38 | 6902 | 2711 | 174043.42 | Kgs | 0 | 0 | 6372 | 568 | 352899
Steel Bars 32mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 5651 | 50.85 | 287353.35 | 5000 | 50.85 | 254250 | 5000 | 651 | 0 | 5000 | 0 | 5000 | 0 | 64.31 | 321550 | 4920 | 80 | 39 | 5612 | 2711 | 174043.42 | Kgs | 268140 | 268140 | 0 | 651 | 19213.35
Steel Bars 32mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 4096 | 50.85 | 208281.6 | 0 | 0 | 0 | 0 | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4096 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 4096 | 208281.6
Steel Bars 32mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 3034 | 50.85 | 154278.9 | 0 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 2653 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 3034 | 154278.9
Steel Bars 32mm - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 1593 | 50.85 | 81004.05 | 0 | 0 | 0 | 0 | 1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1593 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 1593 | 81004.05
Steel Bars 32mm - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 574.88 | 50.85 | 29232.648 | 574.88 | 0 | 0 | 574.88 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0.88 | 574 | 2711 | 174043.42 | Kgs | 0 | 0 | 574.88 | 0 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 621.91 | 50.85 | 31624.1235 | 574.88 | 50.85 | 29232.648 | 574.88 | 47.03 | 0 | 574.88 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 90.91 | 531 | 2711 | 174043.42 | Kgs | 0 | 0 | 574.88 | 47.03 | 31624.1235
Steel Bars 32mm - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 621.91 | 50.85 | 31624.1235 | 574.88 | 50.85 | 29232.648 | 574.88 | 47.03 | 0 | 574.88 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 47.91 | 574 | 2711 | 174043.42 | Kgs | 0 | 0 | 574.88 | 47.03 | 31624.1235
Steel Bars 32mm - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 621.91 | 50.85 | 31624.1235 | 574.88 | 50.85 | 29232.648 | 574.88 | 47.03 | 0 | 574.88 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 14.91 | 607 | 2711 | 174043.42 | Kgs | 0 | 0 | 574.88 | 47.03 | 31624.1235
Steel Bars 32mm - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 621.91 | 50.85 | 31624.1235 | 0 | 0 | 0 | 0 | 621.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.91 | 607 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 621.91 | 31624.1235
Steel Bars 32mm - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 1736.42 | 50.85 | 88296.957 | 1568.38 | 50.85 | 79752.123 | 1568.38 | 168.04 | 0 | 1568.38 | 0 | 0 | 1568.38 | 0 | 0 | 0 | 0 | 219.42 | 1517 | 2711 | 174043.42 | Kgs | 0 | 0 | 1568.38 | 168.04 | 88296.957
Steel Bars 32mm - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 577.29 | 50.85 | 29355.1965 | 417.19 | 50.85 | 21214.1115 | 417.19 | 160.1 | 0 | 417.19 | 0 | 0 | 417.19 | 0 | 0 | 0 | 0 | 198.29 | 379 | 2711 | 174043.42 | Kgs | 0 | 0 | 417.19 | 160.1 | 29355.1965
Steel Bars 32mm - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 577.29 | 50.85 | 29355.1965 | 227.56 | 50.85 | 11571.426 | 227.56 | 349.73 | 0 | 227.56 | 0 | 0 | 227.56 | 0 | 0 | 0 | 0 | 350.29 | 227 | 2711 | 174043.42 | Kgs | 0 | 0 | 227.56 | 349.73 | 29355.1965
Steel Bars 32mm - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 577.29 | 50.85 | 29355.1965 | 0 | 0 | 0 | 0 | 577.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350.29 | 227 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 577.29 | 29355.1965
Steel Bars 32mm - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 577.29 | 100 | 57729 | 0 | 0 | 0 | 0 | 577.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577.29 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 577.29 | 57729
Steel Bars 32mm - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 1736.42 | 50.85 | 88296.957 | 1568.38 | 50.85 | 79752.123 | 1568.38 | 168.04 | 0 | 1568.38 | 0 | 0 | 1568.38 | 0 | 0 | 0 | 0 | 902.42 | 834 | 2711 | 174043.42 | Kgs | 0 | 0 | 1568.38 | 168.04 | 88296.957
Steel Bars 32mm - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 1736.38 | 50.85 | 88294.923 | 0 | 0 | 0 | 0 | 1736.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219.38 | 1517 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 1736.38 | 88294.923
Steel Bars 32mm - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 1568.38 | 50.85 | 79752.123 | 0 | 0 | 0 | 0 | 1568.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.38 | 1517 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 1568.38 | 79752.123
Steel Bars 32mm - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 1479 | 50.85 | 75207.15 | 0 | 0 | 0 | 0 | 1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1479 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 1479 | 75207.15
Steel Bars 32mm - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 1820 | 50.85 | 92547 | 0 | 0 | 0 | 0 | 1820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1820 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 1820 | 92547
Steel Bars 32mm - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 2654 | 50.85 | 134955.9 | 0 | 0 | 0 | 0 | 2654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2654 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 2654 | 134955.9
Steel Bars 32mm - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 872 | 50.85 | 44341.2 | 0 | 0 | 0 | 0 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 872 | 44341.2
Steel Bars 32mm - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 872 | 50.85 | 44341.2 | 0 | 0 | 0 | 0 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 872 | 44341.2
Steel Bars 32mm - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 416 | 50.85 | 21153.6 | 0 | 0 | 0 | 0 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 416 | 21153.6
Steel Bars 32mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.88 | 532 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.88 | 531 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 574.88 | 50.85 | 29232.648 | 0 | 0 | 0 | 0 | 574.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.88 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 574.88 | 29232.648
Steel Bars 32mm - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 1568.38 | 50.85 | 79752.123 | 0 | 0 | 0 | 0 | 1568.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568.38 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 1568.38 | 79752.123
Steel Bars 32mm - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 189.12 | 100 | 18912 | 0 | 0 | 0 | 0 | 189.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.12 | 152 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 189.12 | 18912
Steel Bars 32mm - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 595.94 | 50.85 | 30303.549 | 0 | 0 | 0 | 0 | 595.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.94 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 595.94 | 30303.549
Steel Bars 32mm - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 957.76 | 100 | 95776 | 0 | 0 | 0 | 0 | 957.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957.76 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 957.76 | 95776
Steel Bars 32mm - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 189.12 | 100 | 18912 | 0 | 0 | 0 | 0 | 189.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.12 | 0 | 2711 | 174043.42 | Kgs | 0 | 0 | 0 | 189.12 | 18912
Steel Bars 8mm - Kgs | Labour Camp Work | STEEL | 78 | 53 | 4134 | 78 | 53 | 4134 | 78 | 0 | 0 | 78 | 0 | 78 | 0 | 51.729 | 4034.862 | 78 | 0 | 0 | 78 | 24188.88 | 1529685.0138 | Kgs | 4034.862 | 0 | 0 | 0 | 4134
Steel Bars 8mm - Kgs | Wing-1 Substructure Column Upto Grid Slab Steel | STEEL | 40914.76 | 50.85 | 2080515.546 | 40914.76 | 50.85 | 2080515.546 | 40858.06 | 0 | 56.7 | 40858.06 | 56.7 | 40858.06 | 0 | 69.0806 | 2822497.4201 | 40858.06 | 0 | 2.13 | 40912.63 | 24188.88 | 1529685.0138 | Kgs | 2391947.0926 | 6479732.1352 | 56.7 | 0 | -4399216.5892
Steel Bars 8mm - Kgs | Wing-1 Parking Column Upto Grid Slab Steel | STEEL | 5488.28 | 50.85 | 279079.038 | 5488.28 | 50.85 | 279079.038 | 5488.28 | 0 | 0 | 5488.28 | 0 | 5488.28 | 0 | 73.4853 | 403307.8285 | 5488.28 | 0 | 0 | 5488.28 | 24188.88 | 1529685.0138 | Kgs | 341786.3433 | 738955.5763 | 0 | 0 | -459876.5383
Steel Bars 8mm - Kgs | Weigh Bridge Beam Steel | STEEL | 74.99 | 53 | 3974.47 | 74.99 | 53 | 3974.47 | 74.99 | 0 | 0 | 74.99 | 0 | 74.99 | 0 | 75.2582 | 5643.6134 | 74.99 | 0 | 74.99 | 0 | 24188.88 | 1529685.0138 | Kgs | 4782.7245 | 17442.7676 | 0 | 0 | -13468.2976
Steel Bars 8mm - Kgs | Weigh Bridge Column Steel | STEEL | 60.52 | 53 | 3207.56 | 60.52 | 53 | 3207.56 | 60.52 | 0 | 0 | 60.52 | 0 | 60.52 | 0 | 67.6376 | 4093.4276 | 60.52 | 0 | 60.52 | 0 | 24188.88 | 1529685.0138 | Kgs | 3469.0064 | 6938.0128 | 0 | 0 | -3730.4528
Steel Bars 8mm - Kgs | Wing-1 Substructure Tie Beam Steel | STEEL | 2556.734 | 50.85 | 130009.9239 | 2556.734 | 50.85 | 130009.9239 | 2556.734 | 0 | 0 | 2556.734 | 0 | 2556.734 | 0 | 82.9339 | 212039.9138 | 2556.734 | 0 | 0.004 | 2556.73 | 24188.88 | 1529685.0138 | Kgs | 179694.9244 | 898473.273 | 0 | 0 | -768463.3491
Steel Bars 8mm - Kgs | Wing-1 Parking Tie Beam Steel | STEEL | 299.38 | 50.85 | 15223.473 | 299.38 | 50.85 | 15223.473 | 299.38 | 0 | 0 | 299.38 | 0 | 299.38 | 0 | 82.9339 | 24828.751 | 299.38 | 0 | 0 | 299.38 | 24188.88 | 1529685.0138 | Kgs | 21041.3245 | 105206.6227 | 0 | 0 | -89983.1497
Steel Bars 8mm - Kgs | Wing 1 -1st Slab (P2 Lvl) Column steel (P1 to P2) | STEEL | 9846 | 50.85 | 500669.1 | 9846 | 50.85 | 500669.1 | 9846 | 0 | 0 | 9846 | 0 | 9846 | 0 | 68.5585 | 675026.9249 | 9846 | 0 | 151 | 9695 | 24188.88 | 1529685.0138 | Kgs | 572056.716 | 851107.467 | 0 | 0 | -350438.367
Steel Bars 8mm - Kgs | Wing-1 Substructure RCC Plinth Beam - Steel | STEEL | 1759.17 | 50.85 | 89453.7945 | 1669.034 | 50.85 | 84870.3789 | 1669.034 | 90.136 | 0 | 1669.034 | 0 | 1639.034 | 30 | 79.3721 | 130093.5956 | 1639.034 | 0 | 135.08 | 1624.09 | 24188.88 | 1529685.0138 | Kgs | 110248.8098 | 1639.0836 | 30 | 90.136 | 87814.7109
Steel Bars 8mm - Kgs | Wing-1 Substructure Lift Pit RCC - Steel | STEEL | 554.13 | 50.85 | 28177.5105 | 554.13 | 50.85 | 28177.5105 | 554.13 | 0 | 0 | 554.13 | 0 | 554.13 | 0 | 78.4318 | 43461.3924 | 554.13 | 0 | 4.13 | 550 | 24188.88 | 1529685.0138 | Kgs | 36831.6885 | 5742.576 | 0 | 0 | 22434.9345
Steel Bars 8mm - Kgs | UGWT RCC Wall (Paradi) Steel | STEEL | 4259.18 | 53 | 225736.54 | 4259.18 | 53 | 225736.54 | 4259.18 | 0 | 0 | 4259.18 | 0 | 4259.18 | 0 | 69.9782 | 298049.8994 | 4259.18 | 0 | 68.336 | 4190.844 | 24188.88 | 1529685.0138 | Kgs | 252584.6685 | 366013.242 | 0 | 0 | -140276.702
Steel Bars 8mm - Kgs | UGWT RCC Bottom Slab | STEEL | 6888.27 | 53 | 365078.31 | 6888.27 | 53 | 365078.31 | 6888.27 | 0 | 0 | 6888.27 | 0 | 6888.27 | 0 | 79.591 | 548244.2976 | 6888.27 | 0 | 4067.27 | 2821 | 24188.88 | 1529685.0138 | Kgs | 464613.8115 | 0 | 0 | 0 | 365078.31
Steel Bars 8mm - Kgs | Wing 1 - P2 to P3 Level Column steel | STEEL | 11251.95 | 50.85 | 572161.6575 | 11251.95 | 50.85 | 572161.6575 | 11251.95 | 0 | 0 | 11251.95 | 0 | 11251.95 | 0 | 67.2229 | 756388.8795 | 11251.95 | 0 | 368.95 | 10883 | 24188.88 | 1529685.0138 | Kgs | 641007.525 | 1282015.05 | 0 | 0 | -709853.3925
Steel Bars 8mm - Kgs | Wing 1 - RCC Retaining wall Steel | STEEL | 924.48 | 50.85 | 47009.808 | 924.48 | 50.85 | 47009.808 | 924.48 | 0 | 0 | 924.48 | 0 | 924.48 | 0 | 66.906 | 61853.2589 | 924.48 | 0 | 331.98 | 592.5 | 24188.88 | 1529685.0138 | Kgs | 52418.016 | 104836.032 | 0 | 0 | -57826.224
Steel Bars 8mm - Kgs | Wing-2 Substructure Columns upto Plinth - Steel | STEEL | 50765.07 | 50.85 | 2581403.8095 | 50765.07 | 50.85 | 2581403.8095 | 50765.07 | 0 | 0 | 50765.07 | 0 | 50765.07 | 0 | 67.0246 | 3402509.6364 | 50765.07 | 0 | 3070.07 | 47695 | 24188.88 | 1529685.0138 | Kgs | 2883482.23 | 6106050.7944 | 0 | 0 | -3524646.9849
Steel Bars 8mm - Kgs | Wing -2 Parking Column upto GF Slab - Steel | STEEL | 11186.4 | 50.85 | 568828.44 | 6186.4 | 50.85 | 314578.44 | 6186.4 | 5000 | 0 | 6186.4 | 0 | 6186.4 | 0 | 68.1552 | 421635.24 | 6186.4 | 0 | 9245.4 | 1941 | 24188.88 | 1529685.0138 | Kgs | 357318 | 0 | 0 | 5000 | 568828.44
Steel Bars 8mm - Kgs | Wing-1 Substructure RCC Piling work - Steel | STEEL | 1176.04 | 50.85 | 59801.634 | 1176.04 | 50.85 | 59801.634 | 1176.04 | 0 | 0 | 1176.04 | 0 | 1176.04 | 0 | 69.738 | 82014.6775 | 1176.04 | 0 | 1176.04 | 0 | 24188.88 | 1529685.0138 | Kgs | 69503.964 | 139007.928 | 0 | 0 | -79206.294
Steel Bars 8mm - Kgs | Wing-2 Substructure RCC Tie Beam Reinforcement Steel | STEEL | 1663.82 | 50.85 | 84605.247 | 1663.82 | 50.85 | 84605.247 | 1663.82 | 0 | 0 | 1663.82 | 0 | 1663.82 | 0 | 71.0414 | 118200.1848 | 1663.82 | 0 | 51.82 | 1612 | 24188.88 | 1529685.0138 | Kgs | 100169.6481 | 64603.8648 | 0 | 0 | 20001.3822
Steel Bars 8mm - Kgs | Wing -2 Parking RCC Tie Beam (Non Tower area) Reinforcement | STEEL | 430.04 | 50.85 | 21867.534 | 430.04 | 50.85 | 21867.534 | 430.04 | 0 | 0 | 430.04 | 0 | 430.04 | 0 | 68.8984 | 29629.0495 | 430.04 | 0 | 27.04 | 403 | 24188.88 | 1529685.0138 | Kgs | 25109.364 | 50218.728 | 0 | 0 | -28351.194
Steel Bars 8mm - Kgs | Wing 1 - 1st Slab (P2 Lvl) Steel | STEEL | 10403.55 | 50.85 | 529020.5175 | 10403.55 | 50.85 | 529020.5175 | 10403.55 | 0 | 0 | 10403.55 | 0 | 10403.55 | 0 | 69.6724 | 724840.003 | 10403.55 | 0 | 1701.55 | 8702 | 24188.88 | 1529685.0138 | Kgs | 614271.0843 | 1072691.7875 | 0 | 0 | -543671.27
Steel Bars 8mm - Kgs | Wing-2 Substructure RCC Plinth Beam Reinforcement Steel | STEEL | 2091.16 | 50.85 | 106335.486 | 2091.16 | 50.85 | 106335.486 | 2091.16 | 0 | 0 | 2091.16 | 0 | 2091.16 | 0 | 71.6791 | 149892.4668 | 2091.16 | 0 | 76.16 | 2015 | 24188.88 | 1529685.0138 | Kgs | 127027.5142 | 0 | 0 | 0 | 106335.486
Steel Bars 8mm - Kgs | Wing 1 - P3 level (2nd) Slab & Beam Steel | STEEL | 13883.48 | 50.85 | 705974.958 | 13883.48 | 50.85 | 705974.958 | 13883.48 | 0 | 0 | 13883.48 | 0 | 13883.48 | 0 | 68.8277 | 955568.2178 | 13883.48 | 0 | 825.48 | 13058 | 24188.88 | 1529685.0138 | Kgs | 809803.5744 | 402234.6 | 0 | 0 | 303740.358
Steel Bars 8mm - Kgs | Wing 1 - P4 level (3rd) Slab & Beam Steel | STEEL | 12058 | 50.85 | 613149.3 | 10403 | 50.85 | 528992.55 | 10403 | 1655 | 0 | 10403 | 0 | 10403 | 0 | 70.677 | 735252.6154 | 10403 | 0 | 2552 | 9506 | 24188.88 | 1529685.0138 | Kgs | 623095.4368 | 407415.4092 | 0 | 1655 | 205733.8908
Steel Bars 8mm - Kgs | Wing 1 - P3 to P4 Level Column Steel | STEEL | 9846 | 50.85 | 500669.1 | 9846 | 50.85 | 500669.1 | 9846 | 0 | 0 | 9846 | 0 | 9846 | 0 | 68.6996 | 676416.2616 | 9846 | 0 | 1621 | 8225 | 24188.88 | 1529685.0138 | Kgs | 573234.12 | 1146468.24 | 0 | 0 | -645799.14
Steel Bars 8mm - Kgs | Wing 1 - P5 Level (4th) Slab & Beam Steel | STEEL | 12058 | 50.85 | 613149.3 | 8600 | 50.85 | 437310 | 8600 | 3458 | 0 | 8600 | 0 | 8600 | 0 | 64.9568 | 558628.52 | 8600 | 0 | 1260 | 10798 | 24188.88 | 1529685.0138 | Kgs | 473414 | 0 | 0 | 3458 | 613149.3
Steel Bars 8mm - Kgs | Wing 1 - P4 to P5 Level Column Steel | STEEL | 9846 | 50.85 | 500669.1 | 8000 | 50.85 | 406800 | 7080.64 | 1846 | 919.36 | 7080.64 | 919.36 | 7080.64 | 0 | 65.402 | 463087.8206 | 7080.64 | 0 | 1109 | 8737 | 24188.88 | 1529685.0138 | Kgs | 392447.3056 | 0 | 919.36 | 1846 | 500669.1
Steel Bars 8mm - Kgs | Wing -1 Ramp from P1 to P2 - Steel | STEEL | 1655.07 | 50.85 | 84160.3095 | 1655.07 | 50.85 | 84160.3095 | 1655.07 | 0 | 0 | 1655.07 | 0 | 1655.07 | 0 | 68.6996 | 113702.647 | 1655.07 | 0 | 688.07 | 967 | 24188.88 | 1529685.0138 | Kgs | 96358.1754 | 192716.3508 | 0 | 0 | -108556.0413
Steel Bars 8mm - Kgs | Wing 1 Ramp from P2 to P3 - Steel | STEEL | 1655.07 | 50.85 | 84160.3095 | 1525.206 | 50.85 | 77556.7251 | 1525.206 | 129.864 | 0 | 1525.206 | 0 | 1525.206 | 0 | 69.738 | 106364.816 | 1525.206 | 0 | 43.07 | 1612 | 24188.88 | 1529685.0138 | Kgs | 90139.6746 | 180279.3492 | 0 | 129.864 | -96119.0397
Steel Bars 8mm - Kgs | Wing 1 Ramp from P3 to P4 - Steel | STEEL | 1655.07 | 50.85 | 84160.3095 | 0 | 0 | 0 | 0 | 1655.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 1655 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1655.07 | 84160.3095
Steel Bars 8mm - Kgs | Wing 1 Ramp from P4 to P5 - Steel | STEEL | 1655.07 | 50.85 | 84160.3095 | 0 | 0 | 0 | 0 | 1655.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788.07 | 867 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1655.07 | 84160.3095
Steel Bars 8mm - Kgs | Goel House Gym Work | STEEL | 894.47 | 53 | 47406.91 | 894.47 | 53 | 47406.91 | 894.47 | 0 | 0 | 894.47 | 0 | 894.47 | 0 | 68.1561 | 60963.5495 | 894.47 | 0 | 249.47 | 645 | 24188.88 | 1529685.0138 | Kgs | 51664.025 | 0 | 0 | 0 | 47406.91
Steel Bars 8mm - Kgs | Wing 1 - P5 to P6 level Column Steel | STEEL | 9846 | 50.85 | 500669.1 | 3000 | 50.85 | 152550 | 3000 | 6846 | 0 | 3000 | 0 | 3000 | 0 | 67.673 | 203019 | 3000 | 0 | 14 | 9832 | 24188.88 | 1529685.0138 | Kgs | 172050 | 0 | 0 | 6846 | 500669.1
Steel Bars 8mm - Kgs | Wing 1- P6 Level (5th) Slab & Beam Steel | STEEL | 12058 | 50.85 | 613149.3 | 4058 | 50.85 | 206349.3 | 4058 | 8000 | 0 | 4058 | 0 | 4058 | 0 | 62.8822 | 255175.9676 | 4058 | 0 | 51 | 12007 | 24188.88 | 1529685.0138 | Kgs | 216250.82 | 0 | 0 | 8000 | 613149.3
Steel Bars 8mm - Kgs | Wing 01 Piling work for Non Tower area | STEEL | 745 | 50.85 | 37883.25 | 0 | 0 | 0 | 0 | 745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 592 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 745 | 37883.25
Steel Bars 8mm - Kgs | Wing 02 Piling work for Non Tower area | STEEL | 289.75 | 50.85 | 14733.7875 | 289.75 | 50.85 | 14733.7875 | 289.75 | 0 | 0 | 289.75 | 0 | 0 | 289.75 | 0 | 0 | 0 | 0 | 128.75 | 161 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 289.75 | 0 | 14733.7875
Steel Bars 8mm - Kgs | Wing 1 - 6th Slab (Pod. NTA) Wing 1 P6 to Pod. level Column | STEEL | 1766.88 | 50.85 | 89845.848 | 0 | 0 | 0 | 0 | 1766.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1766.88 | 89845.848
Steel Bars 8mm - Kgs | Wing 1 - 6th Slab (Pod. Bld.) Wing 1 P6 to Pod. level Column | STEEL | 13387.45 | 50.85 | 680751.8325 | 0 | 0 | 0 | 0 | 13387.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.45 | 12813 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 13387.45 | 680751.8325
Steel Bars 8mm - Kgs | Wing-3 Substructure Steel For Column Up to Plinth | STEEL | 896.117 | 50.85 | 45567.5495 | 0 | 0 | 0 | 0 | 896.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896.117 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 896.117 | 45567.5495
Steel Bars 8mm - Kgs | Wing 1 Ramp from P5 to P6 - Steel | STEEL | 1655.07 | 50.85 | 84160.3095 | 0 | 0 | 0 | 0 | 1655.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 1655 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1655.07 | 84160.3095
Steel Bars 8mm - Kgs | Wing 1 - 6th Slab (Podium Floor Lvl) Slab & Beam Steel | STEEL | 10506.55 | 50.85 | 534258.0675 | 0 | 0 | 0 | 0 | 10506.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.55 | 10395 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 10506.55 | 534258.0675
Steel Bars 8mm - Kgs | Wing 1 - Podium To 1st Floor Column, LW Steel | STEEL | 8060 | 50.85 | 409851 | 8060 | 50.85 | 409851 | 8060 | 0 | 0 | 8060 | 0 | 0 | 8060 | 0 | 0 | 0 | 0 | 83 | 7977 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 8060 | 0 | 409851
Steel Bars 8mm - Kgs | Wing 1-1st Floor To 2nd Floor Column, LW Steel | STEEL | 8155 | 50.85 | 414681.75 | 0 | 0 | 0 | 0 | 8155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 8058 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8155 | 414681.75
Steel Bars 8mm - Kgs | Wing 1-2nd Floor To 3rd Floor Column, LW Steel | STEEL | 8182 | 50.85 | 416054.7 | 8182 | 50.85 | 416054.7 | 8182 | 0 | 0 | 8182 | 0 | 0 | 8182 | 0 | 0 | 0 | 0 | 45 | 8137 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 8182 | 0 | 416054.7
Steel Bars 8mm - Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | STEEL | 8241.02 | 50.85 | 419055.867 | 8182 | 50.85 | 416054.7 | 8182 | 59.02 | 0 | 8182 | 0 | 0 | 8182 | 0 | 0 | 0 | 0 | 102.02 | 8139 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 8182 | 59.02 | 419055.867
Steel Bars 8mm - Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | STEEL | 8182 | 50.85 | 416054.7 | 8182 | 50.85 | 416054.7 | 6733.12 | 0 | 1448.88 | 6733.12 | 1448.88 | 6733.12 | 0 | 59.872 | 403125.3606 | 6733.12 | 0 | 43 | 8139 | 24188.88 | 1529685.0138 | Kgs | 341631.7757 | 0 | 1448.88 | 0 | 416054.7
Steel Bars 8mm - Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | STEEL | 8166 | 50.85 | 415241.1 | 0 | 0 | 0 | 0 | 8166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 8140 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8166 | 415241.1
Steel Bars 8mm - Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | STEEL | 8166 | 50.85 | 415241.1 | 0 | 0 | 0 | 0 | 8166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 8139 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8166 | 415241.1
Steel Bars 8mm - Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | STEEL | 8131 | 50.85 | 413461.35 | 0 | 0 | 0 | 0 | 8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4988 | 3143 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8131 | 413461.35
Steel Bars 8mm - Kgs | Wing 1-8th Floor To 9th Floor Column, LW Steel | STEEL | 8076 | 50.85 | 410664.6 | 8076 | 50.85 | 410664.6 | 8076 | 0 | 0 | 8076 | 0 | 0 | 8076 | 0 | 0 | 0 | 0 | 8076 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 8076 | 0 | 410664.6
Steel Bars 8mm - Kgs | Wing 1 . 7th Slab (1st Floor) Shear Wall Steel | STEEL | 6336 | 50.85 | 322185.6 | 0 | 0 | 0 | 0 | 6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 6286 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 6336 | 322185.6
Steel Bars 8mm - Kgs | Wing 1-8th Slab (2nd Floor) Shear Wall Steel | STEEL | 8241 | 50.85 | 419054.85 | 6459 | 50.85 | 328440.15 | 6459 | 1782 | 0 | 6459 | 0 | 1890 | 4569 | 64.3631 | 121646.259 | 1890 | 0 | 1875 | 6366 | 24188.88 | 1529685.0138 | Kgs | 103090.05 | 103090.05 | 4569 | 1782 | 315964.8
Steel Bars 8mm - Kgs | Wing 1-9th Slab (3rd Floor) Shear Wall Steel | STEEL | 8241.02 | 50.85 | 419055.867 | 6459 | 50.85 | 328440.15 | 6459 | 1782.02 | 0 | 6459 | 0 | 0 | 6459 | 0 | 0 | 0 | 0 | 22.02 | 8219 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 6459 | 1782.02 | 419055.867
Steel Bars 8mm - Kgs | Wing 1-10th Slab (4th Floor) Shear Wall Steel | STEEL | 8241.02 | 50.85 | 419055.867 | 6459 | 50.85 | 328440.15 | 6459 | 1782.02 | 0 | 6459 | 0 | 0 | 6459 | 0 | 0 | 0 | 0 | 2197.02 | 6044 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 6459 | 1782.02 | 419055.867
Steel Bars 8mm - Kgs | Wing 1-11th Slab (5th Floor) Shear Wall Steel | STEEL | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 0 | 0
Steel Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Shear Wall Steel | STEEL | 0 | 50.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 0 | 0
Steel Bars 8mm - Kgs | Wing 1 - 7th Slab (1st Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 8281.07 | 50.85 | 421092.4095 | 8281.07 | 0 | 0 | 8281.07 | 0 | 30.68 | 8250.39 | 64.3631 | 1974.6599 | 30.68 | 0 | 223.07 | 8058 | 24188.88 | 1529685.0138 | Kgs | 1673.4406 | 1673.4406 | 8250.39 | 0 | 419418.9689
Steel Bars 8mm - Kgs | Wing 1-8th Slab (2nd Floor) Slab,Beam,Stair. Steel | STEEL | 8553.52 | 50.85 | 434946.492 | 8266.88 | 50.85 | 420370.848 | 8266.88 | 286.64 | 0 | 8266.88 | 0 | 8266.88 | 0 | 64.3631 | 532082.0241 | 8266.88 | 0 | 287.52 | 8266 | 24188.88 | 1529685.0138 | Kgs | 450916.9696 | 450916.9696 | 0 | 286.64 | -15970.4776
Steel Bars 8mm - Kgs | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | STEEL | 8553.52 | 50.85 | 434946.492 | 8266.88 | 50.85 | 420370.848 | 8266.88 | 286.64 | 0 | 8266.88 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 334.52 | 8219 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 8266.88 | 286.64 | 434946.492
Steel Bars 8mm - Kgs | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | STEEL | 8553.52 | 50.85 | 434946.492 | 8266.88 | 50.85 | 420370.848 | 8266.88 | 286.64 | 0 | 8266.88 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 12.52 | 8541 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 8266.88 | 286.64 | 434946.492
Steel Bars 8mm - Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | STEEL | 8553.52 | 50.85 | 434946.492 | 8266.88 | 50.85 | 420370.848 | 5956.88 | 286.64 | 2310 | 5956.88 | 2310 | 5956.88 | 0 | 59.872 | 356650.3194 | 5956.88 | 0 | 91.52 | 8462 | 24188.88 | 1529685.0138 | Kgs | 302246.1343 | 0 | 2310 | 286.64 | 434946.492
Steel Bars 8mm - Kgs | Wing 2 - 1st Slab (Staircase, Beam,Slab) Steel | STEEL | 7009.389 | 50.85 | 356427.4307 | 6527.17 | 50.85 | 331906.5945 | 6527.17 | 482.219 | 0 | 6527.17 | 0 | 1700 | 4827.17 | 64.3631 | 109417.27 | 1700 | 0 | 562.389 | 6447 | 24188.88 | 1529685.0138 | Kgs | 92726.5 | 92726.5 | 4827.17 | 482.219 | 263700.9307
Steel Bars 8mm - Kgs | Wing 2 - P1 To P2 Column & Lift Steel | STEEL | 14732.54 | 50.85 | 749149.659 | 13302.44 | 50.85 | 676429.074 | 13302.44 | 1430.1 | 0 | 13302.44 | 0 | 7772.44 | 5530 | 63.1953 | 491181.419 | 7772.44 | 0 | 1436.54 | 13296 | 24188.88 | 1529685.0138 | Kgs | 416255.4398 | 416255.4398 | 5530 | 1430.1 | 332894.2192
Steel Bars 8mm - Kgs | Wing 2 - P2 To P3 Column & Lift Steel | STEEL | 14732.54 | 50.85 | 749149.659 | 0 | 0 | 0 | 0 | 14732.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161.54 | 12571 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 14732.54 | 749149.659
Steel Bars 8mm - Kgs | Wing 2 . P3 To P4 Column &amp; Lift Steel | STEEL | 14732.54 | 50.85 | 749149.659 | 0 | 0 | 0 | 0 | 14732.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4096.54 | 10636 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 14732.54 | 749149.659
Steel Bars 8mm - Kgs | Wing 2 . P4 To P5 Column &amp; Lift Steel | STEEL | 14732.54 | 50.85 | 749149.659 | 7000 | 50.85 | 355950 | 7000 | 7732.54 | 0 | 7000 | 0 | 7000 | 0 | 64.31 | 450170 | 7000 | 0 | 2162.54 | 12570 | 24188.88 | 1529685.0138 | Kgs | 381500 | 381500 | 0 | 7732.54 | 367649.659
Steel Bars 8mm - Kgs | Wing 2 . 2nd Slab (Staircase, Beam,Slab) Steel | STEEL | 7398.39 | 50.85 | 376208.1315 | 0 | 0 | 0 | 0 | 7398.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.39 | 7333 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 7398.39 | 376208.1315
Steel Bars 8mm - Kgs | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | STEEL | 7476 | 50.85 | 380154.6 | 7476 | 50.85 | 380154.6 | 7476 | 0 | 0 | 7476 | 0 | 7448 | 28 | 64.31 | 478980.88 | 7448 | 0 | 62 | 7414 | 24188.88 | 1529685.0138 | Kgs | 405916 | 405916 | 28 | 0 | -25761.4
Steel Bars 8mm - Kgs | Wing 2 . 4th Slab (Staircase, Beam,Slab) Steel | STEEL | 7476 | 50.85 | 380154.6 | 7476 | 50.85 | 380154.6 | 7476 | 0 | 0 | 7476 | 0 | 7476 | 0 | 64.31 | 480781.56 | 7476 | 0 | 63 | 7413 | 24188.88 | 1529685.0138 | Kgs | 407442 | 407442 | 0 | 0 | -27287.4
Steel Bars 8mm - Kgs | Wing 1-9th Floor To 10th Floor Column, LW Steel | STEEL | 8076 | 50.85 | 410664.6 | 8076 | 50.85 | 410664.6 | 8076 | 0 | 0 | 8076 | 0 | 8076 | 0 | 64.31 | 519367.56 | 8046 | 30 | 8076 | 0 | 24188.88 | 1529685.0138 | Kgs | 438507 | 438507 | 0 | 0 | -27842.4
Steel Bars 8mm - Kgs | Wing 1-10th Floor To 11th Floor Column, LW Steel | STEEL | 8140 | 50.85 | 413919 | 0 | 0 | 0 | 0 | 8140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8140 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8140 | 413919
Steel Bars 8mm - Kgs | Wing 1-11th Floor To 12th Floor Column, LW Steel | STEEL | 8098 | 50.85 | 411783.3 | 0 | 0 | 0 | 0 | 8098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8098 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8098 | 411783.3
Steel Bars 8mm - Kgs | Wing 1-12th Floor To 13th Floor Column, LW Steel | STEEL | 8093 | 50.85 | 411529.05 | 0 | 0 | 0 | 0 | 8093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8093 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8093 | 411529.05
Steel Bars 8mm - Kgs | Wing 1-13th Floor To 14th Floor Column, LW Steel | STEEL | 8087 | 50.85 | 411223.95 | 0 | 0 | 0 | 0 | 8087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8087 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8087 | 411223.95
Steel Bars 8mm - Kgs | Wing 1-14th Floor To 15th Floor Column, LW Steel | STEEL | 8072 | 50.85 | 410461.2 | 0 | 0 | 0 | 0 | 8072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8072 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8072 | 410461.2
Steel Bars 8mm - Kgs | Wing 1-15th Floor To 16th Floor Column, LW Steel | STEEL | 8058 | 50.85 | 409749.3 | 0 | 0 | 0 | 0 | 8058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8058 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8058 | 409749.3
Steel Bars 8mm - Kgs | Wing 1-16th Floor To 17th Floor Column, LW Steel | STEEL | 8069 | 50.85 | 410308.65 | 0 | 0 | 0 | 0 | 8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8069 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8069 | 410308.65
Steel Bars 8mm - Kgs | Wing 1-17th Floor To 18th Floor Column, LW Steel | STEEL | 8069 | 50.85 | 410308.65 | 0 | 0 | 0 | 0 | 8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8069 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8069 | 410308.65
Steel Bars 8mm - Kgs | Wing 1-20th Floor To 21st Floor Column, LW Steel | STEEL | 8025 | 50.85 | 408071.25 | 0 | 0 | 0 | 0 | 8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8025 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8025 | 408071.25
Steel Bars 8mm - Kgs | Wing 1-23rd Floor To 24th Floor Column, LW Steel | STEEL | 8025 | 50.85 | 408071.25 | 0 | 0 | 0 | 0 | 8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8025 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8025 | 408071.25
Steel Bars 8mm - Kgs | Wing 1-26th Floor To 27th Floor Column, LW Steel | STEEL | 8143 | 50.85 | 414071.55 | 0 | 0 | 0 | 0 | 8143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8143 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8143 | 414071.55
Steel Bars 8mm - Kgs | Wing 1-27th Floor To 28th Floor Column, LW Steel | STEEL | 8141 | 50.85 | 413969.85 | 0 | 0 | 0 | 0 | 8141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8141 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8141 | 413969.85
Steel Bars 8mm - Kgs | Wing 1-28th Floor To Terrace Floor Column, LW Steel | STEEL | 8076 | 50.85 | 410664.6 | 0 | 0 | 0 | 0 | 8076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8076 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8076 | 410664.6
Steel Bars 8mm - Kgs | Wing 1-24th Floor To 25th Floor Column, LW Steel | STEEL | 8025 | 50.85 | 408071.25 | 0 | 0 | 0 | 0 | 8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8025 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8025 | 408071.25
Steel Bars 8mm - Kgs | Wing 1-25th Floor To 26th Floor Column, LW Steel | STEEL | 8025 | 50.85 | 408071.25 | 0 | 0 | 0 | 0 | 8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8025 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8025 | 408071.25
Steel Bars 8mm - Kgs | Wing 1-21st Floor To 22nd Floor Column, LW Steel | STEEL | 8025 | 50.85 | 408071.25 | 0 | 0 | 0 | 0 | 8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8025 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8025 | 408071.25
Steel Bars 8mm - Kgs | Wing 1-22nd Floor To 23rd Floor Column, LW Steel | STEEL | 8025 | 50.85 | 408071.25 | 0 | 0 | 0 | 0 | 8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8025 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8025 | 408071.25
Steel Bars 8mm - Kgs | Wing 1-18th Floor To 19th Floor Column, LW Steel | STEEL | 8069 | 50.85 | 410308.65 | 0 | 0 | 0 | 0 | 8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8069 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8069 | 410308.65
Steel Bars 8mm - Kgs | Wing 1-19th Floor To 20th Floor Column, LW Steel | STEEL | 8069 | 50.85 | 410308.65 | 0 | 0 | 0 | 0 | 8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8069 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8069 | 410308.65
Steel Bars 8mm - Kgs | Wing-3 Substructure (M) Steel For Tie Beam | STEEL | 1507.88 | 50.85 | 76675.698 | 0 | 0 | 0 | 0 | 1507.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1507.88 | 76675.698
Steel Bars 8mm - Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.07 | 8220 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8281.07 | 421092.4095
Steel Bars 8mm - Kgs | Wing 1-17th Slab (11th Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8281.07 | 421092.4095
Steel Bars 8mm - Kgs | Wing 1-22th Slab (16 Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8281.07 | 421092.4095
Steel Bars 8mm - Kgs | Wing 1-27th Slab (21st Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8281.07 | 421092.4095
Steel Bars 8mm - Kgs | Wing 1-32th Slab (26th Floor) Slab,Beam,Stair. Steel | STEEL | 8281.07 | 50.85 | 421092.4095 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8281.07 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8281.07 | 421092.4095
Steel Bars 8mm - Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208.88 | 8058 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-14th Slab (8th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-15th Slab (9th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-16th Slab (10th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-18th Slab (12th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-19th Slab (13th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-20th Slab (14th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-21th Slab (15th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-23th Slab (17th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-24th Slab (18th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-25th Slab (19th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-26th Slab (20th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-28th Slab (22nd Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-29th Slab (23rd Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-30th Slab (24th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-31th Slab (25th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-33th Slab (27th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-34th Slab (28th Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Wing 1-35th Slab (Terrace Floor) Slab,Beam,Stair. Steel | STEEL | 8266.88 | 50.85 | 420370.848 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.88 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 8266.88 | 420370.848
Steel Bars 8mm - Kgs | Non Tower Area Column Upto Plinth | STEEL | 5795.05 | 50.85 | 294678.2925 | 5795.05 | 50.85 | 294678.2925 | 5795.05 | 0 | 0 | 5795.05 | 0 | 0 | 5795.05 | 0 | 0 | 0 | 0 | 396.05 | 5399 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 5795.05 | 0 | 294678.2925
Steel Bars 8mm - Kgs | Non Tower Area Intermediate Tie Beam Steel | STEEL | 368.89 | 50.85 | 18758.0565 | 0 | 0 | 0 | 0 | 368.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.89 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 368.89 | 18758.0565
Steel Bars 8mm - Kgs | Labour Camp Construction M-10 & M-20 | STEEL | 1442.07 | 50.85 | 73329.2595 | 0 | 0 | 0 | 0 | 1442.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556.07 | 886 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1442.07 | 73329.2595
Steel Bars 8mm - Kgs | Wing-3 Parking NTA Piling | STEEL | 1214.1 | 50.85 | 61736.985 | 728.46 | 50.85 | 37042.191 | 728.46 | 485.64 | 0 | 728.46 | 0 | 0 | 728.46 | 0 | 0 | 0 | 0 | 165.1 | 1049 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 728.46 | 485.64 | 61736.985
Steel Bars 8mm - Kgs | Non Tower Area NTA Piling | STEEL | 404.7 | 50.85 | 20578.995 | 121.41 | 50.85 | 6173.6985 | 121.41 | 283.29 | 0 | 121.41 | 0 | 0 | 121.41 | 0 | 0 | 0 | 0 | 404.7 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 121.41 | 283.29 | 20578.995
Steel Bars 8mm - Kgs | Wing.1 Substructure RCC Pile Cap work - Steel | STEEL | 1176.04 | 50.85 | 59801.634 | 0 | 0 | 0 | 0 | 1176.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692.04 | 484 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1176.04 | 59801.634
Steel Bars 8mm - Kgs | UGWT RCC Top Slab & Beam Steel | STEEL | 3494.57 | 50.85 | 177698.8845 | 0 | 0 | 0 | 0 | 3494.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803.57 | 1691 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 3494.57 | 177698.8845
Steel Bars 8mm - Kgs | Wing 2 . P5 To P6 Column &amp;amp; Lift Steel | STEEL | 12614.65 | 50.85 | 641454.9525 | 0 | 0 | 0 | 0 | 12614.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.65 | 12570 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 12614.65 | 641454.9525
Steel Bars 8mm - Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | STEEL | 7476 | 50.85 | 380154.6 | 0 | 0 | 0 | 0 | 7476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 7413 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 7476 | 380154.6
Steel Bars 8mm - Kgs | UGWT RCC Grid Slab Reinforcement Work | STEEL | 3425.02 | 50.85 | 174162.267 | 0 | 0 | 0 | 0 | 3425.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3425.02 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 3425.02 | 174162.267
Steel Bars 8mm - Kgs | RCC Raft Reinforcement Work | STEEL | 605.81 | 50.85 | 30805.4385 | 0 | 0 | 0 | 0 | 605.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605.81 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 605.81 | 30805.4385
Steel Bars 8mm - Kgs | Compound Wall Pile Foundation | STEEL | 1711.055 | 50.85 | 87007.1468 | 0 | 0 | 0 | 0 | 1711.055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711.055 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 1711.055 | 87007.1468
Steel Bars 8mm - Kgs | Pile Cap | STEEL | 456.69 | 50.85 | 23222.6865 | 0 | 0 | 0 | 0 | 456.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456.69 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 456.69 | 23222.6865
Steel Bars 8mm - Kgs | Non Tower Area Plinth Beam Steel | STEEL | 457.24 | 50.85 | 23250.654 | 0 | 0 | 0 | 0 | 457.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.24 | 242 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 457.24 | 23250.654
Steel Bars 8mm - Kgs | Non Tower Area Column Ground To P1 Slab Steel | STEEL | 2181.03 | 50.85 | 110905.3755 | 0 | 0 | 0 | 0 | 2181.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2181.03 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 2181.03 | 110905.3755
Steel Bars 8mm - Kgs | Non Tower Area Column 1st Slab P1 To 2nd Slab P2 Steel | STEEL | 2180.68 | 50.85 | 110887.578 | 0 | 0 | 0 | 0 | 2180.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165.68 | 2015 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 2180.68 | 110887.578
Steel Bars 8mm - Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | STEEL | 4871.89 | 50.85 | 247735.6065 | 0 | 0 | 0 | 0 | 4871.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278.89 | 4593 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 4871.89 | 247735.6065
Steel Bars 8mm - Kgs | UGWT RCC Staircase Reinforcement Work | STEEL | 80.31 | 50.85 | 4083.7635 | 0 | 0 | 0 | 0 | 80.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.31 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 80.31 | 4083.7635
Steel Bars 8mm - Kgs | Wing 2 . P6 To Podium Column & Lift Steel | STEEL | 7307.49 | 50.85 | 371585.8665 | 0 | 0 | 0 | 0 | 7307.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7307.49 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 7307.49 | 371585.8665
Steel Bars 8mm - Kgs | Wing 2 . 6th Slab (Staircase, Beam,Slab) Steel | STEEL | 7839.19 | 50.85 | 398622.8115 | 0 | 0 | 0 | 0 | 7839.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7839.19 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 7839.19 | 398622.8115
Steel Bars 8mm - Kgs | Phase 2 Weigh Bridge Steel | STEEL | 197.82 | 50.85 | 10059.147 | 0 | 0 | 0 | 0 | 197.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197.82 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 197.82 | 10059.147
Steel Bars 8mm - Kgs | 1st Slab Parking (P2 Lvl) Slab Beam steel | STEEL | 2985.56 | 50.85 | 151815.726 | 0 | 0 | 0 | 0 | 2985.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2985.56 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 2985.56 | 151815.726
Steel Bars 8mm - Kgs | Non Tower Area NTA 2nd PT Slab (Wing 1) Steel | STEEL | 4871.89 | 50.85 | 247735.6065 | 0 | 0 | 0 | 0 | 4871.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4871.89 | 0 | 24188.88 | 1529685.0138 | Kgs | 0 | 0 | 0 | 4871.89 | 247735.6065