## Requisition_Detail_Browse638581
Requisition Detail Browse
Library : Goel Ganga Group
From Date : 02/07/2000 To date: 02/08/2024
Material : Regal Onyx Copper Tile 1200x600mm
Status : Pending For PO
Page 1 of 1
Total Records: 18 Records 1 to 18
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
GANGA DHAM TOWERS | 2602 | Regal Onyx Copper Tile 1200x600mm | 583106 | 710964 | 19 Jan 2021 | 2021-02-28 | Sq.Ft |  | 1.5 | 1.5 | PARSHURAM KORE | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 27th Fl. Flooring & Tiling Work Flat No 1 | Regal Onyx Copper Tile 1200x600mm | 625355 | 746670 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 27th Fl. Flooring & Tiling Work Flat No 2 | Regal Onyx Copper Tile 1200x600mm | 625366 | 746669 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 27th Fl. Flooring & Tiling Work Flat No 3 | Regal Onyx Copper Tile 1200x600mm | 625377 | 746668 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 27th Fl. Flooring & Tiling Work Flat No 4 | Regal Onyx Copper Tile 1200x600mm | 625389 | 746667 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 28th Fl. Flooring & Tiling Work Flat No 1 | Regal Onyx Copper Tile 1200x600mm | 625400 | 746666 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 28th Fl. Flooring & Tiling Work Flat No 2 | Regal Onyx Copper Tile 1200x600mm | 625411 | 746665 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 28th Fl. Flooring & Tiling Work Flat No 3 | Regal Onyx Copper Tile 1200x600mm | 625422 | 746664 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 28th Fl. Flooring & Tiling Work Flat No 4 | Regal Onyx Copper Tile 1200x600mm | 625433 | 746663 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 29th Fl. Flooring & Tiling Work Flat No 1 | Regal Onyx Copper Tile 1200x600mm | 625444 | 746662 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 29th Fl. Flooring & Tiling Work Flat No 2 | Regal Onyx Copper Tile 1200x600mm | 625455 | 746661 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 29th Fl. Flooring & Tiling Work Flat No 3 | Regal Onyx Copper Tile 1200x600mm | 625466 | 746660 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | A Bldg 29th Fl. Flooring & Tiling Work Flat No 4 | Regal Onyx Copper Tile 1200x600mm | 625477 | 746659 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 83 | 83 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | B Bldg 27th Floor 2701 Tilling Work | Regal Onyx Copper Tile 1200x600mm | 625488 | 746658 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 119 | 119 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | B Bldg 27th Floor 2702 Tilling Work | Regal Onyx Copper Tile 1200x600mm | 625499 | 746657 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 71 | 71 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | B Bldg 28th Floor 2801 Tilling Work | Regal Onyx Copper Tile 1200x600mm | 625510 | 746656 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 119 | 119 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | B Bldg 28th Floor 2802 Tilling Work | Regal Onyx Copper Tile 1200x600mm | 625521 | 746655 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 71 | 71 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase
GANGA DHAM TOWERS | B Bldg 29th Floor 2902 Tilling Work | Regal Onyx Copper Tile 1200x600mm | 625532 | 746654 | 26 Nov 2022 | 2022-12-05 | Sq.Ft |  | 71 | 71 | KantilalJ | 0 | 0 |  | As Per Lead Period | Approved |  | Regular Purchase