## Requisition_Detail_Browse638585
Requisition Detail Browse
From Date : 01/01/2024 To date: 19/07/2024
Status : All
Page 1 of 1
Total Records: 54 Records 1 to 54
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC End Cap 4" | 678719 | 786438 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 20 | 10 | Vinay Mittal | 67967 | 66.15 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC End Cap 4" | 678719 | 780308 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 20 | 10 | Sajid khan | 67904 | 66.15 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC End Cap 8" | 678720 | 780310 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 2 | 2 | Sajid khan | 67904 | 227.91 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Pipe 6" x 10 fts S/S | 678721 | 780306 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 52 | 26 | Sajid khan | 67904 | 1181.27 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Pipe 6" x 10 fts S/S | 678721 | 786452 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 52 | 26 | Vinay Mittal | 67967 | 1181.27 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Reducer Socket 6"x4" | 678722 | 786459 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 50 | 25 | Vinay Mittal | 67967 | 118.40 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Reducer Socket 6"x4" | 678722 | 780307 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 50 | 25 | Sajid khan | 67904 | 118.40 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Shoe Bend 4" | 678723 | 786463 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 632 | 288 | AKSHADA MAHAJAN | 67967 | 65.02 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Shoe Bend 4" | 678723 | 780694 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 632 | 344 | Sajid khan | 67904 | 65.02 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Shoe Bend 6" | 678724 | 780312 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 90 | 45 | Sajid khan | 67904 | 164.26 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Shoe Bend 6" | 678724 | 786458 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 90 | 45 | AKSHADA MAHAJAN | 67967 | 164.26 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | Pvc Shoe Bend 8" | 678725 | 780313 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 120 | 60 | Sajid khan | 67904 | 855.23 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Single Y 4" | 678726 | 786455 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 30 | 15 | AKSHADA MAHAJAN | 67967 | 144.41 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Single Y 4" | 678726 | 780305 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 30 | 15 | Sajid khan | 67904 | 144.41 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Single Y 6" | 678727 | 786453 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 20 | 10 | AKSHADA MAHAJAN | 67967 | 373.00 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Single Y 6" | 678727 | 780311 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 20 | 10 | Sajid khan | 67904 | 373.00 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Socket 6" | 678728 | 780309 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 12 | 6 | Sajid khan | 67904 | 142.36 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Socket 6" | 678728 | 786451 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 12 | 6 | AKSHADA MAHAJAN | 67967 | 142.36 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Socket 4" | 679160 | 786450 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 55 | 27 | AKSHADA MAHAJAN | 67967 | 58.17 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Socket 4" | 679160 | 780695 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 55 | 28 | Sajid khan | 67904 | 58.17 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 3"x10ft S/S | 679207 | 786447 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 13 | 7 | AKSHADA MAHAJAN | 67967 | 655.65 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 3"x10ft S/S | 679207 | 780698 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 13 | 6 | Sajid khan | 67904 | 655.66 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 4" x 10 ft S/S | 679291 | 780699 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 427 | 48 | Sajid khan | 67904 | 1105.31 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 4" x 10 ft S/S | 679291 | 786444 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 427 | 379 | AKSHADA MAHAJAN | 67967 | 1105.31 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 6"x10ft S.S. | 679356 | 786443 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 52 | 26 | AKSHADA MAHAJAN | 67967 | 1824.61 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 6"x10ft S.S. | 679356 | 780696 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 52 | 26 | Sajid khan | 67904 | 1824.61 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 8"x10ft S.S. | 679439 | 803021 | 18 Jan 2024 | 2024-01-18 12:00 | No. |  | 38 | 38 | Sajid khan | 68802 | 3023.57 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | Bullet Fastner 10mm | 690691 | 802850 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 250 | 250 | Sajid khan | 68824 | 5.31 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI C Channel Patti (14SWG) 35MM X 15MM X 3M | 690692 | 802849 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 55 | 55 | Sajid khan | 68975 | 368.16 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI D Clamps 4" | 690693 | 796384 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 200 | 200 | Sajid khan | 68502 | 21.24 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI Nut Bolt 10mm (Dia)x40mm with double washer | 690694 | 802848 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 750 | 750 | Sajid khan | 68824 | 9.44 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI U Clamps 4" | 690695 | 796382 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 550 | 550 | Sajid khan | 68502 | 14.75 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Cleansing Pipe 4" | 690696 | 796381 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 70 | 70 | Sajid khan | 68532 | 109.50 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | Threaded rod 10mmx2mtr | 690697 | 802847 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 80 | 80 | Sajid khan | 68824 | 99.12 | Raised | Before Lead Period | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | PVC Solvent (500 ml.) - | 690698 | 810930 | 08 Apr 2024 | 2024-04-08 12:00 | No. |  | 40 | 40 | Akshada Mahajan | 68891 | 295.66 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Coupler 8" | 695126 | 803204 | 08 May 2024 | 2024-05-08 12:00 | No. | Silent Fitting Required | 8 | 8 | Sajid khan | 68802 | 527.40 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent bend 8" | 695361 | 803449 | 10 May 2024 | 2024-05-10 12:00 | No. |  | 60 | 60 | Sajid khan | 68802 | 690.95 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Pipe 8"x10ft S.S. | 696778 | 805913 | 20 May 2024 | 2024-05-20 12:00 | No. | Silent Pipe Required | 34 | 34 | Sajid khan | 68802 | 3023.57 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | Bullet Fastner 10mm | 696940 | 806137 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 1964 | 1964 | SANKET PATIL | 68824 | 5.31 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI C Channel Patti (14SWG) 35MM X 15MM X 3M | 696941 | 806138 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 57 | 57 | SANKET PATIL | 68975 | 368.16 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI Nut Bolt 10mm (Dia)x40mm with double washer | 696942 | 806139 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 5892 | 5892 | SANKET PATIL | 68824 | 9.44 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI U Clamps 6" | 696943 | 806140 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 110 | 110 | SANKET PATIL | 68824 | 26.55 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | GI U Clamps 8" | 696944 | 806141 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 154 | 154 | SANKET PATIL | 68824 | 33.04 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Reducer Socket 6"x4" | 696945 | 810891 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 50 | 50 | Akshada Mahajan | 68887 | 253.23 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | P V C Reducer Socket 8"x4" | 696946 | 810895 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 85 | 85 | Akshada Mahajan | 68887 | 375.26 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Shoe Bend 4" | 696947 | 810890 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 632 | 632 | Akshada Mahajan | 68887 | 149.88 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Shoe Bend 6" | 696948 | 810894 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 90 | 90 | Akshada Mahajan | 68887 | 446.23 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Shoe Bend 8" | 696949 | 806146 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 110 | 110 | SANKET PATIL | 68802 | 558.38 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Single Y 4" | 696950 | 810892 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 30 | 30 | Akshada Mahajan | 68887 | 280.60 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Single Y 6" | 696951 | 810888 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 20 | 20 | Akshada Mahajan | 68887 | 854.13 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | P V C Single Y 8" | 696952 | 810896 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 55 | 55 | Akshada Mahajan | 68887 | 2135.88 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Socket 4" (Coupler) | 696953 | 810889 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 55 | 55 | Akshada Mahajan | 68887 | 115.66 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | SWR Silent Socket 6" | 696954 | 810893 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 12 | 12 | Akshada Mahajan | 68887 | 250.49 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | Threaded rod 10mmx2mtr | 696955 | 806152 | 22 May 2024 | 2024-05-22 12:00 | No. |  | 690 | 690 | SANKET PATIL | 68824 | 99.12 | Raised | Management | Approved |  | Regular Purchase