## Requisition_Detail_Browse638588
Requisition Detail Browse
From Date : 01/07/2018 To date: 10/08/2024
Material Category : RMC
Status : Pending For PO
Page 1 of 1
Total Records: 44 Records 1 to 44
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
GANGA ALTUS | Tower D Grade Slab RMC Grade Slab-(Cu.Mtrs) | Sand-Metal Mix M20 (Downpour) | 577485 | 823855 | 28 Oct 2020 | 2020-10-30 12:00 | Cu.Mtrs |  | 1.25 | 1.25 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Tower D Grade Slab RMC Grade Slab-(Cu.Mtrs) | Sand-Metal Mix M20 (Downpour) | 577952 | 823854 | 11 Nov 2020 | 2020-11-13 12:00 | Cu.Mtrs |  | 24.25 | 24.25 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Trimix Road Bldg D to F Shops & Gate- front area road work | Sand-Metal Mix M20 (Downpour) | 586146 | 823853 | 02 Apr 2021 | 2021-04-30 12:00 | Cu.Mtrs |  | 10.94 | 10.94 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Tower E Grade Slab Concrete-M20 | Sand-Metal Mix M20 (Downpour) | 592575 | 823851 | 04 Aug 2021 | 2021-08-04 12:00 | Cu.Mtrs |  | 1.5 | 1.5 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Tower E Grade Slab Concrete-M20 | Sand-Metal Mix M20 (Downpour) | 592575 | 823852 | 04 Aug 2021 | 2021-08-04 12:00 | Cu.Mtrs |  | 7.51 | 7.51 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work Footing Concrete | Sand-Metal Mix M25 (Downpour) | 602741 | 814520 | 29 Nov 2021 | 2021-11-29 12:00 | Cu.Mtrs |  | 10.155 | 10.155 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | E-P4-5th Slab RCC 4th to 5th Column Concrete | Sand-Metal Mix M50 Easycrete (Downpour) | 605346 | 797760 | 04 Jan 2022 | 2022-01-04 12:00 | Cu.Mtrs |  | 0.005 | 0.005 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Podium Floor- 6th Slab 5th To 6th Column Concrete-M50 | Sand-Metal Mix M50 Easycrete (Pumpable) | 606762 | 791162 | 22 Jan 2022 | 2022-01-22 12:00 | Cu.Mtrs |  | 0.0016 | 0.0016 | vinay mittal | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Grid Slab Grid Slab Concrete M20 | Sand-Metal Mix M20 (Downpour) | 608794 | 823850 | 23 Feb 2022 | 2022-02-23 12:00 | Cu.Mtrs |  | 10.85 | 10.85 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Podium Floor- 6th Slab 5th To 6th Column Concrete-M50 | Sand-Metal Mix M50 (Downpour) | 610053 | 791292 | 05 Mar 2022 | 2022-04-01 | Cu.Mtrs |  | 0.3292 | 0.3292 | vinay mittal | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Trimix Road Bldg D to F Shops & Gate- front area road work | Sand-Metal Mix M20 (Downpour) | 612067 | 823849 | 08 Apr 2022 | 2022-04-08 12:00 | Cu.Mtrs |  | 23 | 23 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | 3rd PT Slab,Beam Concrete | Sand-Metal Mix M35 PT (Pumpable) Without Flyash | 612465 | 791293 | 21 Apr 2022 | 2022-04-21 12:00 | Cu.Mtrs |  | 0.0011 | 0.0011 | vinay mittal | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work FW Tank- RCC Pardi Concrete M25 | Sand-Metal Mix M25 (Downpour) | 613614 | 814519 | 18 May 2022 | 2022-05-18 12:00 | Cu.Mtrs |  | 1 | 1 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work FW Tank- RCC Pardi Concrete M25 | Sand-Metal Mix M25 (Downpour) | 613774 | 814518 | 21 May 2022 | 2022-05-21 12:00 | Cu.Mtrs |  | 1 | 1 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | 5th PT Slab,Beam Concrete | Sand-Metal Mix M35 PT (Pumpable) Without Flyash | 613853 | 791305 | 23 May 2022 | 2022-05-23 12:00 | Cu.Mtrs |  | 0.42 | 0.42 | vinay mittal | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Trimix Road Bldg D to F Shops & Gate- front area road work | Sand-Metal Mix M20 (Downpour) | 613928 | 823848 | 25 May 2022 | 2022-05-25 12:00 | Cu.Mtrs |  | 7.31 | 7.31 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Trimix Road Bldg D to F Shops & Gate- front area road work | Sand-Metal Mix M20 (Pumpable) | 614520 | 823861 | 31 May 2022 | 2022-05-31 12:00 | Cu.Mtrs |  | 3 | 3 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | OHWT RCC Work- Slab,Beam,Pardi Concrete-M30 | Sand-Metal Mix M30 (Downpour) | 617161 | 783740 | 29 Jun 2022 | 2022-06-29 12:00 | Cu.Mtrs |  | 1 | 1 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work Pump Room-RCC Pardi Concrete-M25 | Sand-Metal Mix M25 (Downpour) | 619625 | 814517 | 27 Aug 2022 | 2022-08-27 12:00 | Cu.Mtrs |  | 2.28 | 2.28 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work Pump Room-RCC Pardi Concrete-M25 | Sand-Metal Mix M25 (Downpour) | 619626 | 814516 | 27 Aug 2022 | 2022-08-27 12:00 | Cu.Mtrs |  | 2 | 2 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work FW Tank- Column Concrete-M50 | Sand-Metal Mix M50 (Downpour) | 619759 | 797756 | 30 Aug 2022 | 2022-08-31 | Cu.Mtrs |  | 0.5 | 0.5 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D-Podium Floor-6th Slab RCC 5th to 6th Column Concrete | Sand-Metal Mix M50 (Downpour) | 621814 | 797757 | 12 Oct 2022 | 2022-10-12 12:00 | Cu.Mtrs |  | 0.01 | 0.01 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | 9th Slab,Beam,SW,ST Concrete M50 | Sand-Metal Mix M50 Easycrete (Pumpable) | 623428 | 779053 | 28 Oct 2022 | 2022-10-28 12:00 | Cu.Mtrs |  | 2.28 | 2.28 | vinay mittal | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Plum Concrete in Pump Room | Sand-Metal Mix M15 (Downpour) | 624733 | 823866 | 15 Nov 2022 | 2022-11-15 12:00 | Cu.Mtrs |  | 30.23 | 30.23 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D-P2 Fl Parapet Wall RCC Work Concrete | Sand-Metal Mix M25 (Downpour) | 634636 | 814515 | 06 Feb 2023 | 2023-02-06 12:00 | Cu.Mtrs |  | 2.235 | 2.235 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D-28th Slab RCC 28th Slab,Beam,ST Concrete | Sand-Metal Mix M30 hi-flow (Pumpable) | 640301 | 791232 | 16 Mar 2023 | 2023-03-20 | Cu.Mtrs |  | 0.32 | 0.32 | vinay mittal | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Footing Concrete- M25 | Sand-Metal Mix M25 (Downpour) | 641377 | 814514 | 01 Apr 2023 | 2023-04-01 12:00 | Cu.Mtrs |  | 7.24 | 7.24 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Footing to 1st Slab Column Concrete | Sand-Metal Mix M25 (Downpour) | 641378 | 814513 | 01 Apr 2023 | 2023-04-01 12:00 | Cu.Mtrs |  | 3.62 | 3.62 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work RCC Pardi Concrete Work M25 | Sand-Metal Mix M25 (Pumpable) | 641699 | 814524 | 06 Apr 2023 | 2023-04-06 12:00 | Cu.Mtrs |  | 29.9572 | 29.9572 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | E-Bldg-1st Slab RCC G.Fl -Parapet Wall Concrete Work-M25 | Sand-Metal Mix M25 (Downpour) | 647999 | 814512 | 03 Jun 2023 | 2023-06-03 12:00 | Cu.Mtrs |  | 2.9227 | 2.9227 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D&E Podium Grid Slab Concrete-M20 | Sand-Metal Mix M20 (Pumpable) | 648136 | 823860 | 08 Jun 2023 | 2023-06-08 12:00 | Cu.Mtrs |  | 18.75 | 18.75 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D&E Bldg Between-P3-4th Slab RCC- Slab,Beam Concrete - 1 | Sand-Metal Mix M35 (Downpour) | 649250 | 824699 | 27 Jun 2023 | 2023-06-27 12:00 | Cu.Mtrs |  | 0.5 | 0.5 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D&E Bldg Between-P5-5th Slab RCC 5th Slab,Beam Concrete - | Sand-Metal Mix M35 (Downpour) | 649251 | 824698 | 27 Jun 2023 | 2023-06-27 12:00 | Cu.Mtrs |  | 1.0276 | 1.0276 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | OWC UNIT - Grid Slab Concrete Work | Sand-Metal Mix M20 (Pumpable) | 650461 | 823859 | 05 Jul 2023 | 2023-07-05 12:00 | Cu.Mtrs |  | 11.73 | 11.73 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work Footing to top slab - Concrete M25 | Sand-Metal Mix M25 (Pumpable) | 656022 | 814523 | 19 Jul 2023 | 2023-07-19 12:00 | Cu.Mtrs |  | 10 | 10 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D-Bldg Parking Grade Slab D-Parking Grid Slab- Concrete Work | Sand-Metal Mix M20 (Pumpable) | 656023 | 823858 | 19 Jul 2023 | 2023-07-19 12:00 | Cu.Mtrs |  | 10 | 10 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Ground Fl Parapet Wall RCC Concrete Work M25 | Sand-Metal Mix M25 (Downpour) | 656572 | 814510 | 31 Jul 2023 | 2023-07-31 12:00 | Cu.Mtrs |  | 0.46 | 0.46 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | P1-Fl Parapet Wall RCC Concrete Work M25 | Sand-Metal Mix M25 (Downpour) | 656573 | 814511 | 31 Jul 2023 | 2023-07-31 12:00 | Cu.Mtrs |  | 6.95 | 6.95 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | 265 KLD STP Concrete Work M-25 Ready Mix and Sand metal - | Sand-Metal Mix M25 (Pumpable) | 665657 | 814522 | 22 Sep 2023 | 2023-09-22 12:00 | Cu.Mtrs |  | 1.2208 | 1.2208 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | Plum Concrete-M20-Pump Room | Sand-Metal Mix M20 (Pumpable) | 669548 | 823856 | 26 Oct 2023 | 2023-10-26 12:00 | Cu.Mtrs |  | 0.55 | 0.55 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D-Bldg Parking Grade Slab D-Parking Grid Slab- Concrete Work | Sand-Metal Mix M20 (Pumpable) | 669549 | 823857 | 26 Oct 2023 | 2023-10-26 12:00 | Cu.Mtrs |  | 10 | 10 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work Footing to top slab - Concrete M25 | Sand-Metal Mix M25 (Pumpable) | 672231 | 814521 | 17 Nov 2023 | 2023-11-17 12:00 | Cu.Mtrs |  | 4 | 4 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | D,E,F-Bldg Side- PQC Road Work(Main Road | Pavement Quality Concrete (M40) | 689082 | 823170 | 02 Apr 2024 | 2024-04-02 12:00 | Cu.Mtrs | Without Fly ash & Without GGBS | 296 | 148 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | 1st PT Slab,Beam Concrete | Ready Mix Concrete M-35 Grade (Downpour) | 697139 | 824840 | 29 May 2024 | 2024-05-29 12:00 | Cu.Mtrs |  | 0.05 | 0.05 | PARSHURAM KORE | 0 | 0 |  | Management | Approved |  | Regular Purchase