## Requisition_Detail_Browse638589
Requisition Detail Browse
Library : Goel Ganga Group
From Date : 01/05/2022 To date: 30/05/2022
Material : Sand-Metal Mix M25 (Downpour)
Status : All
Page 1 of 1
Total Records: 4 Records 1 to 4
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
GANGA ALTUS | RCC Work FW Tank- RCC Pardi Concrete M25 | Sand-Metal Mix M25 (Downpour) | 613614 | 814519 | 18 May 2022 | 2022-05-18 12:00 | Cu.Mtrs |  | 1 | 1 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work FW Tank- RCC Pardi Concrete M25 | Sand-Metal Mix M25 (Downpour) | 613614 | 689096 | 18 May 2022 | 2022-05-18 12:00 | Cu.Mtrs |  | 25 | 24 | Sanket Patil | 62672 | 3229.00 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work FW Tank- RCC Pardi Concrete M25 | Sand-Metal Mix M25 (Downpour) | 613774 | 728877 | 21 May 2022 | 2022-05-21 12:00 | Cu.Mtrs |  | 15 | 14 | vinay mittal | 65352 | 3735.00 | Raised | Management | Approved |  | Regular Purchase
GANGA ALTUS | RCC Work FW Tank- RCC Pardi Concrete M25 | Sand-Metal Mix M25 (Downpour) | 613774 | 814518 | 21 May 2022 | 2022-05-21 12:00 | Cu.Mtrs |  | 1 | 1 | Akshada Mahajan | 0 | 0 |  | Management | Approved |  | Regular Purchase