## Requisition_Tracking-Summary638
Select Supplier
Project : GANGA ASMI
From Date : 01/01/2024 To date: 22/08/2024
Page 1 of 1
Total Records: 202 Records 1 to 202
Srno | ReqSr_no | Task | Material_Name | Tec.Unit | Qty | Supplier | Priority | Req_status | Requisition_Date | Requirement_Date | Remark | Specifications | Approval_Date | Approved_Qty | Approved_By | Rate | Tax_Scheme_Name | BrandName | StockQty | Est_Rate | Discount | Credit | Conversion_Factor | Transport_Rate | Pkg_Forward | Loading | Unloading | Insurance | Installation | OtherCharges1 | OtherCharges2 | HSN_Code | Est_Cost | Consumed_Amt
1 | 677126 | Fixed Assets | CLOUD STORAGE - No. | No. | 1 |  | As Per Lead Period | Approved | 2024-01-08 12:00 | 2024-01-08 12:00 | :: Released from PO 67652 :- PO detail id 155772 :- ReqD_id 777724 |  | 2024-05-08 18:13 | 1 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
2 | 677127 | Fixed Assets | CLOUD USER - No. | No. | 6 |  | As Per Lead Period | Approved | 2024-01-08 12:00 | 2024-01-08 12:00 | :: Released from PO 67652 :- PO detail id 155773 :- ReqD_id 777723 |  | 2024-05-08 18:12 | 6 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 600 | 0
3 | 677888 | DG Maintenance Work | C-Check kit | No. | 1 |  | As Per Lead Period | Approved | 2024-01-16 12:00 | 2024-01-16 12:00 |  |  | 2024-01-16 11:30 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
4 | 678389 | MHADA-Toilet Plumbing Supporting Material | Making nails 12 no 2" | Kgs | 11 |  | Management | Approved | 2024-01-16 12:00 | 2024-01-16 12:00 |  |  | 2024-01-18 15:50 | 11 | Sajid khan | 0 |  | 0 |  | 55 | [12 empty] | 605 | 0
5 | 678907 | MHADA External Plaster South Side External Plaster | Nails 1 1/2" | Kgs | 1.683 |  | Management | Approved | 2024-01-18 12:00 | 2024-01-18 12:00 |  |  | 2024-01-25 18:09 | 1.683 | Sajid khan | 0 |  | 0 |  | 71.4 | [12 empty] | 120.1662 | 0
6 | 678908 | MHADA External Plaster West Side External Plaster | Nails 1 1/2" | Kgs | 2 |  | Management | Approved | 2024-01-18 12:00 | 2024-01-18 12:00 |  |  | 2024-01-25 18:09 | 2 | Sajid khan | 0 |  | 0 |  | 71.4 | [12 empty] | 142.8 | 0
7 | 681173 | Wing-2 Office, Store, Safety Office, Godown PCC | Sand-Metal Mix M15 (Downpour) | Cu.Mtrs | 4 |  | As Per Lead Period | Approved | 2024-01-23 12:00 | 2024-01-23 12:00 | :: Released from PO 67780 :- PO detail id 156066 :- ReqD_id 782654hella infra market pvt ltd |  | 2024-03-29 17:49 | 4 | PARSHURAM KORE | 0 |  | 0 |  | 3165.25 | [12 empty] | 31652.5 | 22409.976
8 | 681287 | Sales Office Sales Office Water Bottle | Sumeru water 200ml - Box Packing | No. | 200 |  | Management | Approved | 2024-01-25 12:00 | 2024-01-25 12:00 |  |  | 2024-01-25 18:09 | 50 | NITIN.PARDESHI | 0 |  | 0 |  | 4.5 | [12 empty] | 1350 | 59000
9 | 681301 | Sales Office Tissue Paper for sales office | Tissue paper | Pack | 10 |  | As Per Lead Period | Approved | 2024-01-26 12:00 | 2024-01-26 12:00 |  |  | 2024-01-30 10:12 | 10 | Sajid khan | 0 |  | 0 |  | 500 | [12 empty] | 15000 | 11800
10 | 682558 | Fixed Assets | Laptop | No. | 3 |  | As Per Lead Period | Approved | 2024-02-02 12:00 | 2024-02-02 12:00 |  |  | 2024-02-07 12:12 | 3 | kantilal.jagtap | 0 |  | 0 |  | 30000 | [12 empty] | 180000 | 115050
11 | 683614 | Site Office Material required for site usage | Engineer Table | No. | 4 |  | As Per Lead Period | Approved | 2024-02-16 12:00 | 2024-02-16 12:00 |  |  | 2024-02-16 12:16 | 4 | SANKET PATIL | 0 |  | 0 |  | 4140 | [12 empty] | 16560 | 0
12 | 685734 | Site Office Material required for site usage | Cupboard | No. | 2 |  | As Per Lead Period | Approved | 2024-03-01 12:00 | 2024-03-01 12:00 |  |  | 2024-03-02 12:50 | 2 | Sajid khan | 0 |  | 0 |  | 4000 | [12 empty] | 8000 | 0
13 | 686127 | New Sales Office Electrical Work | LED Panel Light 15W (Round) 4000K | No. | 90 |  | As Per Lead Period | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 |  |  | 2024-03-04 16:13 | 90 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 9000 | 0
14 | 687839 | Sales office renovation - Electrical work | Ceiling Light | No. | 5 |  | As Per Lead Period | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 | VI SPL (Ceiling Light)- 15 Watt (Brand- Vera LED) |  | 2024-03-18 15:25 | 5 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 500 | 0
15 | 687902 | Site Infra Misc Work | Fastner Hook 10mm | No. | 20 |  | As Per Lead Period | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 | D-Hook with10mm Fastener |  | 2024-03-18 18:18 | 20 | Sajid khan | 0 |  | 0 |  | 47.25 | [12 empty] | 945 | 0
16 | 688047 | Non Tower Area Footing RMC M30 - 78.95 Cu.Mtrs | Sand-Metal Mix M30 (Downpour) | Cu.Mtrs | 13.5 |  | As Per Lead Period | Approved | 2024-03-20 12:00 | 2024-03-20 12:00 | :: Released from PO 68548 :- PO detail id 158307 :- ReqD_id 799777 :: Released from PO 68541 :- PO detail id 158295 :- ReqD_id 799754 :: Released from PO 68409 :- PO detail id 157895 :- ReqD_id 796655 :: Released from PO 68248 :- PO detail id 157470 :- ReqD_id 793175Supplier- Manjulai RMC |  | 2024-04-30 11:53 | 13.5 | Akshada Mahajan | 0 |  | 0 |  | 2100 | [12 empty] | 165803.4 | 128995.3729
17 | 690631 | Wing-1 Flat No 204 Balcony Brickbatt+Finish Coat W/P | M Sand | Cu.Ft | 14.5332 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 69129 :- PO detail id 159900 :- ReqD_id 820635 :: Released from PO 68435 :- PO detail id 157981 :- ReqD_id 795863 |  | 2024-07-08 15:10 | 14.5332 | GULSHAN GANGWANI | 0 |  | 0 |  | 65 | [12 empty] | 944.658 | 0
18 | 690632 | Wing-1 Flat No 205 Balcony Brickbatt+Finish Coat W/P | M Sand | Cu.Ft | 14.5332 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 69129 :- PO detail id 159900 :- ReqD_id 820636 :: Released from PO 68435 :- PO detail id 157981 :- ReqD_id 795862 |  | 2024-07-08 15:10 | 14.5332 | GULSHAN GANGWANI | 0 |  | 0 |  | 65 | [12 empty] | 944.658 | 0
19 | 690633 | Wing-1 Flat No 206 Balcony Brickbatt+Finish Coat W/P | M Sand | Cu.Ft | 19.6596 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 69129 :- PO detail id 159900 :- ReqD_id 820637 :: Released from PO 68435 :- PO detail id 157981 :- ReqD_id 795861 |  | 2024-07-08 15:10 | 19.6596 | GULSHAN GANGWANI | 0 |  | 0 |  | 65 | [12 empty] | 1277.874 | 0
20 | 690634 | Wing-1 Flat No 207 Balcony Brickbatt+Finish Coat W/P | M Sand | Cu.Ft | 19.6596 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 69129 :- PO detail id 159900 :- ReqD_id 820638 :: Released from PO 68435 :- PO detail id 157981 :- ReqD_id 795860 |  | 2024-07-08 15:10 | 19.6596 | GULSHAN GANGWANI | 0 |  | 0 |  | 65 | [12 empty] | 1277.874 | 0
21 | 690635 | Wing-1 Flat No 208 Balcony Brickbatt+Finish Coat W/P | M Sand | Cu.Ft | 14.5332 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 69129 :- PO detail id 159900 :- ReqD_id 820639 :: Released from PO 68435 :- PO detail id 157981 :- ReqD_id 795859 |  | 2024-07-08 15:10 | 14.5332 | GULSHAN GANGWANI | 0 |  | 0 |  | 65 | [12 empty] | 944.658 | 0
22 | 690636 | Wing-1 Flat No 209 Balcony Brickbatt+Finish Coat W/P | M Sand | Cu.Ft | 14.5332 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 69129 :- PO detail id 159900 :- ReqD_id 820640 :: Released from PO 68435 :- PO detail id 157981 :- ReqD_id 795858 |  | 2024-07-08 15:10 | 14.5332 | GULSHAN GANGWANI | 0 |  | 0 |  | 65 | [12 empty] | 944.658 | 0
23 | 690796 | UGWT RCC Plum Concrete Below Raft (C60-R40) | Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 22.95 |  | As Per Lead Period | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | :: Released from PO 68588 :- PO detail id 158373 :- ReqD_id 801339 :: Released from PO 68409 :- PO detail id 157894 :- ReqD_id 796641manjulai RMC |  | 2024-06-19 17:58 | 22.95 | Akshada Mahajan | 0 |  | 0 |  | 2125 | [12 empty] | 235513.75 | 348004.5707
24 | 691342 | Wing 1 (3BHK)-Flat No. 301 Balcony Flooring | Tile Grout | Kgs | 0.5718 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5718 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 57.18 | 0
25 | 691343 | Wing 1 (3BHK)-Flat No. 301 Flat Flooring | Tile Grout | Kgs | 6.9939 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 6.9939 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 699.39 | 0
26 | 691344 | Wing 1 (3BHK)-Flat No. 301 Toilet Flooring | Tile Grout | Kgs | 0.683 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.683 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 68.3 | 0
27 | 691345 | Wing 1 (3BHK)-Flat No. 301 Utility Flooring | Tile Grout | Kgs | 0.3465 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3465 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.65 | 0
28 | 691346 | Wing 1 (3BHK)-Flat No. 302 Balcony Flooring | Tile Grout | Kgs | 0.5719 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5719 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 57.19 | 0
29 | 691347 | Wing 1 (3BHK)-Flat No. 302 Flat Flooring | Tile Grout | Kgs | 7.061 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 7.061 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 706.1 | 0
30 | 691348 | Wing 1 (3BHK)-Flat No. 302 Toilet Flooring | Tile Grout | Kgs | 0.791 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.791 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 79.1 | 0
31 | 691349 | Wing 1 (3BHK)-Flat No. 302 Utility Flooring | Tile Grout | Kgs | 0.3482 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3482 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.82 | 0
32 | 691350 | Wing 1 (2BHK)-Flat No. 303 Balcony Flooring | Tile Grout | Kgs | 0.4252 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4252 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 42.52 | 0
33 | 691351 | Wing 1 (2BHK)-Flat No. 303 Flat Flooring | Tile Grout | Kgs | 5.3183 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3183 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 531.83 | 0
34 | 691352 | Wing 1 (2BHK)-Flat No. 303 Toilet Flooring | Tile Grout | Kgs | 0.7241 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.7241 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 72.41 | 0
35 | 691353 | Wing 1 (2BHK)-Flat No. 303 Utility Flooring | Tile Grout | Kgs | 0.3566 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3566 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 35.66 | 0
36 | 691354 | Wing 1 (2BHK)-Flat No. 305 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
37 | 691355 | Wing 1 (2BHK)-Flat No. 305 Flat Flooring | Tile Grout | Kgs | 5.3721 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3721 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 537.21 | 0
38 | 691356 | Wing 1 (2BHK)-Flat No. 305 Toilet Flooring | Tile Grout | Kgs | 0.704 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.704 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 70.4 | 0
39 | 691357 | Wing 1 (2BHK)-Flat No. 305 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
40 | 691358 | Wing 1 (3BHK)-Flat No. 306 Balcony Flooring | Tile Grout | Kgs | 0.5461 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5461 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 54.61 | 0
41 | 691359 | Wing 1 (3BHK)-Flat No. 306 Flat Flooring | Tile Grout | Kgs | 7.1113 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 7.1113 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 711.13 | 0
42 | 691360 | Wing 1 (3BHK)-Flat No. 306 Toilet Flooring | Tile Grout | Kgs | 0.775 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.775 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 77.5 | 0
43 | 691361 | Wing 1 (3BHK)-Flat No. 306 Utility Flooring | Tile Grout | Kgs | 0.3401 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3401 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.01 | 0
44 | 691362 | Wing 1 (3BHK)-Flat No. 307 Balcony Flooring | Tile Grout | Kgs | 0.5461 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5461 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 54.61 | 0
45 | 691363 | Wing 1 (3BHK)-Flat No. 307 Flat Flooring | Tile Grout | Kgs | 7.1113 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 7.1113 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 711.13 | 0
46 | 691364 | Wing 1 (3BHK)-Flat No. 307 Toilet Flooring | Tile Grout | Kgs | 0.775 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.775 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 77.5 | 0
47 | 691365 | Wing 1 (3BHK)-Flat No. 307 Utility Flooring | Tile Grout | Kgs | 0.3401 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3401 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.01 | 0
48 | 691366 | Wing 1 (2BHK)-Flat No. 308 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
49 | 691367 | Wing 1 (2BHK)-Flat No. 308 Flat Flooring | Tile Grout | Kgs | 5.3721 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3721 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 537.21 | 0
50 | 691368 | Wing 1 (2BHK)-Flat No. 308 Toilet Flooring | Tile Grout | Kgs | 0.704 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.704 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 70.4 | 0
51 | 691369 | Wing 1 (2BHK)-Flat No. 308 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
52 | 691370 | Wing 1 (2BHK)-Flat No. 309 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
53 | 691371 | Wing 1 (2BHK)-Flat No. 309 Flat Flooring | Tile Grout | Kgs | 5.3521 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3521 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 535.21 | 0
54 | 691372 | Wing 1 (2BHK)-Flat No. 309 Toilet Flooring | Tile Grout | Kgs | 0.7241 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.7241 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 72.41 | 0
55 | 691373 | Wing 1 (2BHK)-Flat No. 309 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
56 | 691374 | Wing 1 (2BHK)-Flat No. 304 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
57 | 691375 | Wing 1 (2BHK)-Flat No. 304 Flat Flooring | Tile Grout | Kgs | 5.3715 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3715 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 537.15 | 0
58 | 691376 | Wing 1 (2BHK)-Flat No. 304 Toilet Flooring | Tile Grout | Kgs | 0.704 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.704 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 70.4 | 0
59 | 691377 | Wing 1 (2BHK)-Flat No. 304 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
60 | 691379 | Wing 1- 201 Balcony Flooring | Tile Grout | Kgs | 0.5718 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5718 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 57.18 | 0
61 | 691380 | Wing 1- 201 Flat Flooring | Tile Grout | Kgs | 6.9939 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 6.9939 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 699.39 | 0
62 | 691381 | Wing 1- 201 Master Toilet Flooring | Tile Grout | Kgs | 0.683 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.683 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 68.3 | 0
63 | 691382 | Wing 1- 201 Utility Flooring | Tile Grout | Kgs | 0.3465 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3465 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.65 | 0
64 | 691383 | Wing 1- 202 Balcony Flooring | Tile Grout | Kgs | 0.5719 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5719 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 57.19 | 0
65 | 691384 | Wing 1- 202 Flat Flooring | Tile Grout | Kgs | 7.061 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 7.061 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 706.1 | 0
66 | 691385 | Wing 1- 202 Toilet Flooring | Tile Grout | Kgs | 0.791 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.791 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 113.76 | 0
67 | 691386 | Wing 1- 202 Utility Flooring | Tile Grout | Kgs | 0.3482 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3482 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.82 | 0
68 | 691387 | Wing 1- 203 Balcony Flooring | Tile Grout | Kgs | 0.4252 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4252 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 42.52 | 0
69 | 691388 | Wing 1- 203 Flat Flooring | Tile Grout | Kgs | 5.3183 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3183 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 531.83 | 0
70 | 691389 | Wing 1- 203 Toilet Flooring | Tile Grout | Kgs | 0.7241 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.7241 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 72.41 | 0
71 | 691390 | Wing 1- 203 Utility Flooring | Tile Grout | Kgs | 0.3566 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3566 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 35.66 | 0
72 | 691391 | Wing 1- 205 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
73 | 691392 | Wing 1- 205 Flat Flooring | Tile Grout | Kgs | 5.3721 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3721 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 537.21 | 0
74 | 691393 | Wing 1- 205 Toilet Flooring | Tile Grout | Kgs | 0.704 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.704 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 70.4 | 0
75 | 691394 | Wing 1- 205 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
76 | 691395 | Wing 1- 206 Balcony Flooring | Tile Grout | Kgs | 0.5461 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5461 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 54.61 | 0
77 | 691396 | Wing 1- 206 Flat Flooring | Tile Grout | Kgs | 7.1113 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 7.1113 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 711.13 | 0
78 | 691397 | Wing 1- 206 Toilet Flooring | Tile Grout | Kgs | 0.775 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.775 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 77.5 | 0
79 | 691398 | Wing 1- 206 Utility Flooring | Tile Grout | Kgs | 0.3401 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3401 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.01 | 0
80 | 691399 | Wing 1- 207 Balcony Flooring | Tile Grout | Kgs | 0.5461 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.5461 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 54.61 | 0
81 | 691400 | Wing 1- 207 Flat Flooring | Tile Grout | Kgs | 7.1113 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 7.1113 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 711.13 | 0
82 | 691401 | Wing 1- 207 Toilet Flooring | Tile Grout | Kgs | 0.775 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.775 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 77.5 | 0
83 | 691402 | Wing 1- 207 Utility Flooring | Tile Grout | Kgs | 0.3401 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3401 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.01 | 0
84 | 691403 | Wing 1- 208 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
85 | 691404 | Wing 1- 208 Flat Flooring | Tile Grout | Kgs | 5.3721 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3721 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 537.21 | 0
86 | 691405 | Wing 1- 208 Toilet Flooring | Tile Grout | Kgs | 0.704 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.704 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 70.4 | 0
87 | 691406 | Wing 1- 208 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
88 | 691407 | Wing 1- 209 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
89 | 691408 | Wing 1- 209 Flat Flooring | Tile Grout | Kgs | 5.3521 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3521 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 535.21 | 0
90 | 691409 | Wing 1- 209 Toilet Flooring | Tile Grout | Kgs | 0.7241 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.7241 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 72.41 | 0
91 | 691410 | Wing 1- 209 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
92 | 691411 | Wing 1- 204 Balcony Flooring | Tile Grout | Kgs | 0.4037 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.4037 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 40.37 | 0
93 | 691412 | Wing 1- 204 Flat Flooring | Tile Grout | Kgs | 5.3715 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 5.3715 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 537.15 | 0
94 | 691413 | Wing 1- 204 Toilet Flooring | Tile Grout | Kgs | 0.704 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.704 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 70.4 | 0
95 | 691414 | Wing 1- 204 Utility Flooring | Tile Grout | Kgs | 0.3488 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-04-18 12:18 | 0.3488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 34.88 | 0
96 | 691818 | MHADA-Flat No 203 Toilet Rough (Tar) Plaster | Recron Fiber | Pack | 1.3866 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798393 |  | 2024-05-02 14:02 | 1.3866 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 36.0516 | 0
97 | 691819 | MHADA.Flat No 202 Kitchen otta (Tar) Plaster | Recron Fiber | Pack | 0.5244 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798392 |  | 2024-05-02 14:02 | 0.5244 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 13.6344 | 0
98 | 691820 | MHADA-Flat No 204 WHB (Tar) Plaster | Recron Fiber | Pack | 0.1635 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798391 |  | 2024-05-02 14:02 | 0.1635 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 4.251 | 0
99 | 691821 | MHADA-Flat No 205 WHB (Tar) Plaster | Recron Fiber | Pack | 0.1635 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798390 |  | 2024-05-02 14:02 | 0.1635 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 4.251 | 0
100 | 691822 | MHADA-Flat No 205 Kitchen otta (Tar) Plaster | Recron Fiber | Pack | 0.4418 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798389 |  | 2024-05-02 14:02 | 0.4418 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 11.4868 | 0
101 | 691823 | MHADA-Flat No 204 Kitchen otta (Tar) Plaster | Recron Fiber | Pack | 0.4521 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798388 |  | 2024-05-02 14:02 | 0.4521 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 11.7546 | 0
102 | 691824 | MHADA-Flat No 203 WHB (Tar) Plaster | Recron Fiber | Pack | 0.1635 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798387 |  | 2024-05-02 14:02 | 0.1635 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 4.251 | 0
103 | 691825 | MHADA.Flat No 201 WHB (Tar) Plaster | Recron Fiber | Pack | 0.2397 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798386 |  | 2024-05-02 14:02 | 0.2397 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 6.2322 | 0
104 | 691826 | MHADA.Flat No 201 Kitchen otta (Tar) Plaster | Recron Fiber | Pack | 0.3342 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798385 |  | 2024-05-02 14:02 | 0.3342 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 8.6892 | 0
105 | 691827 | MHADA-Flat No 203 Kitchen otta (Tar) Plaster | Recron Fiber | Pack | 0.4464 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798384 |  | 2024-05-02 14:02 | 0.4464 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 11.6064 | 0
106 | 691828 | MHADA.Flat No 201 Utility (Tar) Plaster | Recron Fiber | Pack | 1.6662 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798383 |  | 2024-05-02 14:02 | 1.6662 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 43.3212 | 0
107 | 691829 | MHADA.Flat No 202 Utility (Tar) Plaster | Recron Fiber | Pack | 1.5258 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798382 |  | 2024-05-02 14:02 | 1.5258 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 39.6708 | 0
108 | 691830 | MHADA.Flat No 203 Utility (Tar) Plaster | Recron Fiber | Pack | 0.9809 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798381 |  | 2024-05-02 14:02 | 0.9809 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 25.5034 | 0
109 | 691831 | MHADA.Flat No 204 Utility (Tar) Plaster | Recron Fiber | Pack | 0.9809 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 | :: Released from PO 68571 :- PO detail id 158336 :- ReqD_id 798380 |  | 2024-05-02 14:02 | 0.9809 | Akshada Mahajan | 0 |  | 0 |  | 26 | [12 empty] | 25.5034 | 0
110 | 692146 | Wing 2 Barrication Work | MS Square Pipe 40mmx40mm 2mm thk | Mtrs | 1000 |  | As Per Lead Period | Approved | 2024-04-23 12:00 | 2024-04-23 12:00 |  |  | 2024-04-25 15:17 | 1000 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 100000 | 0
111 | 692166 | Wing 1- 201 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 699.39 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806712 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804029 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803717 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801167 |  | 2024-05-28 12:10 | 699.39 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 69939 | 0
112 | 692167 | Wing 1- 202 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 706.1 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806713 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804028 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803718 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801166 |  | 2024-05-28 12:10 | 706.1 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 70610 | 0
113 | 692168 | Wing 1- 203 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 531.83 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806714 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804027 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803719 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801165 |  | 2024-05-28 12:10 | 531.83 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 53183 | 0
114 | 692169 | Wing 1- 205 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 537.21 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806715 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804026 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803720 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801164 |  | 2024-05-28 12:10 | 537.21 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 53721 | 0
115 | 692170 | Wing 1- 206 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 711.13 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806716 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804025 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803721 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801163 |  | 2024-05-28 12:10 | 711.13 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 71113 | 0
116 | 692171 | Wing 1- 207 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 711.13 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806717 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804024 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803722 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801162 |  | 2024-05-28 12:10 | 711.13 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 71113 | 0
117 | 692172 | Wing 1- 208 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 537.21 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806718 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804023 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803723 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801161 |  | 2024-05-28 12:10 | 537.21 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 53721 | 0
118 | 692173 | Wing 1- 209 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 535.21 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806719 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804022 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803724 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801160 |  | 2024-05-28 12:10 | 535.21 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 53521 | 0
119 | 692174 | Wing 1- 204 Flat Flooring | Superwhite Tile 600 X 600 (DC) (AGL) | Sq.Ft | 537.15 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158785 :- ReqD_id 806720 :: Released from PO 68652 :- PO detail id 158532 :- ReqD_id 804021 :: Released from PO 68643 :- PO detail id 158513 :- ReqD_id 803725 :: Released from PO 68612 :- PO detail id 158442 :- ReqD_id 801159 |  | 2024-05-28 12:10 | 537.15 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 53715 | 0
120 | 692193 | Wing 1- 201 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.11 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806703 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804020 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803690 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801140 |  | 2024-05-28 12:10 | 33.11 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3311 | 0
121 | 692194 | Flat 202 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.11 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806704 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804019 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803691 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801139 |  | 2024-05-28 12:10 | 33.11 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3311 | 0
122 | 692195 | Wing -1 (2BHK) Flat 203 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 29.84 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806705 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804018 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803692 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801138 |  | 2024-05-28 12:10 | 29.84 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 2984 | 0
123 | 692196 | Wing -1 (2BHK) Flat 204 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.74 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806706 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804017 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803693 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801137 |  | 2024-05-28 12:10 | 31.74 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3174 | 0
124 | 692197 | Wing -1 (2BHK) Flat 205 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.74 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806707 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804016 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803694 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801136 |  | 2024-05-28 12:10 | 31.74 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3174 | 0
125 | 692198 | Flat 206 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.31 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806708 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804015 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803695 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801135 |  | 2024-05-28 12:10 | 33.31 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3331 | 0
126 | 692199 | Flat 207 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 33.31 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806709 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804014 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803696 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801134 |  | 2024-05-28 12:10 | 33.31 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3331 | 0
127 | 692200 | Wing -1 (2BHK) Flat 208 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.74 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806710 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804013 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803697 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801133 |  | 2024-05-28 12:10 | 31.74 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3174 | 0
128 | 692201 | Wing -1 (2BHK) Flat 209 Kitchen Dado (M) | Artific Bianco Tile 300 X 600 (AGL) | Sq.Ft | 31.73 |  | As Per Lead Period | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68780 :- PO detail id 158786 :- ReqD_id 806711 :: Released from PO 68652 :- PO detail id 158531 :- ReqD_id 804012 :: Released from PO 68643 :- PO detail id 158512 :- ReqD_id 803698 :: Released from PO 68612 :- PO detail id 158439 :- ReqD_id 801132 |  | 2024-05-28 12:10 | 31.73 | Akshada Mahajan | 0 |  | 0 |  | 100 | [12 empty] | 3173 | 0
129 | 693476 | Wing 2 - P4 (3rd Slab) to P5 (4th Slab) Column M50 | Sand-Metal Mix M50 hi-flow (Downpour) | Cu.Mtrs | 2.5 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 | :: Released from PO 68806 :- PO detail id 158863 :- ReqD_id 807623 :: Released from PO 68798 :- PO detail id 158851 :- ReqD_id 807573 :: Released from PO 68757 :- PO detail id 158752 :- ReqD_id 806514 :: Released from PO 68573 :- PO detail id 158342 :- ReqD_id 801112Manjulai RMC |  | 2024-06-19 18:03 | 2.5 | Akshada Mahajan | 0 |  | 0 |  | 3150 | [12 empty] | 643293 | 792607.6665
130 | 693571 | Wing 1 (3BHK)-Flat No. 301 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 57.18 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 57.18 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 5718 | 0
131 | 693572 | Wing 1 (3BHK)-Flat No. 301 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.65 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.65 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3465 | 0
132 | 693573 | Wing 1 (3BHK)-Flat No. 302 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 57.19 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 57.19 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 5719 | 0
133 | 693574 | Wing 1 (3BHK)-Flat No. 302 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.82 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.82 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3482 | 0
134 | 693575 | Wing 1 (2BHK)-Flat No. 303 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 42.52 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 42.52 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4252 | 0
135 | 693576 | Wing 1 (2BHK)-Flat No. 303 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 35.66 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 35.66 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3566 | 0
136 | 693577 | Wing 1 (2BHK)-Flat No. 305 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 40.37 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 40.37 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4037 | 0
137 | 693578 | Wing 1 (2BHK)-Flat No. 305 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.88 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.88 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3488 | 0
138 | 693579 | Wing 1 (3BHK)-Flat No. 306 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 54.61 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 54.61 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 5461 | 0
139 | 693580 | Wing 1 (3BHK)-Flat No. 306 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.01 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.01 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3401 | 0
140 | 693581 | Wing 1 (3BHK)-Flat No. 307 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 54.61 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 54.61 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 5461 | 0
141 | 693582 | Wing 1 (3BHK)-Flat No. 307 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.01 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.01 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3401 | 0
142 | 693583 | Wing 1 (2BHK)-Flat No. 308 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 40.37 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 40.37 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4037 | 0
143 | 693584 | Wing 1 (2BHK)-Flat No. 308 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.88 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.88 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3488 | 0
144 | 693585 | Wing 1 (2BHK)-Flat No. 309 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 40.37 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 40.37 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4037 | 0
145 | 693586 | Wing 1 (2BHK)-Flat No. 309 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.88 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.88 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3488 | 0
146 | 693587 | Wing 1 (2BHK)-Flat No. 304 Balcony Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 40.37 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 40.37 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4037 | 0
147 | 693588 | Wing 1 (2BHK)-Flat No. 304 Utility Flooring | Anti-skid Tile 300 X 300 (Grey color) | Sq.Ft | 34.88 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.88 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3488 | 0
148 | 693599 | Wing 1 (3BHK)-Flat No. 301 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 35.52 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 35.52 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3552 | 0
149 | 693600 | Wing 1 (3BHK)-Flat No. 302 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 44.4 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 44.4 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4440 | 0
150 | 693601 | Wing 1 (2BHK)-Flat No. 303 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 39.96 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 39.96 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3996 | 0
151 | 693602 | Wing 1 (2BHK)-Flat No. 305 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 38.75 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 38.75 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3875 | 0
152 | 693603 | Wing 1 (3BHK)-Flat No. 306 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 43.59 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 43.59 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4359 | 0
153 | 693604 | Wing 1 (3BHK)-Flat No. 307 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 43.59 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 43.59 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 4359 | 0
154 | 693605 | Wing 1 (2BHK)-Flat No. 308 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 38.75 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 38.75 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3875 | 0
155 | 693606 | Wing 1 (2BHK)-Flat No. 309 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 39.96 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 39.96 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3996 | 0
156 | 693607 | Wing 1 (2BHK)-Flat No. 304 Toilet Flooring | Artific Gris Tile 300 X 300 (AGL) | Sq.Ft | 38.75 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 38.75 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3875 | 0
157 | 693608 | Wing 1 (3BHK)-Flat No. 301 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 32.78 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 32.78 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3278 | 0
158 | 693609 | Wing 1 (3BHK)-Flat No. 302 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 34.7 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 34.7 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3470 | 0
159 | 693610 | Wing 1 (2BHK)-Flat No. 303 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 32.45 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 32.45 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3245 | 0
160 | 693611 | Wing 1 (2BHK)-Flat No. 305 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 31.64 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 31.64 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3164 | 0
161 | 693612 | Wing 1 (3BHK)-Flat No. 306 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 33.9 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 33.9 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3390 | 0
162 | 693613 | Wing 1 (3BHK)-Flat No. 307 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 33.9 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 33.9 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3390 | 0
163 | 693614 | Wing 1 (2BHK)-Flat No. 308 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 31.64 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 31.64 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3164 | 0
164 | 693615 | Wing 1 (2BHK)-Flat No. 309 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 32.45 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 32.45 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3245 | 0
165 | 693616 | Wing 1 (2BHK)-Flat No. 304 Toilet Flooring | Caron Tan Tile 300 X 300 (AGL) | Sq.Ft | 31.64 |  | Management | Approved | 2024-05-02 12:00 | 2024-05-02 12:00 |  |  | 2024-05-06 11:05 | 31.64 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3164 | 0
166 | 695101 | Wing-3 Sub. Concrete PCC M-15 | Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 34.5 |  | As Per Lead Period | Approved | 2024-05-08 12:00 | 2024-05-08 12:00 | :: Released from PO 68615 :- PO detail id 158447 :- ReqD_id 803175Supplier- Future India RMC |  | 2024-06-19 17:58 | 34.5 | Akshada Mahajan | 0 |  | 0 |  | 2125 | [12 empty] | 201301.25 | 50297.5
167 | 695751 | 1st Flr Fire Staircase Flooring | Kota Tappa 48"x12" (47"x11") - Sq.Ft | Sq.Ft | 80 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 80 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 12000 | 0
168 | 695752 | 2nd Flr Fire Staircase Flooring | Kota Tappa 48"x12" (47"x11") - Sq.Ft | Sq.Ft | 80 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 80 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 12000 | 0
169 | 695753 | 3rd Flr Fire Staircase Flooring | Kota Tappa 48"x12" (47"x11") - Sq.Ft | Sq.Ft | 80 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 80 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 12000 | 0
170 | 695754 | 4th Flr Fire Staircase Flooring | Kota Tappa 48"x12" (47"x11") - Sq.Ft | Sq.Ft | 80 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 80 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 12000 | 0
171 | 695755 | 5th Flr Fire Staircase Flooring | Kota Tappa 48"x12" (47"x11") - Sq.Ft | Sq.Ft | 80 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 80 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 12000 | 0
172 | 695756 | 1st Flr Fire Staircase Flooring | Kota Tappa 54" x 12" (53"x11") | Sq.Ft | 163 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 163 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 16300 | 0
173 | 695757 | 2nd Flr Fire Staircase Flooring | Kota Tappa 54" x 12" (53"x11") | Sq.Ft | 163 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 163 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 16300 | 0
174 | 695758 | 3rd Flr Fire Staircase Flooring | Kota Tappa 54" x 12" (53"x11") | Sq.Ft | 163 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 163 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 16300 | 0
175 | 695759 | 4th Flr Fire Staircase Flooring | Kota Tappa 54" x 12" (53"x11") | Sq.Ft | 163 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 163 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 16300 | 0
176 | 695760 | 5th Flr Fire Staircase Flooring | Kota Tappa 54" x 12" (53"x11") | Sq.Ft | 163 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 163 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 16300 | 0
177 | 695771 | Lobby Flooring | Altus Beige Tile 600 X 600 | Sq.Ft | 1279.371 |  | As Per Lead Period | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 1279.371 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 127937.1 | 0
178 | 695773 | Lobby Flooring | Tile Grout | Kgs | 12.79 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-18 15:10 | 12.79 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1279 | 0
179 | 697160 | Wing 1 Parking Column 1st to 2nd Slab Concrete | Sand-Metal Mix M50 hi-flow (Downpour) | Cu.Mtrs | 0.068 |  | As Per Lead Period | Approved | 2024-05-30 14:29 | 2024-05-30 12:00 | :: Released from PO 68799 :- PO detail id 158852 :- ReqD_id 807595Future India RMC |  | 2024-06-19 18:03 | 0.068 | Akshada Mahajan | 0 |  | 0 |  | 3150 | [12 empty] | 27216 | 2336.4653
180 | 697840 | Wing 2 . 3rd Slab (Staircase, Beam,Slab) Steel | Steel Bars 8mm | Kgs | 7476 |  | Management | Approved | 2024-06-01 17:31 | 2024-06-01 12:00 |  |  | 2024-06-03 18:26 | 28 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 380154.6 | 478980.88
181 | 697844 | Wing 1-9th Slab (3rd Floor) Slab,Beam,Stair. Steel | Steel Bars 10mm | Kgs | 197.66 |  | Management | Approved | 2024-06-01 17:35 | 2024-06-01 12:00 |  |  | 2024-06-03 18:26 | 6.66 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 181105.8345 | 11945.14
182 | 697847 | Wing 1-10th Slab (4th Floor) Slab,Beam,Stair. Steel | Steel Bars 20mm | Kgs | 238.64 |  | Management | Approved | 2024-06-01 17:39 | 2024-06-01 12:00 |  |  | 2024-06-03 18:26 | 0.954 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 212805.7245 | 14864.8824
183 | 702010 | Goel House Material required for rennovation. | Self Tapping 25x8 | Box | 4 |  | Management | Approved | 2024-06-15 19:08 | 2024-06-15 12:00 |  |  | 2024-06-17 11:21 | 4 | PARSHURAM KORE | 0 |  | 0 |  | 640.5 | [12 empty] | 2562 | 0
184 | 702012 | Goel House Material required for rennovation. | SS CSK screw 100x10 Star Head | No. | 70 |  | Management | Approved | 2024-06-15 19:12 | 2024-06-15 12:00 |  |  | 2024-06-17 11:21 | 30 | PARSHURAM KORE | 0 |  | 0 |  | 100 | [12 empty] | 53000 | 5289.526
185 | 702017 | Goel House Material required for rennovation. | Aluminium Section 4" x 3/4" -12'- | No. | 3 |  | Management | Approved | 2024-06-15 19:18 | 2024-06-15 12:00 |  |  | 2024-06-17 11:21 | 2 | PARSHURAM KORE | 0 |  | 0 |  | 1395 | [12 empty] | 34875 | 48863.8
186 | 703539 | Goel House Electrical Work | Cat-6 Lan Cable | Mtrs | 300 |  | Management | Approved | 2024-06-27 17:00 | 2024-06-27 12:00 |  |  | 2024-06-27 18:04 | 300 | Sajid khan | 0 |  | 0 |  | 17.85 | [12 empty] | 5355 | 0
187 | 703544 | DG Set Goel House 180kva DG-set Servicing kit | HMI Controller | No. | 1 |  | Management | Approved | 2024-06-28 12:36 | 2024-06-28 12:00 |  |  | 2024-07-02 11:18 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
188 | 704273 | Equipments For Leveling Work | Auto Level | set | 1 |  | As Per Lead Period | Approved | 2024-07-02 10:43 | 2024-07-02 12:00 |  |  | 2024-07-02 11:18 | 1 | Sajid khan | 0 |  | 0 |  | 22725 | [12 empty] | 22725 | 0
189 | 704869 | Lab & Safety Equipments Site Safety Material | Safety shoes | No. | 6 |  | As Per Lead Period | Approved | 2024-07-03 09:03 | 2024-07-03 12:00 | (Ashish Kumar- 7 No), (Bhumika Pawar-5 No) ,(Prasad Mahamuni-10 No), (Ajinkya Sawant-8 No),(Vikas Garade-11 No), (Anand Ballal (Labour)-8 No) |  | 2024-07-04 11:31 | 1 | AKSHADA MAHAJAN |  |  | 0 |  | 275 | [12 empty] | 33000 | 129370.8
190 | 704869 | Lab & Safety Equipments Site Safety Material | Safety shoes | No. | 6 | DEV SAFETY PRODUCTS | As Per Lead Period | Approved | 2024-07-03 09:03 | 2024-07-03 12:00 | (Ashish Kumar- 7 No), (Bhumika Pawar-5 No) ,(Prasad Mahamuni-10 No), (Ajinkya Sawant-8 No),(Vikas Garade-11 No), (Anand Ballal (Labour)-8 No) |  | 2024-07-04 11:31 | 5 | Sajid khan | 834.4 | C+S GST 12% I/P RD | 0 |  | 275 | 0 | 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 129370.8
191 | 704870 | Lab & Safety Equipments Site Safety Material | Safety Jacket | No. | 20 | DEV SAFETY PRODUCTS | Management | Approved | 2024-07-03 09:04 | 2024-07-03 12:00 | Reflective Safety Jacket with Real Rich Logo for staff |  | 2024-07-04 11:31 | 20 | Sajid khan | 225.76 | C+S GST 5% I/P RD | 0 |  | 250 | 0 | 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46250 | 33806.2
192 | 705278 | Lab & Safety Equipments Site Safety Material | Safety shoes | No. | 2 | DEV SAFETY PRODUCTS | As Per Lead Period | Approved | 2024-07-03 19:03 | 2024-07-03 12:00 | (Sumit Sharma- 10 No) (Kumar Devi- 8 No) (Nikhil Walunj- 9 NO) | Staff shoes required of Karam Brand | 2024-07-04 11:25 | 2 | Sajid khan | 1327.5 | C+S GST 18% I/P RD | 0 |  | 275 | 0 | 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 129370.8
193 | 705279 | Lab & Safety Equipments Site Safety Material | Safety shoes | No. | 1 | DEV SAFETY PRODUCTS | Management | Approved | 2024-07-03 19:04 | 2024-07-03 12:00 | Nikhil Walunj- 9 No |  | 2024-07-04 11:25 | 1 | Sajid khan | 1327.5 | C+S GST 18% I/P RD | 0 |  | 275 | 0 | 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 129370.8
194 | 706708 | Site Illumination CCTV Camera-(No.) | Cat-6 Lan Cable | Mtrs | 610 |  | As Per Lead Period | Approved | 2024-07-16 09:32 | 2024-07-16 12:00 |  |  | 2024-07-18 10:40 | 610 | kantilal.jagtap | 0 |  | 0 |  | 17.85 | [12 empty] | 38109.75 | 40871.6425
195 | 706786 | Labour Camp Work | Red Oxide Color Ltr | Ltrs | 20 |  | As Per Lead Period | Approved | 2024-07-16 12:03 | 2024-07-16 12:00 |  |  | 2024-07-18 10:40 | 20 | kantilal.jagtap | 0 |  | 0 |  | 100 | [12 empty] | 4000 | 0
196 | 707230 | HT/LT Work HT/LT Line Work | HDPE Corr. Pipe 300mm(ID) (D-REX) | Mtrs | 45 |  | As Per Lead Period | Approved | 2024-07-18 16:38 | 2024-07-18 12:00 |  |  | 2024-07-19 10:39 | 45 | kantilal.jagtap | 0 |  | 0 |  | 600 | [12 empty] | 27000 | 0
197 | 707232 | HT/LT Work HT/LT Line Work | HDPE Corr. Pipe 450mm(ID) (D-REX) | Mtrs | 45 |  | Management | Approved | 2024-07-18 16:38 | 2024-07-18 12:00 |  |  | 2024-07-19 10:39 | 45 | kantilal.jagtap | 0 |  | 0 |  | 100 | [12 empty] | 4500 | 0
198 | 707235 | Wing-1 Aluform Misc. Consumables | Foam Sheet 3mm thk. (6.5x4) | Sq.Ft | 6500 |  | As Per Lead Period | Approved | 2024-07-18 17:52 | 2024-07-18 12:00 |  |  | 2024-07-19 10:39 | 6500 | kantilal.jagtap | 0 |  | 0 |  | 2.5 | [12 empty] | 93275 | 17726.904
199 | 707241 | Fixed Assets | MS Angle Box Open Type Rack | No. | 1 |  | Management | Approved | 2024-07-18 18:35 | 2024-07-18 12:00 |  |  | 2024-07-19 10:39 | 1 | kantilal.jagtap | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
200 | 707242 | Fixed Assets | Online UPS with Isolation | No. | 1 |  | As Per Lead Period | Approved | 2024-07-18 18:36 | 2024-07-18 12:00 |  |  | 2024-07-19 10:39 | 1 | kantilal.jagtap | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
201 | 707243 | Fixed Assets | Interconnecting Links & Cables | No. | 1 |  | Management | Approved | 2024-07-18 18:37 | 2024-07-18 12:00 |  |  | 2024-07-19 10:39 | 1 | kantilal.jagtap | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
202 | 707245 | Fixed Assets | Battery 12V 42AH (Quanta) | No. | 8 |  | As Per Lead Period | Approved | 2024-07-18 18:39 | 2024-07-18 12:00 |  |  | 2024-07-19 10:39 | 8 | kantilal.jagtap | 0 |  | 0 |  | 5100 | [12 empty] | 40800 | 0