## Requisition_Tracking-Summary638
Select Supplier
Project : GANGA DHAM TOWERS
From Date : 01/01/2024 To date: 29/08/2024
Page 1 of 1
Total Records: 295 Records 1 to 295
Srno | ReqSr_no | Task | Material_Name | Tec.Unit | Qty | Supplier | Priority | Req_status | Requisition_Date | Requirement_Date | Remark | Specifications | Approval_Date | Approved_Qty | Approved_By | Rate | Tax_Scheme_Name | BrandName | StockQty | Est_Rate | Discount | Credit | Conversion_Factor | Transport_Rate | Pkg_Forward | Loading | Unloading | Insurance | Installation | OtherCharges1 | OtherCharges2 | HSN_Code | Est_Cost | Consumed_Amt
1 | 676854 | Club House Landscaping Plantation Work | Lagerstormia Reginae - No. | No. | 6 |  | Management | Approved | 2024-01-03 12:00 | 2024-01-03 12:00 |  |  | 2024-01-03 18:46 | 6 | Sajid khan | 0 |  | 0 |  | 900 | [12 empty] | 5400 | 0
2 | 676855 | Plantation work from OWC to Club House | Asparagus | No. | 115 |  | Management | Approved | 2024-01-03 12:00 | 2024-01-03 12:00 |  |  | 2024-01-03 18:46 | 115 | Sajid khan | 0 |  | 0 |  | 200 | [12 empty] | 23000 | 0
3 | 677266 | Ho Admin Expensess ( M) | Transfer challan | No. | 10 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-02-21 16:17 | 10 | KANTILAL.JAGTAP | 0 |  | 0 |  | 50 | [12 empty] | 3350 | 5770.5
4 | 678513 | 125 Kva DG B Check Servicing | Transport Charges | No. | 1 |  | Management | Approved | 2024-01-17 12:00 | 2024-01-17 12:00 |  |  | 2024-01-18 16:11 | 1 | Sajid khan | 0 |  | 0 |  | 1500 | [12 empty] | 10500 | 3363
5 | 682703 | C Misc Material | Kiltan ( Hessian Cloth ) | Mtrs | 103.34 |  | Management | Approved | 2024-02-03 12:00 | 2024-02-03 12:00 | :: Released from PO 68971 :- PO detail id 159461 :- ReqD_id 793156 :: Released from PO 67917 :- PO detail id 156519 :- ReqD_id 785368 |  | 2024-06-18 12:50 | 103.34 | Akshada Mahajan | 0 |  | 0 |  | 17.5 | [12 empty] | 105000 | 145025.832
6 | 683363 | Steel MTBT E-Bldg 18th to 22nd Slab | Steel Bars 32mm | Kgs | 2377 |  | Management | Approved | 2024-02-07 12:00 | 2024-02-07 12:00 | For Altus |  | 2024-02-07 18:54 | 917 | Vinay Mittal | 0 |  | 0 |  | 100 | [12 empty] | 337700 | 152488.28
7 | 683391 | A 23rd Floor Lobby & Lift Cladding Tile Adhesive | Tenax Creama Solid 1.5kg Set | set | 0.68 |  | Management | Approved | 2024-02-08 12:00 | 2024-02-08 12:00 | :: Released from PO 67946 :- PO detail id 156615 :- ReqD_id 786506 |  | 2024-03-23 11:14 | 0.68 | vinay mittal | 0 |  | 0 |  | 1000 | [12 empty] | 6343.5 | 4778.2955
8 | 683522 | B 2702 NOC | Tenax Transparent Solid 1.5Kg | set | 0.74 |  | Management | Approved | 2024-02-10 12:00 | 2024-02-10 12:00 | :: Released from PO 67946 :- PO detail id 156614 :- ReqD_id 786837 |  | 2024-05-16 17:57 | 0.74 | Akshada Mahajan | 0 |  | 0 |  | 1000 | [12 empty] | 1000 | 322.14
9 | 683568 | B 16th Floor 1601 CP & Sanitary | Drain Pipe (JWA-CHR-DRNPIPE80) | No. | 1 |  | Management | Approved | 2024-02-13 12:00 | 2024-02-13 12:00 |  |  | 2024-02-13 18:02 | 1 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
10 | 683798 | Temporary Electrical Work required Material | Grinder | No. | 1 |  | Management | Approved | 2024-02-16 12:00 | 2024-02-16 12:00 |  |  | 2024-02-16 17:08 | 1 | Sajid khan | 0 |  | 0 |  | 500 | [12 empty] | 500 | 0
11 | 685346 | A Main Line Electrical Work (M) (upto 26th floor) | PVC Copper Wire 16Sqmm Black | Mtrs | 15.6 |  | Management | Approved | 2024-02-24 12:00 | 2024-02-24 12:00 | :: Released from PO 68080 :- PO detail id 157058 :- ReqD_id 789224 |  | 2024-04-08 18:58 | 1 | Vinay Mittal | 0 |  | 0 |  | 300 | [12 empty] | 1082160 | 598430.0152
12 | 686038 | Steel MTBT E-20th Sl.19th to 20th Column,SW Steel | Steel Bars 10mm | Kgs | 150 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 | :: Released from PO 68130 :- PO detail id 157200 :- ReqD_id 790532 |  | 2024-04-01 16:31 | 150 | vinay mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 82936.35 | 89041.5622
13 | 686103 | GRN For SRA Morwadi Steel | Steel Bars 12mm | Kgs | 460 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 | :: Released from PO 68131 :- PO detail id 157205 :- ReqD_id 790615 | SRA Morwadi | 2024-04-01 16:31 | 460 | vinay mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 1198636.2 | 1225914.76
14 | 686103 | GRN For SRA Morwadi Steel | Steel Bars 12mm | Kgs | 14000 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 |  | SRA Morwadi | 2024-03-02 18:28 | 600 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 1198636.2 | 1225914.76
15 | 686339 | B-Bldg Supporting Material for Electrical Work | G.I. screw 6mmx 35mm full threaded | Box | 10 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-07 12:41 | 10 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 1000 | 0
16 | 686340 | B-Bldg Supporting Material for Electrical Work | G.I. screw 6mmx 75mm full threaded | Box | 10 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-07 12:41 | 10 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 1000 | 0
17 | 686341 | B-Bldg Supporting Material for Electrical Work | G.I. Screw 6mm x 50mm Full Threaded | Box | 10 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-07 12:41 | 10 | SANKET PATIL | 0 |  | 0 |  | 50 | [12 empty] | 500 | 0
18 | 686356 | A Downtake Lines Extra Qty As Per Site Condition | Fusion Machin ( For PPRC Pipe Weilding Purpose ) | No. | 2 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-11 14:43 | 2 | Sajid khan | 0 |  | 0 |  | 350 | [12 empty] | 700 | 0
19 | 686357 | B Downtake line Quantity Diff.as per Site Condition - 1 | Fusion Machin ( For PPRC Pipe Weilding Purpose ) | No. | 2 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-11 14:43 | 2 | Sajid khan | 0 |  | 0 |  | 350 | [12 empty] | 700 | 0
20 | 686551 | Steel MTBT D-31st Slab RCC 30th to 31st Column Stee | Steel Bars 8mm | Kgs | 490 |  | Management | Approved | 2024-03-14 12:00 | 2024-03-14 12:00 | :: Released from PO 68202 :- PO detail id 157382 :- ReqD_id 791497 |  | 2024-04-10 14:39 | 490 | vinay mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 336677.85 | 375742.6267
21 | 686591 | Steel MTBT F-Ent Gt Footing,Colm,Beam,Slab RCC Work | Steel Bars 8mm | Kgs | 1026.796 |  | Management | Approved | 2024-03-14 12:00 | 2024-03-14 12:00 | For Altus |  | 2024-03-14 18:02 | 1.678 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 52212.5766 | 62825.0742
22 | 686657 | Temporary Electrical Work required Material | GI Screw 35 x 8 | No. | 100 |  | Management | Approved | 2024-03-16 12:00 | 2024-03-16 12:00 |  |  | 2024-03-16 11:09 | 100 | Sajid khan | 0 |  | 0 |  | 0.5 | [12 empty] | 50 | 0
23 | 686658 | B Main Line Conduit (Vertical + Horizontal) 27 to 31st fl | GI Screw 35 x 8 | No. | 100 |  | Management | Approved | 2024-03-16 12:00 | 2024-03-16 12:00 |  |  | 2024-03-16 11:09 | 100 | Sajid khan | 0 |  | 0 |  | 0.5 | [12 empty] | 50 | 0
24 | 687912 | B 902 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
25 | 687913 | B 1302 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
26 | 687914 | B 701 AC Machine 5 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
27 | 687915 | B 702 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
28 | 687916 | B 1001 AC Machine 5 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
29 | 687917 | B 1102 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
30 | 687918 | B 1202 AC Machine 5 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
31 | 687919 | B 1502 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
32 | 687920 | B 1602 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
33 | 687921 | B 1902 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
34 | 687922 | 2302 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
35 | 687923 | B 1601 AC Machine 5 BHK | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
36 | 687932 | A 1204 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
37 | 687933 | A 1403 AC Machine 3 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
38 | 687934 | A 1602 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
39 | 687935 | A 1603 AC Machine 3 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
40 | 687936 | A 1502 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
41 | 687937 | A 1604 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | SANKET PATIL | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 71137.28
42 | 687987 | Material required for Sales office use | Tissue paper | Pack | 6 |  | Management | Approved | 2024-03-19 12:00 | 2024-03-19 12:00 |  |  | 2024-03-19 11:15 | 6 | SANKET PATIL | 0 |  | 0 |  | 500 | [12 empty] | 29500 | 60180
43 | 687989 | Material required for Sales office use | M-Fold (RC)-40 CC- 225x215mm | No. | 16 |  | Management | Approved | 2024-03-19 12:00 | 2024-03-19 12:00 |  |  | 2024-03-19 15:24 | 10 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 4100 | 24780
44 | 688001 | D Terrace Blockwork 5" | Jointing Mortar | Kgs | 200 |  | Management | Approved | 2024-03-19 12:00 | 2024-03-19 12:00 |  |  | 2024-03-20 12:12 | 200 | Sajid khan | 0 |  | 0 |  | 13.25 | [12 empty] | 4519.9115 | 810.3122
46 | 688043 | Steel MTBT Altus-Steel-GRN Purpose | Steel Bars 8mm | Kgs | 50 |  | Management | Approved | 2024-03-20 12:00 | 2024-03-20 12:00 | :: Released from PO 68243 :- PO detail id 157463 :- ReqD_id 793171 |  | 2024-04-10 14:39 | 10 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 464187.7845 | 560511.1038
45 | 688043 | Steel MTBT Altus-Steel-GRN Purpose | Steel Bars 8mm | Kgs | 50 |  | Management | Approved | 2024-03-20 12:00 | 2024-03-20 12:00 | :: Released from PO 68243 :- PO detail id 157463 :- ReqD_id 793171 |  | 2024-04-10 14:39 | 10 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 464187.7845 | 560511.1038
47 | 688909 | Tractor Repair & Maintenance final | Tractor Tyre 7.5x16 | No. | 2 |  | Management | Approved | 2024-04-01 12:00 | 2024-04-01 12:00 |  |  | 2024-04-01 15:06 | 2 | Sajid khan | 0 |  | 0 |  | 5900 | [12 empty] | 23600 | 9400
48 | 688912 | A- material for internal CP & Sanitary work | PVC Reducer Socket 11/2"x11/4" | No. | 50 |  | Management | Approved | 2024-04-01 12:00 | 2024-04-01 12:00 | :: Released from PO 68943 :- PO detail id 159377 :- ReqD_id 804938 :: Released from PO 68413 :- PO detail id 157903 :- ReqD_id 794416 |  | 2024-07-24 13:21 | 50 | Akshada Mahajan | 0 |  | 0 |  | 9 | [12 empty] | 450 | 0
49 | 690049 | Steel MTBT Altus-Steel-GRN Purpose | Steel Bars 10mm | Kgs | 10 |  | Management | Approved | 2024-04-06 12:00 | 2024-04-06 12:00 | :: Released from PO 68387 :- PO detail id 157804 :- ReqD_id 795681For Altus (GRN Purpose) |  | 2024-04-10 14:40 | 9.762 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 508.5 | 15.1991
50 | 690309 | Material required for Sales office use | Taski R3 5ltr | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 8 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 5100 | 25718.3
51 | 690310 | Material required for Sales office use | Taski R5 5ltr | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 8 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 4700 | 14650.88
52 | 690311 | Material required for Sales office use | Taski R6 5ltr | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 8 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 5200 | 16855.3701
53 | 690312 | Material required for Sales office use | WET MOP REFILL | No. | 15 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 5 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 15800 | 20714.9
54 | 690313 | Material required for Sales office use | Microfiber Duster | No. | 25 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 7900 | 1360.8
55 | 690319 | Material required for Sales office use | Tissue paper | Pack | 15 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | NITIN.PARDESHI | 0 |  | 0 |  | 500 | [12 empty] | 29500 | 60180
56 | 690421 | Material required for Sales office use | Hand wash Refill | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3000 | 0
57 | 690578 | Safety Material | Rubber Hand Gloves | Pair | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | Sajid khan | 0 |  | 0 |  | 15 | [12 empty] | 1875 | 3148
58 | 690582 | Maintenance Work Filtration Plant & Water body | Cleaning Acid | Ltrs | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | Sajid khan | 0 |  | 0 |  | 67 | [12 empty] | 4840.75 | 1759.09
59 | 690700 | Material required for Sales office use | Spray Bottle | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 5 | NITIN.PARDESHI | 0 |  | 0 |  | 180 | [12 empty] | 11340 | 2124
60 | 690701 | Material required for Sales office use | Table Top Tissue Paper | No. | 25 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 25 | Sajid khan | 0 |  | 0 |  | 510 | [12 empty] | 25500 | 0
61 | 690702 | Mandir peripheral plum concrete & PCC work | Ready Mix Concrete M-15 Grade( PUMPABLE) | Cu.Mtrs | 20.7 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 68408 :- PO detail id 157893 :- ReqD_id 796388 |  | 2024-05-21 14:32 | 20.7 | Akshada Mahajan | 0 |  | 0 |  | 20 | [12 empty] | 480 | 0
62 | 690710 | Material required for Sales office use | Taski R2 5ltr | No. | 15 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 17:59 | 12 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 5900 | 27174.5
63 | 690743 | Pour 5 105.00 to 108.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 2204 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:18 | 1014 | AKSHADA MAHAJAN | 0 |  | 0 |  | 100 | [12 empty] | 610200 | 310195.3298
64 | 690745 | C Bldg 6th Slab (2nd Floor) Steel | Steel Bars 10mm | Kgs | 4484.796 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:18 | 2786 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 228051.8766 | 105911.9463
65 | 690750 | Pour 5 108.00 to 111.00 lvl Drop panel Steel | Steel Bars 12mm | Kgs | 7775 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:18 | 542.99 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 334325 | 448526.2013
66 | 690761 | 7th to 8th Column & SW Steel | Steel Bars 20mm | Kgs | 12986.766 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:17 | 2275.673 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 660377.0511 | 645775.5813
67 | 690762 | 5th to 6th Column & SW Steel | Steel Bar 25mm | Kgs | 11542.885 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:17 | 1600.4445 | AKSHADA MAHAJAN | 0 |  | 0 |  | 1000 | [12 empty] | 17748885 | 1002416.7999
68 | 690776 | Steel MTBT E-19th Sl.18th to 19th Column,SW Steel | Steel Bars 12mm | Kgs | 3625 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | for Arcadia |  | 2024-04-10 18:17 | 1148.027 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 184331.25 | 154427.6248
69 | 690779 | Steel MTBT A-Ret.Wall Steel Work (FootingRaft+Pardi | Steel Bars 10mm | Kgs | 20 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | :: Released from PO 68425 :- PO detail id 157944 :- ReqD_id 796602For Arcadia |  | 2024-06-06 14:15 | 20 | Akshada Mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 508500 | 622206.094
70 | 690780 | Steel MTBT A-Col.-Footing To Plinth- Steel Work New | Steel Bars 8mm | Kgs | 1394.429 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | For Arcadia |  | 2024-04-10 18:17 | 0.429 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 70906.7146 | 89092.2128
71 | 690788 | GRN For SRA Morwadi Steel | Steel Bars 20mm | Kgs | 90 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | :: Released from PO 68424 :- PO detail id 157941 :- ReqD_id 796652 :: Released from PO 68407 :- PO detail id 157891 :- ReqD_id 796593 | GRN For SRA Morwadi Steel | 2024-07-09 17:14 | 90 | akshada mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 5034892.41 | 4788677.932
72 | 690789 | GRN For SRA Morwadi Steel | Steel Bar 25mm | Kgs | 530 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | :: Released from PO 68424 :- PO detail id 157942 :- ReqD_id 796654 :: Released from PO 68407 :- PO detail id 157892 :- ReqD_id 796592 | GRN For SRA Morwadi Steel | 2024-07-09 17:16 | 530 | akshada mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 1057680 | 1243333.499
73 | 690850 | C Bldg 5th Slab-PT Beam Steel | Steel Bars 32mm | Kgs | 400 |  | Management | Approved | 2024-04-12 12:00 | 2024-04-12 12:00 |  |  | 2024-04-12 18:33 | 5.75 | Vinay Mittal | 0 |  | 0 |  | 100 | [12 empty] | 3324205 | 953448.3312
74 | 691888 | Tower A, B & C Bldg ACCL Panel LT cable & Meter room work | Alum Armd Cable 3.5C x 150sqmm | Mtrs | 1 |  | Management | Approved | 2024-04-18 12:00 | 2024-04-18 12:00 | :: Released from PO 68531 :- PO detail id 158227 :- ReqD_id 798676 |  | 2024-06-18 17:26 | 1 | PARSHURAM KORE | 0 |  | 0 |  | 100 | [12 empty] | 2000 | 16673.754
75 | 694600 | D Building Parking Toilet CP & Sanitary | Chair Bracket for W H | No. | 2 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 2 | Sajid khan | 0 |  | 0 |  | 673 | [12 empty] | 1346 | 0
76 | 694609 | Tractor Repair & Maintenance final | 000020316E05FILTER (ENGINE OIL ) | No. | 1 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 400 | 260.3997
77 | 694610 | Tractor Repair & Maintenance final | 006001920A91 FUEL FILTER ELEMENT KIT | No. | 1 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 1 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 300 | 0
78 | 694611 | Tractor Repair & Maintenance final | 30.194MSTAR COOLZ - 1 LITRE | No. | 2 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 2 | Sajid khan | 0 |  | 0 |  | 300 | [12 empty] | 1800 | 669.5982
79 | 694612 | Tractor Repair & Maintenance final | 001081728R2WASHER COPPER BANJO BOLT FUEL PIPE | No. | 2 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 2 | Sajid khan | 0 |  | 0 |  | 300 | [12 empty] | 2400 | 13.0098
80 | 694613 | Tractor Repair & Maintenance final | 006000455F1 Element Air Filter | No. | 1 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 1 | Sajid khan | 0 |  | 0 |  | 550 | [12 empty] | 1100 | 691.9143
81 | 694614 | Tractor Repair & Maintenance final | 006000456F1 ELEMENT AIR FILTER | No. | 1 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 200 | 0
82 | 694618 | Tractor Repair & Maintenance final | 00001247 M Star Oil 7.5 Ltr | Ltrs | 7.5 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 7.5 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 750 | 0
83 | 694619 | Tractor Repair & Maintenance final | 00001248 M-STAR OIL 1 LIT | Ltrs | 1 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 1 | Sajid khan | 0 |  | 0 |  | 350 | [12 empty] | 1400 | 562.8302
84 | 694620 | Tractor Repair & Maintenance final | Seat Sliding | No. | 1 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
85 | 695102 | 4th to 5th Slab SW M50 (Pumpable) | Cement Loose 53 Grade | Metric Tonnes | 2 |  | Management | Approved | 2024-05-08 12:00 | 2024-05-08 12:00 |  |  | 2024-05-08 12:21 | 0.3209 | AKSHADA MAHAJAN | 0 |  | 0 |  | 3880 | [12 empty] | 802723.5 | 662855.98
86 | 695558 | A- material for internal CP & Sanitary work | CP Connector Pipe 1/2" x 24" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 1550 | 0
87 | 695559 | B- material for internal CP & Sanitary work | CP Connector Pipe 1/2" x 24" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 1550 | 0
88 | 695561 | A- material for internal CP & Sanitary work | GI Reducer Elbow 11/2"x 11/4" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 29.2708 | [12 empty] | 907.3948 | 0
89 | 695562 | B- material for internal CP & Sanitary work | GI Reducer Elbow 11/2"x 11/4" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 29.2708 | [12 empty] | 907.3948 | 0
90 | 695575 | B- material for internal CP & Sanitary work | Silicone Sealent | No. | 10 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 18:51 | 10 | Sajid khan | 0 |  | 0 |  | 180 | [12 empty] | 1800 | 0
91 | 695640 | A- material for internal CP & Sanitary work | Habak | Kgs | 3 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-17 17:53 | 3 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 150 | 0
92 | 695641 | B- material for internal CP & Sanitary work | Habak | Kgs | 2 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-17 17:53 | 2 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 100 | 0
93 | 697158 | C Bldg 5th to 6th Non Structural SW Concrete (M60FF) | Cement Loose 53 Grade | Metric Tonnes | 30 |  | Management | Approved | 2024-05-30 12:51 | 2024-05-30 12:00 |  |  | 2024-05-30 12:50 | 10 | AKSHADA MAHAJAN | 0 |  | 0 |  | 3880 | [12 empty] | 247350 | 379894
94 | 698052 | B 101 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
95 | 698053 | B 102 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
96 | 698054 | B 201 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
97 | 698055 | B 202 CP & Sanitary (M) - | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
98 | 698056 | B 401 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
99 | 698057 | B 502 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
100 | 698058 | B 602 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
101 | 698059 | B 701 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
102 | 698060 | B 702 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
103 | 698061 | B 901 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
104 | 698062 | B 902 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
105 | 698063 | B 1001 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
106 | 698064 | B 1002 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
107 | 698065 | B 11th Floor 1101 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
108 | 698066 | B 11th Floor 1102 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
109 | 698067 | B 12th Floor 1202 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
110 | 698068 | B 13th Floor 1301 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
111 | 698069 | B 13th Floor 1302 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
112 | 698070 | B 16th Floor 1601 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
113 | 698071 | B 17th Floor 1701 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
114 | 698072 | B 18th Floor 1801 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
115 | 698073 | B 20th Floor 2001 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
116 | 698074 | B 21st Floor 2101 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
117 | 698075 | B 17th Floor 1702 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
118 | 698076 | B 19th Floor 1902 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
119 | 698077 | B 21st Floor 2102 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
120 | 698078 | A CP & Sanitary Flat No.101 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
121 | 698079 | A CP & Sanitary Flat No.102 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
122 | 698080 | A CP & Sanitary Flat No.103 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
123 | 698081 | A CP & Sanitary Flat No.104 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
124 | 698082 | A CP & Sanitary Flat No.901 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
125 | 698083 | A CP & Sanitary Flat No.902 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
126 | 698084 | A CP & Sanitary Flat No.903 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
127 | 698085 | A CP & Sanitary (M) Flat No.1001 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
128 | 698086 | A CP & Sanitary (M) Flat No.1002 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
129 | 698087 | A CP & Sanitary (M) Flat No.1003 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
130 | 698088 | A CP & Sanitary (M) Flat No.1204 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
131 | 698089 | A CP & Sanitary (M) Flat No.1302 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
132 | 698090 | A CP & Sanitary (M) Flat No.1401 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
133 | 698091 | A CP & Sanitary (M) Flat No.1402 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
134 | 698092 | A CP & Sanitary (M) Flat No.1501 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
135 | 698093 | A CP & Sanitary (M) Flat No.1503 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
136 | 698094 | A CP & Sanitary (M) Flat No.1601 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
137 | 698095 | A CP & Sanitary (M) Flat No.1602 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
138 | 698096 | A CP & Sanitary (M) Flat No.1604 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
139 | 698097 | A CP & Sanitary (M) Flat No.1701 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
140 | 698098 | A CP & Sanitary (M) Flat No.2001 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
141 | 698099 | A CP & Sanitary (M) Flat No.1702 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
142 | 698100 | A CP & Sanitary (M) Flat No.1704 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
143 | 698101 | A CP & Sanitary (M) Flat No.1804 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
144 | 698102 | A CP & Sanitary (M) Flat No.1904 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
145 | 698608 | A Lift- Gap filling bet. lift frame & Italian marble frame | Silicon Tube | No. | 1 |  | Management | Approved | 2024-06-04 14:18 | 2024-06-04 12:00 |  |  | 2024-06-05 17:59 | 1 | Sajid khan | 0 |  | 0 |  | 170 | [12 empty] | 170 | 0
146 | 698609 | B Lift- Gap filling bet. lift frame & Italian marble frame | Silicon Tube | No. | 1 |  | Management | Approved | 2024-06-04 14:18 | 2024-06-04 12:00 |  |  | 2024-06-05 17:59 | 1 | Sajid khan | 0 |  | 0 |  | 170 | [12 empty] | 170 | 0
147 | 699039 | GRN For SRA Morwadi Steel | Steel Bars 8mm | Kgs | 40 |  | Management | Approved | 2024-06-05 15:29 | 2024-06-10 12:00 | :: Released from PO 68869 :- PO detail id 159102 :- ReqD_id 810531 |  | 2024-07-09 17:16 | 40 | akshada mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 5646384 | 6965091.739
148 | 699129 | Material required for Sales office use | Garbage Bag (Big) | Pack | 11 |  | Management | Approved | 2024-06-07 13:16 | 2024-06-07 12:00 |  |  | 2024-06-07 16:12 | 1 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 10700 | 16418.52
149 | 699139 | Safety Material | Rubber Hand Gloves | Pair | 6 |  | Management | Approved | 2024-06-07 13:34 | 2024-06-07 12:00 |  |  | 2024-06-07 16:12 | 6 | Sajid khan | 0 |  | 0 |  | 15 | [12 empty] | 1875 | 3148
150 | 699203 | Material required for Sales office use | 17" Hard Brush (for scrubber m | No. | 6 |  | Management | Approved | 2024-06-07 17:33 | 2024-06-07 12:00 |  |  | 2024-06-08 10:44 | 6 | Sajid khan | 0 |  | 0 |  | 3200 | [12 empty] | 19200 | 0
151 | 702034 | Material required for Sales office use | Hand wash Foam Bottle | No. | 2 |  | Management | Approved | 2024-06-17 15:46 | 2024-06-17 12:00 |  |  | 2024-06-17 15:58 | 2 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 1600 | 1593
152 | 703410 | Pour 5 102.00 to 105.00 lvl Slab Steel | Steel Bars 8mm | Kgs | 1787 |  | Management | Approved | 2024-06-21 18:09 | 2024-06-21 12:00 |  |  | 2024-06-21 18:47 | 1000 | AKSHADA MAHAJAN | 0 |  | 0 |  | 100 | [12 empty] | 514700 | 251564.0091
153 | 703459 | B Bldg 36th Slab Non Structural Wall RMC M30 (S-M Mix) hiflo | Cement Loose 53 Grade | Metric Tonnes | 10 |  | Management | Approved | 2024-06-25 11:37 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 10 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 42058.812 | 0
154 | 703460 | A Bldg 30th slab Nonstructural RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.7644 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.7644 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 80565.872 | 108000
155 | 703461 | A Bldg 31st Slab RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.0112 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.0112 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 194043.456 | 320712.32
156 | 703462 | A Bldg 31st Slab SW& Lift wall RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.1992 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.1992 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 136572.896 | 226145.689
157 | 703463 | A Bldg 31st Slab Nonstructural RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.7644 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.7644 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 80565.872 | 128852
158 | 703464 | A Bldg 32nd Slab RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.14 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.14 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 194543.2 | 320000
159 | 703465 | B Type Ret.Wall Bet.Tower B & C RCC Pardi M40 1st to 2nd Sl | Cement Loose 53 Grade | Metric Tonnes | 4.968 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 4.968 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 19275.84 | 0
160 | 703466 | A Bldg 35th Slab RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.0066 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.0066 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 194043.456 | 380034.96
161 | 703467 | B Bldg 35th Slab Non Structural Wall RMC M30 (S-M Mix) hiflo | Cement Loose 53 Grade | Metric Tonnes | 2.0974 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 2.0974 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 42058.812 | 64694.5
162 | 703468 | A Bldg 36th Slab RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 28.8712 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 28.8712 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 194043.456 | 165059.6245
163 | 703469 | A Bldg 36th Slab Nonstructural RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 20.7644 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 20.7644 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 80565.872 | 0
164 | 703470 | B Bldg 36th Slab SW & Lift Wall RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 6.2814 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 6.2814 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 119840.396 | 182079.22
165 | 703471 | B Bldg 36th Slab Non Structural Wall RMC M30 (S-M Mix) hiflo | Cement Loose 53 Grade | Metric Tonnes | 0.8399 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.8399 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 42058.812 | 0
166 | 703472 | Podium Column upto 1st Slab (Pour 5 & 6) | Cement Loose 53 Grade | Metric Tonnes | 6.5165 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 6.5165 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 79540 | 88080.2
167 | 703473 | Podium C-1st Slab Pour 3 & 3A M35 PT | Cement Loose 53 Grade | Metric Tonnes | 11.5 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 11.5 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 44620 | 0
168 | 703474 | B Bldg 37th Slab Beam RMC M30 (S-M Mix) Hiflow | Cement Loose 53 Grade | Metric Tonnes | 35.3947 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 35.3947 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 137331.436 | 0
169 | 703475 | B Bldg 37th Slab SW & Lift Wall RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 30.8867 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 30.8867 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 119840.396 | 0
170 | 703557 | A Bldg 36th Slab (31st Floor)Non Structural SW steel | Steel Bars 8mm | Kgs | 377 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 377 | Sajid khan | 0 |  | 0 |  | 53 | [12 empty] | 120946 | 121813.0415
171 | 703558 | B Bldg 35th Slab (30th floor) Slab steel | Steel Bars 8mm | Kgs | 707 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 119 | AKSHADA MAHAJAN | 0 |  | 0 |  | 53 | [12 empty] | 195994 | 244395.0108
172 | 703559 | B Bldg 35th Slab (30th floor) Non-Structural walls | Steel Bars 8mm | Kgs | 490 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 490 | Sajid khan | 0 |  | 0 |  | 53 | [12 empty] | 86231 | 73179.4803
173 | 703560 | B Bldg 36th To 37th Slab Shear Wall Steel | Steel Bars 8mm | Kgs | 6645 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 3485 | AKSHADA MAHAJAN | 0 |  | 0 |  | 53 | [12 empty] | 451533.5 | 301467.3135
174 | 703563 | A Bldg 35th Slab (30th Floor) 33 slab steel As Per Revised | Steel Bars 8mm | Kgs | 17785 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 17785 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1778500 | 0
175 | 703564 | A Bldg 36th Slab (31st Floor) 33 slab steel As Per Revised | Steel Bars 8mm | Kgs | 17785 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 17785 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1778500 | 0
176 | 703565 | 5th Slab Non Structural wall Steel | Steel Bars 8mm | Kgs | 1875.3 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1875.3 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 187530 | 0
177 | 703568 | B Bldg 35th Slab (30th floor) Slab steel | Steel Bars 10mm | Kgs | 2256.28 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 610.28 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 113348 | 119228.0852
178 | 703569 | B Bldg 36th Slab (31st floor) Slab steel | Steel Bars 10mm | Kgs | 2636 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2636 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 113348 | 0
179 | 703570 | B Bldg 34th To 35th Slab Shear Wall | Steel Bars 10mm | Kgs | 1656.87 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1656.87 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 148129.41 | 107658.8772
180 | 703571 | A Bldg Terrace to OHWT/LMR Slab Shear Wall Steel | Steel Bars 10mm | Kgs | 478.83 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 478.83 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 47883 | 0
181 | 703572 | STP-A.B.C Deck Slab steel & concrete | Steel Bars 10mm | Kgs | 300 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 300 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 30000 | 0
182 | 703573 | Pour 6 102.00 to 105.00 lvl Drop panel Steel | Steel Bars 10mm | Kgs | 1116 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1116 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 190500 | 47269.779
183 | 703574 | Pour 6 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 10mm | Kgs | 1905 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1905 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 190500 | 0
184 | 703575 | Pour 3 102.00 to 105.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 3153.93 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 3153.93 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 315393 | 0
185 | 703576 | Pour 3 105.00 to 108.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 3153.93 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 3153.93 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 315393 | 0
186 | 703577 | Pour 3A 102.00 to 105.00 lvl Column Steel | Steel Bars 10mm | Kgs | 70.79 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 70.79 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 7079 | 0
187 | 703578 | Pour 3A 102.00 to 105.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 6102 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 6102 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 610200 | 0
188 | 703579 | Pour 3A 105.00 to 108.00 lvl Column Steel | Steel Bars 10mm | Kgs | 70.79 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 70.79 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 7079 | 0
189 | 703580 | Pour 3A 105.00 to 108.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 6102 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 6102 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 610200 | 0
190 | 703581 | Pour 3A 108.00 to 111.00 lvl Column Steel | Steel Bars 10mm | Kgs | 70.79 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 70.79 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 7079 | 0
191 | 703582 | 5th to 6th Column & SW Steel | Steel Bars 10mm | Kgs | 5820.453 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 5820.453 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 582045.3 | 0
192 | 703583 | 6th to 7th Column & SW Steel | Steel Bars 10mm | Kgs | 5379.14 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 5379.14 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 281514.1936 | 9790.0201
193 | 703584 | 7th Slab (3rd Floor) Slab Steel | Steel Bars 10mm | Kgs | 1373.197 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1373.197 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 227968.33 | 0
194 | 703585 | A Bldg 34th Slab (29th Floor) 33 slab steel As Per Revised | Steel Bars 12mm | Kgs | 5141.33 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 | :: Released from PO 69209 :- PO detail id 160142 :- ReqD_id 818471 |  | 2024-07-11 11:41 | 5141.33 | Akshada Mahajan | 0 |  | 0 |  | 43 | [12 empty] | 436077.19 | 315178
195 | 703586 | A Bldg 35th Slab (30th Floor) 33 slab steel As Per Revised | Steel Bars 12mm | Kgs | 141.33 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 | :: Released from PO 69209 :- PO detail id 160142 :- ReqD_id 818470 |  | 2024-07-11 11:41 | 18.67 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 436077.19 | 609220.1799
196 | 703593 | Pour 3 102.00 to 105.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 7843.89 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 7843.89 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 337287.27 | 0
197 | 703594 | Pour 3 105.00 to 108.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 7843.89 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 7843.89 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 337287.27 | 0
198 | 703595 | Pour 3A 102.00 to 105.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 3831 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 671 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 164733 | 182942.512
199 | 703596 | Pour 3A 105.00 to 108.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 3831 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1991 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 164733 | 106523.488
200 | 703601 | Meditation Hall Plinth Beam Steel | Steel Bars 16mm | Kgs | 318.97 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 318.97 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 16267.47 | 0
201 | 703602 | Meditation Hall Column Steel | Steel Bars 16mm | Kgs | 370.41 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 370.41 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 18890.91 | 0
202 | 703603 | Meditation Hall 1st slab Beam Steel | Steel Bars 16mm | Kgs | 507.43 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 507.43 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 25878.93 | 0
203 | 703604 | Meditation Hall 2nd Slab Beam Steel | Steel Bars 16mm | Kgs | 529.84 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 529.84 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 27021.84 | 0
204 | 703605 | Meditation Hall 1st to 2nd floor Column Steel | Steel Bars 16mm | Kgs | 408.05 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 408.05 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 20810.55 | 0
205 | 703606 | Pump room slab,beam,column steel | Steel Bars 16mm | Kgs | 113.26 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 113.26 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 5776.26 | 0
206 | 703615 | Pour 6 102.00 to 105.00 lvl P1 Column Steel | Steel Bars 16mm | Kgs | 1128.9 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 237.41 | AKSHADA MAHAJAN | 0 |  | 0 |  | 51 | [12 empty] | 57573.9 | 51611.2089
207 | 703616 | Pour 6 102.00 to 105.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
208 | 703617 | Pour 6 105.00 to 108.00 lvl P1 Column Steel | Steel Bars 16mm | Kgs | 1128.9 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1128.9 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 57573.9 | 0
209 | 703618 | Pour 6 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
210 | 703619 | Pour 3 102.00 to 105.00 lvl Dowel Bars | Steel Bars 16mm | Kgs | 1759.49 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1759.49 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 89733.99 | 0
211 | 703620 | Pour 3 102.00 to 105.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
212 | 703621 | Pour 3 105.00 to 108.00 lvl Dowel Bars | Steel Bars 16mm | Kgs | 1759.49 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1759.49 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 89733.99 | 0
213 | 703622 | Pour 3 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
214 | 703623 | Pour 3A 102.00 to 105.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
215 | 703624 | Pour 3A 105.00 to 108.00 lvl Column Steel | Steel Bars 16mm | Kgs | 79.72 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 79.72 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 4065.72 | 0
216 | 703625 | Pour 3A 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
217 | 703626 | Pour 3A 108.00 to 111.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
218 | 703627 | Bursting Steel for P.T | Steel Bars 16mm | Kgs | 2567 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2567 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 130917 | 0
219 | 703628 | A Bldg 36th to 37th Slab SW & lift wall steel | Steel Bars 20mm | Kgs | 82.96 |  | Management | Approved | 2024-07-01 15:23 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 82.96 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 16924.35 | 15688.9305
220 | 703629 | A Bldg 34th Slab (29th Floor) 33 slab steel As Per Revised | Steel Bars 20mm | Kgs | 1157 |  | Management | Approved | 2024-07-01 15:23 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1157 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 2814000 | 99984.6037
221 | 703630 | B Bldg OHWT Steel | Steel Bars 20mm | Kgs | 130.64 |  | Management | Approved | 2024-07-01 15:23 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 130.64 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 130640 | 0
222 | 703631 | Steel MTBT A-Footing A-Bldg Footing Steel | Steel Bars 20mm | Kgs | 500 |  | Management | Approved | 2024-07-01 15:23 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 500 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 25425 | 0
223 | 703632 | Ramp Slab & Beams - Concrete & Steel | Steel Bars 20mm | Kgs | 2305.904 |  | Management | Approved | 2024-07-01 15:23 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2305.904 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 137345.85 | 24632.3786
224 | 703633 | 9th Slab (5th Floor) Slab Beam Steel | Steel Bars 20mm | Kgs | 3296.958 |  | Management | Approved | 2024-07-01 15:23 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 3296.958 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 167650.3143 | 0
225 | 703634 | 8th to 9th Column & SW Steel | Steel Bars 20mm | Kgs | 15643 |  | Management | Approved | 2024-07-01 15:23 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1143 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 795446.55 | 839451.4
226 | 703635 | EWS Bldg RCC 1st Slab First Slab RCC | Steel Bar 25mm | Kgs | 0.4 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.4 | Sajid khan | 0 |  | 0 |  | 40 | [12 empty] | 16256 | 17749.9952
227 | 703636 | C Bldg shear walls steel upto 2nd Slab including plinth beam | Steel Bar 25mm | Kgs | 0.5 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.5 | Sajid khan | 0 |  | 0 |  | 40 | [12 empty] | 2957620 | 3920649.8457
228 | 703637 | A Bldg OHWT Steel | Steel Bar 25mm | Kgs | 0.89 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.89 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 763890 | 48096.1628
229 | 703638 | Steel for Fire ramp from 105.00 lvl to 108.00 lvl | Steel Bar 25mm | Kgs | 1000 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1000 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 4340914.5 | 209974.1939
230 | 703639 | 115.20 lvl Tie Beam Steel | Steel Bar 25mm | Kgs | 0.95 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.95 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 291950 | 18343.3596
231 | 703640 | A Bldg Terrace to OHWT/LMR Slab Shear Wall Steel | Steel Bar 25mm | Kgs | 648.61 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 648.61 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 648610 | 0
232 | 703641 | 6th to 7th Column & SW Steel | Steel Bar 25mm | Kgs | 4028.395 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 4028.395 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 916743.8858 | 841488.88
233 | 703642 | 7th Slab (3rd Floor) Slab Beam Steel | Steel Bar 25mm | Kgs | 1237.685 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1237.685 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 248095.6245 | 227017.0057
234 | 703643 | Ramp Slab & Beams - Concrete & Steel | Steel Bar 25mm | Kgs | 9335 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 9335 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 474684.75 | 0
235 | 703644 | 8th Slab (3rd Floor) Slab Beam Steel | Steel Bar 25mm | Kgs | 4878.97 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 4878.97 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 248095.6245 | 0
236 | 703645 | 7th to 8th Column & SW Steel | Steel Bar 25mm | Kgs | 13028.395 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 5528.395 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 916743.8858 | 733754
237 | 703646 | 8th to 9th Column & SW Steel | Steel Bar 25mm | Kgs | 11489 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 11489 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 584215.65 | 0
238 | 703647 | UGWT & Pump Room RCC Work Steel | Steel Bars 32mm | Kgs | 1038 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1038 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 48590 | 3817.9448
239 | 703648 | B Bldg 22th Slab Steel | Steel Bars 32mm | Kgs | 1456 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1456 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80883 | 17804.345
240 | 703649 | B Bldg 23rd Slab Steel | Steel Bars 32mm | Kgs | 1881 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1881 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80883 | 0
241 | 703650 | Club House 1st Slab Steel | Steel Bars 32mm | Kgs | 1505 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1505 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 64715 | 0
242 | 703651 | C Bldg shear walls steel upto 2nd Slab including plinth beam | Steel Bars 32mm | Kgs | 1108 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1108 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 47644 | 0
243 | 703652 | B Bldg 26th Slab Steel- - | Steel Bars 32mm | Kgs | 1400 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1400 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80883 | 33004.777
244 | 703653 | B 33rd slab Steel | Steel Bars 32mm | Kgs | 775.75 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 775.75 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80872.25 | 77339.7305
245 | 703654 | A Bldg 34th Floor Steel | Steel Bars 32mm | Kgs | 0.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.33 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 49937.19 | 81308.313
246 | 703655 | A Bldg 35th Slab (30th Floor) slab steel | Steel Bars 32mm | Kgs | 0.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.33 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 49937.19 | 81308.313
247 | 703656 | A Bldg 36th Slab (31st Floor) Slab steel | Steel Bars 32mm | Kgs | 0.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.33 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 49937.19 | 81308.313
248 | 703657 | Steel for Fire ramp from 105.00 lvl to 108.00 lvl | Steel Bars 32mm | Kgs | 664.998 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 664.998 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 302980.8 | 151751.9762
249 | 703658 | C Bldg 5th Slab-PT Beam Steel | Steel Bars 32mm | Kgs | 22842.05 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 17842.05 | AKSHADA MAHAJAN | 0 |  | 0 |  | 100 | [12 empty] | 3324205 | 953448.3312
250 | 703659 | Pour 6 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 32mm | Kgs | 1770.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1770.33 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 188100 | 7019.7649
251 | 703660 | 5th to 6th Column & SW Steel | Steel Bars 32mm | Kgs | 14098.656 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 14098.656 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1409865.6 | 0
252 | 703661 | C bldg 6th Slab (2nd Floor) beam steel | Steel Bars 32mm | Kgs | 547.141 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 547.141 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 27822.1198 | 0
253 | 703662 | 6th to 7th Column & SW Steel | Steel Bars 32mm | Kgs | 2919.84 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2919.84 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 148473.864 | 0
254 | 703663 | 7th Slab (3rd Floor) Slab Beam Steel | Steel Bars 32mm | Kgs | 516.312 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 516.312 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 26254.4652 | 0
255 | 703664 | 8th Slab (3rd Floor) Slab Beam Steel | Steel Bars 32mm | Kgs | 516.312 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 516.312 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 26254.4652 | 0
256 | 703665 | 7th to 8th Column & SW Steel | Steel Bars 32mm | Kgs | 2919.84 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2919.84 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 148473.864 | 0
257 | 704889 | Labour Camp Electrical Work | Drill Bit 6mm | No. | 25 |  | Management | Approved | 2024-07-03 10:58 | 2024-07-03 12:00 |  |  | 2024-07-04 12:07 | 25 | Sajid khan | 0 |  | 0 |  | 385.88 | [12 empty] | 9647 | 0
258 | 704930 | D 2nd Floor M. Plates, Switches, Sockets | Angle Holder | No. | 33 |  | Management | Approved | 2024-07-03 14:32 | 2024-07-03 12:00 |  |  | 2024-07-04 12:07 | 33 | Sajid khan | 0 |  | 0 |  | 28 | [12 empty] | 924 | 0
259 | 704931 | D Parking floor Rework due to Labour camp | Angle Holder | No. | 33 |  | Management | Approved | 2024-07-03 14:32 | 2024-07-03 12:00 |  |  | 2024-07-04 12:07 | 33 | Sajid khan | 0 |  | 0 |  | 28 | [12 empty] | 924 | 0
260 | 704935 | D 2nd Floor M. Plates, Switches, Sockets | Ceiling Rose | No. | 15 |  | Management | Approved | 2024-07-03 14:40 | 2024-07-03 12:00 |  |  | 2024-07-04 12:07 | 15 | Sajid khan | 0 |  | 0 |  | 32 | [12 empty] | 480 | 0
261 | 704936 | D Parking floor Rework due to Labour camp | Ceiling Rose | No. | 15 |  | Management | Approved | 2024-07-03 14:40 | 2024-07-03 12:00 |  |  | 2024-07-04 12:07 | 15 | Sajid khan | 0 |  | 0 |  | 32 | [12 empty] | 480 | 0
262 | 706550 | Drive way periphery planters Brickwork & Plaster | Cement 43 Grade | Bags | 41.5025 |  | Management | Approved | 2024-07-13 11:25 | 2024-07-13 12:00 |  |  | 2024-07-13 11:49 | 0.3837 | AKSHADA MAHAJAN | 0 |  | 0 |  | 375 | [12 empty] | 24000 | 13980.392
263 | 707115 | A 2702 Electrical Wiring - 1 No. | PVC Copper Wire 2.5 Sqmm yellow | Mtrs | 300 |  | Management | Approved | 2024-07-16 16:31 | 2024-07-16 12:00 |  |  | 2024-07-17 11:26 | 300 | kantilal.jagtap | 0 |  | 0 |  | 14.28 | [12 empty] | 4284 | 0
264 | 707176 | A,B,C D & Development Housekeeping | Phenyl | Ltrs | 5 |  | Management | Approved | 2024-07-18 09:23 | 2024-07-18 12:00 |  | Tiger Brand | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 260 | [12 empty] | 7800 | 0
265 | 707177 | A,B,C D & Development Housekeeping | Handgloves -HUSQ | Pair | 5 |  | Management | Approved | 2024-07-18 09:23 | 2024-07-18 12:00 |  | Rubber Handglove For Houdekeeping | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 350 | [12 empty] | 1750 | 0
266 | 707178 | A,B,C D & Development Housekeeping | Garbage Bag (Big) | Pack | 10 |  | Management | Approved | 2024-07-18 09:24 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 10 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1000 | 0
267 | 707179 | A,B,C D & Development Housekeeping | Toilet Brush Two Side | No. | 4 |  | Management | Approved | 2024-07-18 09:24 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 4 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 900 | 200.6
268 | 707180 | A,B,C D & Development Housekeeping | Check Duster | No. | 12 |  | Management | Approved | 2024-07-18 09:24 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 12 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3600 | 365.4
269 | 707181 | A,B,C D & Development Housekeeping | Nirma Washing Powder 1Kg | Kgs | 5 |  | Management | Approved | 2024-07-18 09:25 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 30 | [12 empty] | 300 | 224.2
270 | 707182 | A,B,C D & Development Housekeeping | Room Freshner | No. | 6 |  | Management | Approved | 2024-07-18 09:25 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 6 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 600 | 0
271 | 707183 | A,B,C D & Development Housekeeping | Plastic Bucket | No. | 5 |  | Management | Approved | 2024-07-18 09:27 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 157.5 | [12 empty] | 2205 | 283.2
272 | 707187 | Extra Material received &required at Site for Flooring & Til | Telephonic Black Granite | Sq.Ft | 0.6 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 0.6 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 90806.04 | 169044.9024
273 | 707188 | B 1301 | Telephonic Black Granite | Sq.Ft | 41.2 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 41.2 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3213.6 | 0
274 | 707189 | B 1401 | Telephonic Black Granite | Sq.Ft | 41.2 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 41.2 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3213.6 | 0
275 | 707190 | A 204 | Telephonic Black Granite | Sq.Ft | 53.95 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 53.95 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 4208.1 | 0
276 | 707191 | A 703 (GGG Std) | Telephonic Black Granite | Sq.Ft | 44.66 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 44.66 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3483.48 | 0
277 | 707192 | B 2101 | Telephonic Black Granite | Sq.Ft | 41.2 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 41.2 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3213.6 | 0
278 | 707193 | B 2401 - 1 Sq.Ft | Telephonic Black Granite | Sq.Ft | 41.2 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 41.2 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3213.6 | 0
279 | 707194 | D 1st Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
280 | 707195 | D 2nd Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
281 | 707196 | D 3rd Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
282 | 707197 | D 4th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
283 | 707198 | D 5th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
284 | 707199 | D 6th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
285 | 707200 | D 7th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
286 | 707201 | D 8th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
287 | 707202 | D 9th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
288 | 707203 | D 10th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
289 | 707204 | D 11th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
290 | 707205 | D 12th Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
291 | 707206 | D Bldg Ground Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
292 | 707207 | D Terrace Floor Lift granite frame | Telephonic Black Granite | Sq.Ft | 40.9 |  | Management | Approved | 2024-07-18 13:21 | 2024-07-18 12:00 |  | 9 ft ( L) X 3 Ft ( B) Size Require | 2024-07-20 15:05 | 40.9 | kantilal.jagtap | 0 |  | 0 |  | 78 | [12 empty] | 3190.2 | 0
293 | 707330 | Safety Material | Safety shoes | No. | 12 |  | Management | Approved | 2024-07-24 16:18 | 2024-07-24 12:00 |  |  | 2024-07-24 17:31 | 12 | KANTILAL.JAGTAP | 0 |  | 0 |  | 275 | [12 empty] | 103675 | 430356.9
294 | 707357 | Store Equipments | Umbrella | No. | 6 |  | Management | Approved | 2024-07-27 11:57 | 2024-07-27 12:00 |  |  | 2024-07-27 18:33 | 6 | Sajid khan | 0 |  | 0 |  | 160 | [12 empty] | 2720 | 1848
295 | 707358 | Site Expenses (New) | Umbrella | No. | 3 |  | Management | Approved | 2024-07-27 11:57 | 2024-07-27 12:00 |  |  | 2024-07-27 18:33 | 3 | Sajid khan | 0 |  | 0 |  | 160 | [12 empty] | 1440 | 1008