## Requisition_Tracking-Summary638
Select Supplier
Project : SRA MORWADI
From Date : 01/01/2024 To date: 29/08/2024
Page 1 of 1
Total Records: 106 Records 1 to 106
Srno | ReqSr_no | Task | Material_Name | Tec.Unit | Qty | Supplier | Priority | Req_status | Requisition_Date | Requirement_Date | Remark | Specifications | Approval_Date | Approved_Qty | Approved_By | Rate | Tax_Scheme_Name | BrandName | StockQty | Est_Rate | Discount | Credit | Conversion_Factor | Transport_Rate | Pkg_Forward | Loading | Unloading | Insurance | Installation | OtherCharges1 | OtherCharges2 | HSN_Code | Est_Cost | Consumed_Amt
1 | 677258 | Site Expenses for Office stationary | Copy Power A4 | Ream | 2 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-01-11 17:50 | 2 | Sajid khan | 0 |  | 0 |  | 168 | [12 empty] | 336 | 0
2 | 677259 | Site Expenses for Office stationary | Cello Tape 2" | No. | 12 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-01-11 17:50 | 12 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 1800 | 0
3 | 677260 | Site Expenses for Office stationary | Fevistick 15gm | No. | 6 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-01-11 17:50 | 6 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 600 | 0
4 | 677261 | Site Expenses for Office stationary | Highliter | No. | 6 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-01-11 17:50 | 6 | Sajid khan | 0 |  | 0 |  | 9.45 | [12 empty] | 56.7 | 0
5 | 677262 | Site Expenses for Office stationary | Permenant Marker | No. | 6 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-01-11 17:50 | 6 | Sajid khan | 0 |  | 0 |  | 18.9 | [12 empty] | 113.4 | 0
6 | 677263 | Site Expenses for Office stationary | Whitner Pen | No. | 6 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-01-11 17:50 | 6 | Sajid khan | 0 |  | 0 |  | 27 | [12 empty] | 162 | 0
7 | 677754 | Site Expenses for Office stationary | Caution Tape (250Mtrs) | Mtrs | 10 |  | Management | Approved | 2024-01-15 12:00 | 2024-01-15 12:00 |  |  | 2024-01-15 14:32 | 10 | Sajid khan | 0 |  | 0 |  | 1.2 | [12 empty] | 12 | 0
8 | 678494 | B-Raft Concrete Work M-25 | Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 191.756 |  | Management | Approved | 2024-01-16 12:00 | 2024-01-16 12:00 | :: Released from PO 67829 :- PO detail id 156174 :- ReqD_id 783892 :: Released from PO 67733 :- PO detail id 155960 :- ReqD_id 779164 |  | 2024-04-08 11:21 | 91.756 | AKSHADA MAHAJAN | 0 |  | 0 |  | 3355.93 | [12 empty] | 1287287.765 | 975333.948
9 | 681297 | 40 Kva DG B Check Servicing | Service Charges | No. | 1 |  | Management | Approved | 2024-01-25 12:00 | 2024-01-25 12:00 | :: Released from PO 67804 :- PO detail id 156128 :- ReqD_id 783107 |  | 2024-02-17 17:09 | 1 | Akshada Mahajan | 0 |  | 0 |  | 1500 | [12 empty] | 1500 | 0
10 | 683333 | B-Raft Work B Bldg.-Raft RCC Work | Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 94.5 |  | Management | Approved | 2024-02-07 12:00 | 2024-02-07 12:00 | :: Released from PO 67975 :- PO detail id 156800 :- ReqD_id 785649 |  | 2024-03-29 17:41 | 14.5 | AKSHADA MAHAJAN | 0 |  | 0 |  | 3355.93 | [12 empty] | 1491059.8346 | 1626295.3498
11 | 683333 | B-Raft Work B Bldg.-Raft RCC Work | Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 11 |  | Management | Approved | 2024-02-07 12:00 | 2024-02-07 12:00 | :: Released from PO 68329 :- PO detail id 157692 :- ReqD_id 793702 :: Released from PO 67975 :- PO detail id 156800 :- ReqD_id 785649 |  | 2024-04-08 11:21 | 11 | Akshada Mahajan | 0 |  | 0 |  | 3355.93 | [12 empty] | 1491059.8346 | 1626295.3498
12 | 683333 | B-Raft Work B Bldg.-Raft RCC Work | Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 6 |  | Management | Approved | 2024-02-07 12:00 | 2024-02-07 12:00 | :: Released from PO 67897 :- PO detail id 156361 :- ReqD_id 785637 |  | 2024-04-08 11:21 | 6 | Akshada Mahajan | 0 |  | 0 |  | 3355.93 | [12 empty] | 1491059.8346 | 1626295.3498
13 | 683375 | B Parking-GF (1st Slab) B Bldg 1st Slab Steel | Steel Bars 10mm | Kgs | 896.68 |  | Management | Approved | 2024-02-08 12:00 | 2024-02-08 12:00 |  |  | 2024-02-08 12:46 | 271.72 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 83458.5795 | 36651.4042
14 | 685193 | Labour Camp Dustbin For Labour Camp | Dustbin | No. | 4 |  | Management | Approved | 2024-02-19 12:00 | 2024-02-19 12:00 |  |  | 2024-02-20 11:05 | 4 | Sajid khan | 0 |  | 0 |  | 2500 | [12 empty] | 10000 | 0
15 | 685542 | A-Footing & Pile Cap & Raft PCC M-15 | Sand-Metal Mix M15 (Downpour) | Cu.Mtrs | 20 |  | Management | Approved | 2024-02-29 12:00 | 2024-02-29 12:00 | :: Released from PO 68108 :- PO detail id 157128 :- ReqD_id 789771 |  | 2024-03-29 17:37 | 20 | PARSHURAM KORE | 0 |  | 0 |  | 3165.25 | [12 empty] | 347569.772 | 233960.0966
16 | 685912 | Office & Store Setup | Transfer challan | No. | 2 |  | Management | Approved | 2024-03-01 12:00 | 2024-03-01 12:00 |  |  | 2024-03-02 11:02 | 2 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 100 | 0
17 | 685915 | Office & Store Setup | Issue Slip Book | No. | 50 |  | Management | Approved | 2024-03-01 12:00 | 2024-03-01 12:00 |  |  | 2024-03-02 11:02 | 50 | Sajid khan | 0 |  | 0 |  | 20 | [12 empty] | 1000 | 0
18 | 685917 | Office & Store Setup | Gate Pass Book | No. | 3 |  | Management | Approved | 2024-03-01 12:00 | 2024-03-01 12:00 |  |  | 2024-03-02 11:02 | 3 | Sajid khan | 0 |  | 0 |  | 120 | [12 empty] | 360 | 0
19 | 685918 | Office & Store Setup | DAILY REPORT BOOK | No. | 5 |  | Management | Approved | 2024-03-01 12:00 | 2024-03-01 12:00 |  |  | 2024-03-02 11:02 | 5 | Sajid khan | 0 |  | 0 |  | 80 | [12 empty] | 400 | 0
20 | 687953 | Dept. Labour-Misc. work-Dynamic Test,preparation,curing & ot | Ghamela | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-21 13:45 | 2 | Sajid khan | 0 |  | 0 |  | 70 | [12 empty] | 140 | 0
21 | 687955 | Labour Camp Lab Camp Miscl. Work | Cement Loose 43 grade (OPC) | Kgs | 20 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:50 | 20 | Sajid khan | 0 |  | 0 |  | 5.1 | [12 empty] | 102 | 0
22 | 687956 | A Parking-1st Floor (2nd Slab) Wall Tie Filling | GP2 Waterproofing Chemical | Kgs | 10 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 | :: Released from PO 68295 :- PO detail id 157578 :- ReqD_id 792983 |  | 2024-04-01 16:27 | 10 | vinay mittal | 0 |  | 0 |  | 150 | [12 empty] | 67500 | 9086
23 | 688042 | B1- SUB-STRUCTURE Screeding Work | Sand-Metal Mix M15 (Downpour) | Cu.Mtrs | 0.08 |  | Management | Approved | 2024-03-20 12:00 | 2024-03-20 12:00 | :: Released from PO 68240 :- PO detail id 157442 :- ReqD_id 793155 |  | 2024-03-29 17:38 | 0.08 | PARSHURAM KORE | 0 |  | 0 |  | 3165.25 | [12 empty] | 38236.22 | 45881.988
24 | 688051 | B1- Footing PCC M-15 | Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 16.73 |  | Management | Approved | 2024-03-21 12:00 | 2024-03-21 12:00 | :: Released from PO 68254 :- PO detail id 157481 :- ReqD_id 793193 |  | 2024-04-08 11:24 | 16.73 | Akshada Mahajan | 0 |  | 0 |  | 2125 | [12 empty] | 128605 | 169186.7041
25 | 689047 | Portable Office Container for Site office & Store | Container Office 20 x 8 x 8.5" | No. | 1 |  | Management | Approved | 2024-04-02 12:00 | 2024-04-02 12:00 |  |  | 2024-04-02 14:30 | 1 | Sajid khan | 0 |  | 0 |  | 177750 | [12 empty] | 533250 | 231280
26 | 690860 | Safety Setup -Safety PPE & Equipments | Megaphone | No. | 1 |  | Management | Approved | 2024-04-15 12:00 | 2024-04-15 12:00 |  |  | 2024-04-17 10:25 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
27 | 691832 | CCTV Camera Work. | HARD DISK 6TB | No. | 1 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 15000 | [12 empty] | 30000 | 13962.36
28 | 691833 | CCTV Camera Work. | LED Monitor 18.5" | No. | 1 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 7500 | [12 empty] | 15000 | 5782
29 | 691834 | CCTV Camera Work. | 2MP Full HD IR Network Bullet Camera | No. | 2 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 2 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1800 | 44322.088
30 | 691835 | CCTV Camera Work. | 4+2 POE Switch | No. | 1 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 200 | 2678.36
31 | 691836 | CCTV Camera Work. | 5 x 5 Camera Termination Box | No. | 2 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 2 | Sajid khan | 0 |  | 0 |  | 10 | [12 empty] | 180 | 625.5168
32 | 691837 | CCTV Camera Work. | D-link CAT 6 cable | Mtrs | 305 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 305 | Sajid khan | 0 |  | 0 |  | 13 | [12 empty] | 23790 | 45428.591
33 | 691838 | CCTV Camera Work. | Installation Charges | No. | 1 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 750 | [12 empty] | 9000 | 2920.5
34 | 691839 | CCTV Camera Work. | NVR 16 Channel CP-UNR-4K4162-V2 | No. | 1 |  | Management | Approved | 2024-04-17 12:00 | 2024-04-17 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 9750 | [12 empty] | 9750 | 0
35 | 691971 | Plumbing Setup Temporary Curing Line | ASTM Elbow 1" | No. | 24 |  | Management | Approved | 2024-04-18 12:00 | 2024-04-18 12:00 |  |  | 2024-05-02 16:10 | 24 | Sajid khan | 0 |  | 0 |  | 17.07 | [12 empty] | 409.68 | 0
36 | 691991 | Plumbing Setup Temporary Curing Line | Curing Pipe 1/2" | Bundle | 3 |  | Management | Approved | 2024-04-18 12:00 | 2024-04-18 12:00 |  |  | 2024-05-02 16:10 | 3 | Sajid khan | 0 |  | 0 |  | 500 | [12 empty] | 1500 | 0
37 | 691992 | Plumbing Setup Temporary Curing Line | GI Clips 2" | No. | 24 |  | Management | Approved | 2024-04-18 12:00 | 2024-04-18 12:00 |  |  | 2024-05-02 16:10 | 24 | Sajid khan | 0 |  | 0 |  | 2.5 | [12 empty] | 60 | 0
38 | 691994 | Plumbing Setup Temporary Curing Line | Teflon Tape | No. | 12 |  | Management | Approved | 2024-04-18 12:00 | 2024-04-18 12:00 |  |  | 2024-05-02 16:10 | 12 | Sajid khan | 0 |  | 0 |  | 6.24 | [12 empty] | 74.88 | 0
39 | 692228 | A Parking-1st Floor Column/LW/SW 1st To 2nd Slab Concrete M- | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 2.128 |  | Management | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 | :: Released from PO 68697 :- PO detail id 158640 :- ReqD_id 799826 :: Released from PO 68552 :- PO detail id 158311 :- ReqD_id 799768 |  | 2024-06-19 18:01 | 2.128 | Akshada Mahajan | 0 |  | 0 |  | 4012 | [12 empty] | 344229.6 | 330792.1018
40 | 692230 | Plumbing Setup Temporary Curing Line | Submersible Pumpset 5hp | No. | 1 |  | Management | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 50000 | [12 empty] | 50000 | 0
41 | 692232 | Plumbing Setup Temporary Curing Line | Starter | No. | 1 |  | Management | Approved | 2024-04-25 12:00 | 2024-04-25 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 2081.25 | [12 empty] | 2081.25 | 0
42 | 692242 | B Parking-2nd Floor (3rd Slab) Fire Sleeve Fixing | PVC Pipe 8" x 10 fts S/S | No. | 1 |  | Management | Approved | 2024-04-27 12:00 | 2024-04-27 12:00 |  |  | 2024-05-02 16:10 | 1 | Sajid khan | 0 |  | 0 |  | 1148.18 | [12 empty] | 1148.18 | 0
43 | 692243 | A.Pile Cap &amp;amp; Raft Concrete (grid Slab Adj) | Sand-Metal Mix M20 (Pumpable) | Cu.Mtrs | 12 |  | Management | Approved | 2024-04-27 12:00 | 2024-04-27 12:00 | :: Released from PO 68808 :- PO detail id 158865 :- ReqD_id 807637 :: Released from PO 68759 :- PO detail id 158754 :- ReqD_id 806525 :: Released from PO 68734 :- PO detail id 158713 :- ReqD_id 799841will be used for A Bldg Grid slab |  | 2024-06-19 18:03 | 12 | Akshada Mahajan | 0 |  | 0 |  | 2125 | [12 empty] | 340000 | 191343.9232
44 | 692243 | A.Pile Cap &amp;amp; Raft Concrete (grid Slab Adj) | Sand-Metal Mix M20 (Pumpable) | Cu.Mtrs | 90 |  | Management | Approved | 2024-04-27 12:00 | 2024-04-27 12:00 | :: Released from PO 68754 :- PO detail id 158749 :- ReqD_id 806166will be used for A Bldg Grid slab |  | 2024-06-19 18:02 | 90 | Akshada Mahajan | 0 |  | 0 |  | 2125 | [12 empty] | 340000 | 191343.9232
45 | 695094 | A Parking-2nd Floor Misc.Work (M) | Kiltan ( Hessian Cloth ) | Mtrs | 31 |  | Management | Approved | 2024-05-07 12:00 | 2024-05-07 12:00 | :: Released from PO 68640 :- PO detail id 158505 :- ReqD_id 803185 |  | 2024-07-11 15:55 | 31 | GULSHAN GANGWANI | 0 |  | 0 |  | 17.5 | [12 empty] | 50750 | 24418.8
46 | 695395 | Labour Camp Plumbing Line | ASTM Ball Valve 2" | No. | 6 |  | Management | Approved | 2024-05-13 12:00 | 2024-05-13 12:00 |  |  | 2024-07-04 10:28 | 6 | kantilal.jagtap | 0 |  | 0 |  | 1562 | [12 empty] | 9372 | 0
47 | 695398 | Labour Camp Plumbing Line | ASTM Elbow 1" | No. | 15 |  | Management | Approved | 2024-05-13 12:00 | 2024-05-13 12:00 |  |  | 2024-05-15 11:36 | 15 | Sajid khan | 0 |  | 0 |  | 17.07 | [12 empty] | 256.05 | 0
48 | 695401 | Labour Camp Plumbing Line | ASTM Solvent Cement 717 Black - 946 ml | No. | 4 |  | Management | Approved | 2024-05-13 12:00 | 2024-05-13 12:00 |  |  | 2024-05-15 11:36 | 4 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 400 | 0
49 | 695403 | Labour Camp Plumbing Line | Teflon Tape | No. | 12 |  | Management | Approved | 2024-05-13 12:00 | 2024-05-13 12:00 |  |  | 2024-05-14 11:20 | 12 | Sajid khan | 0 |  | 0 |  | 6.24 | [12 empty] | 74.88 | 0
50 | 695543 | Electrical Work Site Setup | Earth Tester | No. | 1 |  | Management | Approved | 2024-05-15 12:00 | 2024-05-15 12:00 |  |  | 2024-05-15 17:12 | 1 | Sajid khan | 0 |  | 0 |  | 2000 | [12 empty] | 2000 | 0
51 | 695552 | Electrical Work Site Setup | Rubber Matt 3ft x 3ft | No. | 10 |  | Management | Approved | 2024-05-15 12:00 | 2024-05-15 12:00 |  |  | 2024-05-15 17:12 | 10 | Sajid khan | 0 |  | 0 |  | 450 | [12 empty] | 4500 | 0
52 | 695729 | Safety Setup Safety Material for Labours | Pollution Mask | No. | 5 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-17 17:54 | 5 | Sajid khan | 0 |  | 0 |  | 4 | [12 empty] | 20 | 0
53 | 695730 | Safety Setup Safety Material for Labours | Mask (N95) | No. | 5 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-17 17:54 | 5 | Sajid khan | 0 |  | 0 |  | 120 | [12 empty] | 600 | 0
54 | 695737 | Safety Setup Safety Material for Labours | Safety Jacket | No. | 10 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 | :: Released from PO 68717 :- PO detail id 158672 :- ReqD_id 804891 | Green jacket for staff | 2024-07-23 13:10 | 10 | Akshada Mahajan | 0 |  | 0 |  | 250 | [12 empty] | 2500 | 0
55 | 696685 | A-3rd Floor Lobby Electrical Conduct | Brown Tape 2" | No. | 4 |  | Management | Approved | 2024-05-20 12:00 | 2024-05-20 12:00 |  |  | 2024-05-21 12:46 | 4 | Sajid khan | 0 |  | 0 |  | 8 | [12 empty] | 32 | 0
56 | 696785 | A Parking-2nd Floor (3rd Slab) Fire Sleeve Fixing | PVC Pipe 4" x 10 Ft S/S | No. | 3 |  | Management | Approved | 2024-05-20 12:00 | 2024-05-20 12:00 |  |  | 2024-05-21 12:46 | 3 | Sajid khan | 0 |  | 0 |  | 489.3 | [12 empty] | 1467.9 | 0
57 | 696786 | A Parking-2nd Floor (3rd Slab) Fire Sleeve Fixing | PVC Pipe 63mm x 10fts | No. | 8 |  | Management | Approved | 2024-05-20 12:00 | 2024-05-20 12:00 |  |  | 2024-05-21 12:46 | 8 | Sajid khan | 0 |  | 0 |  | 249.8 | [12 empty] | 1998.4 | 0
58 | 696798 | 3rd Floor Internal flat Plumbing Sleeves | PVC Pipe 3" x 10 fts S/S | No. | 2 |  | Management | Approved | 2024-05-20 12:00 | 2024-05-20 12:00 |  |  | 2024-05-21 12:46 | 2 | Sajid khan | 0 |  | 0 |  | 264.6 | [12 empty] | 529.2 | 0
59 | 696799 | 3rd Floor Internal flat Plumbing Sleeves | PVC Pipe 4" 10 Ft S/S Pipe | No. | 1 |  | Management | Approved | 2024-05-20 12:00 | 2024-05-20 12:00 |  |  | 2024-05-21 12:46 | 1 | Sajid khan | 0 |  | 0 |  | 298.125 | [12 empty] | 298.125 | 0
60 | 697102 | UGWT Bottom Raft PCC M-15 | Sand-Metal Mix M15 (Downpour) | Cu.Mtrs | 2 |  | Management | Approved | 2024-05-27 12:00 | 2024-05-27 12:00 | :: Released from PO 68777 :- PO detail id 158776 :- ReqD_id 806627 |  | 2024-06-19 18:03 | 2 | Akshada Mahajan | 0 |  | 0 |  | 3165.25 | [12 empty] | 72800.75 | 73314.919
61 | 697117 | Phase 2 Quality Lab Setup | Cube Mould 15x15x15 cm | No. | 18 |  | Management | Approved | 2024-05-28 12:00 | 2024-05-28 12:00 |  |  | 2024-05-28 16:43 | 18 | kantilal.jagtap | 0 |  | 0 |  | 950 | [12 empty] | 17100 | 0
62 | 697118 | Phase 2 Quality Lab Setup | Slump Cone with Tamping Rod. | set | 1 |  | Management | Approved | 2024-05-28 12:00 | 2024-05-28 12:00 |  |  | 2024-05-28 16:43 | 1 | kantilal.jagtap | 0 |  | 0 |  | 500 | [12 empty] | 500 | 0
63 | 697119 | Phase 2 Quality Lab Setup | Cube Casting Scoop | No. | 2 |  | Management | Approved | 2024-05-28 12:00 | 2024-05-28 12:00 |  |  | 2024-05-28 16:43 | 2 | kantilal.jagtap | 0 |  | 0 |  | 500 | [12 empty] | 1000 | 0
64 | 697120 | Phase 2 Quality Lab Setup | Wheelbarrow | No. | 1 |  | Management | Approved | 2024-05-28 12:00 | 2024-05-28 12:00 |  |  | 2024-05-28 16:43 | 1 | kantilal.jagtap | 0 |  | 0 |  | 2700 | [12 empty] | 2700 | 0
65 | 697124 | Office & Store Setup Phase 2 Site Office | Engineer Table | No. | 5 |  | Management | Approved | 2024-05-28 12:00 | 2024-05-28 12:00 |  |  | 2024-05-28 16:43 | 5 | kantilal.jagtap | 0 |  | 0 |  | 4140 | [12 empty] | 20700 | 0
66 | 697125 | Office & Store Setup Phase 2 Site Office | Table Fan 16" | No. | 5 |  | Management | Approved | 2024-05-28 12:00 | 2024-05-28 12:00 |  |  | 2024-05-28 16:43 | 5 | kantilal.jagtap | 0 |  | 0 |  | 1111 | [12 empty] | 5555 | 0
67 | 697142 | DG Set DG Maintainance Work | Banjo washer (19mm) | No. | 8 |  | Management | Approved | 2024-05-29 12:00 | 2024-05-29 12:00 |  |  | 2024-05-29 16:57 | 8 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 800 | 0
68 | 697448 | Phase 2 Site Setup Electrical Work | Rubber Matt 3ft x 3ft | No. | 6 |  | Management | Approved | 2024-05-31 11:29 | 2024-05-31 12:00 |  |  | 2024-05-31 16:07 | 6 | Sajid khan | 0 |  | 0 |  | 450 | [12 empty] | 2700 | 0
69 | 697450 | Phase 2 Site Setup Electrical Work | Earth Tester | No. | 1 |  | Management | Approved | 2024-05-31 11:29 | 2024-05-31 12:00 |  |  | 2024-05-31 16:07 | 1 | Sajid khan | 0 |  | 0 |  | 2000 | [12 empty] | 2000 | 0
70 | 698007 | A Parking-2nd Floor (3rd Slab))- Beam,Slab & Stair. Concrete | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 0.06 |  | Management | Approved | 2024-06-03 14:38 | 2024-06-03 12:00 | :: Released from PO 68842 :- PO detail id 159008 :- ReqD_id 808427 |  | 2024-06-19 18:11 | 0.06 | PARSHURAM KORE | 0 |  | 0 |  | 4012 | [12 empty] | 565210.56 | 426053.7235
71 | 699210 | Office & Store Setup Phase 2 Site Office | Security Cabin | No. | 1 |  | Management | Approved | 2024-06-09 11:52 | 2024-06-09 12:00 |  |  | 2024-06-10 12:35 | 1 | sanket patil | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
72 | 699239 | Phase 2 Labour camp Plumbing Setup | Tank Nipple 11/4" | No. | 6 |  | Management | Approved | 2024-06-10 15:09 | 2024-06-10 12:00 |  |  | 2024-06-11 11:46 | 6 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 900 | 0
73 | 699247 | Phase 2 Labour camp Plumbing Setup | ASTM Pipe 1/2" x 10 fts | No. | 100 |  | Management | Approved | 2024-06-10 15:18 | 2024-06-10 12:00 |  |  | 2024-06-11 11:46 | 100 | Sajid khan | 0 |  | 0 |  | 110.56 | [12 empty] | 11056 | 0
74 | 699254 | Phase 2 Labour camp Plumbing Setup | ASTM Solvent Cement 717 Black - 946 ml | No. | 5.28 |  | Management | Approved | 2024-06-10 15:23 | 2024-06-10 12:00 |  |  | 2024-06-11 11:46 | 0.28 | deepika mulik | 0 |  | 0 |  | 100 | [12 empty] | 528 | 0
75 | 699254 | Phase 2 Labour camp Plumbing Setup | ASTM Solvent Cement 717 Black - 946 ml | No. | 5.28 |  | Management | Approved | 2024-06-10 15:23 | 2024-06-10 12:00 |  |  | 2024-06-11 11:46 | 0.28 | deepika mulik | 0 |  | 0 |  | 100 | [12 empty] | 528 | 0
76 | 699254 | Phase 2 Labour camp Plumbing Setup | ASTM Solvent Cement 717 Black - 946 ml | No. | 5.28 |  | Management | Approved | 2024-06-10 15:23 | 2024-06-10 12:00 |  |  | 2024-06-11 11:46 | 0.56 | deepika mulik | 0 |  | 0 |  | 100 | [12 empty] | 528 | 0
77 | 699254 | Phase 2 Labour camp Plumbing Setup | ASTM Solvent Cement 717 Black - 946 ml | No. | 5.28 |  | Management | Approved | 2024-06-10 15:23 | 2024-06-10 12:00 |  |  | 2024-06-11 11:46 | 4.44 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 528 | 0
78 | 699254 | Phase 2 Labour camp Plumbing Setup | ASTM Solvent Cement 717 Black - 946 ml | No. | 5.28 |  | Management | Approved | 2024-06-10 15:23 | 2024-06-10 12:00 |  |  | 2024-06-11 11:46 | 0.56 | deepika mulik | 0 |  | 0 |  | 100 | [12 empty] | 528 | 0
79 | 701974 | A Parking-GF (1st Slab) Beam,Slab & Stair. Concrete M30 | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 0.351 |  | Management | Approved | 2024-06-15 09:31 | 2024-06-15 12:00 | :: Released from PO 68956 :- PO detail id 159420 :- ReqD_id 814376 |  | 2024-07-04 16:52 | 0.351 | Akshada Mahajan | 0 |  | 0 |  | 4012 | [12 empty] | 641976.168 | 632265.0649
80 | 701975 | A Parking-1st Floor (2nd Slab)- Beam,Slab & Stair. Concrete | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 5.014 |  | Management | Approved | 2024-06-15 09:31 | 2024-06-15 12:00 | :: Released from PO 68956 :- PO detail id 159420 :- ReqD_id 814377 |  | 2024-07-04 16:52 | 3.014 | AKSHADA MAHAJAN | 0 |  | 0 |  | 4012 | [12 empty] | 641976.168 | 620301.837
81 | 701976 | A Parking-2nd Floor (3rd Slab)Column/LW/SW Conc-M30-2nd to 3 | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 0.61 |  | Management | Approved | 2024-06-15 09:31 | 2024-06-15 12:00 | :: Released from PO 68956 :- PO detail id 159420 :- ReqD_id 814378 |  | 2024-07-04 16:52 | 0.61 | Akshada Mahajan | 0 |  | 0 |  | 4012 | [12 empty] | 309204.84 | 265720.6732
82 | 702021 | Staff Rainy Equipments | Rain Coat | No. | 22 |  | Management | Approved | 2024-06-17 13:00 | 2024-06-17 12:00 | 1 SATISH JAGTAP 2 MANGESH KSHIRSAGAR 3 RANJEET DALAVI 4 YOGESH AGARWAL 5 JITENDRA SHINDE 6 SATISH ICHAKE 7 SHRIKANT DEOKAR 8 SHUBHAM BORKAR 9 SURESH WAGHMARE 10 DARSHAN UJJAINKAR 11 HARISH INGALE 12 MALHAR KAMBLE 13 MIHIR PARASAR 14 PRATIK SHETE 15 UDAY NARAYAN 16 VIJAY MANDAL 17 Dipak Tripathi 18 MARUTI KAMBLE 19 VIKAS PARDE 20 NARAYAN SHUKLA |  | 2024-06-18 17:57 | 22 | Sajid khan | 0 |  | 0 |  | 420 | [12 empty] | 9240 | 0
83 | 702022 | Staff Rainy Equipments | Umbrella | No. | 6 |  | Management | Approved | 2024-06-17 13:00 | 2024-06-17 12:00 |  |  | 2024-06-18 17:57 | 6 | Sajid khan | 0 |  | 0 |  | 160 | [12 empty] | 960 | 0
84 | 702031 | A Parking-2nd Floor (3rd Slab)Column/LW/SW Conc-M30-2nd to 3 | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 1 |  | Management | Approved | 2024-06-17 15:29 | 2024-06-17 12:00 |  |  | 2024-06-18 17:57 | 1 | Sajid khan | 0 |  | 0 |  | 4012 | [12 empty] | 309204.84 | 265720.6732
85 | 702044 | Material For Store,Office & Labour camp | Self Tapping 25x8 | Box | 1.5 |  | Management | Approved | 2024-06-17 17:30 | 2024-06-17 12:00 | :: Released from PO 69199 :- PO detail id 160113 :- ReqD_id 815037 |  | 2024-07-15 17:49 | 0.5 | kantilal.jagtap | 0 |  | 0 |  | 640.5 | [12 empty] | 960.75 | 649
86 | 702045 | Material For Store,Office & Labour camp | Tadi Patti 8" | No. | 2 |  | Management | Approved | 2024-06-17 17:30 | 2024-06-17 12:00 |  |  | 2024-06-18 17:57 | 2 | Sajid khan | 0 |  | 0 |  | 60 | [12 empty] | 120 | 0
87 | 703548 | Phase 1 Torch for Security | Rechargeble LED Torch Light | set | 2 |  | Management | Approved | 2024-07-01 10:56 | 2024-07-01 12:00 |  |  | 2024-07-02 12:06 | 2 | Sajid khan | 0 |  | 0 |  | 90 | [12 empty] | 180 | 0
88 | 703549 | Phase 2 Torch for Security | Rechargeble LED Torch Light | set | 2 |  | Management | Approved | 2024-07-01 10:56 | 2024-07-01 12:00 |  |  | 2024-07-02 12:06 | 2 | Sajid khan | 0 |  | 0 |  | 90 | [12 empty] | 180 | 0
89 | 704231 | A-Flat No 613 Electrical Work | Fan Box | No. | 4 |  | Management | Approved | 2024-07-01 18:54 | 2024-07-01 12:00 |  |  | 2024-07-02 12:06 | 4 | Sajid khan | 0 |  | 0 |  | 74.42 | [12 empty] | 297.68 | 0
90 | 704232 | A-Flat No 614 Electrical Work | Fan Box | No. | 4 |  | Management | Approved | 2024-07-01 18:54 | 2024-07-01 12:00 |  |  | 2024-07-02 12:06 | 4 | Sajid khan | 0 |  | 0 |  | 74.42 | [12 empty] | 297.68 | 0
91 | 704240 | A-4th Floor Lobby Electrical Conduct | Tape Roll | No. | 4 |  | Management | Approved | 2024-07-01 18:59 | 2024-07-01 12:00 |  |  | 2024-07-02 12:06 | 4 | Sajid khan | 0 |  | 0 |  | 1327.5 | [12 empty] | 5310 | 0
92 | 704890 | B Parking-2nd Floor (3rd Slab) Fire Sleeve Fixing | PVC Agri Pipe 63mm x 20fts 4KG | No. | 2 |  | Management | Approved | 2024-07-03 12:22 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 2 | Sajid khan | 0 |  | 0 |  | 192 | [12 empty] | 384 | 0
93 | 704891 | B 4th Slab Fire Sleeve | PVC Agri Pipe 63mm x 20fts 4KG | No. | 2 |  | Management | Approved | 2024-07-03 12:22 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 2 | Sajid khan | 0 |  | 0 |  | 192 | [12 empty] | 384 | 0
94 | 704892 | B 4th Slab Fire Sleeve | PVC Agri Pipe 90mm x 10fts 4KG | No. | 2 |  | Management | Approved | 2024-07-03 12:23 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 2 | Sajid khan | 0 |  | 0 |  | 192 | [12 empty] | 384 | 0
95 | 704893 | B Parking-2nd Floor (3rd Slab) Fire Sleeve Fixing | PVC Agri Pipe 110mm x 20fts 4KG | No. | 1 |  | Management | Approved | 2024-07-03 12:23 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 1 | Sajid khan | 0 |  | 0 |  | 192 | [12 empty] | 192 | 0
96 | 704894 | B 4th Slab Fire Sleeve | PVC Agri Pipe 110mm x 20fts 4KG | No. | 2 |  | Management | Approved | 2024-07-03 12:23 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 2 | Sajid khan | 0 |  | 0 |  | 192 | [12 empty] | 384 | 0
97 | 705142 | A-4th Slab Lobby Electrical Conduct | Tape Roll | No. | 4 |  | Management | Approved | 2024-07-03 15:10 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 4 | Sajid khan | 0 |  | 0 |  | 1327.5 | [12 empty] | 5310 | 0
98 | 705143 | A-5th Floor Lobby Electrical Conduct | Tape Roll | No. | 4 |  | Management | Approved | 2024-07-03 15:10 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 4 | Sajid khan | 0 |  | 0 |  | 1327.5 | [12 empty] | 5310 | 0
99 | 705144 | A-6th Floor Lobby Electrical Conduct | Tape Roll | No. | 4 |  | Management | Approved | 2024-07-03 15:10 | 2024-07-03 12:00 |  |  | 2024-07-04 13:10 | 4 | Sajid khan | 0 |  | 0 |  | 1327.5 | [12 empty] | 5310 | 0
100 | 706127 | B1-3rd Slab,Beam Concrete | Cement Loose 53 Grade | Metric Tonnes | 9.17 |  | Management | Approved | 2024-07-04 15:32 | 2024-07-04 12:00 |  |  | 2024-07-05 15:38 | 7.5011 | AKSHADA MAHAJAN |  |  | 0 |  | 3880 | [12 empty] | 35579.6 | 12283.104
101 | 706129 | B1 Upper Ground Partition Wall Concrete | Cement Loose 53 Grade | Metric Tonnes | 2.99 |  | Management | Approved | 2024-07-04 15:32 | 2024-07-04 12:00 |  |  | 2024-07-05 15:38 | 2.99 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 22736.8 | 21123.2
102 | 706136 | A Bldg 3rd To 4th Slab column & non str. wall concrete | Cement Loose 53 Grade | Metric Tonnes | 19.45 |  | Management | Approved | 2024-07-04 18:20 | 2024-07-04 12:00 |  |  | 2024-07-05 15:38 | 19.45 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 150932 | 143930.0001
103 | 706137 | B Bldg 4th Slab Beam,Slab,Staircase Concrete | Cement Loose 53 Grade | Metric Tonnes | 3.98 |  | Management | Approved | 2024-07-04 18:20 | 2024-07-04 12:00 |  |  | 2024-07-05 15:38 | 3.98 | Sajid khan | 0 |  | 0 |  | 3880 | [12 empty] | 90908.4 | 143930.0019
104 | 707247 | B Parking-2nd Floor (3rd Slab)Column/LW/SW Conc-M30-2nd to 3 | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 1 |  | Management | Approved | 2024-07-19 10:58 | 2024-07-19 12:00 |  |  | 2024-07-19 18:15 | 1 | kantilal.jagtap | 0 |  | 0 |  | 4012 | [12 empty] | 278432.8 | 237637.865
105 | 707248 | B Bldg Column 3rd to 4th Slab | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 5 |  | Management | Approved | 2024-07-19 10:58 | 2024-07-19 12:00 | :: Released from PO 69303 :- PO detail id 160352 :- ReqD_id 824692 |  | 2024-07-30 11:39 | 5 | Akshada Mahajan | 0 |  | 0 |  | 4012 | [12 empty] | 242445.16 | 171270.9608
106 | 707248 | B Bldg Column 3rd to 4th Slab | Sand-Metal Mix M30 (Pumpable) | Cu.Mtrs | 38.43 |  | Management | Approved | 2024-07-19 10:58 | 2024-07-19 12:00 |  |  | 2024-07-19 18:15 | 10.43 | AKSHADA MAHAJAN |  |  | 0 |  | 4012 | [12 empty] | 242445.16 | 171270.9608