## Requisition_Tracking-Summary638
Select Supplier
Project : GANGA ALTUS
From Date : 01/01/2024 To date: 05/09/2024
Page 1 of 1
Total Records: 192 Records 1 to 192
Srno | ReqSr_no | Task | Material_Name | Tec.Unit | Qty | Supplier | Priority | Req_status | Requisition_Date | Requirement_Date | Remark | Specifications | Approval_Date | Approved_Qty | Approved_By | Rate | Tax_Scheme_Name | BrandName | StockQty | Est_Rate | Discount | Credit | Conversion_Factor | Transport_Rate | Pkg_Forward | Loading | Unloading | Insurance | Installation | OtherCharges1 | OtherCharges2 | HSN_Code | Est_Cost | Consumed_Amt
1 | 682787 | E Bldg.-Domestic Water Line | Hold Tite (500 gm) | Pack | 4 |  | Management | Approved | 2024-02-03 12:00 | 2024-02-03 12:00 |  |  | 2024-02-07 12:12 | 4 | kantilal.jagtap | 0 |  | 0 |  | 130 | [12 empty] | 4160 | 0
2 | 686003 | F-Entrance Gate-AAC Blockwork 8" | AAC Block 650x240x200 | No. | 320 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 |  |  | 2024-05-07 14:35 | 320 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 32000 | 0
3 | 686006 | D&E-Entrance Gate-AAC Blockwork 8" | AAC Block 650x240x200 | No. | 320 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 |  |  | 2024-05-07 14:35 | 320 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 32000 | 0
4 | 686135 | E - Internal Plumbing - (PPR-C, PVC, ASTM) | Hold Tite (1 Kgs) | Kgs | 10.02 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 |  |  | 2024-03-04 16:11 | 10.02 | Sajid khan | 0 |  | 0 |  | 206.4 | [12 empty] | 8256 | 7688.176
5 | 687746 | D-206-3BHK Int Flat Wiring Work | PVC Copper Wire 1.5 Sqmm Grey | Mtrs | 85 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 | :: Released from PO 68406 :- PO detail id 157886 :- ReqD_id 792359 |  | 2024-04-16 18:59 | 77.85 | Vinay Mittal | 0 |  | 0 |  | 100 | [12 empty] | 8500 | 113.6171
6 | 689082 | D,E,F-Bldg Side- PQC Road Work(Main Road | Pavement Quality Concrete (M40) | Cu.Mtrs | 296 |  | Management | Approved | 2024-04-02 12:00 | 2024-04-02 12:00 | :: Released from PO 68366 :- PO detail id 157757 :- ReqD_id 795645 :: Released from PO 68364 :- PO detail id 157755 :- ReqD_id 794546 | Without Fly ash & Without GGBS | 2024-07-10 17:50 | 148 | Akshada Mahajan | 0 |  | 0 |  | 3000 | [12 empty] | 1332000 | 1429166.44
7 | 689243 | Stilt Floor- Common Toilet | Chair Bracket for W H | No. | 2 |  | Management | Approved | 2024-04-03 12:00 | 2024-04-03 12:00 |  |  | 2024-04-03 12:22 | 2 | Sajid khan | 0 |  | 0 |  | 673 | [12 empty] | 1346 | 0
8 | 689244 | F-Bldg OPD No- 10 Customer Changes | Connector pipe 4"x 6 FT | No. | 1 |  | Management | Approved | 2024-04-03 12:00 | 2024-04-03 12:00 |  |  | 2024-04-03 12:22 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
9 | 689245 | Stilt Floor- Common Toilet | Connector pipe 4"x 6 FT | No. | 2 |  | Management | Approved | 2024-04-03 12:00 | 2024-04-03 12:00 |  |  | 2024-04-03 12:22 | 2 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 200 | 0
10 | 689250 | OPD No.10-Duct inlet line Connection PPRC | GI Clamps - 1-1/4" | No. | 8 |  | Management | Approved | 2024-04-03 12:00 | 2024-04-03 12:00 |  |  | 2024-04-03 12:22 | 8 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 1200 | 0
11 | 689251 | L.G Floor F-Waiting Area Near Entrance-Ele.W | LED LIGHT 6000K ROUND 15WATT (6") | No. | 2 |  | Management | Approved | 2024-04-03 12:00 | 2024-04-03 12:00 |  |  | 2024-04-03 12:22 | 2 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 2000 | 0
12 | 689252 | L.G Floor F-Reception Area Near Lift & Stair-Ele.W | LED LIGHT 6000K ROUND 15WATT (6") | No. | 3 |  | Management | Approved | 2024-04-03 12:00 | 2024-04-03 12:00 |  |  | 2024-04-03 12:22 | 3 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 3000 | 0
13 | 689253 | L.G Floor F-Fire & Regular St.-Wiring& Ele. | LED LIGHT 6000K ROUND 15WATT (6") | No. | 12 |  | Management | Approved | 2024-04-03 12:00 | 2024-04-03 12:00 |  |  | 2024-04-03 12:22 | 12 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 12000 | 0
14 | 697139 | 1st PT Slab,Beam Concrete | Ready Mix Concrete M-35 Grade (Downpour) | Cu.Mtrs | 0.05 |  | Management | Approved | 2024-05-29 12:00 | 2024-05-29 12:00 | :: Released from PO 68795 :- PO detail id 158848 :- ReqD_id 807565 |  | 2024-07-24 12:14 | 0.05 | PARSHURAM KORE | 0 |  | 0 |  | 4400 | [12 empty] | 17600 | 20449.1105
15 | 699218 | Electrical Material for Transformer Room | Screw 35 x 8 | No. | 500 |  | Management | Approved | 2024-06-10 12:38 | 2024-06-10 12:00 |  | Half Threaded SS Screw | 2024-06-10 13:57 | 500 | Sajid khan | 0 |  | 0 |  | 0.7176 | [12 empty] | 358.8 | 0
16 | 699256 | Electrical Material for Transformer Room | Earthing Strip Insulator - No. | No. | 250 |  | Management | Approved | 2024-06-10 18:45 | 2024-06-10 12:00 |  | 50mm Epoxy Earthing Strip Insulator | 2024-06-11 11:42 | 250 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 25000 | 0
17 | 699257 | Miscellaneous Electrical Material | Alum. Lugs 120 Sqmm (ring type | No. | 24 |  | Management | Approved | 2024-06-10 19:43 | 2024-06-10 12:00 |  |  | 2024-06-11 11:42 | 24 | Sajid khan | 0 |  | 0 |  | 16 | [12 empty] | 384 | 0
18 | 699258 | Miscellaneous Electrical Material | Alum. Lugs 16 Sqmm Ring Type | No. | 24 |  | Management | Approved | 2024-06-10 19:44 | 2024-06-10 12:00 |  |  | 2024-06-11 11:42 | 24 | Sajid khan | 0 |  | 0 |  | 6 | [12 empty] | 144 | 0
19 | 699264 | Miscellaneous Electrical Material | Bus bar 100 amp with MCCB | No. | 3 |  | Management | Approved | 2024-06-10 19:46 | 2024-06-10 12:00 |  |  | 2024-06-11 11:42 | 3 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 300 | 0
20 | 699267 | Miscellaneous Electrical Material | Live cable dector tester | No. | 2 |  | Management | Approved | 2024-06-10 19:49 | 2024-06-10 12:00 |  |  | 2024-06-11 11:42 | 2 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 200 | 0
21 | 699268 | Miscellaneous Electrical Material | Meco Clamp Meter DT-2250 | No. | 1 |  | Management | Approved | 2024-06-10 19:50 | 2024-06-10 12:00 |  |  | 2024-06-11 11:42 | 1 | Sajid khan | 0 |  | 0 |  | 2266 | [12 empty] | 2266 | 0
22 | 702440 | E-906-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815903 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
23 | 702441 | E-1001-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815902 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
24 | 702442 | E-1002-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815901 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
25 | 702443 | E-1005-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815900 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
26 | 702444 | E-1006-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815899 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
27 | 702445 | E-1101-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815898 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
28 | 702446 | E-1102-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815897 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
29 | 702447 | E-1105-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815896 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
30 | 702448 | E-1106-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815895 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
31 | 702449 | E-1201-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815894 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
32 | 702450 | E-1205-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815893 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
33 | 702451 | E-1206-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815892 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
34 | 702452 | E-1301-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815891 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
35 | 702453 | E-1302-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815890 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
36 | 702454 | E-1305-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815889 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
37 | 702455 | E-1306-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815888 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
38 | 702456 | E-1401-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815887 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
39 | 702457 | E-1402-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815886 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
40 | 702458 | E-1405-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815885 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
41 | 702459 | E-1406-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815884 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
42 | 702460 | E-1501-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815883 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
43 | 702461 | E-1502-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815882 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
44 | 702462 | E-1505-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815881 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
45 | 702462 | E-1505-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815881 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
46 | 702463 | E-1506-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815880 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
47 | 702463 | E-1506-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815880 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
49 | 702464 | E-1601-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815879 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
48 | 702464 | E-1601-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815879 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
51 | 702465 | E-1602-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815878 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
50 | 702465 | E-1602-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815878 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
52 | 702466 | E-1605-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815877 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
53 | 702466 | E-1605-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815877 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
55 | 702467 | E-1606-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815876 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
54 | 702467 | E-1606-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815876 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
56 | 702468 | E-1701-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815875 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
57 | 702468 | E-1701-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815875 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
59 | 702469 | E-1705-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815874 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
58 | 702469 | E-1705-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815874 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
60 | 702470 | E-1706-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815873 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
61 | 702470 | E-1706-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815873 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
63 | 702471 | E-1801-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815872 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
62 | 702471 | E-1801-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815872 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
64 | 702472 | E-1802-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815871 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
65 | 702472 | E-1802-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815871 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
66 | 702473 | E-1805-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815870 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
67 | 702473 | E-1805-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815870 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
68 | 702474 | E-1806-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815869 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
69 | 702474 | E-1806-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815869 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
71 | 702475 | E-1901-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815868 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
70 | 702475 | E-1901-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815868 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
72 | 702476 | E-1902-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815867 |  | 2024-07-01 12:58 | 0 | GULSHAN GANGWANI | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
73 | 702476 | E-1902-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815867 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
74 | 702477 | E-1905-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815866 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
75 | 702478 | E-1906-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815865 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
76 | 702479 | E-2001-3BHK Door Shutter & Hardware | Cylindrical Lock with Key - Yale (CA5147 US32D) | No. | 3 |  | Management | Approved | 2024-06-18 17:44 | 2024-06-18 12:00 | :: Released from PO 69021 :- PO detail id 159598 :- ReqD_id 815864 |  | 2024-07-01 12:58 | 0 | KantilalJ | 0 |  | 0 |  | 1200 | [12 empty] | 3600 | 1575.3
77 | 702946 | D.G. Set Servicing & Battery | Transport Charges | No. | 1 |  | Management | Approved | 2024-06-19 12:34 | 2024-06-19 12:00 |  |  | 2024-06-20 11:12 | 1 | Sajid khan | 0 |  | 0 |  | 1500 | [12 empty] | 4500 | 0
78 | 703698 | F 1st Floor OPD Electrical Work | 16 Amp socket 1067 | No. | 6 |  | Management | Approved | 2024-07-01 18:25 | 2024-07-01 12:00 |  |  | 2024-07-02 10:58 | 6 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 600 | 0
79 | 705413 | Alu-Form Consumable Material D-Bldg | Nitobond SBR (Latex) | Ltrs | 40 |  | Management | Approved | 2024-07-03 21:22 | 2024-07-03 12:00 |  |  | 2024-07-04 13:09 | 40 | Sajid khan | 0 |  | 0 |  | 265 | [12 empty] | 148400 | 62776
80 | 705499 | East Side Compound Wall AAC Blockwork 8" | AAC Block 650x240x200 | No. | 488 |  | Management | Approved | 2024-07-04 12:59 | 2024-07-04 12:00 |  |  | 2024-07-04 13:09 | 488 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 48800 | 0
81 | 706281 | D-Flat.No.1602 Brickbat Waterproofing | Cement 43 Grade | Bags | 5.68 |  | Management | Approved | 2024-07-13 11:11 | 2024-07-13 12:00 |  |  | 2024-07-13 13:02 | 5.68 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 1562 | 0
82 | 706282 | D-Flat.No.1605 Brickbat Waterproofing | Cement 43 Grade | Bags | 5.68 |  | Management | Approved | 2024-07-13 11:11 | 2024-07-13 12:00 |  |  | 2024-07-13 13:02 | 5.68 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 1562 | 0
83 | 706283 | D-Flat.No.1606 Brickbat Waterproofing | Cement 43 Grade | Bags | 5.68 |  | Management | Approved | 2024-07-13 11:11 | 2024-07-13 12:00 |  |  | 2024-07-13 13:02 | 5.68 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 1562 | 0
84 | 706284 | D-Flat.No.1701 Brickbat Waterproofing | Cement 43 Grade | Bags | 5.68 |  | Management | Approved | 2024-07-13 11:11 | 2024-07-13 12:00 |  |  | 2024-07-13 13:02 | 5.68 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 1562 | 0
85 | 706285 | D-Flat.No.1702 Brickbat Waterproofing | Cement 43 Grade | Bags | 5.68 |  | Management | Approved | 2024-07-13 11:11 | 2024-07-13 12:00 |  |  | 2024-07-13 13:02 | 4.3282 | AKSHADA MAHAJAN | 0 |  | 0 |  | 275 | [12 empty] | 1562 | 459.612
86 | 706680 | Labour Camp Dustbin & Water tank | Dustbin | No. | 8 |  | Management | Approved | 2024-07-15 11:51 | 2024-07-15 12:00 | Green Plastic Pedal Dustbin 65 Ltr - 4 Nos, Red Plastic Pedal Dustbin 65 Ltr - 4 Nos Required | Green Plastic Pedal Dustbin 65 Ltr - 4 Nos, Red Plastic Pedal Dustbin 65 Ltr - 4 Nos | 2024-07-16 17:02 | 8 | akshada mahajan | 0 |  | 0 |  | 2500 | [12 empty] | 20000 | 0
87 | 706695 | Labour Camp Dustbin & Water tank | Hand Gloves (Rubber) | Pair | 6 |  | Management | Approved | 2024-07-15 12:20 | 2024-07-15 12:00 |  |  | 2024-07-16 17:02 | 6 | akshada mahajan | 0 |  | 0 |  | 80 | [12 empty] | 960 | 0
88 | 711172 | D-Bldg LG Floor ST-01 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
89 | 711173 | D-Bldg Ground Floor- ST-01 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
90 | 711174 | D-Bldg P1 Floor- ST-01 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
91 | 711175 | D-Bldg P2 Floor - ST-01 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
92 | 711176 | D-Bldg P5 Floor - ST-01 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
93 | 711177 | D-Bldg P3 Floor ST-01 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
94 | 711178 | D-Bldg LG Floor ST-02 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
95 | 711179 | D-Bldg Ground Floor- ST-02 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
96 | 711180 | D-Bldg P1 Floor - ST-02 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
97 | 711181 | D-Bldg P2 Floor - ST-02 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
98 | 711182 | D-Bldg P5 Floor- ST-02 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
99 | 711183 | D-Bldg P3 Floor ST-02 Flooring Work | Crush Sand | Cu.Ft | 15.45 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.45 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 509.85 | 0
100 | 711184 | P2 Floor Fire Staircase-Sand Face Plaster | Crush Sand | Cu.Ft | 33 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 33 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 3082.0779 | 0
101 | 711185 | P3 Floor Fire Staircase-Sand Face Plaster | Crush Sand | Cu.Ft | 99.8206 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 99.8206 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 3294.0798 | 0
102 | 711186 | P5 Floor Fire Staircase-Sand Face Plaster | Crush Sand | Cu.Ft | 73.287 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 73.287 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2418.471 | 0
103 | 711187 | LG Floor Regular Staircase.Sand Face Plaster | Crush Sand | Cu.Ft | 91.2679 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 91.2679 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 3011.8407 | 0
104 | 711188 | Ground Regular Fire Staircase.Sand Face Plaster | Crush Sand | Cu.Ft | 54.723 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 54.723 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1805.859 | 0
105 | 711189 | P1 Floor Regular Staircase.Sand Face Plaster | Crush Sand | Cu.Ft | 57.5246 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 57.5246 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1898.3118 | 0
106 | 711190 | P2 Floor Regular Staircase.Sand Face Plaster | Crush Sand | Cu.Ft | 57.5246 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 57.5246 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1898.3118 | 0
107 | 711191 | P3 Floor Regular Staircase.Sand Face Plaster | Crush Sand | Cu.Ft | 63.9472 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 63.9472 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2110.2576 | 0
108 | 711192 | P5 Floor Regular Staircase.Sand Face Plaster | Crush Sand | Cu.Ft | 57.5246 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 57.5246 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1898.3118 | 0
109 | 711193 | D-L.G. Floor-Flooring & Skirting Work(Including Wastage & Ma | Crush Sand | Cu.Ft | 30.64 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.64 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1011.12 | 0
110 | 711194 | D-Ground Floor-Flooring & Skirting Work(Including Wastage & | Crush Sand | Cu.Ft | 75.06 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 75.06 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2476.98 | 0
111 | 711195 | D-P1-Floor-Flooring & Skirting Work(Including Wastage & Main | Crush Sand | Cu.Ft | 30.24 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.24 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 997.92 | 0
112 | 711196 | D-P2 Floor-Flooring & Skirting Work(Including Wastage & Main | Crush Sand | Cu.Ft | 30.24 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.24 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 997.92 | 0
113 | 711197 | D-P3 Floor-Flooring & Skirting Work(Including Wastage & Main | Crush Sand | Cu.Ft | 30.24 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.24 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 997.92 | 0
114 | 711198 | D-P5 Floor-Flooring & Skirting Work(Including Wastage & Main | Crush Sand | Cu.Ft | 30.24 |  | Management | Approved | 2024-08-02 12:44 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.24 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 997.92 | 0
115 | 711199 | E-702-2BHK(Near Refuse Area) Flooring,Dado- Bedding (Near Re | Crush Sand | Cu.Ft | 52.46 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.46 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1731.18 | 0
116 | 711200 | E-705-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
117 | 711201 | E-706-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
118 | 711202 | E-801-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
119 | 711203 | E-802-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
120 | 711204 | E-803-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
121 | 711205 | E-804-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
122 | 711206 | E-805-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
123 | 711207 | E-806-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
124 | 711208 | E-807-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
125 | 711209 | E-808-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
126 | 711210 | E-901-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
127 | 711211 | E-902-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
128 | 711212 | E-903-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
129 | 711213 | E-904-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
130 | 711214 | E-905-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
131 | 711215 | E-906-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 37 |  | Management | Approved | 2024-08-02 12:46 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
132 | 711218 | 2nd Slab cement Slurry | Cement 43 Grade | Bags | 12 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 12 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 3926.67 | 0
133 | 711219 | 1st PT Slab-material for grout filling work | Cement 43 Grade | Bags | 11 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 11 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 3025 | 0
134 | 711220 | 2nd PT Slab-material for grout filling work | Cement 43 Grade | Bags | 15 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 4125 | 0
135 | 711221 | 3rd PT Slab-Material for grout filling work | Cement 43 Grade | Bags | 15 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 4125 | 0
136 | 711222 | Cover Block for RCC 1st slab | Cement 43 Grade | Bags | 9 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 9 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 2475 | 0
137 | 711223 | 4th Slab PT-Material for grout filling work | Cement 43 Grade | Bags | 15 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 4125 | 0
138 | 711224 | F-Bldg -Stilt Floor 1st Slab RCC Band Material | Cement 43 Grade | Bags | 9.646 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 9.646 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 2652.65 | 0
139 | 711225 | F-Bldg LG Floor RCC Band Material | Cement 43 Grade | Bags | 28.7714 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 28.7714 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 9287.85 | 1775.918
140 | 711226 | F-Bldg 3rd Floor Northside External Plaster (M) | Cement 43 Grade | Bags | 12.3671 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 12.3671 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 7800.9525 | 5679.984
141 | 711227 | F-Bldg LG Floor Westside External Plaster (M) | Cement 43 Grade | Bags | 36.7339 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 36.7339 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 10101.8225 | 0
142 | 711228 | F-Bldg Stilt Floor Westside External Plaster (M) | Cement 43 Grade | Bags | 30.7498 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.7498 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 8456.195 | 0
143 | 711229 | F-Bldg 1st Floor Westside External Plaster (M) | Cement 43 Grade | Bags | 30.7498 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.7498 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 8456.195 | 0
144 | 711230 | F-Bldg 2nd Floor Westside External Plaster (M) | Cement 43 Grade | Bags | 30.7498 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.7498 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 8456.195 | 0
145 | 711231 | F-Bldg 3rd Floor Westside External Plaster (M) | Cement 43 Grade | Bags | 30.7498 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.7498 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 8456.195 | 0
146 | 711232 | F-Bldg 1st Floor Southside External Plaster (M) | Cement 43 Grade | Bags | 26.8574 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 26.8574 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 7385.785 | 0
147 | 711233 | F-Bldg 3rd Floor Southside External Plaster (M) | Cement 43 Grade | Bags | 27.3317 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 27.3317 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 7516.2175 | 0
148 | 711234 | F-Bldg LG Floor Eastside External Plaster (M) | Cement 43 Grade | Bags | 32.9736 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 32.9736 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 9067.74 | 0
149 | 711235 | F-Bldg Stilt Floor Eastside External Plaster (M) | Cement 43 Grade | Bags | 34.4354 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 34.4354 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 9469.735 | 0
150 | 711236 | F-Bldg 1st Floor Eastside External Plaster (M) | Cement 43 Grade | Bags | 20.5088 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 20.5088 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 5639.92 | 0
151 | 711237 | F-Bldg 2nd Floor Eastside External Plaster (M) | Cement 43 Grade | Bags | 18.3665 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 18.3665 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 5050.7875 | 0
152 | 711238 | F-Bldg 3rd Floor Eastside External Plaster (M) | Cement 43 Grade | Bags | 18.3665 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 18.3665 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 5050.7875 | 0
153 | 711239 | LG Floor Duct External Plaster (M) | Cement 43 Grade | Bags | 15.0662 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 15.0662 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 4143.205 | 0
154 | 711240 | Stilt Floor Duct External Plaster (M) | Cement 43 Grade | Bags | 49.3387 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 49.3387 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 13568.1425 | 0
155 | 711241 | 1st Floor Duct External Plaster (M) | Cement 43 Grade | Bags | 46.1605 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 46.1605 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 12694.1375 | 0
156 | 711242 | F-Bldg LG. Floor Lift Wall BBM & Sand Face Plaster Work | Cement 43 Grade | Bags | 4.38 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 4.38 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 1204.5 | 0
157 | 711243 | F-Bldg Stilt Floor Lift Wall BBM & Sand Face Plaster Work | Cement 43 Grade | Bags | 3.03 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 3.03 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 833.25 | 0
158 | 711244 | F-Bldg 1st Floor Lift Wall BBM & Sand Face Plaster Work | Cement 43 Grade | Bags | 3.03 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 3.03 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 833.25 | 0
159 | 711245 | F-Bldg 2nd Floor Lift Wall BBM & Sand Face Plaster Work | Cement 43 Grade | Bags | 3.03 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 3.03 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 833.25 | 0
160 | 711246 | F-Bldg 3rd Floor Lift Wall BBM & Sand Face Plaster Work | Cement 43 Grade | Bags | 3.03 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 3.03 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 833.25 | 0
161 | 711247 | F-Bldg 2nd Floor Chemical Grouting Work | Cement 43 Grade | Bags | 0.27 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 0.27 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 74.25 | 0
162 | 711248 | LG Fl Common Toilet Flooring & Dado Bedding Material | Cement 43 Grade | Bags | 0.75 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 0.75 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 206.25 | 0
163 | 711249 | 1st Fl Int+Common Toilet Flooring & Dado Bedding Material | Cement 43 Grade | Bags | 5.66 |  | Management | Approved | 2024-08-02 14:52 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 5.66 | Sajid khan | 0 |  | 0 |  | 275 | [12 empty] | 1556.5 | 0
164 | 711250 | Alu Form Consumable Material E-Bldg | Potato Greece | Kgs | 180 |  | Management | Approved | 2024-08-02 15:19 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 180 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 972000 | 774498.9
165 | 711398 | Stilt Fl Lobby Flooring- Bedding Material | Crush Sand | Cu.Ft | 59.95 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 59.95 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1978.35 | 0
166 | 711399 | E-906-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 30.04 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 30.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
167 | 711400 | E-907-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
168 | 711401 | E-908-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
169 | 711402 | E-1001-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
170 | 711403 | E-1002-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
171 | 711404 | E-1003-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
172 | 711405 | E-1004-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
173 | 711406 | E-1005-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
174 | 711407 | E-1006-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
175 | 711408 | E-1007-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
176 | 711409 | E-1008-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
177 | 711410 | E-1101-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
178 | 711411 | E-1102-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
179 | 711412 | E-1103-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:35 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
180 | 711413 | E-1303-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:37 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
181 | 711414 | E-1304-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:37 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
182 | 711415 | E-1305-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:37 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
183 | 711416 | E-1306-3BHK Flooring,Dado-Bedding | Crush Sand | Cu.Ft | 67.04 |  | Management | Approved | 2024-08-02 18:37 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 67.04 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 2212.32 | 0
184 | 711417 | E-1307-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:37 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
185 | 711418 | E-1308-2BHK Flooring,Dado- Bedding | Crush Sand | Cu.Ft | 52.37 |  | Management | Approved | 2024-08-02 18:37 | 2024-08-02 12:00 |  |  | 2024-08-05 12:00 | 52.37 | Sajid khan | 0 |  | 0 |  | 33 | [12 empty] | 1728.21 | 0
186 | 711568 | D-302-3BHK D-302 Customer changes | Wash Basin (Chime-S2040139-Cera Sn. white) | No. | 1 |  | Management | Approved | 2024-08-03 14:47 | 2024-08-03 12:00 |  |  | 2024-08-05 12:00 | 1 | Sajid khan | 0 |  | 0 |  | 729 | [12 empty] | 729 | 0
187 | 711569 | D-Bond-it Balance Qty.-Staircase-Fire+Regular | Bondit 151 | Kgs | 18.5 |  | Management | Approved | 2024-08-03 15:03 | 2024-08-03 12:00 |  |  | 2024-08-05 12:00 | 18.5 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 2775 | 0
188 | 711570 | E-Bond-it Balance Qty.-Flats | Bondit 151 | Kgs | 66.94 |  | Management | Approved | 2024-08-03 15:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:00 | 66.94 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 55041 | 47790
189 | 711571 | E-Bond-it Balance Qty.-Staircase-Fire+Regular | Bondit 151 | Kgs | 18.25 |  | Management | Approved | 2024-08-03 15:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:00 | 18.25 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 2737.5 | 0
190 | 711687 | E-Drainage & Rainwater Line Vertical | GI C- Bracket 6" x 8" | No. | 216 |  | Management | Approved | 2024-08-03 23:10 | 2024-08-03 12:00 |  |  | 2024-08-05 12:00 | 216 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 43200 | 17841.6
191 | 711688 | E Bldg.-Domestic Water Line | ASTM Bushing 2" x 1 1/2" | No. | 48 |  | Management | Approved | 2024-08-05 09:53 | 2024-08-05 12:00 |  |  | 2024-08-05 12:00 | 48 | Sajid khan | 0 |  | 0 |  | 23.55 | [12 empty] | 1130.4 | 0
192 | 711689 | E-Flushing Water Line | ASTM Bushing 2" x 1 1/2" | No. | 24 |  | Management | Approved | 2024-08-05 09:53 | 2024-08-05 12:00 |  |  | 2024-08-05 12:00 | 24 | Sajid khan | 0 |  | 0 |  | 23.55 | [12 empty] | 1130.4 | 335.904