## Requisition_Tracking-Summary638
Select Supplier
Project : GANGA ARCADIA - A BUILDING
From Date : 01/01/2024 To date: 07/09/2024
Page 1 of 1
Total Records: 11 Records 1 to 11
Srno | ReqSr_no | Task | Material_Name | Tec.Unit | Qty | Supplier | Priority | Req_status | Requisition_Date | Requirement_Date | Remark | Specifications | Approval_Date | Approved_Qty | Approved_By | Rate | Tax_Scheme_Name | BrandName | StockQty | Est_Rate | Discount | Credit | Conversion_Factor | Transport_Rate | Pkg_Forward | Loading | Unloading | Insurance | Installation | OtherCharges1 | OtherCharges2 | HSN_Code | Est_Cost | Consumed_Amt
1 | 688897 | A-1st Slab Electrical Conduit Work | Fan Box | No. | 2 |  | Management | Approved | 2024-04-01 12:00 | 2024-04-01 12:00 |  |  | 2024-04-01 11:25 | 2 | Sajid khan | 0 |  | 0 |  | 74.42 | [12 empty] | 148.84 | 0
2 | 693874 | A-2nd Slab Electrical Conduit Work | Fan Box | No. | 30 |  | Management | Approved | 2024-05-03 12:00 | 2024-05-03 12:00 |  |  | 2024-05-03 10:39 | 30 | Sajid khan | 0 |  | 0 |  | 74.42 | [12 empty] | 2232.6 | 0
3 | 695093 | A-1st Slab RCC-Slab, Beam,Staircase -Concrete M35 | Ready Mix Concrete M-35 Grade (Pumpable) | Cu.Mtrs | 1.6455 |  | Management | Approved | 2024-05-07 12:00 | 2024-05-07 12:00 | :: Released from PO 68605 :- PO detail id 158417 :- ReqD_id 803046 |  | 2024-07-25 12:35 | 1.6455 | PARSHURAM KORE | 0 |  | 0 |  | 100 | [12 empty] | 24012 | 1252904.7534
4 | 695778 | A-SBR for Arcadia | Nitobond SBR (Latex) | Ltrs | 40 |  | Management | Approved | 2024-05-18 12:00 | 2024-05-18 12:00 |  |  | 2024-05-18 12:48 | 40 | Sajid khan | 0 |  | 0 |  | 265 | [12 empty] | 15900 | 0
5 | 695804 | A-Bldg PCC Work-M15 | Sand-Metal Mix M15 (Pumpable) | Cu.Mtrs | 1 |  | Management | Approved | 2024-05-18 12:00 | 2024-05-18 12:00 | :: Released from PO 68687 :- PO detail id 158620 :- ReqD_id 804931 |  | 2024-07-18 14:54 | 1 | PARSHURAM KORE | 0 |  | 0 |  | 2125 | [12 empty] | 191250 | 313649.8461
6 | 697094 | A-Bldg PCC Work-M15 | Ready Mix Concrete M-15 Grade( D/P) - | Cu.Mtrs | 6.18 |  | Management | Approved | 2024-05-25 12:00 | 2024-05-25 12:00 | :: Released from PO 68763 :- PO detail id 158760 :- ReqD_id 806609 |  | 2024-07-23 14:15 | 6.18 | Akshada Mahajan | 0 |  | 0 |  | 3500 | [12 empty] | 252630 | 279854.8517
7 | 702018 | A-Cement Slurry for RMC | Cement 43 Grade | Bags | 50 |  | Management | Approved | 2024-06-16 11:40 | 2024-06-16 12:00 |  |  | 2024-06-20 11:22 | 50 | Sajid khan | 0 |  | 0 |  | 375 | [12 empty] | 18750 | 0
8 | 707382 | Material require for dewatering. | Hose Pipe 2" | Mtrs | 30 |  | Management | Approved | 2024-07-29 19:12 | 2024-07-29 12:00 |  |  | 2024-07-30 10:51 | 30 | Sajid khan | 0 |  | 0 |  | 500 | [12 empty] | 15000 | 0
9 | 707383 | Material require for dewatering. | Hose Pipe 4" Mtr | Mtrs | 60 |  | Management | Approved | 2024-07-29 19:12 | 2024-07-29 12:00 |  |  | 2024-07-30 10:51 | 60 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 6000 | 0
10 | 712099 | UGWT-Raft Concrete M25 | Cement Loose 53 Grade | Metric Tonnes | 2.392 |  | Management | Approved | 2024-08-07 16:41 | 2024-08-07 12:00 |  |  | 2024-08-07 16:25 | 0.849 | AKSHADA MAHAJAN |  |  | 0 |  | 3880 | [12 empty] | 9280.96 | 11418.2005
11 | 712146 | Material require for dewatering. | Plumbing Materials | No. | 1 |  | Management | Approved | 2024-08-07 16:55 | 2024-08-07 12:00 |  |  | 2024-08-07 17:57 | 1 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 200 | 531