## Requisition_Tracking-Summary638
Select Supplier
Project : GANGA DHAM TOWERS
From Date : 01/01/2024 To date: 28/09/2024
Page 1 of 1
Total Records: 289 Records 1 to 289
Srno | ReqSr_no | Task | Material_Name | Tec.Unit | Qty | Supplier | Priority | Req_status | Requisition_Date | Requirement_Date | Remark | Specifications | Approval_Date | Approved_Qty | Approved_By | Rate | Tax_Scheme_Name | BrandName | StockQty | Est_Rate | Discount | Credit | Conversion_Factor | Transport_Rate | Pkg_Forward | Loading | Unloading | Insurance | Installation | OtherCharges1 | OtherCharges2 | HSN_Code | Est_Cost | Consumed_Amt
1 | 676854 | Club House Landscaping Plantation Work | Lagerstormia Reginae - No. | No. | 6 |  | Management | Approved | 2024-01-03 12:00 | 2024-01-03 12:00 |  |  | 2024-01-03 18:46 | 6 | Sajid khan | 0 |  | 0 |  | 900 | [12 empty] | 5400 | 0
2 | 676855 | Plantation work from OWC to Club House | Asparagus | No. | 115 |  | Management | Approved | 2024-01-03 12:00 | 2024-01-03 12:00 |  |  | 2024-01-03 18:46 | 115 | Sajid khan | 0 |  | 0 |  | 200 | [12 empty] | 23000 | 0
3 | 677266 | Ho Admin Expensess ( M) | Transfer challan | No. | 10 |  | Management | Approved | 2024-01-10 12:00 | 2024-01-10 12:00 |  |  | 2024-02-21 16:17 | 10 | KANTILAL.JAGTAP | 0 |  | 0 |  | 50 | [12 empty] | 3350 | 5770.5
4 | 678513 | 125 Kva DG B Check Servicing | Transport Charges | No. | 1 |  | Management | Approved | 2024-01-17 12:00 | 2024-01-17 12:00 |  |  | 2024-01-18 16:11 | 1 | Sajid khan | 0 |  | 0 |  | 1500 | [12 empty] | 10500 | 3363
5 | 682703 | C Misc Material | Kiltan ( Hessian Cloth ) | Mtrs | 103.34 |  | Management | Approved | 2024-02-03 12:00 | 2024-02-03 12:00 | :: Released from PO 68971 :- PO detail id 159461 :- ReqD_id 793156 :: Released from PO 67917 :- PO detail id 156519 :- ReqD_id 785368 |  | 2024-06-18 12:50 | 103.34 | Akshada Mahajan | 0 |  | 0 |  | 17.5 | [12 empty] | 105000 | 145025.832
6 | 683363 | Steel MTBT E-Bldg 18th to 22nd Slab | Steel Bars 32mm | Kgs | 2377 |  | Management | Approved | 2024-02-07 12:00 | 2024-02-07 12:00 | For Altus |  | 2024-02-07 18:54 | 917 | Vinay Mittal | 0 |  | 0 |  | 100 | [12 empty] | 337700 | 152488.28
7 | 683391 | A 23rd Floor Lobby & Lift Cladding Tile Adhesive | Tenax Creama Solid 1.5kg Set | set | 0.68 |  | Management | Approved | 2024-02-08 12:00 | 2024-02-08 12:00 | :: Released from PO 67946 :- PO detail id 156615 :- ReqD_id 786506 |  | 2024-03-23 11:14 | 0.68 | vinay mittal | 0 |  | 0 |  | 1000 | [12 empty] | 6343.5 | 4778.2955
8 | 683522 | B 2702 NOC | Tenax Transparent Solid 1.5Kg | set | 0.74 |  | Management | Approved | 2024-02-10 12:00 | 2024-02-10 12:00 | :: Released from PO 67946 :- PO detail id 156614 :- ReqD_id 786837 |  | 2024-05-16 17:57 | 0.74 | Akshada Mahajan | 0 |  | 0 |  | 1000 | [12 empty] | 1000 | 322.14
9 | 683568 | B 16th Floor 1601 CP & Sanitary | Drain Pipe (JWA-CHR-DRNPIPE80) | No. | 1 |  | Management | Approved | 2024-02-13 12:00 | 2024-02-13 12:00 |  |  | 2024-02-13 18:02 | 1 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
10 | 683798 | Temporary Electrical Work required Material | Grinder | No. | 1 |  | Management | Approved | 2024-02-16 12:00 | 2024-02-16 12:00 |  |  | 2024-02-16 17:08 | 1 | Sajid khan | 0 |  | 0 |  | 500 | [12 empty] | 500 | 0
11 | 685346 | A Main Line Electrical Work (M) (upto 26th floor) | PVC Copper Wire 16Sqmm Black | Mtrs | 15.6 |  | Management | Approved | 2024-02-24 12:00 | 2024-02-24 12:00 | :: Released from PO 68080 :- PO detail id 157058 :- ReqD_id 789224 |  | 2024-04-08 18:58 | 1 | Vinay Mittal | 0 |  | 0 |  | 300 | [12 empty] | 1082160 | 598430.0152
12 | 686038 | Steel MTBT E-20th Sl.19th to 20th Column,SW Steel | Steel Bars 10mm | Kgs | 150 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 | :: Released from PO 68130 :- PO detail id 157200 :- ReqD_id 790532 |  | 2024-04-01 16:31 | 150 | vinay mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 82936.35 | 89041.5622
13 | 686103 | GRN For SRA Morwadi Steel | Steel Bars 12mm | Kgs | 14000 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 |  | SRA Morwadi | 2024-03-02 18:28 | 600 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 1766122.2 | 1857040.1
14 | 686103 | GRN For SRA Morwadi Steel | Steel Bars 12mm | Kgs | 460 |  | Management | Approved | 2024-03-02 12:00 | 2024-03-02 12:00 | :: Released from PO 68131 :- PO detail id 157205 :- ReqD_id 790615 | SRA Morwadi | 2024-04-01 16:31 | 460 | vinay mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 1766122.2 | 1857040.1
15 | 686339 | B-Bldg Supporting Material for Electrical Work | G.I. screw 6mmx 35mm full threaded | Box | 10 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-07 12:41 | 10 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 1000 | 0
16 | 686340 | B-Bldg Supporting Material for Electrical Work | G.I. screw 6mmx 75mm full threaded | Box | 10 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-07 12:41 | 10 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 1000 | 0
17 | 686341 | B-Bldg Supporting Material for Electrical Work | G.I. Screw 6mm x 50mm Full Threaded | Box | 10 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-07 12:41 | 10 | SANKET PATIL | 0 |  | 0 |  | 50 | [12 empty] | 500 | 0
18 | 686356 | A Downtake Lines Extra Qty As Per Site Condition | Fusion Machin ( For PPRC Pipe Weilding Purpose ) | No. | 2 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-11 14:43 | 2 | Sajid khan | 0 |  | 0 |  | 350 | [12 empty] | 700 | 0
19 | 686357 | B Downtake line Quantity Diff.as per Site Condition - 1 | Fusion Machin ( For PPRC Pipe Weilding Purpose ) | No. | 2 |  | Management | Approved | 2024-03-07 12:00 | 2024-03-07 12:00 |  |  | 2024-03-11 14:43 | 2 | Sajid khan | 0 |  | 0 |  | 350 | [12 empty] | 700 | 0
20 | 686551 | Steel MTBT D-31st Slab RCC 30th to 31st Column Stee | Steel Bars 8mm | Kgs | 490 |  | Management | Approved | 2024-03-14 12:00 | 2024-03-14 12:00 | :: Released from PO 68202 :- PO detail id 157382 :- ReqD_id 791497 |  | 2024-04-10 14:39 | 490 | vinay mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 336677.85 | 375742.6267
21 | 686591 | Steel MTBT F-Ent Gt Footing,Colm,Beam,Slab RCC Work | Steel Bars 8mm | Kgs | 1026.796 |  | Management | Approved | 2024-03-14 12:00 | 2024-03-14 12:00 | For Altus |  | 2024-03-14 18:02 | 1.678 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 52212.5766 | 62825.0742
22 | 686657 | Temporary Electrical Work required Material | GI Screw 35 x 8 | No. | 100 |  | Management | Approved | 2024-03-16 12:00 | 2024-03-16 12:00 |  |  | 2024-03-16 11:09 | 100 | Sajid khan | 0 |  | 0 |  | 0.5 | [12 empty] | 50 | 0
23 | 686658 | B Main Line Conduit (Vertical + Horizontal) 27 to 31st fl | GI Screw 35 x 8 | No. | 100 |  | Management | Approved | 2024-03-16 12:00 | 2024-03-16 12:00 |  |  | 2024-03-16 11:09 | 100 | Sajid khan | 0 |  | 0 |  | 0.5 | [12 empty] | 50 | 0
24 | 687912 | B 902 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
25 | 687913 | B 1302 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
26 | 687914 | B 701 AC Machine 5 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
27 | 687915 | B 702 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
28 | 687916 | B 1001 AC Machine 5 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
29 | 687917 | B 1102 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
30 | 687918 | B 1202 AC Machine 5 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
31 | 687919 | B 1502 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
32 | 687920 | B 1602 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
33 | 687921 | B 1902 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
34 | 687922 | 2302 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
35 | 687923 | B 1601 AC Machine 5 BHK | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 2 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 50000 | 0
36 | 687932 | A 1204 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
37 | 687933 | A 1403 AC Machine 3 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
38 | 687934 | A 1602 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
39 | 687935 | A 1603 AC Machine 3 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
40 | 687936 | A 1502 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 4 | Sajid khan | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 0
41 | 687937 | A 1604 AC Machine 4 Bhk | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) | No. | 4 |  | Management | Approved | 2024-03-18 12:00 | 2024-03-18 12:00 |  |  | 2024-03-19 11:28 | 2 | SANKET PATIL | 0 |  | 0 |  | 25000 | [12 empty] | 100000 | 71137.28
42 | 687987 | Material required for Sales office use | Tissue paper | Pack | 6 |  | Management | Approved | 2024-03-19 12:00 | 2024-03-19 12:00 |  |  | 2024-03-19 11:15 | 6 | SANKET PATIL | 0 |  | 0 |  | 500 | [12 empty] | 29500 | 60180
43 | 687989 | Material required for Sales office use | M-Fold (RC)-40 CC- 225x215mm | No. | 16 |  | Management | Approved | 2024-03-19 12:00 | 2024-03-19 12:00 |  |  | 2024-03-19 15:24 | 10 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 4100 | 24780
44 | 688001 | D Terrace Blockwork 5" | Jointing Mortar | Kgs | 200 |  | Management | Approved | 2024-03-19 12:00 | 2024-03-19 12:00 |  |  | 2024-03-20 12:12 | 200 | Sajid khan | 0 |  | 0 |  | 13.25 | [12 empty] | 4519.9115 | 810.3122
45 | 688043 | Steel MTBT Altus-Steel-GRN Purpose | Steel Bars 8mm | Kgs | 50 |  | Management | Approved | 2024-03-20 12:00 | 2024-03-20 12:00 | :: Released from PO 68243 :- PO detail id 157463 :- ReqD_id 793171 |  | 2024-04-10 14:39 | 10 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 464187.7845 | 560511.1038
46 | 688043 | Steel MTBT Altus-Steel-GRN Purpose | Steel Bars 8mm | Kgs | 50 |  | Management | Approved | 2024-03-20 12:00 | 2024-03-20 12:00 | :: Released from PO 68243 :- PO detail id 157463 :- ReqD_id 793171 |  | 2024-04-10 14:39 | 10 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 464187.7845 | 560511.1038
47 | 690049 | Steel MTBT Altus-Steel-GRN Purpose | Steel Bars 10mm | Kgs | 10 |  | Management | Approved | 2024-04-06 12:00 | 2024-04-06 12:00 | :: Released from PO 68387 :- PO detail id 157804 :- ReqD_id 795681For Altus (GRN Purpose) |  | 2024-04-10 14:40 | 9.762 | AKSHADA MAHAJAN | 0 |  | 0 |  | 50.85 | [12 empty] | 508.5 | 15.1991
48 | 690309 | Material required for Sales office use | Taski R3 5ltr | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 8 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 5100 | 25718.3
49 | 690310 | Material required for Sales office use | Taski R5 5ltr | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 8 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 4700 | 14650.88
50 | 690311 | Material required for Sales office use | Taski R6 5ltr | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 8 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 5200 | 16855.3701
51 | 690312 | Material required for Sales office use | WET MOP REFILL | No. | 15 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 5 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 15800 | 20714.9
52 | 690313 | Material required for Sales office use | Microfiber Duster | No. | 25 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 7900 | 1360.8
53 | 690319 | Material required for Sales office use | Tissue paper | Pack | 15 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | NITIN.PARDESHI | 0 |  | 0 |  | 500 | [12 empty] | 29500 | 60180
54 | 690421 | Material required for Sales office use | Hand wash Refill | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3000 | 0
55 | 690578 | Safety Material | Rubber Hand Gloves | Pair | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | Sajid khan | 0 |  | 0 |  | 15 | [12 empty] | 1875 | 3148
56 | 690582 | Maintenance Work Filtration Plant & Water body | Cleaning Acid | Ltrs | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 10 | Sajid khan | 0 |  | 0 |  | 67 | [12 empty] | 4840.75 | 1759.09
57 | 690700 | Material required for Sales office use | Spray Bottle | No. | 10 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 5 | NITIN.PARDESHI | 0 |  | 0 |  | 180 | [12 empty] | 11340 | 2124
58 | 690701 | Material required for Sales office use | Table Top Tissue Paper | No. | 25 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 13:39 | 25 | Sajid khan | 0 |  | 0 |  | 510 | [12 empty] | 25500 | 0
59 | 690702 | Mandir peripheral plum concrete & PCC work | Ready Mix Concrete M-15 Grade( PUMPABLE) | Cu.Mtrs | 20.7 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 | :: Released from PO 68408 :- PO detail id 157893 :- ReqD_id 796388 |  | 2024-05-21 14:32 | 20.7 | Akshada Mahajan | 0 |  | 0 |  | 20 | [12 empty] | 480 | 0
60 | 690710 | Material required for Sales office use | Taski R2 5ltr | No. | 15 |  | Management | Approved | 2024-04-08 12:00 | 2024-04-08 12:00 |  |  | 2024-04-08 17:59 | 12 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 5900 | 27174.5
61 | 690743 | Pour 5 105.00 to 108.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 2204 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:18 | 1014 | AKSHADA MAHAJAN | 0 |  | 0 |  | 100 | [12 empty] | 610200 | 310195.3298
62 | 690745 | C Bldg 6th Slab (2nd Floor) Steel | Steel Bars 10mm | Kgs | 4484.796 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:18 | 2786 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 228051.8766 | 105911.9463
63 | 690750 | Pour 5 108.00 to 111.00 lvl Drop panel Steel | Steel Bars 12mm | Kgs | 7775 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:18 | 542.99 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 334325 | 448526.2013
64 | 690761 | 7th to 8th Column & SW Steel | Steel Bars 20mm | Kgs | 12986.766 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:17 | 1892.135 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 660377.0511 | 667196.869
65 | 690762 | 5th to 6th Column & SW Steel | Steel Bar 25mm | Kgs | 11542.885 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 |  |  | 2024-04-10 18:17 | 1600.4445 | AKSHADA MAHAJAN | 0 |  | 0 |  | 1000 | [12 empty] | 17748885 | 1002416.7999
66 | 690776 | Steel MTBT E-19th Sl.18th to 19th Column,SW Steel | Steel Bars 12mm | Kgs | 3625 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | for Arcadia |  | 2024-04-10 18:17 | 1148.027 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 184331.25 | 154427.6248
67 | 690779 | Steel MTBT A-Ret.Wall Steel Work (FootingRaft+Pardi | Steel Bars 10mm | Kgs | 20 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | :: Released from PO 68425 :- PO detail id 157944 :- ReqD_id 796602For Arcadia |  | 2024-06-06 14:15 | 20 | Akshada Mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 508500 | 622206.094
68 | 690780 | Steel MTBT A-Col.-Footing To Plinth- Steel Work New | Steel Bars 8mm | Kgs | 1394.429 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | For Arcadia |  | 2024-04-10 18:17 | 0.429 | Vinay Mittal | 0 |  | 0 |  | 50.85 | [12 empty] | 70906.7146 | 89092.2128
69 | 690788 | GRN For SRA Morwadi Steel | Steel Bars 20mm | Kgs | 90 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | :: Released from PO 68424 :- PO detail id 157941 :- ReqD_id 796652 :: Released from PO 68407 :- PO detail id 157891 :- ReqD_id 796593 | GRN For SRA Morwadi Steel | 2024-07-09 17:14 | 90 | akshada mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 5737130.91 | 5425388.452
70 | 690789 | GRN For SRA Morwadi Steel | Steel Bar 25mm | Kgs | 530 |  | Management | Approved | 2024-04-10 12:00 | 2024-04-10 12:00 | :: Released from PO 68424 :- PO detail id 157942 :- ReqD_id 796654 :: Released from PO 68407 :- PO detail id 157892 :- ReqD_id 796592 | GRN For SRA Morwadi Steel | 2024-07-09 17:16 | 530 | akshada mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 1057680 | 1243333.499
71 | 690850 | C Bldg 5th Slab-PT Beam Steel | Steel Bars 32mm | Kgs | 400 |  | Management | Approved | 2024-04-12 12:00 | 2024-04-12 12:00 |  |  | 2024-04-12 18:33 | 5.75 | Vinay Mittal | 0 |  | 0 |  | 100 | [12 empty] | 3324205 | 953448.3312
72 | 691888 | Tower A, B & C Bldg ACCL Panel LT cable & Meter room work | Alum Armd Cable 3.5C x 150sqmm | Mtrs | 1 |  | Management | Approved | 2024-04-18 12:00 | 2024-04-18 12:00 | :: Released from PO 68531 :- PO detail id 158227 :- ReqD_id 798676 |  | 2024-06-18 17:26 | 1 | PARSHURAM KORE | 0 |  | 0 |  | 100 | [12 empty] | 2000 | 16673.754
73 | 694600 | D Building Parking Toilet CP & Sanitary | Chair Bracket for W H | No. | 2 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 |  |  | 2024-05-06 11:21 | 2 | Sajid khan | 0 |  | 0 |  | 673 | [12 empty] | 1346 | 0
74 | 694611 | Tractor Repair & Maintenance final | 30.194MSTAR COOLZ - 1 LITRE | No. | 2 |  | Management | Approved | 2024-05-04 12:00 | 2024-05-04 12:00 | :: Released from PO 69384 :- PO detail id 160517 :- ReqD_id 802725 |  | 2024-08-09 14:37 | 1 | AKSHADA MAHAJAN | 0 |  | 0 |  | 300 | [12 empty] | 1800 | 925.3547
75 | 695558 | A- material for internal CP & Sanitary work | CP Connector Pipe 1/2" x 24" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 1550 | 0
76 | 695559 | B- material for internal CP & Sanitary work | CP Connector Pipe 1/2" x 24" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 1550 | 0
77 | 695561 | A- material for internal CP & Sanitary work | GI Reducer Elbow 11/2"x 11/4" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 29.2708 | [12 empty] | 907.3948 | 0
78 | 695562 | B- material for internal CP & Sanitary work | GI Reducer Elbow 11/2"x 11/4" | No. | 31 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 12:38 | 31 | Sajid khan | 0 |  | 0 |  | 29.2708 | [12 empty] | 907.3948 | 0
79 | 695575 | B- material for internal CP & Sanitary work | Silicone Sealent | No. | 10 |  | Management | Approved | 2024-05-16 12:00 | 2024-05-16 12:00 |  |  | 2024-05-16 18:51 | 10 | Sajid khan | 0 |  | 0 |  | 180 | [12 empty] | 1800 | 0
80 | 695640 | A- material for internal CP & Sanitary work | Habak | Kgs | 3 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-17 17:53 | 3 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 150 | 0
81 | 695641 | B- material for internal CP & Sanitary work | Habak | Kgs | 2 |  | Management | Approved | 2024-05-17 12:00 | 2024-05-17 12:00 |  |  | 2024-05-17 17:53 | 2 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 100 | 0
82 | 698052 | B 101 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
83 | 698053 | B 102 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
84 | 698054 | B 201 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
85 | 698055 | B 202 CP & Sanitary (M) - | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
86 | 698056 | B 401 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
87 | 698057 | B 502 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
88 | 698058 | B 602 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
89 | 698059 | B 701 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
90 | 698060 | B 702 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
91 | 698061 | B 901 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
92 | 698062 | B 902 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
93 | 698063 | B 1001 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
94 | 698064 | B 1002 CP & Sanitary (M) | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
95 | 698065 | B 11th Floor 1101 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
96 | 698066 | B 11th Floor 1102 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
97 | 698067 | B 12th Floor 1202 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
98 | 698068 | B 13th Floor 1301 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
99 | 698069 | B 13th Floor 1302 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
100 | 698070 | B 16th Floor 1601 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
101 | 698071 | B 17th Floor 1701 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
102 | 698072 | B 18th Floor 1801 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
103 | 698073 | B 20th Floor 2001 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
104 | 698074 | B 21st Floor 2101 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
105 | 698075 | B 17th Floor 1702 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
106 | 698076 | B 19th Floor 1902 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
107 | 698077 | B 21st Floor 2102 CP & Sanitary | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:54 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
108 | 698078 | A CP & Sanitary Flat No.101 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
109 | 698079 | A CP & Sanitary Flat No.102 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
110 | 698080 | A CP & Sanitary Flat No.103 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
111 | 698081 | A CP & Sanitary Flat No.104 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
112 | 698082 | A CP & Sanitary Flat No.901 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
113 | 698083 | A CP & Sanitary Flat No.902 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
114 | 698084 | A CP & Sanitary Flat No.903 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
115 | 698085 | A CP & Sanitary (M) Flat No.1001 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
116 | 698086 | A CP & Sanitary (M) Flat No.1002 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
117 | 698087 | A CP & Sanitary (M) Flat No.1003 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:56 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
118 | 698088 | A CP & Sanitary (M) Flat No.1204 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
119 | 698089 | A CP & Sanitary (M) Flat No.1302 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
120 | 698090 | A CP & Sanitary (M) Flat No.1401 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
121 | 698091 | A CP & Sanitary (M) Flat No.1402 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
122 | 698092 | A CP & Sanitary (M) Flat No.1501 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
123 | 698093 | A CP & Sanitary (M) Flat No.1503 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
124 | 698094 | A CP & Sanitary (M) Flat No.1601 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
125 | 698095 | A CP & Sanitary (M) Flat No.1602 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
126 | 698096 | A CP & Sanitary (M) Flat No.1604 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
127 | 698097 | A CP & Sanitary (M) Flat No.1701 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
128 | 698098 | A CP & Sanitary (M) Flat No.2001 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
129 | 698099 | A CP & Sanitary (M) Flat No.1702 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
130 | 698100 | A CP & Sanitary (M) Flat No.1704 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
131 | 698101 | A CP & Sanitary (M) Flat No.1804 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
132 | 698102 | A CP & Sanitary (M) Flat No.1904 | Wall Hung commod With seat Cover -S1044106 | No. | 1 |  | Management | Approved | 2024-06-03 15:58 | 2024-06-03 12:00 |  |  | 2024-06-04 12:17 | 1 | Sajid khan | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
133 | 698608 | A Lift- Gap filling bet. lift frame & Italian marble frame | Silicon Tube | No. | 1 |  | Management | Approved | 2024-06-04 14:18 | 2024-06-04 12:00 |  |  | 2024-06-05 17:59 | 1 | Sajid khan | 0 |  | 0 |  | 170 | [12 empty] | 170 | 0
134 | 698609 | B Lift- Gap filling bet. lift frame & Italian marble frame | Silicon Tube | No. | 1 |  | Management | Approved | 2024-06-04 14:18 | 2024-06-04 12:00 |  |  | 2024-06-05 17:59 | 1 | Sajid khan | 0 |  | 0 |  | 170 | [12 empty] | 170 | 0
135 | 699039 | GRN For SRA Morwadi Steel | Steel Bars 8mm | Kgs | 40 |  | Management | Approved | 2024-06-05 15:29 | 2024-06-10 12:00 | :: Released from PO 68869 :- PO detail id 159102 :- ReqD_id 810531 |  | 2024-07-09 17:16 | 40 | akshada mahajan | 0 |  | 0 |  | 50.85 | [12 empty] | 8340417 | 9443130.139
136 | 699129 | Material required for Sales office use | Garbage Bag (Big) | Pack | 11 |  | Management | Approved | 2024-06-07 13:16 | 2024-06-07 12:00 |  |  | 2024-06-07 16:12 | 1 | NITIN.PARDESHI | 0 |  | 0 |  | 100 | [12 empty] | 10700 | 16418.52
137 | 699139 | Safety Material | Rubber Hand Gloves | Pair | 6 |  | Management | Approved | 2024-06-07 13:34 | 2024-06-07 12:00 |  |  | 2024-06-07 16:12 | 6 | Sajid khan | 0 |  | 0 |  | 15 | [12 empty] | 1875 | 3148
138 | 699203 | Material required for Sales office use | 17" Hard Brush (for scrubber m | No. | 6 |  | Management | Approved | 2024-06-07 17:33 | 2024-06-07 12:00 |  |  | 2024-06-08 10:44 | 6 | Sajid khan | 0 |  | 0 |  | 3200 | [12 empty] | 19200 | 0
139 | 702034 | Material required for Sales office use | Hand wash Foam Bottle | No. | 2 |  | Management | Approved | 2024-06-17 15:46 | 2024-06-17 12:00 |  |  | 2024-06-17 15:58 | 2 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 1600 | 1593
140 | 703410 | Pour 5 102.00 to 105.00 lvl Slab Steel | Steel Bars 8mm | Kgs | 1787 |  | Management | Approved | 2024-06-21 18:09 | 2024-06-21 12:00 |  |  | 2024-06-21 18:47 | 1000 | AKSHADA MAHAJAN | 0 |  | 0 |  | 100 | [12 empty] | 514700 | 251564.0091
141 | 703460 | A Bldg 30th slab Nonstructural RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.7644 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.006 | AKSHADA MAHAJAN | 0 |  | 0 |  | 3880 | [12 empty] | 80565.872 | 111193.75
142 | 703460 | A Bldg 30th slab Nonstructural RMC M30 (S-M Mix) hiflow | Cement Loose 53 Grade | Metric Tonnes | 0.7644 |  | Management | Approved | 2024-06-25 11:38 | 2024-06-25 12:00 |  |  | 2024-06-25 12:05 | 0.3209 | AKSHADA MAHAJAN | 0 |  | 0 |  | 3880 | [12 empty] | 80565.872 | 111193.75
143 | 703557 | A Bldg 36th Slab (31st Floor)Non Structural SW steel | Steel Bars 8mm | Kgs | 377 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 377 | Sajid khan | 0 |  | 0 |  | 53 | [12 empty] | 120946 | 121813.0415
144 | 703558 | B Bldg 35th Slab (30th floor) Slab steel | Steel Bars 8mm | Kgs | 707 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 119 | AKSHADA MAHAJAN | 0 |  | 0 |  | 53 | [12 empty] | 195994 | 244395.0108
145 | 703559 | B Bldg 35th Slab (30th floor) Non-Structural walls | Steel Bars 8mm | Kgs | 490 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 490 | Sajid khan | 0 |  | 0 |  | 53 | [12 empty] | 86231 | 73179.4803
146 | 703560 | B Bldg 36th To 37th Slab Shear Wall Steel | Steel Bars 8mm | Kgs | 6645 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1270 | SANKET PATIL | 0 |  | 0 |  | 53 | [12 empty] | 451533.5 | 429115.1055
147 | 703563 | A Bldg 35th Slab (30th Floor) 33 slab steel As Per Revised | Steel Bars 8mm | Kgs | 17785 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 17785 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1778500 | 0
148 | 703565 | 5th Slab Non Structural wall Steel | Steel Bars 8mm | Kgs | 1875.3 |  | Management | Approved | 2024-07-01 15:14 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1875.3 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 187530 | 0
149 | 703568 | B Bldg 35th Slab (30th floor) Slab steel | Steel Bars 10mm | Kgs | 2256.28 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 610.28 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 113348 | 119228.0852
150 | 703569 | B Bldg 36th Slab (31st floor) Slab steel | Steel Bars 10mm | Kgs | 2636 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2636 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 113348 | 0
151 | 703570 | B Bldg 34th To 35th Slab Shear Wall | Steel Bars 10mm | Kgs | 1656.87 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1656.87 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 148129.41 | 107658.8772
152 | 703571 | A Bldg Terrace to OHWT/LMR Slab Shear Wall Steel | Steel Bars 10mm | Kgs | 478.83 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 478.83 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 47883 | 0
153 | 703572 | STP-A.B.C Deck Slab steel & concrete | Steel Bars 10mm | Kgs | 300 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 300 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 30000 | 0
154 | 703573 | Pour 6 102.00 to 105.00 lvl Drop panel Steel | Steel Bars 10mm | Kgs | 1116 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1116 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 190500 | 47269.779
155 | 703574 | Pour 6 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 10mm | Kgs | 1905 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1905 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 190500 | 0
156 | 703577 | Pour 3A 102.00 to 105.00 lvl Column Steel | Steel Bars 10mm | Kgs | 70.79 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 70.79 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 7079 | 0
157 | 703578 | Pour 3A 102.00 to 105.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 6102 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 6102 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 610200 | 0
158 | 703579 | Pour 3A 105.00 to 108.00 lvl Column Steel | Steel Bars 10mm | Kgs | 70.79 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 70.79 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 7079 | 0
159 | 703580 | Pour 3A 105.00 to 108.00 lvl Slab Steel | Steel Bars 10mm | Kgs | 6102 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 6102 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 610200 | 0
160 | 703581 | Pour 3A 108.00 to 111.00 lvl Column Steel | Steel Bars 10mm | Kgs | 70.79 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 70.79 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 7079 | 0
161 | 703583 | 6th to 7th Column & SW Steel | Steel Bars 10mm | Kgs | 5379.14 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2507.453 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 281514.1936 | 170178.9081
162 | 703584 | 7th Slab (3rd Floor) Slab Steel | Steel Bars 10mm | Kgs | 1373.197 |  | Management | Approved | 2024-07-01 15:17 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1373.197 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 227968.33 | 0
163 | 703585 | A Bldg 34th Slab (29th Floor) 33 slab steel As Per Revised | Steel Bars 12mm | Kgs | 5141.33 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 | :: Released from PO 69209 :- PO detail id 160142 :- ReqD_id 818471 |  | 2024-07-11 11:41 | 5141.33 | Akshada Mahajan | 0 |  | 0 |  | 43 | [12 empty] | 436077.19 | 315178
164 | 703586 | A Bldg 35th Slab (30th Floor) 33 slab steel As Per Revised | Steel Bars 12mm | Kgs | 141.33 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 | :: Released from PO 69209 :- PO detail id 160142 :- ReqD_id 818470 |  | 2024-07-11 11:41 | 18.67 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 436077.19 | 609220.1799
165 | 703593 | Pour 3 102.00 to 105.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 7843.89 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 843.89 | SANKET PATIL | 0 |  | 0 |  | 43 | [12 empty] | 337287.27 | 390962.6
166 | 703594 | Pour 3 105.00 to 108.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 7843.89 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 7843.89 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 337287.27 | 0
167 | 703595 | Pour 3A 102.00 to 105.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 3831 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 671 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 164733 | 182942.512
168 | 703596 | Pour 3A 105.00 to 108.00 lvl Slab Steel | Steel Bars 12mm | Kgs | 3831 |  | Management | Approved | 2024-07-01 15:19 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1991 | AKSHADA MAHAJAN | 0 |  | 0 |  | 43 | [12 empty] | 164733 | 106523.488
169 | 703619 | Pour 3 102.00 to 105.00 lvl Dowel Bars | Steel Bars 16mm | Kgs | 1759.49 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 75.76 | SANKET PATIL | 0 |  | 0 |  | 51 | [12 empty] | 89733.99 | 94039.3512
170 | 703620 | Pour 3 102.00 to 105.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
171 | 703621 | Pour 3 105.00 to 108.00 lvl Dowel Bars | Steel Bars 16mm | Kgs | 1759.49 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1759.49 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 89733.99 | 0
172 | 703622 | Pour 3 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
173 | 703623 | Pour 3A 102.00 to 105.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
174 | 703624 | Pour 3A 105.00 to 108.00 lvl Column Steel | Steel Bars 16mm | Kgs | 79.72 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 79.72 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 4065.72 | 0
175 | 703625 | Pour 3A 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
176 | 703626 | Pour 3A 108.00 to 111.00 lvl Drop panel Steel | Steel Bars 16mm | Kgs | 2351 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2351 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 119901 | 0
177 | 703627 | Bursting Steel for P.T | Steel Bars 16mm | Kgs | 2567 |  | Management | Approved | 2024-07-01 15:21 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2567 | Sajid khan | 0 |  | 0 |  | 51 | [12 empty] | 130917 | 0
178 | 703635 | EWS Bldg RCC 1st Slab First Slab RCC | Steel Bar 25mm | Kgs | 0.4 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.4 | Sajid khan | 0 |  | 0 |  | 40 | [12 empty] | 16256 | 17749.9952
179 | 703636 | C Bldg shear walls steel upto 2nd Slab including plinth beam | Steel Bar 25mm | Kgs | 0.5 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.5 | Sajid khan | 0 |  | 0 |  | 40 | [12 empty] | 2957620 | 3920649.8457
180 | 703637 | A Bldg OHWT Steel | Steel Bar 25mm | Kgs | 0.89 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.89 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 763890 | 48096.1628
181 | 703639 | 115.20 lvl Tie Beam Steel | Steel Bar 25mm | Kgs | 0.95 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.95 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 291950 | 18343.3596
182 | 703640 | A Bldg Terrace to OHWT/LMR Slab Shear Wall Steel | Steel Bar 25mm | Kgs | 648.61 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 648.61 | Sajid khan | 0 |  | 0 |  | 1000 | [12 empty] | 648610 | 0
183 | 703642 | 7th Slab (3rd Floor) Slab Beam Steel | Steel Bar 25mm | Kgs | 1237.685 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1008.445 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 248095.6245 | 239820.4723
184 | 703646 | 8th to 9th Column & SW Steel | Steel Bar 25mm | Kgs | 11489 |  | Management | Approved | 2024-07-01 15:24 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 11489 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 584215.65 | 0
185 | 703647 | UGWT & Pump Room RCC Work Steel | Steel Bars 32mm | Kgs | 1038 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1038 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 48590 | 3817.9448
186 | 703648 | B Bldg 22th Slab Steel | Steel Bars 32mm | Kgs | 1456 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1456 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80883 | 17804.345
187 | 703649 | B Bldg 23rd Slab Steel | Steel Bars 32mm | Kgs | 1881 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1881 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80883 | 0
188 | 703650 | Club House 1st Slab Steel | Steel Bars 32mm | Kgs | 1505 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1505 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 64715 | 0
189 | 703651 | C Bldg shear walls steel upto 2nd Slab including plinth beam | Steel Bars 32mm | Kgs | 1108 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1108 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 47644 | 0
190 | 703652 | B Bldg 26th Slab Steel- - | Steel Bars 32mm | Kgs | 1400 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1400 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80883 | 33004.777
191 | 703653 | B 33rd slab Steel | Steel Bars 32mm | Kgs | 775.75 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 775.75 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 80872.25 | 77339.7305
192 | 703654 | A Bldg 34th Floor Steel | Steel Bars 32mm | Kgs | 0.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.33 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 49937.19 | 81308.313
193 | 703655 | A Bldg 35th Slab (30th Floor) slab steel | Steel Bars 32mm | Kgs | 0.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.33 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 49937.19 | 81308.313
194 | 703656 | A Bldg 36th Slab (31st Floor) Slab steel | Steel Bars 32mm | Kgs | 0.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 0.33 | Sajid khan | 0 |  | 0 |  | 43 | [12 empty] | 49937.19 | 81308.313
195 | 703657 | Steel for Fire ramp from 105.00 lvl to 108.00 lvl | Steel Bars 32mm | Kgs | 664.998 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 664.998 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 302980.8 | 151751.9762
196 | 703658 | C Bldg 5th Slab-PT Beam Steel | Steel Bars 32mm | Kgs | 22842.05 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 17842.05 | AKSHADA MAHAJAN | 0 |  | 0 |  | 100 | [12 empty] | 3324205 | 953448.3312
197 | 703659 | Pour 6 105.00 to 108.00 lvl Drop panel Steel | Steel Bars 32mm | Kgs | 1770.33 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 1770.33 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 188100 | 7019.7649
198 | 703660 | 5th to 6th Column & SW Steel | Steel Bars 32mm | Kgs | 14098.656 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 11098.656 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 1409865.6 | 172886.4
199 | 703661 | C bldg 6th Slab (2nd Floor) beam steel | Steel Bars 32mm | Kgs | 547.141 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 547.141 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 27822.1198 | 0
200 | 703662 | 6th to 7th Column & SW Steel | Steel Bars 32mm | Kgs | 2919.84 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2919.84 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 148473.864 | 0
201 | 703663 | 7th Slab (3rd Floor) Slab Beam Steel | Steel Bars 32mm | Kgs | 516.312 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 516.312 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 26254.4652 | 0
202 | 703664 | 8th Slab (3rd Floor) Slab Beam Steel | Steel Bars 32mm | Kgs | 516.312 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 516.312 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 26254.4652 | 0
203 | 703665 | 7th to 8th Column & SW Steel | Steel Bars 32mm | Kgs | 2919.84 |  | Management | Approved | 2024-07-01 15:25 | 2024-07-01 12:00 |  |  | 2024-07-02 12:05 | 2919.84 | Sajid khan | 0 |  | 0 |  | 50.85 | [12 empty] | 148473.864 | 0
204 | 704889 | Labour Camp Electrical Work | Drill Bit 6mm | No. | 25 |  | Management | Approved | 2024-07-03 10:58 | 2024-07-03 12:00 |  |  | 2024-07-04 12:07 | 25 | Sajid khan | 0 |  | 0 |  | 385.88 | [12 empty] | 9647 | 0
205 | 706550 | Drive way periphery planters Brickwork & Plaster | Cement 43 Grade | Bags | 41.5025 |  | Management | Approved | 2024-07-13 11:25 | 2024-07-13 12:00 |  |  | 2024-07-13 11:49 | 0.3837 | AKSHADA MAHAJAN | 0 |  | 0 |  | 375 | [12 empty] | 24000 | 13980.392
206 | 707176 | A,B,C D & Development Housekeeping | Phenyl | Ltrs | 5 |  | Management | Approved | 2024-07-18 09:23 | 2024-07-18 12:00 |  | Tiger Brand | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 260 | [12 empty] | 7800 | 0
207 | 707177 | A,B,C D & Development Housekeeping | Handgloves -HUSQ | Pair | 5 |  | Management | Approved | 2024-07-18 09:23 | 2024-07-18 12:00 |  | Rubber Handglove For Houdekeeping | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 350 | [12 empty] | 1750 | 0
208 | 707178 | A,B,C D & Development Housekeeping | Garbage Bag (Big) | Pack | 10 |  | Management | Approved | 2024-07-18 09:24 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 10 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1000 | 0
209 | 707179 | A,B,C D & Development Housekeeping | Toilet Brush Two Side | No. | 4 |  | Management | Approved | 2024-07-18 09:24 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 4 | Sajid khan | 0 |  | 0 |  | 150 | [12 empty] | 900 | 200.6
210 | 707180 | A,B,C D & Development Housekeeping | Check Duster | No. | 12 |  | Management | Approved | 2024-07-18 09:24 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 12 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3600 | 365.4
211 | 707181 | A,B,C D & Development Housekeeping | Nirma Washing Powder 1Kg | Kgs | 5 |  | Management | Approved | 2024-07-18 09:25 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 30 | [12 empty] | 300 | 224.2
212 | 707182 | A,B,C D & Development Housekeeping | Room Freshner | No. | 6 |  | Management | Approved | 2024-07-18 09:25 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 6 | Sajid khan | 0 |  | 0 |  | 50 | [12 empty] | 600 | 0
213 | 707183 | A,B,C D & Development Housekeeping | Plastic Bucket | No. | 5 |  | Management | Approved | 2024-07-18 09:27 | 2024-07-18 12:00 |  |  | 2024-07-22 10:52 | 5 | Sajid khan | 0 |  | 0 |  | 157.5 | [12 empty] | 2205 | 283.2
214 | 707357 | Store Equipments | Umbrella | No. | 6 |  | Management | Approved | 2024-07-27 11:57 | 2024-07-27 12:00 |  |  | 2024-07-27 18:33 | 6 | Sajid khan | 0 |  | 0 |  | 160 | [12 empty] | 2720 | 1848
215 | 707358 | Site Expenses (New) | Umbrella | No. | 3 |  | Management | Approved | 2024-07-27 11:57 | 2024-07-27 12:00 |  |  | 2024-07-27 18:33 | 3 | Sajid khan | 0 |  | 0 |  | 160 | [12 empty] | 1440 | 1008
216 | 707388 | Transformer Room Tapping Fitting Arrangements | New Tapping Fitting Arrangement | No. | 1 |  | Management | Approved | 2024-07-30 15:27 | 2024-07-30 12:00 |  |  | 2024-07-30 15:29 | 1 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 100 | 0
217 | 707389 | Transformer Room Tapping Fitting Arrangements | Labour charges with testing | No. | 1 |  | Management | Approved | 2024-07-30 15:28 | 2024-07-30 12:00 |  |  | 2024-07-30 15:29 | 1 | SANKET PATIL | 0 |  | 0 |  | 1 | [12 empty] | 1 | 0
218 | 711585 | Refuge & Terrace Floor Fire Door | Anchor Fastner 8x80mm Fire Rates | No. | 30 |  | Management | Approved | 2024-08-03 17:27 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 30 | Sajid khan | 0 |  | 0 |  | 35 | [12 empty] | 1050 | 0
219 | 711587 | Refuge & Terrace Floor Fire Door | Butt Hinges 101x75x3mm SS Ball Bearing | No. | 12 |  | Management | Approved | 2024-08-03 17:28 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 12 | Sajid khan | 0 |  | 0 |  | 200 | [12 empty] | 2400 | 0
220 | 711588 | Refuge & Terrace Floor Fire Door | Door Closer for Fire Door | No. | 3 |  | Management | Approved | 2024-08-03 17:28 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 3 | Sajid khan | 0 |  | 0 |  | 1500 | [12 empty] | 4500 | 0
221 | 711589 | Refuge & Terrace Floor Fire Door | Fire Clear Glass (2Hr) | No. | 3 |  | Management | Approved | 2024-08-03 17:29 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 3 | Sajid khan | 0 |  | 0 |  | 1500 | [12 empty] | 4500 | 0
222 | 711591 | Refuge & Terrace Floor Fire Door | Fire Rated Gasket 13mm x 4mm Thick | No. | 6 |  | Management | Approved | 2024-08-03 17:29 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 6 | Sajid khan | 0 |  | 0 |  | 4284 | [12 empty] | 25704 | 0
223 | 711592 | Refuge & Terrace Floor Fire Door | Lever Handle SD or SS | Pair | 3 |  | Management | Approved | 2024-08-03 17:30 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 3 | Sajid khan | 0 |  | 0 |  | 400 | [12 empty] | 1200 | 0
224 | 711593 | Refuge & Terrace Floor Fire Door | Panic Bar YPE-RM-501P Single Point Rim Type | No. | 3 |  | Management | Approved | 2024-08-03 17:30 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 3 | Sajid khan | 0 |  | 0 |  | 3500 | [12 empty] | 10500 | 0
225 | 711632 | Tower C 1st Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
226 | 711633 | Tower C 2nd Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
227 | 711634 | Tower C 3rd Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
228 | 711635 | Tower C 4th Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
229 | 711636 | Tower C 5th Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
230 | 711637 | Tower C 6th Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
231 | 711638 | Tower C 7th Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
232 | 711639 | Tower C 8th Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
233 | 711640 | Tower C 9th Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
234 | 711641 | Tower C 10th Floor Shear walls Conduits | Coalesce resi Struct Cabling Box 395x303x90mm | No. | 4 |  | Management | Approved | 2024-08-03 18:04 | 2024-08-03 12:00 |  |  | 2024-08-05 12:02 | 4 | Sajid khan | 0 |  | 0 |  | 3000 | [12 empty] | 12000 | 0
235 | 712361 | Tractor Repair & Maintenance | PISTON CYLINDER SEAL KIT | No. | 1 |  | Management | Approved | 2024-08-09 12:01 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 1 | Sajid khan | 0 |  | 0 |  | 1823 | [12 empty] | 1823 | 0
236 | 712364 | Tractor Repair & Maintenance | 000704348R1 O RING | No. | 12 |  | Management | Approved | 2024-08-09 12:03 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 11 | AKSHADA MAHAJAN | 0 |  | 0 |  | 10 | [12 empty] | 120 | 11.1581
237 | 712365 | Tractor Repair & Maintenance | 007201350C1GASKET (SUCTION STRAINER - OIB) | No. | 22 |  | Management | Approved | 2024-08-09 12:03 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 21 | AKSHADA MAHAJAN | 0 |  | 0 |  | 600 | [12 empty] | 13200 | 23.2467
238 | 712366 | Tractor Repair & Maintenance | 007700388C91 LAMP ASSEMBLY (PARK AND TURN SIGNAL) | No. | 2 |  | Management | Approved | 2024-08-09 12:04 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 1 | AKSHADA MAHAJAN | 0 |  | 0 |  | 450 | [12 empty] | 1350 | 493.84
239 | 712367 | Tractor Repair & Maintenance | LAMP COMBINATION REAR | No. | 1 |  | Management | Approved | 2024-08-09 12:04 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 1 | Sajid khan | 0 |  | 0 |  | 516.95 | [12 empty] | 516.95 | 0
240 | 712368 | Tractor Repair & Maintenance | BULB HALOGEN 55/60W M/S PHOENIX | No. | 2 |  | Management | Approved | 2024-08-09 12:04 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 2 | Sajid khan | 0 |  | 0 |  | 122.03 | [12 empty] | 244.06 | 0
241 | 712370 | Tractor Repair & Maintenance | WIRING HARNESS REAR (ARJUN CE) | No. | 1 |  | Management | Approved | 2024-08-09 12:05 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 1 | Sajid khan | 0 |  | 0 |  | 1238 | [12 empty] | 1238 | 0
242 | 712371 | Tractor Repair & Maintenance | 1262OIB Oil | No. | 40 |  | Management | Approved | 2024-08-09 12:05 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 40 | Sajid khan | 0 |  | 0 |  | 600 | [12 empty] | 24000 | 0
243 | 712372 | Tractor Repair & Maintenance | 1263OIB Oil | No. | 5 |  | Management | Approved | 2024-08-09 12:05 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 5 | Sajid khan | 0 |  | 0 |  | 600 | [12 empty] | 3000 | 0
244 | 712374 | Spare parts for Tower Crane | RESISTANCE P-30424-53 | No. | 1 |  | Management | Approved | 2024-08-09 12:12 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 1 | Sajid khan | 0 |  | 0 |  | 12000 | [12 empty] | 12000 | 0
245 | 712375 | Spare parts for Tower Crane | LUBRICANT P-61032-70 | No. | 5 |  | Management | Approved | 2024-08-09 12:12 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 5 | Sajid khan | 0 |  | 0 |  | 1650 | [12 empty] | 8250 | 0
246 | 712376 | Spare parts for Tower Crane | Packing & Forwarding | No. | 1 |  | Management | Approved | 2024-08-09 12:13 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 1 | Sajid khan | 0 |  | 0 |  | 7000 | [12 empty] | 7000 | 0
247 | 712402 | Tractor Repair & Maintenance | 007700388C91 LAMP ASSEMBLY (PARK AND TURN SIGNAL) | No. | 1 |  | Management | Approved | 2024-08-09 15:58 | 2024-08-09 12:00 |  |  | 2024-08-09 16:00 | 1 | Sajid khan | 0 |  | 0 |  | 450 | [12 empty] | 1350 | 493.84
248 | 712405 | Tower A Lift Repaire & Maintanance | Safety Device Assembly SSD/3500 | No. | 1 |  | Management | Approved | 2024-08-09 16:06 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 1 | Sajid khan | 0 |  | 0 |  | 260000 | [12 empty] | 260000 | 0
249 | 712406 | Tower A Lift Repaire & Maintanance | NORD GEARBOX MODEL: SK9042.1AF-132 M/40 BRE | No. | 1 |  | Management | Approved | 2024-08-09 16:07 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 1 | Sajid khan | 0 |  | 0 |  | 10000 | [12 empty] | 10000 | 0
250 | 712407 | Tower A Lift Repaire & Maintanance | DRIVING PINION (6m,21T) SPM-2J-05-03-R0 | No. | 2 |  | Management | Approved | 2024-08-09 16:08 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 2 | Sajid khan | 0 |  | 0 |  | 15000 | [12 empty] | 30000 | 0
251 | 712408 | Tower A Lift Repaire & Maintanance | RACK ROLLER ASSEMBLY SPM-2J-07-00-R1 | No. | 2 |  | Management | Approved | 2024-08-09 16:08 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 2 | Sajid khan | 0 |  | 0 |  | 15000 | [12 empty] | 30000 | 0
252 | 712410 | Tower A Lift Repaire & Maintanance | TOP LEVER ROLLER ASSLY | No. | 6 |  | Management | Approved | 2024-08-09 16:09 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 6 | Sajid khan | 0 |  | 0 |  | 630 | [12 empty] | 5040 | 19824
253 | 712411 | Tower A Lift Repaire & Maintanance | BOTTOM LEVER ROLLER ASSEMBLY (SPM-2E-59-00-R0) | No. | 6 |  | Management | Approved | 2024-08-09 16:10 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 6 | Sajid khan | 0 |  | 0 |  | 15000 | [12 empty] | 90000 | 0
254 | 712412 | Tower A Lift Repaire & Maintanance | SIDE GUIDE ROLLER ASSEMBLY | No. | 4 |  | Management | Approved | 2024-08-09 16:10 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 4 | Sajid khan | 0 |  | 0 |  | 365 | [12 empty] | 3650 | 39648
255 | 712413 | Tower- C Lift Repair & Maintenance | ANCHOR SAFETY BOLT HST M20 X 170 / 30 | No. | 7 |  | Management | Approved | 2024-08-09 16:52 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 7 | Sajid khan | 0 |  | 0 |  | 1200 | [12 empty] | 8400 | 0
256 | 712416 | Tower- C Lift Repair & Maintenance | ANCHOR SAFETY BOLT HST M16 X 165 / 50 | No. | 60 |  | Management | Approved | 2024-08-09 17:06 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 60 | Sajid khan | 0 |  | 0 |  | 600 | [12 empty] | 36000 | 0
257 | 712417 | Tower- C Lift Repair & Maintenance | HEX BOLT ASSEMBLY 16 X 150 | No. | 6 |  | Management | Approved | 2024-08-09 17:06 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 6 | Sajid khan | 0 |  | 0 |  | 650 | [12 empty] | 3900 | 0
258 | 712418 | Tower- C Lift Repair & Maintenance | HEX BOLT ASSEMBLY 16 X 125 | No. | 6 |  | Management | Approved | 2024-08-09 17:06 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 6 | Sajid khan | 0 |  | 0 |  | 550 | [12 empty] | 3300 | 0
259 | 712419 | Tower- C Lift Repair & Maintenance | Safety Device Assembly SSD/3500 | No. | 1 |  | Management | Approved | 2024-08-09 17:07 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 1 | Sajid khan | 0 |  | 0 |  | 260000 | [12 empty] | 260000 | 0
260 | 712420 | Tower- C Lift Repair & Maintenance | Hoist Motor Cover | No. | 2 |  | Management | Approved | 2024-08-09 17:07 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 2 | Sajid khan | 0 |  | 0 |  | 7500 | [12 empty] | 15000 | 0
261 | 712422 | Tower- C Lift Repair & Maintenance | Tie Frame Assembly | No. | 17 |  | Management | Approved | 2024-08-09 17:08 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 17 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 1700 | 0
262 | 712423 | Tower- C Lift Repair & Maintenance | CABIN DOOR NUT BOLT-10X65 | No. | 12 |  | Management | Approved | 2024-08-09 17:09 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 12 | Sajid khan | 0 |  | 0 |  | 55 | [12 empty] | 660 | 0
263 | 712424 | Tower- C Lift Repair & Maintenance | Base enclosure | No. | 1 |  | Management | Approved | 2024-08-09 17:09 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 1 | Sajid khan | 0 |  | 0 |  | 105000 | [12 empty] | 105000 | 0
264 | 712425 | Tower- C Lift Repair & Maintenance | HEX HD BOLT M12 X 75 LONG | No. | 12 |  | Management | Approved | 2024-08-09 17:10 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 12 | Sajid khan | 0 |  | 0 |  | 250 | [12 empty] | 3000 | 0
265 | 712426 | Tower- C Lift Repair & Maintenance | DRIVING PINION (FOR ROSSI MOTOR) | No. | 2 |  | Management | Approved | 2024-08-09 17:10 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 2 | Sajid khan | 0 |  | 0 |  | 120 | [12 empty] | 240 | 0
266 | 712427 | Tower- C Lift Repair & Maintenance | RACK WHEEL ROLLER ASSEMBLY | No. | 3 |  | Management | Approved | 2024-08-09 17:10 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 3 | Sajid khan | 0 |  | 0 |  | 325 | [12 empty] | 975 | 0
267 | 712428 | Tower- C Lift Repair & Maintenance | BOTTOM LEVER ROLLER ASSEMBLY | No. | 4 |  | Management | Approved | 2024-08-09 17:11 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 4 | Sajid khan | 0 |  | 0 |  | 12500 | [12 empty] | 50000 | 0
268 | 712429 | Tower- C Lift Repair & Maintenance | SIDE GUIDE ROLLER ASSEMBLY | No. | 4 |  | Management | Approved | 2024-08-09 17:11 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 4 | Sajid khan | 0 |  | 0 |  | 365 | [12 empty] | 1460 | 0
269 | 712430 | Tower- C Lift Repair & Maintenance | Limit Switch for Rack Search | No. | 1 |  | Management | Approved | 2024-08-09 17:12 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 1 | Sajid khan | 0 |  | 0 |  | 6500 | [12 empty] | 6500 | 0
270 | 712431 | Tower- C Lift Repair & Maintenance | BUSBAR ASSEMBLY | Mtrs | 60 |  | Management | Approved | 2024-08-09 17:12 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 60 | Sajid khan | 0 |  | 0 |  | 4500 | [12 empty] | 270000 | 0
271 | 712432 | Tower- C Lift Repair & Maintenance | M06X30 ALAN BOLT | No. | 18 |  | Management | Approved | 2024-08-09 17:12 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 18 | Sajid khan | 0 |  | 0 |  | 65 | [12 empty] | 1170 | 0
272 | 712433 | Tower- C Lift Repair & Maintenance | FULL SLIDING ENTRY DOOR | No. | 1 |  | Management | Approved | 2024-08-09 17:13 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 1 | Sajid khan | 0 |  | 0 |  | 75000 | [12 empty] | 75000 | 0
273 | 712434 | Tower- C Lift Repair & Maintenance | ROSSI GEARBOX WITHOUT MOTOR (6.9 kW) | No. | 1 |  | Management | Approved | 2024-08-09 17:13 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 1 | Sajid khan | 0 |  | 0 |  | 125000 | [12 empty] | 125000 | 0
274 | 712435 | Tower- C Lift Repair & Maintenance | TOP LEVER ROLLER ASSLY | No. | 2 |  | Management | Approved | 2024-08-09 17:14 | 2024-08-09 12:00 |  |  | 2024-08-09 18:59 | 2 | Sajid khan | 0 |  | 0 |  | 630 | [12 empty] | 1260 | 0
275 | 712765 | B GF Parking Flooring Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 24 |  | Management | Approved | 2024-08-16 10:31 | 2024-08-16 12:00 |  |  | 2024-08-16 10:41 | 24 | Sajid khan | 0 |  | 0 |  | 2000 | [12 empty] | 400000 | 297702.0072
276 | 712770 | Tower Crane Toolkits & Material | Cotton waste | Kgs | 40 |  | Management | Approved | 2024-08-16 12:17 | 2024-08-16 12:00 |  |  | 2024-08-16 14:42 | 40 | Sajid khan | 0 |  | 0 |  | 5 | [12 empty] | 200 | 0
277 | 713022 | C Bldg 5th Slab Staircase Steel | Binding Wire | Kgs | 18.25 |  | Management | Approved | 2024-08-17 14:34 | 2024-08-17 12:00 |  |  | 2024-08-17 14:46 | 0.245 | AKSHADA MAHAJAN | 0 |  | 0 |  | 61.9 | [12 empty] | 1129.675 | 1359.7376
278 | 714068 | Steel For ASMI GRN Purpose | Steel Bars 10mm | Kgs | 11170 |  | Management | Approved | 2024-08-20 10:55 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 1000 | SANKET PATIL | 0 |  | 0 |  | 100 | [12 empty] | 12581000 | 7588273.863
279 | 714069 | Steel For ASMI GRN Purpose | Steel Bars 12mm | Kgs | 20570 |  | Management | Approved | 2024-08-20 10:55 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 2000 | SANKET PATIL | 0 |  | 0 |  | 43 | [12 empty] | 6628579 | 9187407.214
280 | 714070 | Steel For ASMI GRN Purpose | Steel Bars 16mm | Kgs | 13800 |  | Management | Approved | 2024-08-20 10:56 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 1000 | SANKET PATIL | 0 |  | 0 |  | 51 | [12 empty] | 7257198 | 8531493.8812
281 | 714071 | Steel For ASMI GRN Purpose | Steel Bars 20mm | Kgs | 13020 |  | Management | Approved | 2024-08-20 10:56 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 1000 | SANKET PATIL | 0 |  | 0 |  | 1000 | [12 empty] | 195890000 | 11736863.725
282 | 714073 | GRN For SRA Morwadi Steel | Steel Bars 8mm | Kgs | 52980 |  | Management | Approved | 2024-08-20 11:01 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 9980 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 8340417 | 9443130.139
283 | 714074 | GRN For SRA Morwadi Steel | Steel Bars 10mm | Kgs | 5860 |  | Management | Approved | 2024-08-20 11:01 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 2460 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 2251638 | 2564415.864
284 | 714075 | GRN For SRA Morwadi Steel | Steel Bars 12mm | Kgs | 12220 |  | Management | Approved | 2024-08-20 11:03 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 920 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 1766122.2 | 1857040.1
285 | 714076 | GRN For SRA Morwadi Steel | Steel Bars 16mm | Kgs | 35390 |  | Management | Approved | 2024-08-20 11:03 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 4490 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 5938771.5 | 6740842.563
286 | 714077 | GRN For SRA Morwadi Steel | Steel Bars 20mm | Kgs | 13900 |  | Management | Approved | 2024-08-20 11:03 | 2024-08-20 12:00 |  |  | 2024-08-20 11:04 | 2500 | SANKET PATIL | 0 |  | 0 |  | 50.85 | [12 empty] | 5737130.91 | 5425388.452
287 | 714091 | Pour 6 108.00 to 111.00 lvl P1 Column Concrete-M50 | Ready Mix Concrete M50 Easycrete (Downpour) | Cu.Mtrs | 15 |  | Management | Approved | 2024-08-20 13:09 | 2024-08-20 12:00 |  |  | 2024-08-22 10:57 | 15 | Sajid khan | 0 |  | 0 |  | 3150 | [12 empty] | 85500.45 | 0
288 | 714522 | Pour 3A 108.00 to 111.00 lvl RMC M35 (S-M Mix)-Drop panel | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | Cu.Mtrs | 0.13 |  | Management | Approved | 2024-08-23 15:43 | 2024-08-23 12:00 |  |  | 2024-08-23 15:46 | 0.13 | Sajid khan | 0 |  | 0 |  | 100 | [12 empty] | 3217 | 206465.8753
289 | 715715 | B GF Parking Flooring Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 30 |  | Management | Approved | 2024-08-29 09:44 | 2024-08-29 12:00 |  |  | 2024-08-29 10:37 | 30 | Sajid khan | 0 |  | 0 |  | 2000 | [12 empty] | 400000 | 297702.0072