## Short_Supply_POwise638578484745
Short Supply Report
From 30-04-2022 To 29-07-2024
Page 1 of 1
Total Records: 280 Records 1 To 280
Project Name | Supplier Name | PO Sr No | PO Date | Rate | PO Qty | Material Name | Brand | Unit | Recd Qty | Bal Qty | Bal %
GANGA DHAM TOWERS | SANITARY PARK | 62516 | 2022-05-04 11:23 | 0.01 | 2 | Powder Coated MS Frame (JWA-BLK-FFONTE 170x75) | JAQUAR | No. | 0 | 2 | 100
GANGA DHAM TOWERS | MANGESH AGENCIES | 63143 | 2022-07-08 11:43 | 89.25 | 3400 | Safety net 5x10 mtrs |  | Sq.m. | 2900 | 500 | 14.7059
GANGA DHAM TOWERS | PRINCE DISTRIBUTOR | 63178 | 2022-07-12 14:19 | 35.872 | 198 | SWR Silent Coupler 1 1/2" (2305702) SF |  | No. | 30 | 168 | 84.8485
GANGA DHAM TOWERS | PRINCE DISTRIBUTOR | 63178 | 2022-07-12 14:19 | 1594.9588 | 224 | SWR Silent Aerator 4" (70001576) |  | No. | 223 | 1 | 0.4464
GANGA DHAM TOWERS | MANGESH AGENCIES | 63213 | 2022-07-14 10:55 | 89.25 | 2400 | Safety net 5x10 mtrs |  | Sq.m. | 1950 | 450 | 18.75
GANGA DHAM TOWERS | KANAD ELECTRICAL SERVICES | 63317 | 2022-07-25 16:36 | 1416 | 24 | CT Coil 1000/5 Ring type |  | No. | 12 | 12 | 50
GANGA DHAM TOWERS | OSWAL GRANITE | 63324 | 2022-07-26 11:51 | 236 | 814.31 | Telephonic Black Granite |  | Sq.Ft | 238.11 | 576.2 | 70.7593
GANGA DHAM TOWERS | KANAD ELECTRICAL SERVICES | 63501 | 2022-08-17 14:53 | 20886 | 1 | 22 KV Heat SShrink Straight Joint Kit 300sqx3 core - No. |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | VISHWAS SALES CORPORATION | 63859 | 2022-10-13 11:48 | 3714.8524 | 142 | PRV 1-1/4" |  | No. | 42 | 100 | 70.4225
GANGA DHAM TOWERS | VISHWAS SALES CORPORATION | 63859 | 2022-10-13 11:48 | 4110.8724 | 51 | PRV 1-1/2" |  | No. | 23 | 28 | 54.902
GANGA DHAM TOWERS | VISHWAS SALES CORPORATION | 63859 | 2022-10-13 11:48 | 5624.2811 | 55 | PRV 2" |  | No. | 34 | 21 | 38.1818
GANGA DHAM TOWERS | VISHWAS SALES CORPORATION | 63859 | 2022-10-13 11:48 | 1622.0812 | 37 | PRV 3/4" |  | No. | 18 | 19 | 51.3514
GANGA DHAM TOWERS | T K ENTERPRISES | 63983 | 2022-11-08 17:11 | 212.4 | 84 | Non Return Valve 1/2" |  | No. | 40 | 44 | 52.381
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 64125 | 2022-11-29 17:39 | 3812.3908 | 13 | Pop Up Box 8M (54017) |  | No. | 0 | 13 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 64125 | 2022-11-29 17:39 | 221.7928 | 1630 | 6/13 Amp International Socket (573473) | LEGRAND | No. | 1199 | 431 | 26.4417
GANGA DHAM TOWERS | SAITECH FIRE SYSTEM PRIVATE LIMITED | 64168 | 2022-12-07 17:15 | 31329 | 1 | Fire door with shutter 1200x2475mm |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | INNOVADOOR PRODUCTS PRIVATE LIMITED | 64309 | 2022-12-24 18:04 | 5561.9773 | 60 | Flush Door 35mm 37.5" x 90.5" - No. |  | No. | 59 | 1 | 1.6667
GANGA DHAM TOWERS | PRISM JOHNSON LIMITED | 64324 | 2022-12-27 10:30 | 4028.0008 | 50 | Sand-Metal Mix M35 (Pumpable) |  | Cu.Mtrs | 36 | 14 | 28
GANGA DHAM TOWERS | SAITECH FIRE SYSTEM PRIVATE LIMITED | 64564 | 2023-01-31 16:23 | 31329 | 81 | Fire door with shutter 1200x2475mm |  | No. | 77 | 4 | 4.9383
GANGA DHAM TOWERS | SAITECH FIRE SYSTEM PRIVATE LIMITED | 64565 | 2023-01-31 17:00 | 31329 | 75 | Fire door with shutter 1200x2475mm |  | No. | 71 | 4 | 5.3333
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64928 | 2023-03-11 10:36 | 167560 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64929 | 2023-03-11 10:39 | 167560 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64930 | 2023-03-11 10:41 | 135700 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64933 | 2023-03-11 11:13 | 153400 | 1 | Kitchen Trolley (Option 1) |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64934 | 2023-03-11 11:22 | 159300 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64937 | 2023-03-11 12:06 | 135700 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 6268.0927 | 208 | Basin Mixer-71100000 | HANSGROHE | No. | 120 | 88 | 42.3077
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 5138.133 | 261 | CP Spout-13414000 | HANSGROHE | No. | 110 | 151 | 57.8544
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 2995.135 | 492 | Health Faucet (32129000) | HANSGROHE | No. | 280 | 212 | 43.0894
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 731.6 | 450 | Angle Cock-13903000 | HANSGROHE | No. | 280 | 170 | 37.7778
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 708 | 1136 | Angle Cock-13902000 | HANSGROHE | No. | 570 | 566 | 49.8239
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 2362.4426 | 336 | Rain Shower Overhead-28423000 | HANSGROHE | No. | 100 | 236 | 70.2381
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 5434.9219 | 264 | Basin Mixer-31730000 | HANSGROHE | No. | 100 | 164 | 62.1212
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 7492.3156 | 255 | CP S/L Bath Mixer-31945000 | HANSGROHE | No. | 150 | 105 | 41.1765
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 5324.6379 | 184 | CP Spout-71410000 | HANSGROHE | No. | 115 | 69 | 37.5
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 64940 | 2023-03-11 12:43 | 8017.746 | 104 | S/L Mixer Focus 71280000 | HANSGROHE | No. | 50 | 54 | 51.9231
GANGA DHAM TOWERS | VARMORA GRANITO PVT LTD. | 64947 | 2023-03-13 10:51 | 76.2599 | 1028 | Brazillan Nero Tile 1200x600mm |  | Sq.Ft | 0 | 1028 | 100
GANGA DHAM TOWERS | VARMORA GRANITO PVT LTD. | 64947 | 2023-03-13 10:51 | 39.3388 | 2658 | Lumire LT Tile 600x300mm |  | Sq.Ft | 2645.37 | 12.63 | 0.4752
GANGA DHAM TOWERS | VARMORA GRANITO PVT LTD. | 64947 | 2023-03-13 10:51 | 54.0499 | 3000.56 | Terastone Brown 600x600mm |  | Sq.Ft | 0 | 3000.56 | 100
GANGA DHAM TOWERS | VARMORA GRANITO PVT LTD. | 64947 | 2023-03-13 10:51 | 54.0499 | 4043 | Sparten Beige Tile 600x600mm |  | Sq.Ft | 0 | 4043 | 100
GANGA DHAM TOWERS | VARMORA GRANITO PVT LTD. | 64947 | 2023-03-13 10:51 | 49.9199 | 1347 | Traventine Brown Tile 1200x600mm | VARMORA | Sq.Ft | 0 | 1347 | 100
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64964 | 2023-03-14 16:12 | 167560 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64967 | 2023-03-14 16:57 | 153400 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 64968 | 2023-03-14 16:58 | 153400 | 1 | Kitchen Trolley |  | No. | 0.3 | 0.7 | 70
GANGA DHAM TOWERS | GLOBAL TRADERS | 65049 | 2023-03-23 10:32 | 0.826 | 1500 | Washer 6mm |  | No. | 0 | 1500 | 100
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 65145 | 2023-04-05 17:27 | 135700 | 1 | Kitchen Trolley |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | A Y Enterprises | 65179 | 2023-04-11 12:28 | 11296.9896 | 104 | Wall.Hung Commode Architectura Square( 5685R001) |  | No. | 73 | 31 | 29.8077
GANGA DHAM TOWERS | A Y Enterprises | 65179 | 2023-04-11 12:28 | 5148.2575 | 107 | Wall H. Seat Cover QR/SC Architectura square (9M58S101) |  | No. | 68 | 39 | 36.4486
GANGA DHAM TOWERS | A Y Enterprises | 65179 | 2023-04-11 12:28 | 13190.2524 | 173 | Subway 2.0 WB 550x440mm Table Top (71135501) |  | No. | 146 | 27 | 15.6069
GANGA DHAM TOWERS | A Y Enterprises | 65179 | 2023-04-11 12:28 | 10377.51 | 290 | Wall Hung Commode Architectura Round (5684R001). |  | No. | 97 | 193 | 66.5517
GANGA DHAM TOWERS | A Y Enterprises | 65179 | 2023-04-11 12:28 | 4064.4864 | 288 | Wall H. Seat Cover Architectura Round (98M9C101) |  | No. | 84 | 204 | 70.8333
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 65182 | 2023-04-11 12:45 | 3.1294 | 77 | PVC Socket 1" |  | No. | 0 | 77 | 100
GANGA DHAM TOWERS | Neptune Engineers Private Limited | 65319 | 2023-04-26 17:28 | 31104 | 14 | Split AC 1 TR (RAS-13SKCV3SG-IN + RAS-13SACV3SG-IN) |  | No. | 0 | 14 | 100
GANGA DHAM TOWERS | Neptune Engineers Private Limited | 65319 | 2023-04-26 17:28 | 36480 | 30 | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) |  | No. | 0 | 30 | 100
GANGA DHAM TOWERS | Neptune Engineers Private Limited | 65319 | 2023-04-26 17:28 | 45440 | 18 | Split AC 2 TR (RAS-24SKCV3SG-IN + RAS-24SACV3SG-IN) |  | No. | 0 | 18 | 100
GANGA DHAM TOWERS | Neptune Engineers Private Limited | 65320 | 2023-04-26 18:07 | 36480 | 4 | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) |  | No. | 0 | 4 | 100
GANGA DHAM TOWERS | LOTUS SAFETY PRODUCTS | 65404 | 2023-05-05 12:13 | 1.47 | 4233 | Shedding Net |  | Sq.Ft | 3228 | 1005 | 23.742
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 65418 | 2023-05-06 11:40 | 19529 | 103 | Digital Biometric Lock Yale - 4115A Brown |  | No. | 25 | 78 | 75.7282
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 65418 | 2023-05-06 11:40 | 410.64 | 925 | Cylinder without Key - Yale (60mm SN BK-S) | YALE | No. | 704 | 221 | 23.8919
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 65418 | 2023-05-06 11:40 | 631.3 | 1542 | Lock Body - Yale (24-8545 BR SS04-S) | YALE | No. | 1353 | 189 | 12.2568
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 65418 | 2023-05-06 11:40 | 1091.5 | 1529 | Lever Handle - Yale (YMC511-RE-SS) - Pair | YALE | Pair | 1267 | 262 | 17.1354
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 65461 | 2023-05-10 14:44 | 19529 | 40 | Digital Biometric Lock Yale - 4115A Brown |  | No. | 0 | 40 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 65591 | 2023-05-27 15:09 | 6491.3688 | 41 | Pop Up Box 8M (54017) |  | No. | 32 | 9 | 21.9512
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65680 | 2023-06-08 11:05 | 122.72 | 786 | Mirror 6mm Clear |  | Sq.Ft | 307.75 | 478.25 | 60.8461
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65680 | 2023-06-08 11:05 | 11.8 | 876 | C.N.C. Edge Polish |  | R.Ft | 341 | 535 | 61.0731
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65680 | 2023-06-08 11:05 | 15.34 | 228 | Stud Holes |  | No. | 88 | 140 | 61.4035
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65680 | 2023-06-08 11:05 | 23.6 | 228 | Mirror Cap |  | No. | 88 | 140 | 61.4035
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65680 | 2023-06-08 11:05 | 11.8 | 786 | PVC Safety Film |  | Sq.Ft | 307.75 | 478.25 | 60.8461
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65680 | 2023-06-08 11:05 | 44.84 | 786 | Labour installation |  | Sq.Ft | 307.75 | 478.25 | 60.8461
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65681 | 2023-06-08 11:56 | 122.72 | 115 | Mirror 6mm Clear |  | Sq.Ft | 0 | 115 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65681 | 2023-06-08 11:56 | 11.8 | 126 | C.N.C. Edge Polish |  | R.Ft | 0 | 126 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65681 | 2023-06-08 11:56 | 15.34 | 32 | Stud Holes |  | No. | 0 | 32 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65681 | 2023-06-08 11:56 | 23.6 | 32 | Mirror Cap |  | No. | 0 | 32 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65681 | 2023-06-08 11:56 | 11.8 | 115 | PVC Safety Film |  | Sq.Ft | 0 | 115 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 65681 | 2023-06-08 11:56 | 44.84 | 115 | Labour installation |  | Sq.Ft | 0 | 115 | 100
GANGA DHAM TOWERS | MAMAS DECOR | 65782 | 2023-06-22 10:31 | 1584.6458 | 49.96 | Wallpaper (Code C1-0206) (P 48) 0.53mX9.5m - ROLL |  | ROLL | 1 | 48.96 | 97.9984
GANGA DHAM TOWERS | V TECH POWER SYSTEMS | 65789 | 2023-06-23 10:34 | 4533167.06 | 3 | DG 650KVA |  | No. | 2 | 1 | 33.3333
GANGA DHAM TOWERS | V TECH POWER SYSTEMS | 65789 | 2023-06-23 10:34 | 154580 | 1 | EB APPROVAL |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | SHIRKES KITCHEN INTERIORS PVT LTD | 65832 | 2023-06-29 10:33 | 189342.8 | 1 | Kitchen Trolley |  | No. | 0.55 | 0.45 | 45
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 65839 | 2023-06-29 13:05 | 48.1436 | 11 | Casing Caping 1" |  | No. | 0 | 11 | 100
GANGA DHAM TOWERS | SUNARTH INDUSTRIES LLP | 65963 | 2023-07-12 15:56 | 10500 | 310 | 3.3 KW AC 001 Lite Charger |  | No. | 0 | 310 | 100
GANGA DHAM TOWERS | SUNARTH INDUSTRIES LLP | 65963 | 2023-07-12 15:56 | 997500 | 1 | 60KW DC Dual Gun Charger |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | C. BHOGILAL WEST END | 66035 | 2023-07-19 12:27 | 1262.4017 | 318 | Shower Arm-27411000 | HANSGROHE | No. | 210 | 108 | 33.9623
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 66136 | 2023-08-02 12:17 | 7.375 | 1370 | GI U Clamps 25mm |  | No. | 312 | 1058 | 77.2263
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 66136 | 2023-08-02 12:17 | 8.85 | 5091 | GI U Clamps 32mm |  | No. | 4891 | 200 | 3.9285
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 66170 | 2023-08-05 11:07 | 11.8 | 4580 | PVC Safety Film |  | Sq.Ft | 0 | 4580 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 66170 | 2023-08-05 11:07 | 11.8 | 5466.8 | C.N.C. Edge Polish |  | R.Ft | 0 | 5466.8 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 66170 | 2023-08-05 11:07 | 15.34 | 1031 | Stud Holes |  | No. | 0 | 1031 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 66170 | 2023-08-05 11:07 | 122.72 | 4778.18 | Mirror 6mm Clear |  | Sq.Ft | 0 | 4778.18 | 100
GANGA DHAM TOWERS | MAHAVIR DESIGNER GLASS | 66170 | 2023-08-05 11:07 | 23.6 | 1339 | Mirror Cap |  | No. | 0 | 1339 | 100
GANGA DHAM TOWERS | MAHAVIR ENTERPRISES. | 66216 | 2023-08-10 19:04 | 68.9993 | 23387.495 | Geneva Beige Polished (1200 mmx 600 mm) |  | Sq.Ft | 23281 | 106.495 | 0.4554
GANGA DHAM TOWERS | MAHAVIR ENTERPRISES. | 66216 | 2023-08-10 19:04 | 68.9993 | 20320.9 | Basil Polished 600 x 1200 |  | Sq.Ft | 5316.5 | 15004.4 | 73.8373
GANGA DHAM TOWERS | OM ENTERPRISES | 66232 | 2023-08-12 17:11 | 2334.04 | 6 | Cube Mould 15x15x15 cm |  | No. | 0 | 6 | 100
GANGA DHAM TOWERS | LOTUS SAFETY PRODUCTS | 66352 | 2023-08-23 18:51 | 1339.3 | 2 | Safety shoes | KARAM | No. | 0 | 2 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 66408 | 2023-08-30 17:49 | 14927 | 253 | Veneer Door Frame (Bedroom Door) (Size at Actual) |  | No. | 129 | 124 | 49.0119
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 66408 | 2023-08-30 17:49 | 14927 | 22 | Veneer Door Frame (Store room Door) (Size at Actual) |  | No. | 20 | 2 | 9.0909
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 66408 | 2023-08-30 17:49 | 16225 | 40 | Veneer Door Frame (Main Door) (Size at Actual) |  | No. | 11 | 29 | 72.5
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 66408 | 2023-08-30 17:49 | 14927 | 32 | Veneer Door Frame (Servant room Door) (Size at Actual) |  | No. | 21 | 11 | 34.375
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 66408 | 2023-08-30 17:49 | 13938.75 | 40 | Veneer Door Shutter (Safety Door) (Size at Actual) |  | No. | 0 | 40 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 66408 | 2023-08-30 17:49 | 17036.25 | 40 | Veneer Door Frame (Safety Door) (Size at Actual) |  | No. | 0 | 40 | 100
GANGA DHAM TOWERS | A Y Enterprises | 66420 | 2023-08-31 13:40 | 35676.71 | 118 | Subway 2.0 WWC Rimless with slim seat cover (5614R201) |  | No. | 71 | 47 | 39.8305
GANGA DHAM TOWERS | NX SAFETY FIRE SERVICES | 66525 | 2023-09-09 12:08 | 236 | 3 | Fire Exting. Refilling ABC 1 Kg |  | No. | 0 | 3 | 100
GANGA DHAM TOWERS | NX SAFETY FIRE SERVICES | 66525 | 2023-09-09 12:08 | 560.5 | 2 | Fire Exting. Refilling ABC 5Kg |  | No. | 0 | 2 | 100
GANGA DHAM TOWERS | NX SAFETY FIRE SERVICES | 66525 | 2023-09-09 12:08 | 678.5 | 2 | Fire Exting. Refilling DCP 6Kg |  | No. | 0 | 2 | 100
GANGA DHAM TOWERS | YASH MARKETING (FIRM) | 66785 | 2023-10-06 16:23 | 113.28 | 125 | Abro Tape 1" |  | Bundle | 40 | 85 | 68
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 1125.72 | 95 | Shower Rose (OHS-1989) |  | No. | 62 | 33 | 34.7368
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 859.04 | 239 | CP Angle Cock OPP-15053PM |  | No. | 0 | 239 | 100
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 2983.5002 | 53 | CP Flush Valve FLV-1085 Square Plate | JAQUAR | No. | 30 | 23 | 43.3962
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 882.64 | 98 | Bib Cock with Wall Flange CON-047KN |  | No. | 60 | 38 | 38.7755
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 890.9 | 100 | Bib Cock with Nosel CON-049NKN |  | No. | 60 | 40 | 40
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 1142.24 | 114 | CP Health Faucet ALD573 |  | No. | 50 | 64 | 56.1404
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 3167.12 | 85 | CP Pillar Cock OPAL Jaquar 15011BPM |  | No. | 67 | 18 | 21.1765
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 453.12 | 306 | Waste Coupling ALD-705L130 |  | No. | 0 | 306 | 100
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 6269.34 | 94 | CP Basin Mixure 15117PM( Opel ) |  | No. | 20 | 74 | 78.7234
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 1401.84 | 522 | Bottle Trap ALD-769L300x190 |  | No. | 80 | 442 | 84.6743
GANGA DHAM TOWERS | SANITARY PARK | 66980 | 2023-10-24 12:13 | 509.76 | 99 | Shower Arm (SHA477) |  | No. | 64 | 35 | 35.3535
GANGA DHAM TOWERS | ABHIKALPAN | 67096 | 2023-11-03 11:11 | 519.2 | 20 | Panel Puller |  | No. | 0 | 20 | 100
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | 67175 | 2023-11-10 16:47 | 4599.994 | 10 | Ready Mix Concrete M-20 Grade |  | Cu.Mtrs | 6.925 | 3.075 | 30.75
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 67240 | 2023-11-22 13:29 | 87.32 | 450 | Plumbing Nails 2.5" |  | Kgs | 350 | 100 | 22.2222
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67241 | 2023-11-22 14:48 | 451.985 | 4 | Encloser Box |  | No. | 0 | 4 | 100
GANGA DHAM TOWERS | YASH MARKETING (FIRM) | 67256 | 2023-11-23 15:18 | 36.58 | 60 | Thermacol 10mm Thick.1mtr X 1m |  | No. | 0 | 60 | 100
GANGA DHAM TOWERS | YASH MARKETING (FIRM) | 67256 | 2023-11-23 15:18 | 1.2745 | 22 | Foam Sheet 3mm thk. (6.5x4) |  | Sq.Ft | 0 | 22 | 100
GANGA DHAM TOWERS | SHREEJI INTERNATIONAL | 67416 | 2023-12-11 14:48 | 247.8 | 100 | Engineering Diary Small |  | No. | 0 | 100 | 100
GANGA DHAM TOWERS | MAIL TECH STATIONERY | 67438 | 2023-12-13 14:36 | 44.84 | 10 | Sani Cubes |  | No. | 0 | 10 | 100
GANGA DHAM TOWERS | MAIL TECH STATIONERY | 67438 | 2023-12-13 14:36 | 70.8 | 6 | Air Freshner |  | No. | 0 | 6 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 67614 | 2024-01-03 18:25 | 206.5 | 467 | Magnetic Catcher - Yale (YMDC-20-SS) - No. | YALE | No. | 0 | 467 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 67614 | 2024-01-03 18:25 | 206.5 | 119 | Magnetic Catcher Yale (YMDC-20-SS) | YALE | No. | 110 | 9 | 7.563
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 67618 | 2024-01-04 12:04 | 65 | 100 | Bougain Villa Milli |  | No. | 0 | 100 | 100
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 67618 | 2024-01-04 12:04 | 45 | 350 | Tecoma Gaudichavadi |  | No. | 200 | 150 | 42.8571
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 67618 | 2024-01-04 12:04 | 265 | 55 | Buddha Belly Bamboo |  | No. | 0 | 55 | 100
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 67618 | 2024-01-04 12:04 | 850 | 5 | Shita ashok - No. |  | No. | 3 | 2 | 40
GANGA DHAM TOWERS | SUNSHINE ASSOCIATES | 67740 | 2024-01-17 14:38 | 156.94 | 100 | Potato Greece |  | Kgs | 0 | 100 | 100
GANGA DHAM TOWERS | OSWAL GRANITE | 67819 | 2024-01-30 10:20 | 200.6 | 3571.35 | Black Granite (Shot Blasted) |  | Sq.Ft | 3552.1656 | 19.1844 | 0.5372
GANGA DHAM TOWERS | SHRUSHTI FLORALS | 67892 | 2024-02-07 10:46 | 20 | 500 | Compost |  | Kgs | 0 | 500 | 100
GANGA DHAM TOWERS | SUNSHINE ASSOCIATES | 67898 | 2024-02-07 11:40 | 236 | 40 | Grease EP2 |  | Kgs | 36 | 4 | 10
GANGA DHAM TOWERS | MEGAPOWER SOLUTIONS PRIVATE LIMITED | 67925 | 2024-02-09 19:04 | 7622.8 | 1 | Head, Piston, Chamber Dismantle & assemble |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | MEGAPOWER SOLUTIONS PRIVATE LIMITED | 67925 | 2024-02-09 19:04 | 3363 | 1 | Transport Charges |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | OSWAL GRANITE | 67982 | 2024-02-14 19:06 | 126.26 | 400 | Candy white leather finish |  | Sq.Ft | 395.96 | 4.04 | 1.01
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 68170 | 2024-03-13 11:20 | 4263.4993 | 464.68 | Sand-Metal Mix M60 hi-flow (Pumpable) |  | Cu.Mtrs | 252.5 | 212.18 | 45.6615
GANGA DHAM TOWERS | BHAWANI CHEMTECH | 68174 | 2024-03-13 13:17 | 8.26 | 120.0006 | HCL Acid |  | Ltrs | 120 | 0.0006 | 0.0005
GANGA DHAM TOWERS | OSWAL GRANITE | 68212 | 2024-03-18 18:01 | 106.2 | 593.52 | Sadharalli Polish granite |  | Sq.Ft | 589.2 | 4.32 | 0.7279
GANGA DHAM TOWERS | SA BUILDING SOLUTIONS | 68214 | 2024-03-18 18:35 | 65.52 | 1570.67 | AAC Block 650x240x100 - No. |  | No. | 1570 | 0.67 | 0.0427
GANGA DHAM TOWERS | LEO ASSOCIATES | 68260 | 2024-03-22 12:46 | 224.2 | 160.0679 | Hackad Plast Chemical | CHOKSEY | Ltrs | 160 | 0.0679 | 0.0424
GANGA DHAM TOWERS | DATTAGURU ENTERPRISES | 68328 | 2024-03-30 11:44 | 60.9 | 3791.26 | M Sand |  | Cu.Ft | 2166 | 1625.26 | 42.8686
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 68369 | 2024-04-06 10:20 | 14927 | 79 | Veneer Door Frame (Servant room Door) (Size at Actual) |  | No. | 12 | 67 | 84.8101
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 68369 | 2024-04-06 10:20 | 12213 | 77 | Veneer Door Shutter (Servant room Door) (Size at Actual) |  | No. | 12 | 65 | 84.4156
GANGA DHAM TOWERS | BLUE TECHNOLOGIES COMPANY | 68384 | 2024-04-06 18:35 | 7847 | 1 | Removal Charges |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | SA BUILDING SOLUTIONS | 68403 | 2024-04-10 15:08 | 1900.0017 | 45.48 | Broken Siporex Blocks |  | Metric Tonnes | 16.79 | 28.69 | 63.0827
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | 68404 | 2024-04-10 18:27 | 4977.0051 | 7.85 | Ready Mix Concrete M25 Regular Downpour |  | Cu.Mtrs | 5.5 | 2.35 | 29.9363
GANGA DHAM TOWERS | CENTER STONE PRIVATE LIMITED | 68405 | 2024-04-10 19:15 | 343.38 | 2188.58 | Silky Grey Marble |  | Sq.Ft | 1225.08 | 963.5 | 44.024
GANGA DHAM TOWERS | M B SALES CORPORATION | 68413 | 2024-04-11 15:33 | 180.8527 | 864 | ASTM Brass MTA 32mm | PRINCE | No. | 764 | 100 | 11.5741
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68416 | 2024-04-11 18:08 | 23.364 | 100 | PVC Conduit Bend 1.1/4" |  | No. | 0 | 100 | 100
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 68423 | 2024-04-12 17:23 | 62.3453 | 15000 | Steel Bars 16mm | UMA FE 550D/PUSHPA FE 550D | Kgs | 14990 | 10 | 0.0667
GANGA DHAM TOWERS | CLASSIK MARBLE AND GRANITE | 68440 | 2024-04-13 18:40 | 70.8 | 1464.08 | Kota Tappa 60"x12" (59"x11") |  | Sq.Ft | 1460 | 4.08 | 0.2787
GANGA DHAM TOWERS | DATTAGURU ENTERPRISES | 68442 | 2024-04-15 11:19 | 8.736 | 9000.0024 | Red Bricks 4" |  | No. | 8850 | 150.0024 | 1.6667
GANGA DHAM TOWERS | AGARWAL AGENCIES | 68467 | 2024-04-17 14:43 | 35 | 701 | Aqua water -20lit |  | No. | 539 | 162 | 23.1098
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 68504 | 2024-04-20 15:44 | 16225 | 37 | Veneer Door Frame (Main Door) (Size at Actual) |  | No. | 30 | 7 | 18.9189
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 68504 | 2024-04-20 15:44 | 13275 | 66 | Veneer Door Shutter (Main Door) (Size at Actual) |  | No. | 30 | 36 | 54.5455
GANGA DHAM TOWERS | DEV SAFETY PRODUCTS | 68586 | 2024-05-04 11:04 | 225.75 | 30 | Safety Jacket |  | No. | 0 | 30 | 100
GANGA DHAM TOWERS | DEV SAFETY PRODUCTS | 68586 | 2024-05-04 11:04 | 159.3 | 30 | Helmet Yellow for Labours |  | No. | 0 | 30 | 100
GANGA DHAM TOWERS | ORIENT CEMENT LIMITED. | 68613 | 2024-05-08 12:28 | 7800 | 34.72 | Cement Loose 53 Grade | BIRLA A1 OPC 53 | Metric Tonnes | 0 | 34.72 | 100
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 68622 | 2024-05-08 18:24 | 18 | 2300 | Taiwan Lawn |  | Sq.Ft | 2090 | 210 | 9.1304
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 68622 | 2024-05-08 18:24 | 15 | 180 | Roeo |  | No. | 0 | 180 | 100
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 68622 | 2024-05-08 18:24 | 950 | 6 | Terinalia Metallica |  | No. | 3 | 3 | 50
GANGA DHAM TOWERS | SHRUSHTI ROPE VATIKA | 68622 | 2024-05-08 18:24 | 20 | 100 | Varnonia |  | No. | 0 | 100 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68646 | 2024-05-11 16:44 | 1338.12 | 62 | 15W HLR-2973 |  | No. | 0 | 62 | 100
GANGA DHAM TOWERS | JAYLEELA AGENCIES | 68655 | 2024-05-14 18:42 | 4121.326 | 5 | RCC Chamber 600x900 Cover With Frame (Heavy Duty) |  | No. | 0 | 5 | 100
GANGA DHAM TOWERS | TECHNOVISION ENERGY PVT LTD | 68665 | 2024-05-16 13:41 | 138650 | 1 | Online Ups 30KVA (3ph-I/P/3ph O/P, 360VDC) |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 68704 | 2024-05-20 18:52 | 3823.4994 | 22.9 | Sand-Metal Mix M15 (Downpour) |  | Cu.Mtrs | 18 | 4.9 | 21.3974
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 68714 | 2024-05-22 11:18 | 3823.5 | 10 | Sand-Metal Mix M15 (Downpour) |  | Cu.Mtrs | 8 | 2 | 20
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 68714 | 2024-05-22 11:18 | 3824.001 | 5.42 | Sand-Metal Mix M25 (Downpour) |  | Cu.Mtrs | 4 | 1.42 | 26.1993
GANGA DHAM TOWERS | KANHAIYA ENTERPRISES | 68724 | 2024-05-23 15:06 | 3540 | 1 | Clamp digital multi meter |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | SONA MARBLE | 68789 | 2024-05-28 17:24 | 22.05 | 4916.945 | Kota Skirting Polished 24"x3" (23"x3") |  | R.Ft | 4424 | 492.945 | 10.0254
GANGA DHAM TOWERS | ABHUVA INNOVATION PRIVATE LIMITED | 68792 | 2024-05-29 12:03 | 174.64 | 66 | GFRP Bars 8mm |  | Kgs | 33 | 33 | 50
GANGA DHAM TOWERS | ULTRATECH CEMENT LTD | 68809 | 2024-05-30 17:38 | 7400 | 140 | Cement Loose 53 Grade | ULTRATECH OPC 53 | Metric Tonnes | 113.68 | 26.32 | 18.8
GANGA DHAM TOWERS | LEO ASSOCIATES | 68836 | 2024-06-03 11:47 | 224.2 | 209.28 | Hackad Plast Chemical | CHOKSEY | Ltrs | 200 | 9.28 | 4.4343
GANGA DHAM TOWERS | AQUAPROOF & ANCHORING SYSTEMS | 68837 | 2024-06-03 11:50 | 20.65 | 500 | GP2 Waterproofing Chemical | FOSROCK | Kgs | 480 | 20 | 4
GANGA DHAM TOWERS | AQUAPROOF & ANCHORING SYSTEMS | 68837 | 2024-06-03 11:50 | 1056.1 | 241.72 | Bioflex Grey |  | Bags | 241 | 0.72 | 0.2979
GANGA DHAM TOWERS | M B SALES CORPORATION | 68840 | 2024-06-03 16:12 | 1251.7438 | 21 | RCC Round Ch. Cover 24" (MD) |  | No. | 20 | 1 | 4.7619
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 68868 | 2024-06-06 12:54 | 65.667 | 5000 | Steel Bars 8mm | PUSHPA FE 550 D | Kgs | 4940 | 60 | 1.2
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 68868 | 2024-06-06 12:54 | 63.8616 | 10000 | Steel Bars 20mm | PUSHPA FE 550 D | Kgs | 9810 | 190 | 1.9
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 68869 | 2024-06-06 13:01 | 63.8616 | 10000 | Steel Bars 10mm | PUSHPA FE 550 D | Kgs | 9780 | 220 | 2.2
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 68873 | 2024-06-06 14:45 | 65.667 | 15000 | Steel Bars 8mm | PUSHPA FE 550 D | Kgs | 14960 | 40 | 0.2667
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 68873 | 2024-06-06 14:45 | 63.8616 | 10000 | Steel Bars 16mm | PUSHPA FE 550 D | Kgs | 9930 | 70 | 0.7
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | 68896 | 2024-06-09 12:06 | 5952.9938 | 226.0173 | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash |  | Cu.Mtrs | 174 | 52.0173 | 23.0147
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68908 | 2024-06-11 11:37 | 188.6013 | 2000 | PVC Copper Wire 16 Sqmm Blue | R R KABEL | Mtrs | 1500 | 500 | 25
GANGA DHAM TOWERS | WEATHER CONTROLLING SOLUTIONS INDIA PRIVATE LIMITED | 68910 | 2024-06-11 12:37 | 35568.64 | 176 | Split AC 1.5 TR (RAS-18SKCV3SG-IN + RAS-18SACV3SG-IN) |  | No. | 0 | 176 | 100
GANGA DHAM TOWERS | WEATHER CONTROLLING SOLUTIONS INDIA PRIVATE LIMITED | 68910 | 2024-06-11 12:37 | 30327.04 | 85 | Split AC 1 TR (RAS-13SKCV3SG-IN + RAS-13SACV3SG-IN) |  | No. | 0 | 85 | 100
GANGA DHAM TOWERS | WEATHER CONTROLLING SOLUTIONS INDIA PRIVATE LIMITED | 68910 | 2024-06-11 12:37 | 44304.64 | 74 | Split AC 2 TR (RAS-24SKCV3SG-IN + RAS-24SACV3SG-IN) |  | No. | 0 | 74 | 100
GANGA DHAM TOWERS | KANAD ELECTRICAL SERVICES | 68913 | 2024-06-11 14:04 | 605340 | 1 | Distribution Panel |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 68966 | 2024-06-17 13:03 | 3823.4996 | 50 | Sand-Metal Mix M15 (Downpour) |  | Cu.Mtrs | 18 | 32 | 64
GANGA DHAM TOWERS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68982 | 2024-06-18 18:26 | 135.346 | 200 | CP Extension Piece 3/4" |  | No. | 0 | 200 | 100
GANGA DHAM TOWERS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68982 | 2024-06-18 18:26 | 921.816 | 1423 | Floor Drain Pop Up (Art#45218) |  | No. | 325 | 1098 | 77.1609
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68986 | 2024-06-19 12:53 | 557.6975 | 300 | Copper Flexi. cable10sqmmx4cor |  | Mtrs | 0 | 300 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68986 | 2024-06-19 12:53 | 45.6413 | 200 | PVC Copper Wire 4 Sqmm red |  | Mtrs | 0 | 200 | 100
GANGA DHAM TOWERS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68996 | 2024-06-20 15:39 | 651.124 | 240 | Waste coupling Pop Up Brass 1.25"x3"( Viking - 5224) |  | No. | 40 | 200 | 83.3333
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 12213 | 142 | Veneer Door Shutter (Bedroom Door) (Size at Actual) |  | No. | 0 | 142 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 12213 | 18 | Veneer Door Shutter (Kitchen room Door) (Size at Actual) |  | No. | 0 | 18 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 14927 | 196 | Veneer Door Frame (Toilet Door) (Size at Actual) |  | No. | 0 | 196 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 12213 | 42 | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | No. | 0 | 42 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 12213 | 196 | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | No. | 0 | 196 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 14927 | 42 | Veneer Door Frame (Dry Balcony Door) (Size at Actual) |  | No. | 0 | 42 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 14927 | 18 | Veneer Door Frame (Kitchen room Door) (Size at Actual) |  | No. | 0 | 18 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 14927 | 6 | Veneer Door Frame (Store room Door) (Size at Actual) |  | No. | 0 | 6 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 12213 | 25 | Veneer Door Shutter (Servant room Door) (Size at Actual) |  | No. | 0 | 25 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 14927 | 25 | Veneer Door Frame (Servant room Door) (Size at Actual) |  | No. | 0 | 25 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 12213 | 6 | Veneer Door Shutter (Store room Door) (Size at Actual) |  | No. | 0 | 6 | 100
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69001 | 2024-06-20 19:18 | 14927 | 142 | Veneer Door Frame (Bedroom Door) (Size at Actual) |  | No. | 0 | 142 | 100
GANGA DHAM TOWERS | AQUAPROOF & ANCHORING SYSTEMS | 69009 | 2024-06-21 15:06 | 46.02 | 5000 | Wall Tie 200 mm |  | No. | 4000 | 1000 | 20
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69027 | 2024-06-22 18:30 | 59.911 | 3500 | Steel Bars 10mm | PUSHPA FE 550 D | Kgs | 3220 | 280 | 8
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69028 | 2024-06-22 18:42 | 59.911 | 15000 | Steel Bars 10mm | PUSHPA FE 550 D | Kgs | 14960 | 40 | 0.2667
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69030 | 2024-06-22 18:56 | 59.911 | 7000 | Steel Bars 10mm | PUSHPA FE 550 D | Kgs | 6900 | 100 | 1.4286
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 69033 | 2024-06-24 11:33 | 2.36 | 1260 | Nut 8mm with washer |  | No. | 0 | 1260 | 100
GANGA DHAM TOWERS | GAJANAN SUPPLIERS | 69043 | 2024-06-25 14:41 | 20 | 5000 | POYTA SOIL |  | Cu.Ft | 702 | 4298 | 85.96
GANGA DHAM TOWERS | GREENCON INFRATECH SOLUTIONS | 69045 | 2024-06-25 15:33 | 1103.3 | 71 | Pull Handle 25mm - Yale (YEH-11A-300) | YALE | Pair | 35 | 36 | 50.7042
GANGA DHAM TOWERS | RTECH ENTERPRISES. | 69048 | 2024-06-25 17:41 | 31186.22 | 7 | 2MP IP Camera |  | No. | 0 | 7 | 100
GANGA DHAM TOWERS | RTECH ENTERPRISES. | 69048 | 2024-06-25 17:41 | 354000 | 1 | Biometric Access System |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69053 | 2024-06-26 18:57 | 63.8616 | 1060 | Steel Bars 16mm | PUSHPA FE 550 D | Kgs | 280 | 780 | 73.5849
GANGA DHAM TOWERS | M B SALES CORPORATION | 69072 | 2024-07-01 12:09 | 687.4114 | 255 | ASTM Pipe 50mm x 10 Fts |  | No. | 200 | 55 | 21.5686
GANGA DHAM TOWERS | M B SALES CORPORATION | 69072 | 2024-07-01 12:09 | 32.6801 | 206 | ASTM Socket 2" |  | No. | 110 | 96 | 46.6019
GANGA DHAM TOWERS | M B SALES CORPORATION | 69072 | 2024-07-01 12:09 | 464.0233 | 30 | SWR Silent Shoe Bend 6" (2275806) - No. |  | No. | 0 | 30 | 100
GANGA DHAM TOWERS | ASH CONCEPTS | 69073 | 2024-07-01 13:17 | 9.52 | 1867.056 | FlyAsh Bricks 3"x6"x9" |  | No. | 1867 | 0.056 | 0.003
GANGA DHAM TOWERS | ASH CONCEPTS | 69091 | 2024-07-03 12:54 | 8.064 | 14720.112 | FlyAsh Bricks 3"x4"x9" |  | No. | 5705.495 | 9014.617 | 61.2401
GANGA DHAM TOWERS | ASH CONCEPTS | 69091 | 2024-07-03 12:54 | 9.52 | 15732.344 | FlyAsh Bricks 3"x6"x9" |  | No. | 15732 | 0.344 | 0.0022
GANGA DHAM TOWERS | M B SALES CORPORATION | 69124 | 2024-07-05 16:38 | 576.95 | 10 | Silent plug bend 160mm |  | No. | 0 | 10 | 100
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 69127 | 2024-07-05 18:05 | 277.3001 | 82.85 | Tag |  | Kgs | 13 | 69.85 | 84.309
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69158 | 2024-07-08 11:05 | 550.116 | 608 | HYBEC Surface Panel Light 8 Watt EB -9672 |  | No. | 0 | 608 | 100
GANGA DHAM TOWERS | MAHALAXMI ENTERPRISES | 69166 | 2024-07-08 15:16 | 68.25 | 1446.1493 | M Sand |  | Cu.Ft | 646 | 800.1493 | 55.3296
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | 69173 | 2024-07-08 18:27 | 6218.4938 | 213.91 | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash |  | Cu.Mtrs | 101 | 112.91 | 52.7839
GANGA DHAM TOWERS | MAHALAXMI ENTERPRISES | 69175 | 2024-07-08 20:00 | 37.8 | 3502.5025 | Crush Sand |  | Cu.Ft | 1471 | 2031.5025 | 58.0015
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | 69176 | 2024-07-08 20:02 | 5208.4962 | 50.17 | Ready Mix Concrete M-15 Grade( PUMPABLE) |  | Cu.Mtrs | 40 | 10.17 | 20.2711
GANGA DHAM TOWERS | MAHALAXMI ENTERPRISES | 69179 | 2024-07-09 11:16 | 34.65 | 1893.1138 | Aggregate 1/2 Inch |  | Cu.Ft | 790 | 1103.1138 | 58.2698
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69186 | 2024-07-09 18:14 | 59.911 | 500 | Steel Bar 25mm |  | Kgs | 100 | 400 | 80
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69186 | 2024-07-09 18:14 | 59.911 | 578.16 | Steel Bars 20mm |  | Kgs | 20 | 558.16 | 96.5407
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69186 | 2024-07-09 18:14 | 61.7151 | 145.7 | Steel Bars 8mm |  | Kgs | 40 | 105.7 | 72.5463
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69206 | 2024-07-11 10:23 | 57.8932 | 11500 | Steel Bars 16mm | PUSHPA FE 550 D | Kgs | 11370 | 130 | 1.1304
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69207 | 2024-07-11 10:29 | 59.6986 | 19850 | Steel Bars 8mm | PUSHPA FE 550 D | Kgs | 19690 | 160 | 0.806
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69207 | 2024-07-11 10:29 | 57.8932 | 7970 | Steel Bars 10mm | PUSHPA FE 550 D | Kgs | 7640 | 330 | 4.1405
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69207 | 2024-07-11 10:29 | 57.8932 | 7380 | Steel Bars 12mm | PUSHPA FE 550 D | Kgs | 7320 | 60 | 0.813
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69207 | 2024-07-11 10:29 | 57.8932 | 8660 | Steel Bars 16mm | PUSHPA FE 550 D | Kgs | 8460 | 200 | 2.3095
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69207 | 2024-07-11 10:29 | 57.8932 | 13320 | Steel Bars 20mm | PUSHPA FE 550 D | Kgs | 13210 | 110 | 0.8258
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69207 | 2024-07-11 10:29 | 57.8932 | 11720 | Steel Bar 25mm | PUSHPA FE 550 D | Kgs | 11690 | 30 | 0.256
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69211 | 2024-07-11 11:47 | 59.6986 | 23160 | Steel Bars 8mm | PUSHPA FE 550 D | Kgs | 22940 | 220 | 0.9499
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69211 | 2024-07-11 11:47 | 57.8932 | 10000 | Steel Bars 10mm | PUSHPA FE 550 D | Kgs | 9790 | 210 | 2.1
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69211 | 2024-07-11 11:47 | 57.8932 | 34000 | Steel Bars 12mm | PUSHPA FE 550 D | Kgs | 33810 | 190 | 0.5588
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69211 | 2024-07-11 11:47 | 57.8932 | 14500 | Steel Bars 20mm | PUSHPA FE 550 D | Kgs | 14470 | 30 | 0.2069
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69211 | 2024-07-11 11:47 | 57.8932 | 7500 | Steel Bar 25mm | PUSHPA FE 550 D | Kgs | 7480 | 20 | 0.2667
GANGA DHAM TOWERS | RUDDRAH VENTURES LLP | 69211 | 2024-07-11 11:47 | 59.6986 | 5000 | Steel Bars 32mm | PUSHPA FE 550 D | Kgs | 4940 | 60 | 1.2
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69228 | 2024-07-12 10:39 | 4462.9996 | 166.8625 | Sand-Metal Mix M50 Easycrete (Pumpable) |  | Cu.Mtrs | 84.6575 | 82.205 | 49.2651
GANGA DHAM TOWERS | DARLESHA HARDWARE | 69231 | 2024-07-12 16:33 | 571.416 | 10 | Pad Lock Small |  | No. | 0 | 10 | 100
GANGA DHAM TOWERS | AVDHOOT GALVANIZING LLP | 69251 | 2024-07-13 18:59 | 94.4 | 100 | GI Earthing Patti 25mm x 3mm |  | Kgs | 0 | 100 | 100
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | 2024-07-14 00:16 | 4248.0001 | 86.374 | Sand-Metal Mix M25 (Pumpable) |  | Cu.Mtrs | 36 | 50.374 | 58.3208
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69261 | 2024-07-15 15:19 | 4462.9995 | 303.095 | Sand-Metal Mix M50 Easycrete (Pumpable) |  | Cu.Mtrs | 44.5 | 258.595 | 85.3181
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69264 | 2024-07-15 17:29 | 22.5262 | 140.9 | PVC Conduit Pipe 1" mtrs | GREATWHITE | Mtrs | 140 | 0.9 | 0.6388
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | 2024-07-15 18:27 | 4022.9998 | 31.995 | Sand-Metal Mix M25 (Downpour) |  | Cu.Mtrs | 18.5 | 13.495 | 42.1785
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69273 | 2024-07-16 15:09 | 4237.9998 | 18.4655 | Sand-Metal Mix M50 Easycrete (Downpour) |  | Cu.Mtrs | 6 | 12.4655 | 67.507
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 119.15 | 888.1 | PVC Copper Wire 10 Sqmm black |  | Mtrs | 0 | 888.1 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 119.15 | 888.1 | PVC Copper Wire 10 Sqmm blue |  | Mtrs | 0 | 888.1 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 119.15 | 888.1 | PVC Copper Wire 10 Sqmm red |  | Mtrs | 0 | 888.1 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 119.15 | 888.1 | PVC Copper Wire 10 Sqmm yellow |  | Mtrs | 0 | 888.1 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 29.6912 | 9007 | PVC Copper Wire 2.5 Sqmm black |  | Mtrs | 9000 | 7 | 0.0777
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 29.6912 | 5860.32 | PVC Copper Wire 2.5 Sqmm green |  | Mtrs | 5860 | 0.32 | 0.0055
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 29.6912 | 10642.32 | PVC Copper Wire 2.5 Sqmm yellow |  | Mtrs | 6000 | 4642.32 | 43.6213
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 45.6413 | 2252.48 | PVC Copper Wire 4 Sqmm black |  | Mtrs | 2252 | 0.48 | 0.0213
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 45.6414 | 400 | PVC Copper Wire 4 Sqmm green |  | Mtrs | 0 | 400 | 100
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69283 | 2024-07-17 17:09 | 21.0701 | 14555 | RG-6 Co-Axial Cable |  | Mtrs | 0 | 14555 | 100
GANGA DHAM TOWERS | A Y Enterprises | 69296 | 2024-07-18 17:03 | 129.8 | 570 | Rubber washer for commode 1-1/4" |  | No. | 0 | 570 | 100
GANGA DHAM TOWERS | DEV SAFETY PRODUCTS | 69308 | 2024-07-20 15:14 | 3363 | 2 | Wire Rope Sling 2.5MT 1mtr-16sqmm |  | No. | 0 | 2 | 100
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 69310 | 2024-07-20 16:54 | 1239 | 24 | Tenax Transparent Solid 1.5Kg |  | set | 0 | 24 | 100
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 69310 | 2024-07-20 16:54 | 843.7 | 62 | Tenax Creama Solid 1.5kg Set |  | set | 0 | 62 | 100
GANGA DHAM TOWERS | SEJAL ENTERPRISES | 69310 | 2024-07-20 16:54 | 3421.9994 | 16.5109 | Feviquick |  | Kgs | 16.5 | 0.0109 | 0.066
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | 69314 | 2024-07-20 18:31 | 5658.001 | 76.72 | Ready Mix Concrete M25 Regular Pumpable |  | Cu.Mtrs | 14 | 62.72 | 81.7518
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69317 | 2024-07-22 13:48 | 4022.9978 | 27 | Sand-Metal Mix M35 (Downpour) |  | Cu.Mtrs | 19 | 8 | 29.6296
GANGA DHAM TOWERS | SAR INFOTECH | 69321 | 2024-07-23 11:23 | 56640 | 1 | LAPTOP |  | No. | 0 | 1 | 100
GANGA DHAM TOWERS | SAR INFOTECH | 69321 | 2024-07-23 11:23 | 27848 | 2 | Printer |  | No. | 0 | 2 | 100
GANGA DHAM TOWERS | MAHALAXMI ENTERPRISES | 69322 | 2024-07-23 11:24 | 34.65 | 2343.1491 | Aggregate 1/2 Inch |  | Cu.Ft | 0 | 2343.1491 | 100
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | 2024-07-23 17:50 | 4022.9999 | 54.7 | Sand-Metal Mix M25 (Downpour) |  | Cu.Mtrs | 10.942 | 43.758 | 79.9963
GANGA DHAM TOWERS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69337 | 2024-07-26 17:08 | 45.6414 | 148.09 | PVC Copper Wire 4 Sqmm black | R R KABEL | Mtrs | 148 | 0.09 | 0.0608
GANGA DHAM TOWERS | PROTON READY MIX CONCRETE PRIVATE LIMITED | 69341 | 2024-07-27 15:36 | 5157.0957 | 70 | Ready Mix Concrete M-15 Grade( PUMPABLE) |  | Cu.Mtrs | 35.5 | 34.5 | 49.2857
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | 2024-07-27 17:52 | 4248 | 26.45 | Sand-Metal Mix M25 (Pumpable) |  | Cu.Mtrs | 0 | 26.45 | 100