## Short_Supply_POwise638578694949
Short Supply Report
From 01-11-2023 To 29-07-2024
Page 1 of 1
Total Records: 284 Records 1 To 284
Project Name | Supplier Name | PO Sr No | PO Date | Rate | PO Qty | Material Name | Brand | Unit | Recd Qty | Bal Qty | Bal %
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67069 | 2023-11-01 15:25 | 165.2 | 111 | Metal Bulkhead (In-Built LED) 12 WAtt - No. |  | No. | 101 | 10 | 9.009
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 67118 | 2023-11-06 11:52 | 94.4004 | 24.016 | Conplast WL Fosroc (20 lit/Bucket) |  | Ltrs | 0 | 24.016 | 100
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 67118 | 2023-11-06 11:52 | 171.1 | 570 | Shuttering oil-oil based |  | Ltrs | 470 | 100 | 17.5439
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 24.2962 | 120 | PVC Elbow 50mm | PRINCE | No. | 3 | 117 | 97.5
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 7.598 | 1 | PVC Socket 11/4" | PRINCE | No. | 0 | 1 | 100
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 110.1883 | 153.5 | PVC Pipe 11/4"x10 ft | PRINCE | No. | 153 | 0.5 | 0.3257
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 22.2433 | 3 | PVC Bend 1.5" (50mm) | PRINCE | No. | 0 | 3 | 100
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 262.1252 | 175.6 | PVC Pipe 2" x 10 ft S/S | PRINCE | No. | 175 | 0.6 | 0.3417
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 142.184 | 161.5 | ASTM Pipe 1/2" x 10 fts | PRINCE | No. | 161 | 0.5 | 0.3096
GANGA ALTUS | PRINCE DISTRIBUTOR | 67176 | 2023-11-10 16:52 | 166.144 | 21.8 | PVC Solvent (500 ml.) - | NEOSEAL | No. | 21 | 0.8 | 3.6697
GANGA ALTUS | SEJAL ENTERPRISES | 67222 | 2023-11-20 17:42 | 84.96 | 240 | Abro Tape 2" |  | Bundle | 0 | 240 | 100
GANGA ALTUS | YASH MARKETING (FIRM) | 67229 | 2023-11-21 16:29 | 73.16 | 1500 | Binding Wire |  | Kgs | 0 | 1500 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 67279 | 2023-11-25 15:44 | 4199.9977 | 7.82 | Ready Mix Concrete M-15 Downpour |  | Cu.Mtrs | 7 | 0.82 | 10.4859
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 67303 | 2023-11-28 12:18 | 2584.2 | 2 | Pharma (Vol- 1 cft) |  | No. | 0 | 2 | 100
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 67303 | 2023-11-28 12:18 | 6490 | 2 | Tray |  | No. | 0 | 2 | 100
GANGA ALTUS | YASH MARKETING (FIRM) | 67342 | 2023-12-05 11:56 | 1.2744 | 3500 | Foam Sheet 3mm thk. (6.5x4) |  | Sq.Ft | 3492 | 8 | 0.2286
GANGA ALTUS | YASH MARKETING (FIRM) | 67389 | 2023-12-09 13:16 | 5.31 | 13000 | Plastic Hollow Sheet 6.5x4 |  | Sq.Ft | 12984 | 16 | 0.1231
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67395 | 2023-12-09 15:54 | 62.1267 | 6 | 3 Module C1 1103 Support Frame with Cover Plate | VINAY | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67395 | 2023-12-09 15:54 | 20.1779 | 47 | Blank Plate (1036) - No. | VINAY | No. | 0 | 47 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67398 | 2023-12-09 17:24 | 1748.48 | 3 | 63 Amp 4 Pole MCB (408683) | LEGRAND | No. | 0 | 3 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67398 | 2023-12-09 17:24 | 4541.678 | 10 | RCCB 63 Amp. 4P 30ma (411898) |  | No. | 0 | 10 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67402 | 2023-12-09 18:25 | 27.7775 | 8 | 6A One way Switch (1001) | VINAY | No. | 0 | 8 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 67405 | 2023-12-09 18:49 | 4999.9986 | 7.29 | Ready Mix Concrete M-35 Grade (Downpour) |  | Cu.Mtrs | 7 | 0.29 | 3.9781
GANGA ALTUS | SHREEJI INTERNATIONAL | 67414 | 2023-12-11 13:05 | 247.8 | 100 | Engineering Diary Small |  | No. | 0 | 100 | 100
GANGA ALTUS | SHANTI SALES | 67426 | 2023-12-11 19:25 | 348.1 | 255 | RCC NP2 Class Pipe 10" |  | Mtrs | 254 | 1 | 0.3922
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 67433 | 2023-12-13 10:47 | 295 | 170 | Satin Matt Paint | DULUX | Ltrs | 60 | 110 | 64.7059
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 67433 | 2023-12-13 10:47 | 184.493 | 140 | Solvent Base Primer |  | Ltrs | 20 | 120 | 85.7143
GANGA ALTUS | ABHA CORPORATION | 67482 | 2023-12-18 11:11 | 47.2 | 33 | Fan Rod 1Ft6" |  | No. | 32 | 1 | 3.0303
GANGA ALTUS | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 67562 | 2023-12-26 14:31 | 24544 | 32 | Fire door with shutter 1100x2400mm Single Leaf - No. |  | No. | 19 | 13 | 40.625
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 67575 | 2023-12-29 11:29 | 113.4924 | 2329.24 | Primer (Water base) |  | Ltrs | 1600 | 729.24 | 31.3081
GANGA ALTUS | SHANTI SALES | 67581 | 2023-12-29 13:06 | 271.4 | 5 | Hold Tite (1 Kgs) |  | Kgs | 0 | 5 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 67604 | 2024-01-02 15:04 | 4949.9946 | 4.02 | Ready Mix Concrete M-30 Grade FF (Downpour) |  | Cu.Mtrs | 3 | 1.02 | 25.3731
GANGA ALTUS | SHREEJI INTERNATIONAL | 67605 | 2024-01-02 16:37 | 708 | 30 | ORGANISER |  | No. | 0 | 30 | 100
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 67641 | 2024-01-05 15:21 | 2584.2 | 6 | Pharma (Vol- 1 cft) |  | No. | 2 | 4 | 66.6667
GANGA ALTUS | GURUKRUPA TRADERS | 67648 | 2024-01-05 18:14 | 8024 | 15 | Halogen Lamp 500 Watts |  | No. | 10 | 5 | 33.3333
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67711 | 2024-01-12 16:35 | 1222.15 | 2 | 32amp TPN MCB 408680 | LEGRAND | No. | 0 | 2 | 100
GANGA ALTUS | V H ENTERPRISES | 67716 | 2024-01-13 11:07 | 3427.3107 | 15 | 4 Way TPN DB DD 8 WAY In comer 1.2 Thick with TV Tele. |  | No. | 14 | 1 | 6.6667
GANGA ALTUS | LEO ASSOCIATES | 67760 | 2024-01-18 14:35 | 224.2 | 6 | Hackad Plast Chemical | CHOKSEY | Ltrs | 5.58 | 0.42 | 7
GANGA ALTUS | SEJAL ENTERPRISES | 67772 | 2024-01-20 11:47 | 212.4 | 10 | Tag |  | Kgs | 0 | 10 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 54.28 | 3000 | Cat-6 Lan Cable |  | Mtrs | 0 | 3000 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 16826.8 | 4 | HARD DISK |  | No. | 0 | 4 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 455.95 | 2 | HDMI Cables |  | No. | 0 | 2 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 2279.76 | 10 | 2MP IP Dome camera |  | No. | 0 | 10 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 3365.36 | 4 | 2MP IP Bullet 6MM Lens |  | No. | 0 | 4 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 13135.76 | 2 | 32 Channel NVR CP PLUS |  | No. | 0 | 2 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 4179.56 | 8 | 8+2 POE Switch |  | No. | 0 | 8 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 21712 | 1 | Installation Charges |  | No. | 0 | 1 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 54.28 | 64 | Junction Box |  | No. | 0 | 64 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 15176.68 | 1 | Monitor LED |  | No. | 0 | 1 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 1248.44 | 7 | 2U Rack - No. |  | No. | 0 | 7 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 7924.88 | 1 | 15U Rack |  | No. | 0 | 1 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67799 | 2024-01-25 15:13 | 2334.04 | 50 | 2MP IP Bullet camera |  | No. | 0 | 50 | 100
GANGA ALTUS | NPLUS1 TECHNOLOGIES PRIVATE LIMITED | 67811 | 2024-01-29 14:32 | 28.025 | 320 | Cat-6 Lan Cable |  | Mtrs | 305 | 15 | 4.6875
GANGA ALTUS | SHANTI SALES | 67832 | 2024-02-02 10:15 | 2.124 | 96 | GI Clips 1/2" |  | No. | 0 | 96 | 100
GANGA ALTUS | SHANTI SALES | 67832 | 2024-02-02 10:15 | 271.4004 | 22.38 | Hold Tite (1 Kgs) |  | Kgs | 0 | 22.38 | 100
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | 67855 | 2024-02-03 12:26 | 14.75 | 7905.816 | Wall Putty (Rakshak) Cement Based |  | Kgs | 7905 | 0.816 | 0.0103
GANGA ALTUS | LEO ASSOCIATES | 67858 | 2024-02-03 12:50 | 224.2 | 300.96 | Hackad Plast Chemical | CHOKSEY | Ltrs | 300 | 0.96 | 0.319
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 67859 | 2024-02-03 12:55 | 113.4924 | 786.3205 | Primer (Water base) |  | Ltrs | 600 | 186.3205 | 23.6952
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 67859 | 2024-02-03 12:55 | 43.3331 | 2941.8017 | OBD PAINT WHITE COLOUR - |  | Ltrs | 2261.68 | 680.1217 | 23.1192
GANGA ALTUS | T K ENTERPRISES | 67881 | 2024-02-06 11:03 | 29264 | 1 | Bosch GSH 5 5kg Breaker & Chipper Machine (Heavy Duty) |  | No. | 0 | 1 | 100
GANGA ALTUS | EIDELBERG ENGINEERS PRIVATE LIMITED | 67911 | 2024-02-07 19:07 | 4124.9997 | 16.03 | Sand-Metal Mix M30 hi-flow (Downpour) |  | Cu.Mtrs | 16 | 0.03 | 0.1871
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 2985.6711 | 35 | PRV 1" |  | No. | 0 | 35 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 1636.436 | 40 | PRV 3/4" |  | No. | 0 | 40 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 3747.7271 | 48 | PRV 1-1/4" |  | No. | 0 | 48 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 4147.2517 | 48 | PRV 1-1/2" |  | No. | 0 | 48 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 5674.0533 | 24 | PRV 2" |  | No. | 0 | 24 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67935 | 2024-02-10 12:10 | 61.36 | 20 | 3 Pin Top (15 Amp) |  | No. | 0 | 20 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67935 | 2024-02-10 12:10 | 16.4255 | 80 | Round Plate 6" | VINAY | No. | 0 | 80 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67935 | 2024-02-10 12:10 | 20.1781 | 83 | Blank Plate (1036) - No. | VINAY | No. | 0 | 83 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67935 | 2024-02-10 12:10 | 165.6721 | 28 | 12 Module C1 1112 Support Frame with Cover Plate | VINAY | No. | 0 | 28 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67935 | 2024-02-10 12:10 | 27.777 | 27 | 6A One way Switch (1001) | VINAY | No. | 0 | 27 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 67935 | 2024-02-10 12:10 | 49.9141 | 75 | 2 Module C1 1102 Support Frame with Cover Plate | VINAY | No. | 0 | 75 | 100
GANGA ALTUS | K K MARKETING | 67967 | 2024-02-12 15:51 | 111.5574 | 19.5 | PVC Pipe 11/4"x10 ft | PRINCE | No. | 19 | 0.5 | 2.5641
GANGA ALTUS | K K MARKETING | 67967 | 2024-02-12 15:51 | 54.0676 | 580 | ASTM Ball Valve 1/2" | PRINCE | No. | 338 | 242 | 41.7241
GANGA ALTUS | K K MARKETING | 67967 | 2024-02-12 15:51 | 73.9152 | 62 | ASTM Ball Valve 3/4" | PRINCE | No. | 61 | 1 | 1.6129
GANGA ALTUS | YASH MARKETING (FIRM) | 68025 | 2024-02-19 17:49 | 5.31 | 30619.53 | Floor Guard Sheet (4ft x 6ft) | SUPREME | Sq.Ft | 30600 | 19.53 | 0.0638
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 68039 | 2024-02-20 16:24 | 34.9988 | 2115.94 | Lucia (300x300) Code - T816081FA |  | Sq.Ft | 2115.75 | 0.19 | 0.009
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 68039 | 2024-02-20 16:24 | 36.993 | 7994.13 | Lucia LT (300x600) Code - T816081LA |  | Sq.Ft | 7916.73 | 77.4 | 0.9682
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 68039 | 2024-02-20 16:24 | 36.993 | 1434.12 | Prism Terra HL (300x600) Code - T816174HA |  | Sq.Ft | 1433.68 | 0.44 | 0.0307
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68078 | 2024-02-24 18:09 | 15.3412 | 6.8 | Rawal Plug 25 x 8 |  | Pack | 0 | 6.8 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68081 | 2024-02-24 18:24 | 12.2909 | 6000 | 2 Pair telephone cable |  | Mtrs | 0 | 6000 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68081 | 2024-02-24 18:24 | 18.8533 | 6000 | RG-6 Co-Axial Cable-- Mtr |  | Mtrs | 0 | 6000 | 100
GANGA ALTUS | LEO ASSOCIATES | 68146 | 2024-03-07 17:05 | 903.88 | 600 | Mcon NSA Grey (Gold) 50kg |  | Bags | 399 | 201 | 33.5
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 68218 | 2024-03-19 10:47 | 1056.1 | 123.07 | Bioflex Grey |  | Bags | 123 | 0.07 | 0.0569
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 68253 | 2024-03-21 12:36 | 448.4 | 522.0542 | Biotile |  | Bags | 522 | 0.0542 | 0.0104
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 68272 | 2024-03-22 18:54 | 1056.1 | 101.36 | Bioflex Grey |  | Bags | 100 | 1.36 | 1.3418
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68278 | 2024-03-23 14:04 | 181.8867 | 6 | M.C.B. SP 10 Amp.(408590) |  | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68278 | 2024-03-23 14:04 | 181.8867 | 6 | M.C.B. SP 20 Amp.(408593) | LEGRAND | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68278 | 2024-03-23 14:04 | 1748.4767 | 6 | 40 Amp 4 Pole MCB 408681 | LEGRAND | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68278 | 2024-03-23 14:04 | 1803.9833 | 6 | 411851 DX3 DP RCCB 25A 30MA | LEGRAND | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68278 | 2024-03-23 14:04 | 545.16 | 6 | MCB 25A DP (408616) | LEGRAND | No. | 0 | 6 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 68279 | 2024-03-23 14:07 | 6095.83 | 2 | Ferrule Brass 1.5" - No. |  | No. | 0 | 2 | 100
GANGA ALTUS | V H ENTERPRISES | 68304 | 2024-03-28 10:46 | 4612.38 | 1 | 100 Amp 4 Pole MCB (IH24P0C100) | HONEYWELL | No. | 0 | 1 | 100
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 68324 | 2024-03-29 18:51 | 448.4 | 28.6 | Biotile |  | Bags | 28 | 0.6 | 2.0979
GANGA ALTUS | DEV SAFETY PRODUCTS | 68325 | 2024-03-29 18:53 | 590 | 3 | Fire Exting. Refilling CO2 4.5Kg |  | No. | 0 | 3 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68334 | 2024-03-30 17:36 | 198.59 | 2 | Spreader Link |  | No. | 0 | 2 | 100
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 68358 | 2024-04-04 16:44 | 43.3331 | 1001.1653 | OBD PAINT WHITE COLOUR - |  | Ltrs | 0 | 1001.1653 | 100
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 68358 | 2024-04-04 16:44 | 113.4924 | 448.542 | Primer (Water base) |  | Ltrs | 0 | 448.542 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 10.832 | 10 | PPR-C Tee 20mm |  | No. | 0 | 10 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 38.444 | 10 | PPR-C Brass FTA 20mm |  | No. | 0 | 10 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 7.0094 | 16 | PPR-C Elbow 20mm |  | No. | 0 | 16 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 53.525 | 10 | PPR-C Brass MTA 20mm |  | No. | 0 | 10 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 29.9475 | 4 | PPR-C Reducer Bushing 50mmx40mm |  | No. | 0 | 4 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 36.745 | 12 | PPR-C Brass Elbow 20mm |  | No. | 0 | 12 | 100
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 68388 | 2024-04-08 12:02 | 113.4924 | 804.7063 | Primer (Water base) |  | Ltrs | 0 | 804.7063 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68433 | 2024-04-13 16:52 | 21.9037 | 6997.4 | PVC Conduit Pipe 1" mtrs |  | Mtrs | 6996 | 1.4 | 0.02
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68433 | 2024-04-13 16:52 | 48.1441 | 121.14 | Casing Caping 1" |  | No. | 121 | 0.14 | 0.1156
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68446 | 2024-04-15 16:41 | 3383.65 | 550 | XLPE Cable 22KV 3C/300Sqmm |  | Mtrs | 540 | 10 | 1.8182
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68462 | 2024-04-16 19:13 | 59.1516 | 12800 | PVC Copper Wire 6 Sqmm black | R R KABEL | Mtrs | 6000 | 6800 | 53.125
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68462 | 2024-04-16 19:13 | 103.8594 | 12500 | PVC Copper Wire 10 Sqmm black | R R KABEL | Mtrs | 5000 | 7500 | 60
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68462 | 2024-04-16 19:13 | 59.1516 | 8400 | PVC Copper Wire 6 Sqmm red | R R KABEL | Mtrs | 4000 | 4400 | 52.381
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68462 | 2024-04-16 19:13 | 103.8594 | 8700 | PVC Copper Wire 10 Sqmm red | R R KABEL | Mtrs | 5000 | 3700 | 42.5287
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68462 | 2024-04-16 19:13 | 103.8594 | 8700 | PVC Copper Wire 10 Sqmm blue | R R KABEL | Mtrs | 5000 | 3700 | 42.5287
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68462 | 2024-04-16 19:13 | 25.8698 | 8500 | PVC Copper Wire 2.5 Sqmm green | R R KABEL | Mtrs | 8400 | 100 | 1.1765
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68462 | 2024-04-16 19:13 | 103.8594 | 8700 | PVC Copper Wire 10 Sqmm yellow | R R KABEL | Mtrs | 5000 | 3700 | 42.5287
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 68472 | 2024-04-17 16:19 | 5379.9972 | 12.08 | Ready Mix Concrete M-40 Grade (Pumpable) |  | Cu.Mtrs | 12 | 0.08 | 0.6623
GANGA ALTUS | DHRUVI ENTERPRISES | 68484 | 2024-04-18 13:08 | 8.96 | 20728.2575 | Red Bricks 4" |  | No. | 10000 | 10728.2575 | 51.7567
GANGA ALTUS | SEJAL ENTERPRISES | 68502 | 2024-04-20 14:46 | 14.75 | 813 | GI U Clamps 4" |  | No. | 580 | 233 | 28.6593
GANGA ALTUS | SEJAL ENTERPRISES | 68502 | 2024-04-20 14:46 | 21.24 | 200 | GI D Clamps 4" |  | No. | 100 | 100 | 50
GANGA ALTUS | DEV SAFETY PRODUCTS | 68508 | 2024-04-20 18:15 | 1.3965 | 5062.62 | Shedding Net |  | Sq.Ft | 1614.6 | 3448.02 | 68.1074
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 68513 | 2024-04-22 14:19 | 4376.9977 | 38.97 | Ready Mix Concrete M-15 Downpour |  | Cu.Mtrs | 10 | 28.97 | 74.3392
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 68513 | 2024-04-22 14:19 | 4826.9917 | 6.28 | Ready Mix Concrete M25 Regular Downpour |  | Cu.Mtrs | 4.5 | 1.78 | 28.3439
GANGA ALTUS | BONDWELL POLYMERS | 68524 | 2024-04-22 18:01 | 171.1 | 443.96 | Bondit 151 |  | Kgs | 440 | 3.96 | 0.892
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68528 | 2024-04-23 11:21 | 1271.21 | 2 | 32amp TPN MCB 408680 | LEGRAND | No. | 0 | 2 | 100
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 145.7773 | 96 | ASTM Ball Valve 1-1/4" | PRINCE | No. | 8 | 88 | 91.6667
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 59.5427 | 96 | PVC Socket 4" | PRINCE | No. | 87 | 9 | 9.375
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 11.0188 | 144 | PVC End Cap 50mm | PRINCE | No. | 0 | 144 | 100
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 147.14 | 1 | PVC Single Y 4" | PRINCE | No. | 0 | 1 | 100
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 114.2948 | 89 | PVC Pipe 11/4"x10 ft |  | No. | 69 | 20 | 22.4719
GANGA ALTUS | PRIME SALES CORPORATION | 68533 | 2024-04-24 10:23 | 31.4999 | 140.806 | Aggregate 1/2 Inch |  | Cu.Ft | 0 | 140.806 | 100
GANGA ALTUS | PRIME SALES CORPORATION | 68533 | 2024-04-24 10:23 | 31.5 | 220.7 | Aggregate 3/4 Inch |  | Cu.Ft | 0 | 220.7 | 100
GANGA ALTUS | DARLESHA HARDWARE | 68542 | 2024-04-25 13:03 | 1.7558 | 15038 | SS Screw 38 x 8 |  | No. | 15000 | 38 | 0.2527
GANGA ALTUS | DARLESHA HARDWARE | 68542 | 2024-04-25 13:03 | 1.2673 | 4440 | Screw 25 x 8. |  | No. | 4400 | 40 | 0.9009
GANGA ALTUS | YASH MARKETING (FIRM) | 68580 | 2024-05-03 11:51 | 1.2744 | 2024 | Foam Sheet 3mm thk. (6.5x4) |  | Sq.Ft | 2016 | 8 | 0.3953
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68582 | 2024-05-03 12:34 | 607.1133 | 3 | 16amp DP MCB 408633 | LEGRAND | No. | 0 | 3 | 100
GANGA ALTUS | NAMO PAVERS AND DESIGNER TILES | 68611 | 2024-05-07 19:05 | 37.76 | 3390.66 | Paver Block Matt Finish |  | Sq.Ft | 3250 | 140.66 | 4.1485
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 68629 | 2024-05-10 16:29 | 5957.0058 | 42.278 | Ready Mix Concrete M50 Regular Pumpable |  | Cu.Mtrs | 16 | 26.278 | 62.1553
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | 68675 | 2024-05-17 14:29 | 14.75 | 10000 | Wall Putty (Rakshak) Cement Based |  | Kgs | 6800 | 3200 | 32
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 68678 | 2024-05-17 16:24 | 448.4 | 413.1448 | Biotile |  | Bags | 376 | 37.1448 | 8.9907
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | 68679 | 2024-05-17 16:25 | 43.3331 | 1302.0315 | OBD PAINT WHITE COLOUR - |  | Ltrs | 0 | 1302.0315 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68691 | 2024-05-18 17:05 | 1884.27 | 6 | MCB 4 Pole 40 Amp - 30 Ma | LEGRAND | No. | 0 | 6 | 100
GANGA ALTUS | ADVANCE MEDICAL ENGINEERING SYSTEM | 68699 | 2024-05-20 16:02 | 1770 | 2 | Isolation nValve Dia 15mm |  | No. | 0 | 2 | 100
GANGA ALTUS | LEO ASSOCIATES | 68702 | 2024-05-20 17:21 | 224.2 | 312.93 | Hackad Plast Chemical | CHOKSEY | Ltrs | 300 | 12.93 | 4.1319
GANGA ALTUS | YASH MARKETING (FIRM) | 68705 | 2024-05-21 12:21 | 5.31 | 23580.4 | Floor Guard Sheet (4ft x 6ft) | SUPREME | Sq.Ft | 23568 | 12.4 | 0.0526
GANGA ALTUS | YASH MARKETING (FIRM) | 68705 | 2024-05-21 12:21 | 79.06 | 750 | Binding Wire |  | Kgs | 730.4 | 19.6 | 2.6133
GANGA ALTUS | K K MARKETING | 68731 | 2024-05-23 18:08 | 7.5969 | 163 | PVC End Cap 1-1/4" | PRINCE | No. | 0 | 163 | 100
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | 68742 | 2024-05-24 15:21 | 14.75 | 30585.4908 | Wall Putty (Rakshak) Cement Based |  | Kgs | 4375 | 26210.4908 | 85.6958
GANGA ALTUS | KISHOR THAKKAR | 68749 | 2024-05-24 17:00 | 80.24 | 299 | Plumbing Nails 11/2" |  | Kgs | 0 | 299 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 68785 | 2024-05-28 15:42 | 4826.9903 | 33.182 | Ready Mix Concrete M25 Regular Downpour |  | Cu.Mtrs | 33 | 0.182 | 0.5485
GANGA ALTUS | YASHOM ENTERPRISES | 68794 | 2024-05-29 14:32 | 8.512 | 16000 | Red Bricks 4" |  | No. | 15252.477 | 747.523 | 4.672
GANGA ALTUS | K K MARKETING | 68802 | 2024-05-30 16:42 | 527.4 | 8 | SWR Silent Coupler 8" | SUPREME | No. | 4 | 4 | 50
GANGA ALTUS | SEJAL ENTERPRISES | 68824 | 2024-05-31 16:25 | 33.04 | 154 | GI U Clamps 8" |  | No. | 0 | 154 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 68824 | 2024-05-31 16:25 | 44.84 | 625 | Floor Trap Jali with cover 150mmx150mm (Grey Colour) |  | No. | 555 | 70 | 11.2
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68852 | 2024-06-04 16:41 | 29.6912 | 268 | PVC Copper Wire 2.5 Sqmm red | R R KABEL | Mtrs | 200 | 68 | 25.3731
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68852 | 2024-06-04 16:41 | 18.2191 | 804.49 | PVC Copper Wire 1.5 Sqmm yellow | R R KABEL | Mtrs | 800 | 4.49 | 0.5581
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 68852 | 2024-06-04 16:41 | 45.6413 | 401.5 | PVC Copper Wire 4 Sqmm yellow | R R KABEL | Mtrs | 400 | 1.5 | 0.3736
GANGA ALTUS | SAFA ENTERPRISES | 68857 | 2024-06-05 12:16 | 3890.7567 | 6 | ELCB 4 Pole 63 AMP 500MA |  | No. | 0 | 6 | 100
GANGA ALTUS | K K MARKETING | 68887 | 2024-06-07 16:29 | 2135.8756 | 55 | P V C Single Y 8" | PRINCE | No. | 14 | 41 | 74.5455
GANGA ALTUS | K K MARKETING | 68887 | 2024-06-07 16:29 | 854.131 | 20 | SWR Silent Single Y 6" | PRINCE | No. | 14 | 6 | 30
GANGA ALTUS | K K MARKETING | 68887 | 2024-06-07 16:29 | 446.2289 | 90 | SWR Silent Shoe Bend 6" | PRINCE | No. | 66 | 24 | 26.6667
GANGA ALTUS | K K MARKETING | 68887 | 2024-06-07 16:29 | 149.8836 | 632 | SWR Silent Shoe Bend 4" | PRINCE | No. | 531 | 101 | 15.981
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 6.6045 | 24 | ASTM Red. Bush 1-1/2" x 1-1/4" | PRINCE | No. | 9 | 15 | 62.5
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 145.7775 | 32 | ASTM Ball Valve 1-1/4" | PRINCE | No. | 0 | 32 | 100
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 195.2593 | 38 | ASTM Pipe 3/4" x 10 fts | PRINCE | No. | 36 | 2 | 5.2632
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 1690.468 | 200 | SWR Silent Aerator 4" (70001576) | PRINCE | No. | 193 | 7 | 3.5
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 1194.278 | 332 | SWR Silent Pipe 4" x 10 ft S/S | PRINCE | No. | 330 | 2 | 0.6024
GANGA ALTUS | AGARWAL AGENCIES | 68932 | 2024-06-12 18:14 | 35 | 200 | Aqua water -20lit |  | No. | 115 | 85 | 42.5
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 57.0648 | 288 | Flexible Pipe 1-1/4" x 2fts |  | No. | 0 | 288 | 100
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 605.1277 | 107 | Cera Garnet Bib Cock (F2002153) |  | No. | 53 | 54 | 50.4673
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 64.3808 | 480 | CP Extension Piece 1/2" x 1" | VIKING | No. | 0 | 480 | 100
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 181.5383 | 192 | Shower Arm (F7040101-Cera) | CERA | No. | 94 | 98 | 51.0417
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 695.8968 | 192 | Shower Rose (7020305-Cera) | CERA | No. | 0 | 192 | 100
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 712.4003 | 208 | Health faucet ( F8030107 -Cera) | CERA | No. | 0 | 208 | 100
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 550.116 | 480 | Angle Cock (F1015201-Cera) | CERA | No. | 240 | 240 | 50
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 1030.619 | 103 | Wash Basin (Chime-S2040139-Cera Sn. white) | CERA | No. | 51 | 52 | 50.4854
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 646.3863 | 192 | Bath Spout (F1015661-Cera) | CERA | No. | 95 | 97 | 50.5208
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 3892.9498 | 337 | W.H. Commode with seat cover (Cordo-S1043108-Cera Sn. white) | CERA | No. | 163 | 174 | 51.632
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 805.92 | 192 | Pillar Cock (F1015101-Cera) | CERA | No. | 95 | 97 | 50.5208
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 2380.7751 | 149 | Wash Basin (Calburt S2020137-Cera Sn. white) | CERA | No. | 74 | 75 | 50.3356
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 907.6913 | 104 | Sink Cock (F1015251-Cera) |  | No. | 52 | 52 | 50
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68947 | 2024-06-14 16:32 | 421.26 | 192 | RAGBOLTS For Wallhung | VIKING | Pair | 48 | 144 | 75
GANGA ALTUS | S K CERAMICS | 68948 | 2024-06-14 17:06 | 39.9996 | 2458.46 | Ancona Bruno 600x600 Tiles |  | Sq.Ft | 0 | 2458.46 | 100
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 68951 | 2024-06-15 10:59 | 36.993 | 1892.129 | Prism Terra HL (300x600) Code - T816174HA |  | Sq.Ft | 1878.89 | 13.239 | 0.6997
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 68951 | 2024-06-15 10:59 | 36.993 | 1198.69 | Lucia DK (300x600) Code - T816081DA |  | Sq.Ft | 1191.26 | 7.43 | 0.6198
GANGA ALTUS | KANHAIYA ENTERPRISES | 68955 | 2024-06-15 13:23 | 14.16 | 576 | Teflon Tape |  | No. | 0 | 576 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 68958 | 2024-06-15 15:51 | 15.3402 | 26.69 | Rawal Plug 25 x 8 |  | Pack | 26 | 0.69 | 2.5852
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 68969 | 2024-06-17 14:39 | 4826.9909 | 7.48 | Ready Mix Concrete M25 Regular Downpour |  | Cu.Mtrs | 6 | 1.48 | 19.7861
GANGA ALTUS | BNY METALCOAT PRIVATE LIMITED | 68975 | 2024-06-18 10:41 | 368.16 | 112 | GI C Channel Patti (14SWG) 35MM X 15MM X 3M |  | No. | 111.666 | 0.334 | 0.2982
GANGA ALTUS | SWASTIK AIR SYSTEMS | 69034 | 2024-06-24 12:05 | 158720 | 2 | 4.0 TR (5 STAR) - No. |  | No. | 0 | 2 | 100
GANGA ALTUS | K K MARKETING | 69047 | 2024-06-25 16:45 | 323.7213 | 125 | PVC Pipe 3" 6Ft Long D/S |  | No. | 47 | 78 | 62.4
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69054 | 2024-06-26 19:01 | 18.2191 | 6208.11 | PVC Copper Wire 1.5 Sqmm black |  | Mtrs | 6200 | 8.11 | 0.1306
GANGA ALTUS | S K CERAMICS | 69065 | 2024-06-28 19:10 | 42.5001 | 2073.16 | Vitrified Tile 600x600 Tropic Super White |  | Sq.Ft | 1835.31 | 237.85 | 11.4728
GANGA ALTUS | ASH CONCEPTS | 69074 | 2024-07-01 13:35 | 9.52 | 296.04 | FlyAsh Bricks 3"x6"x9" |  | No. | 0 | 296.04 | 100
GANGA ALTUS | ASH CONCEPTS | 69074 | 2024-07-01 13:35 | 8.064 | 21870.72 | FlyAsh Bricks 3"x4"x9" |  | No. | 4500 | 17370.72 | 79.4245
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | 69077 | 2024-07-01 19:25 | 525.1 | 241 | Cylindrical Lock with Key - Yale (CA5147 US32D) |  | No. | 236 | 5 | 2.0747
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | 69077 | 2024-07-01 19:25 | 1103.3 | 122 | Handle D-Type YEH-11B-300 |  | Pair | 0 | 122 | 100
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | 69077 | 2024-07-01 19:25 | 578.2 | 165 | CYLINDRICAL 60/70MMBS CA5122 US32D |  | No. | 160 | 5 | 3.0303
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | 69077 | 2024-07-01 19:25 | 389.4 | 224 | Eye piece V0401A US15 |  | No. | 81 | 143 | 63.8393
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | 69077 | 2024-07-01 19:25 | 206.5 | 656 | Magnetic Catcher Yale (YMDC-20-SS) |  | No. | 294 | 362 | 55.1829
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 69078 | 2024-07-02 11:00 | 171.926 | 223 | PVC Connector 1/2"x 24" - No. | VIKING | No. | 0 | 223 | 100
GANGA ALTUS | YASH MARKETING (FIRM) | 69090 | 2024-07-02 18:55 | 1.2744 | 2000 | Foam Sheet 3mm thk. (6.5x4) |  | Sq.Ft | 0 | 2000 | 100
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 69110 | 2024-07-05 11:29 | 448.4 | 455.866 | Biotile |  | Bags | 0 | 455.866 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 105.6691 | 23 | 6 Module Plate 1106 |  | No. | 0 | 23 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 139.1225 | 8 | 12 Module Box (1800012) |  | No. | 0 | 8 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 2912.14 | 1 | 63 amp RCCB 411878 |  | No. | 0 | 1 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 38.2311 | 9 | 2 Module Box (180001) |  | No. | 0 | 9 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 92.395 | 8 | 8M Surface Box (Hori) H290008 |  | No. | 0 | 8 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 165.6714 | 7 | 12 Module Plate 1112 |  | No. | 0 | 7 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 86.0222 | 9 | 16 Amp One Way Switch without Indicator 1051 |  | No. | 0 | 9 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 151.865 | 8 | 8M Plate (Hzl) H1108 |  | No. | 0 | 8 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 38.2333 | 6 | 2 Module Plate Inner 1301 |  | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 1818.36 | 1 | 63 Amp 4 Pole MCB (408683) |  | No. | 0 | 1 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 103.55 | 2 | 16 Amp. Switch with indicator (1052) |  | No. | 0 | 2 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 62.1267 | 6 | 3 Module Plate 1103 |  | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 72.2158 | 19 | 4 Module C1 1104 Support Frame with Cover Plate |  | No. | 0 | 19 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 32.9233 | 6 | 2 Module Box (290001) |  | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 105.6688 | 33 | 6 Module C1 1106 Support Frame with Cover Plate |  | No. | 0 | 33 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 47.26 | 6 | 3 Module Box (290003) |  | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 79.6504 | 23 | 6 Module Inner Plate 1306 |  | No. | 0 | 23 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 165.6723 | 13 | 12 Module C1 1112 Support Frame with Cover Plate |  | No. | 0 | 13 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 71.1537 | 19 | 6Module Box (290006) |  | No. | 0 | 19 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 60.5339 | 36 | 4 Module Box (180004) |  | No. | 0 | 36 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 1315.32 | 2 | 25amp 4 Pole MCB 408790 |  | No. | 0 | 2 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 130.0957 | 7 | 12 Module Inner Plate- IN 1312 |  | No. | 0 | 7 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 180.01 | 4 | 18 Module Inner Plate- IN 1318 |  | No. | 0 | 4 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 63.1891 | 89 | 6 A Socket |  | No. | 0 | 89 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 83.8978 | 9 | 6 Module Box (180006) |  | No. | 0 | 9 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 85.4907 | 27 | 6A Uni. Socket 1058 (Vinay Corum) |  | No. | 0 | 27 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 63.1892 | 50 | 6 Amp Socket 5 Pin without shutter 1024 |  | No. | 0 | 50 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 151.8667 | 12 | 8 Module C1 H-1108 Support Frame with Cover Plate - No. |  | No. | 0 | 12 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 101.42 | 8 | 8 Module plate Inner (1308) |  | No. | 0 | 8 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 92.3945 | 11 | 8 Module Surface Box |  | No. | 0 | 11 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 143.9 | 4 | 18 Module Surface Box 290018 |  | No. | 0 | 4 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 62.127 | 138 | 3 Module C1 1103 Support Frame with Cover Plate |  | No. | 0 | 138 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 49.914 | 139 | 2 Module C1 1102 Support Frame with Cover Plate |  | No. | 0 | 139 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 49.9133 | 6 | 2 Module Plate 1102 |  | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 120.006 | 10 | 16 Amp. Socket with shutter (1057) |  | No. | 0 | 10 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 46.1967 | 6 | 3 Module Inner Plate 1303 |  | No. | 0 | 6 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 1818.3571 | 7 | 40 Amp 4 Pole MCB 408681 |  | No. | 0 | 7 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 193.285 | 4 | 18 module plate-1118 |  | No. | 0 | 4 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 456.94 | 1 | 507793 40amp 4way Enclosuer Box |  | No. | 0 | 1 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69157 | 2024-07-06 19:16 | 27.7773 | 175 | 6A One way Switch (1001) |  | No. | 0 | 175 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69160 | 2024-07-08 11:17 | 51.507 | 88 | 3 Module Box (180003) |  | No. | 0 | 88 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69164 | 2024-07-08 14:52 | 10.1952 | 744 | Round Plate 4" - No. |  | No. | 0 | 744 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69164 | 2024-07-08 14:52 | 121.5986 | 7 | Surface Box 12m (290012) |  | No. | 0 | 7 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69164 | 2024-07-08 14:52 | 262.8447 | 19 | Fan step Regulator (1075) |  | No. | 0 | 19 | 100
GANGA ALTUS | SATAV STONE CO. PVT. LTD. | 69169 | 2024-07-08 16:15 | 65.1 | 1955.1087 | M Sand |  | Cu.Ft | 1955 | 0.1087 | 0.0056
GANGA ALTUS | K K MARKETING | 69170 | 2024-07-08 16:47 | 77.3373 | 96 | PVC Nahani Trap 4"X 3" |  | No. | 19 | 77 | 80.2083
GANGA ALTUS | VENKATESH ENTERPRISES (PROP PRASHANT VELANKAR) | 69171 | 2024-07-08 17:43 | 8.512 | 19065.4315 | Red Bricks 4" |  | No. | 0 | 19065.4315 | 100
GANGA ALTUS | V H ENTERPRISES | 69174 | 2024-07-08 18:34 | 1500.345 | 4 | SPN DB DD 12 Way IHPSPNDD012 |  | No. | 2 | 2 | 50
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69180 | 2024-07-09 11:32 | 5822.4977 | 53.58 | Ready Mix Concrete M-40 Grade (Pumpable) |  | Cu.Mtrs | 34.5 | 19.08 | 35.6103
GANGA ALTUS | KANAD ELECTRICAL SERVICES | 69194 | 2024-07-10 13:14 | 749300 | 1 | DG Distribution Panel |  | Job | 0 | 1 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69195 | 2024-07-10 15:21 | 32.55 | 1018.34 | Aggregate 10mm cft |  | Cu.Ft | 584 | 434.34 | 42.6518
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69196 | 2024-07-10 15:26 | 5571.9989 | 40.44 | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | Cu.Mtrs | 36 | 4.44 | 10.9792
GANGA ALTUS | K K MARKETING | 69200 | 2024-07-10 17:29 | 15.5701 | 191 | PVC Elbow 1 1/2 " | PRINCE | No. | 90 | 101 | 52.8796
GANGA ALTUS | SUPERMIX RMC INDIA | 69202 | 2024-07-10 18:09 | 2895.13 | 148 | Pavement Quality Concrete (M40) |  | Cu.Mtrs | 31.5 | 116.5 | 78.7162
GANGA ALTUS | SUPERMIX RMC INDIA | 69217 | 2024-07-11 15:32 | 3399.9999 | 35.735 | Sand-Metal Mix M25 (Pumpable) |  | Cu.Mtrs | 33 | 2.735 | 7.6536
GANGA ALTUS | SUPERMIX RMC INDIA | 69217 | 2024-07-11 15:32 | 3400.0001 | 59.4 | Sand-Metal Mix M25 (Downpour) |  | Cu.Mtrs | 0 | 59.4 | 100
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 69218 | 2024-07-11 16:39 | 36.993 | 3442.7 | Lucia LT (300x600) Code - T816081LA |  | Sq.Ft | 3389.75 | 52.95 | 1.538
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69219 | 2024-07-11 17:19 | 69.561 | 60 | Corum TV Socket Single Outlet (1014). | VINAY | No. | 0 | 60 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69219 | 2024-07-11 17:19 | 19.2576 | 172 | Ceiling Rose | VINAY | No. | 0 | 172 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69219 | 2024-07-11 17:19 | 23.2224 | 448 | Angle Holder | VINAY | No. | 0 | 448 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69219 | 2024-07-11 17:19 | 20.178 | 315 | Blank Plate (1036) - No. | VINAY | No. | 0 | 315 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69227 | 2024-07-12 10:36 | 5571.999 | 77 | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | Cu.Mtrs | 24 | 53 | 68.8312
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 69229 | 2024-07-12 10:59 | 36.993 | 474.79 | Prism Terra HL (300x600) Code - T816174HA |  | Sq.Ft | 445.52 | 29.27 | 6.1648
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 69229 | 2024-07-12 10:59 | 36.993 | 7116.888 | Lucia LT (300x600) Code - T816081LA |  | Sq.Ft | 0 | 7116.888 | 100
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 69229 | 2024-07-12 10:59 | 36.9929 | 56.45 | Arrow Chips DK (300x600) Code - T816129DA |  | Sq.Ft | 0 | 56.45 | 100
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 69229 | 2024-07-12 10:59 | 36.9894 | 542.8 | Arrow Chips DK (300x600) Code -T816029DA |  | Sq.Ft | 154.97 | 387.83 | 71.4499
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | 69229 | 2024-07-12 10:59 | 34.9988 | 1323.49 | Calyx Blue (300x300) Code - T813125FA |  | Sq.Ft | 141.57 | 1181.92 | 89.3033
GANGA ALTUS | SUPERMIX RMC INDIA | 69254 | 2024-07-15 10:57 | 3274.9989 | 34.2404 | Sand-Metal Mix M15 (Pumpable) |  | Cu.Mtrs | 0 | 34.2404 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69259 | 2024-07-15 13:11 | 5091.9996 | 25 | Ready Mix Concrete M25 Regular Downpour |  | Cu.Mtrs | 18 | 7 | 28
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69259 | 2024-07-15 13:11 | 5271.9993 | 24 | Ready Mix Concrete M25 Regular Pumpable |  | Cu.Mtrs | 0 | 24 | 100
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | 69276 | 2024-07-16 17:50 | 448.4 | 601.51 | Biotile |  | Bags | 0 | 601.51 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69280 | 2024-07-17 12:05 | 18.2191 | 50 | PVC Copper Wire 1.5 Sqmm yellow | R R KABEL | Mtrs | 49.06 | 0.94 | 1.88
GANGA ALTUS | SATAV STONE CO. PVT. LTD. | 69284 | 2024-07-17 17:42 | 65.1 | 1181.42 | M Sand |  | Cu.Ft | 787 | 394.42 | 33.3852
GANGA ALTUS | ASH CONCEPTS | 69292 | 2024-07-18 14:52 | 106.2 | 300 | RCC Half Round Gutters 6" x 1m |  | No. | 0 | 300 | 100
GANGA ALTUS | ASH CONCEPTS | 69292 | 2024-07-18 14:52 | 3231.2653 | 15 | RCC Chamber Cover with Frame 24"x36" (HD) |  | No. | 0 | 15 | 100
GANGA ALTUS | ASH CONCEPTS | 69292 | 2024-07-18 14:52 | 480.85 | 776 | RCC NP2 Class Pipe 12" |  | Mtrs | 50 | 726 | 93.5567
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69298 | 2024-07-18 17:52 | 566.4 | 200 | Single Phase Energy Meter |  | No. | 10 | 190 | 95
GANGA ALTUS | ASH CONCEPTS | 69299 | 2024-07-18 18:43 | 12186.048 | 10 | RCC Chamber Cover with Frame 36" x 48" (HD) |  | No. | 0 | 10 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69313 | 2024-07-20 18:22 | 1818.36 | 2 | MCB 63 amp 4 pole |  | No. | 0 | 2 | 100
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 69313 | 2024-07-20 18:22 | 1271.2133 | 6 | MCB 32 Amp. 4 Pole | LEGRAND | No. | 0 | 6 | 100
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69328 | 2024-07-23 18:08 | 4641.9995 | 23.85 | Ready Mix Concrete M-15 Grade( D/P) - |  | Cu.Mtrs | 5 | 18.85 | 79.0356
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | 69332 | 2024-07-24 18:14 | 35.7 | 2366.0349 | Crush Sand |  | Cu.Ft | 220.5082 | 2145.5267 | 90.6803