## Short_Supply_POwise638598615720
Short Supply Report
From 30-12-2019 To 21-08-2024
Page 1 of 1
Total Records: 137 Records 1 To 137
Project Name | Supplier Name | PO Sr No | PO Date | Rate | PO Qty | Material Name | Brand | Unit | Recd Qty | Bal Qty | Bal %
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60042 | 2021-08-13 12:02 | 29.25 | 1 | ASTM Tank Nipple 1" |  | No. | 0 | 1 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60042 | 2021-08-13 12:02 | 4.12 | 50 | ASTM Socket 1/2" |  | No. | 0 | 50 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60042 | 2021-08-13 12:02 | 95.84 | 3 | ASTM Ball Valve 1/2" |  | No. | 0 | 3 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60042 | 2021-08-13 12:02 | 73.0825 | 6 | ASTM Pipe 1/2" x 10 fts |  | No. | 0 | 6 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 10.7525 | 4 | PPR-C Reducer Socket 25mmx20mm |  | No. | 0 | 4 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 27 | 17 | PPR-C Socket 25mm |  | No. | 0 | 17 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 123 | 47 | PVC Pipe 4" 3Ft Long D/S |  | No. | 0 | 47 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 217 | 1 | PVC Pipe 4" 6 FT Long D/S |  | No. | 0 | 1 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 1405 | 9 | Trigger Spray Chrome 27513000 |  | No. | 0 | 9 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 66 | 4 | PPR-C Ballvalve 20mm (Plas-Bo |  | No. | 0 | 4 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 14.11 | 4 | ASTM Tee 1" |  | No. | 0 | 4 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 77.67 | 11 | PVC Plain Tee 4" |  | No. | 0 | 11 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 60110 | 2021-08-19 13:28 | 64.92 | 21 | ASTM Brass Elbow 1/2" |  | No. | 0 | 21 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 2 | CP Flanges |  | No. | 0 | 2 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 2 | GI Bracket 4"x8" |  | No. | 0 | 2 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 1.69 | 20 | GI Clips 1 1/4" |  | No. | 18 | 2 | 10
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 3.3 | 18 | GI Clips 2 1/2" |  | No. | 0 | 18 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 20 | 161 | GI D Clamps 4" |  | No. | 135 | 26 | 16.1491
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 15 | GI U Clamps 6" |  | No. | 9 | 6 | 40
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 69.6 | 14 | ASTM MTA 1/2" |  | No. | 0 | 14 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 3 | ASTM Plain Elbow 3/4" |  | No. | 0 | 3 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 5 | PPR-C Elbow 25mm |  | No. | 0 | 5 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 34.6 | 31 | PPR-C MTA 1/2" |  | No. | 28 | 3 | 9.6774
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 2 | ASTM Plain Tee 1-1/2" |  | No. | 0 | 2 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 9 | PVC Elbow 40mm - No. |  | No. | 0 | 9 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 3.5 | 22 | PVC Socket 1" |  | No. | 0 | 22 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 59.8 | 6 | PVC Socket 4" |  | No. | 5 | 1 | 16.6667
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 1 | Screw 8x80 |  | No. | 0 | 1 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 3.41 | 4 | ASTM Red Bush 1/2" x 3/4" - No |  | No. | 3 | 1 | 25
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 12.05 | 9 | ASTM Red. Bush 1-1/2" x 1" |  | No. | 7 | 2 | 22.2222
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 24.696 | 2 | ASTM Red. Bush 2"x11/2" |  | No. | 0 | 2 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 1 | ASTM Red. Socket 4" x 3" |  | No. | 0 | 1 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 7 | ASTM Red. Socket 11/2"X11/4" |  | No. | 0 | 7 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 4.99 | 6 | ASTM Reducer Bushing 1" x 3/4" |  | No. | 0 | 6 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 2 | ASTM Reducer Tee 1-1/2"x1-1/4" |  | No. | 1 | 1 | 50
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 100 | 2 | ASTM Socket 1" |  | No. | 0 | 2 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 74 | 1 | ASTM Socket 3" |  | No. | 0 | 1 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 5.59 | 10 | ASTM Socket 3/4" |  | No. | 4 | 6 | 60
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 34.1 | 4 | ASTM Tee 1-1/2" |  | No. | 2 | 2 | 50
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63068 | 2022-06-28 19:13 | 23.81 | 11 | ASTM Tee 11/4" |  | No. | 1 | 10 | 90.9091
GANGA ALTUS | NAFE TRADERS | 63236 | 2022-07-16 14:16 | 23.6 | 210 | Fastner 12mm x 100mm |  | No. | 200 | 10 | 4.7619
GANGA ALTUS | K K MARKETING | 63512 | 2022-08-18 13:20 | 421.1417 | 9.6 | PVC Solvent (500 ml.) - | PRINCE | No. | 9 | 0.6 | 6.25
GANGA ALTUS | K K MARKETING | 63514 | 2022-08-18 13:32 | 37.76 | 188 | GI D Clamps 4" |  | No. | 130 | 58 | 30.8511
GANGA ALTUS | K K MARKETING | 63514 | 2022-08-18 13:32 | 296.1792 | 9.6 | Hold Tite (1 Kgs) |  | Kgs | 9 | 0.6 | 6.25
GANGA ALTUS | K K MARKETING | 63514 | 2022-08-18 13:32 | 18.88 | 192 | GI D Clamps 11/4" |  | No. | 0 | 192 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 2.646 | 2 | ASTM End Cap 1/2" |  | No. | 1 | 1 | 50
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 14.11 | 3 | ASTM Tee 1" |  | No. | 0 | 3 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 7 | 63 | PPR-C End Cap 20mm |  | No. | 44 | 19 | 30.1587
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 170 | 7 | ASTM Brass FTA 1-1/4" |  | No. | 0 | 7 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 257 | 2 | ASTM Brass FTA 1 1/2" |  | No. | 0 | 2 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 6.174 | 22 | ASTM Tee 1/2" |  | No. | 0 | 22 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 50.26 | 7 | ASTM Brass FTA 1/2" |  | No. | 0 | 7 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 14.11 | 10 | ASTM Socket 11/4" |  | No. | 0 | 10 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 100 | 5 | ASTM Reducer Tee 1" x 1/2" |  | No. | 0 | 5 | 100
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 63745 | 2022-09-26 12:03 | 54.8 | 20 | PPR-C Brass MTA 1/2" |  | No. | 0 | 20 | 100
GANGA ALTUS | T K ENTERPRISES | 63987 | 2022-11-09 12:26 | 90.86 | 360 | Plumbing Nails 2.5" |  | Kgs | 350 | 10 | 2.7778
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 64140 | 2022-12-02 16:05 | 0.75 | 15 | GI Clips 1/2" |  | No. | 13 | 2 | 13.3333
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 64140 | 2022-12-02 16:05 | 95.84 | 11 | ASTM Ball Valve 1/2" |  | No. | 10 | 1 | 9.0909
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 64140 | 2022-12-02 16:05 | 64.92 | 19 | ASTM Brass Elbow 1/2" |  | No. | 18 | 1 | 5.2632
GANGA ALTUS | MATERIAL TO BE TRANSFERED | 64140 | 2022-12-02 16:05 | 17.7 | 39 | Teflon Tape |  | No. | 38 | 1 | 2.5641
GANGA ALTUS | K K MARKETING | 64293 | 2022-12-22 17:08 | 528.0763 | 10.4 | PVC Pipe 2" x 10 ft S/S | PRINCE | No. | 10 | 0.4 | 3.8462
GANGA ALTUS | K K MARKETING | 64293 | 2022-12-22 17:08 | 343.0023 | 86.5 | PVC Pipe 11/4"x10 ft | PRINCE | No. | 86 | 0.5 | 0.578
GANGA ALTUS | SEJAL ENTERPRISES | 64305 | 2022-12-24 16:27 | 7.08 | 80 | GI D Clamps 3/4" |  | No. | 0 | 80 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 64305 | 2022-12-24 16:27 | 224.2018 | 5.45 | Tag |  | Kgs | 5.23 | 0.22 | 4.0367
GANGA ALTUS | K K MARKETING | 65381 | 2023-05-02 12:06 | 111.63 | 4 | ASTM Red. Socket 75mm x 65mm |  | No. | 0 | 4 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 65692 | 2023-06-09 14:07 | 15.34 | 32 | GI U Clamps 4" |  | No. | 0 | 32 | 100
GANGA ALTUS | K K MARKETING | 65704 | 2023-06-10 17:21 | 145.7773 | 96 | ASTM Ball Valve 1-1/4" |  | No. | 0 | 96 | 100
GANGA ALTUS | K K MARKETING | 65704 | 2023-06-10 17:21 | 303.8736 | 144 | PVC Pipe 3" 6Ft Long D/S |  | No. | 114 | 30 | 20.8333
GANGA ALTUS | K K MARKETING | 65704 | 2023-06-10 17:21 | 146.0877 | 3 | ASTM Pipe 1/2" x 10 fts |  | No. | 2 | 1 | 33.3333
GANGA ALTUS | SEJAL ENTERPRISES | 66272 | 2023-08-18 14:07 | 7.08 | 93 | GI D Clamps 3/4" |  | No. | 0 | 93 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 66282 | 2023-08-19 12:32 | 212.4 | 5.6 | Tag |  | Kgs | 0 | 5.6 | 100
GANGA ALTUS | PRINCE DISTRIBUTOR | 66321 | 2023-08-22 15:55 | 329.2198 | 22.75 | ASTM Solvent Cement 472ml |  | No. | 22 | 0.75 | 3.2967
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 66414 | 2023-08-31 10:45 | 712.4003 | 172 | Health faucet ( F8030107 -Cera) |  | No. | 123 | 49 | 28.4884
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 66838 | 2023-10-11 11:37 | 660.1392 | 192 | S/L Divertor (F1015701-exposed-Cera) |  | No. | 136 | 56 | 29.1667
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 262.1252 | 175.6 | PVC Pipe 2" x 10 ft S/S | PRINCE | No. | 175 | 0.6 | 0.3417
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 7.598 | 1 | PVC Socket 11/4" | PRINCE | No. | 0 | 1 | 100
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 110.1883 | 153.5 | PVC Pipe 11/4"x10 ft | PRINCE | No. | 153 | 0.5 | 0.3257
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 142.184 | 161.5 | ASTM Pipe 1/2" x 10 fts | PRINCE | No. | 161 | 0.5 | 0.3096
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 24.2962 | 120 | PVC Elbow 50mm | PRINCE | No. | 3 | 117 | 97.5
GANGA ALTUS | PRINCE DISTRIBUTOR | 67165 | 2023-11-09 18:35 | 22.2433 | 3 | PVC Bend 1.5" (50mm) | PRINCE | No. | 0 | 3 | 100
GANGA ALTUS | PRINCE DISTRIBUTOR | 67176 | 2023-11-10 16:52 | 166.144 | 21.8 | PVC Solvent (500 ml.) - | NEOSEAL | No. | 21 | 0.8 | 3.6697
GANGA ALTUS | SHANTI SALES | 67581 | 2023-12-29 13:06 | 271.4 | 5 | Hold Tite (1 Kgs) |  | Kgs | 0 | 5 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 67772 | 2024-01-20 11:47 | 212.4 | 10 | Tag |  | Kgs | 0 | 10 | 100
GANGA ALTUS | SHANTI SALES | 67832 | 2024-02-02 10:15 | 271.4004 | 22.38 | Hold Tite (1 Kgs) |  | Kgs | 0 | 22.38 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 1636.436 | 40 | PRV 3/4" |  | No. | 0 | 40 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 4147.2517 | 48 | PRV 1-1/2" |  | No. | 0 | 48 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 2985.6711 | 35 | PRV 1" |  | No. | 0 | 35 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 5674.0533 | 24 | PRV 2" |  | No. | 0 | 24 | 100
GANGA ALTUS | THE STEEL STOCK HOLDERS SYNDICATE | 67931 | 2024-02-10 11:28 | 3747.7271 | 48 | PRV 1-1/4" |  | No. | 0 | 48 | 100
GANGA ALTUS | K K MARKETING | 67967 | 2024-02-12 15:51 | 111.5574 | 19.5 | PVC Pipe 11/4"x10 ft | PRINCE | No. | 19 | 0.5 | 2.5641
GANGA ALTUS | K K MARKETING | 67967 | 2024-02-12 15:51 | 73.9152 | 62 | ASTM Ball Valve 3/4" | PRINCE | No. | 61 | 1 | 1.6129
GANGA ALTUS | K K MARKETING | 67967 | 2024-02-12 15:51 | 54.0676 | 580 | ASTM Ball Valve 1/2" | PRINCE | No. | 338 | 242 | 41.7241
GANGA ALTUS | SEJAL ENTERPRISES | 68279 | 2024-03-23 14:07 | 6095.83 | 2 | Ferrule Brass 1.5" - No. |  | No. | 0 | 2 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 10.832 | 10 | PPR-C Tee 20mm |  | No. | 0 | 10 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 29.9475 | 4 | PPR-C Reducer Bushing 50mmx40mm |  | No. | 0 | 4 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 7.0094 | 16 | PPR-C Elbow 20mm |  | No. | 0 | 16 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 53.525 | 10 | PPR-C Brass MTA 20mm |  | No. | 0 | 10 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 38.444 | 10 | PPR-C Brass FTA 20mm |  | No. | 0 | 10 | 100
GANGA ALTUS | KPT PIPING SYSTEM PRIVATE LIMITED | 68360 | 2024-04-04 17:39 | 36.745 | 12 | PPR-C Brass Elbow 20mm |  | No. | 0 | 12 | 100
GANGA ALTUS | SEJAL ENTERPRISES | 68502 | 2024-04-20 14:46 | 14.75 | 813 | GI U Clamps 4" |  | No. | 580 | 233 | 28.6593
GANGA ALTUS | SEJAL ENTERPRISES | 68502 | 2024-04-20 14:46 | 21.24 | 200 | GI D Clamps 4" |  | No. | 100 | 100 | 50
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 114.2948 | 89 | PVC Pipe 11/4"x10 ft |  | No. | 69 | 20 | 22.4719
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 145.7773 | 96 | ASTM Ball Valve 1-1/4" | PRINCE | No. | 8 | 88 | 91.6667
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 11.0188 | 144 | PVC End Cap 50mm | PRINCE | No. | 0 | 144 | 100
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 59.5427 | 96 | PVC Socket 4" | PRINCE | No. | 87 | 9 | 9.375
GANGA ALTUS | K K MARKETING | 68532 | 2024-04-23 18:42 | 147.14 | 1 | PVC Single Y 4" | PRINCE | No. | 0 | 1 | 100
GANGA ALTUS | K K MARKETING | 68731 | 2024-05-23 18:08 | 7.5969 | 163 | PVC End Cap 1-1/4" | PRINCE | No. | 0 | 163 | 100
GANGA ALTUS | KISHOR THAKKAR | 68749 | 2024-05-24 17:00 | 80.24 | 299 | Plumbing Nails 11/2" |  | Kgs | 0 | 299 | 100
GANGA ALTUS | K K MARKETING | 68802 | 2024-05-30 16:42 | 527.4 | 8 | SWR Silent Coupler 8" | SUPREME | No. | 4 | 4 | 50
GANGA ALTUS | SEJAL ENTERPRISES | 68824 | 2024-05-31 16:25 | 44.84 | 625 | Floor Trap Jali with cover 150mmx150mm (Grey Colour) |  | No. | 555 | 70 | 11.2
GANGA ALTUS | SEJAL ENTERPRISES | 68824 | 2024-05-31 16:25 | 33.04 | 154 | GI U Clamps 8" |  | No. | 0 | 154 | 100
GANGA ALTUS | K K MARKETING | 68887 | 2024-06-07 16:29 | 854.131 | 20 | SWR Silent Single Y 6" | PRINCE | No. | 14 | 6 | 30
GANGA ALTUS | K K MARKETING | 68887 | 2024-06-07 16:29 | 446.2289 | 90 | SWR Silent Shoe Bend 6" | PRINCE | No. | 66 | 24 | 26.6667
GANGA ALTUS | K K MARKETING | 68887 | 2024-06-07 16:29 | 149.8836 | 632 | SWR Silent Shoe Bend 4" | PRINCE | No. | 531 | 101 | 15.981
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 6.6045 | 24 | ASTM Red. Bush 1-1/2" x 1-1/4" | PRINCE | No. | 9 | 15 | 62.5
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 145.7775 | 32 | ASTM Ball Valve 1-1/4" | PRINCE | No. | 0 | 32 | 100
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 195.2593 | 38 | ASTM Pipe 3/4" x 10 fts | PRINCE | No. | 36 | 2 | 5.2632
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 1690.468 | 200 | SWR Silent Aerator 4" (70001576) | PRINCE | No. | 193 | 7 | 3.5
GANGA ALTUS | K K MARKETING | 68891 | 2024-06-07 18:17 | 1194.278 | 332 | SWR Silent Pipe 4" x 10 ft S/S | PRINCE | No. | 330 | 2 | 0.6024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 64.3808 | 480 | CP Extension Piece 1/2" x 1" | VIKING | No. | 280 | 200 | 41.6667
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 550.116 | 480 | Angle Cock (F1015201-Cera) | CERA | No. | 290 | 190 | 39.5833
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 712.4003 | 208 | Health faucet ( F8030107 -Cera) | CERA | No. | 0 | 208 | 100
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 646.3863 | 192 | Bath Spout (F1015661-Cera) | CERA | No. | 145 | 47 | 24.4792
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 2380.7751 | 149 | Wash Basin (Calburt S2020137-Cera Sn. white) | CERA | No. | 74 | 75 | 50.3356
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 3892.9498 | 337 | W.H. Commode with seat cover (Cordo-S1043108-Cera Sn. white) | CERA | No. | 163 | 174 | 51.632
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 181.5383 | 192 | Shower Arm (F7040101-Cera) | CERA | No. | 144 | 48 | 25
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 1030.619 | 103 | Wash Basin (Chime-S2040139-Cera Sn. white) | CERA | No. | 51 | 52 | 50.4854
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 695.8968 | 192 | Shower Rose (7020305-Cera) | CERA | No. | 100 | 92 | 47.9167
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 605.1277 | 107 | Cera Garnet Bib Cock (F2002153) |  | No. | 73 | 34 | 31.7757
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 907.6913 | 104 | Sink Cock (F1015251-Cera) |  | No. | 72 | 32 | 30.7692
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 68946 | 2024-06-14 16:18 | 57.0648 | 288 | Flexible Pipe 1-1/4" x 2fts |  | No. | 0 | 288 | 100
GANGA ALTUS | KANHAIYA ENTERPRISES | 68955 | 2024-06-15 13:23 | 14.16 | 576 | Teflon Tape |  | No. | 0 | 576 | 100
GANGA ALTUS | K K MARKETING | 69047 | 2024-06-25 16:45 | 323.7213 | 125 | PVC Pipe 3" 6Ft Long D/S |  | No. | 47 | 78 | 62.4
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | 69078 | 2024-07-02 11:00 | 171.926 | 223 | PVC Connector 1/2"x 24" - No. | VIKING | No. | 0 | 223 | 100
GANGA ALTUS | K K MARKETING | 69170 | 2024-07-08 16:47 | 77.3373 | 96 | PVC Nahani Trap 4"X 3" |  | No. | 19 | 77 | 80.2083
GANGA ALTUS | K K MARKETING | 69200 | 2024-07-10 17:29 | 15.5701 | 191 | PVC Elbow 1 1/2 " | PRINCE | No. | 90 | 101 | 52.8796
GANGA ALTUS | M B SALES CORPORATION | 69477 | 2024-08-12 14:34 | 1137.52 | 55 | SWR Silent Swept Tee 8" |  | No. | 0 | 55 | 100